## Schedule
Customer | Job # | Description | Total $ | PO Recvd | Promised Date | Current Phase | % Complete | Est Hrs | Remaining Hrs | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08 | 06/15 | 06/22 | 06/29 | 07/06 | 07/13 | 07/20 | 07/27 | 08/03 | 08/10 | 08/17
MERRICK INDUSTRIES, INC. | 25-118 | MH-5301-HP-05000-CASING | 125500 | 2025-11-07 |  | PRE-FAB | 14.9 | 679 | 578 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: FABRICATION; 04/13: TESTING; 04/20: CLEANING; 04/27: SHIPPING
AIRGAS NITROUS OXIDE | 25-055 | SST N20 REACTOR | 136000 | 2025-06-12 |  | PRE-FAB | 0 | 540 | 540 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: FABRICATION; 04/13: TESTING; 04/20: CLEANING; 04/27: SHIPPING
HARPERLOVE | 25-101 | T-1615 RUPTURE DISK CATCH TANK | 357000 | 2025-10-27 |  | FABRICATION | 19.9 | 560 | 449 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
MERRICK INDUSTRIES, INC. | 25-117 | MH-5301-HP-02000-CASING | 125500 | 2025-11-07 |  | FABRICATION | 34.6 | 679 | 444 | 03/23: FABRICATION; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
SYMS ENGINEERING, INC. | 24-046 | NMP STORAGE TANK (TK-F502R) | 197500 | 2024-08-15 |  | FABRICATION | 44.6 | 581 | 322 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
SYNTHOMER INC. | 25-083 | REACTOR 12 | 163700 | 2025-07-14 |  | TESTING | 42.8 | 511 | 292 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
RECO COMMERCIAL SYSTEMS | 25-070 | BUFFER TANK #15 | 102250 | 2025-06-13 |  | FABRICATION | 42.9 | 476 | 272 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
RECO COMMERCIAL SYSTEMS | 25-071 | BUFFER TANK #16 | 102250 | 2025-06-13 |  | FABRICATION | 46.8 | 476 | 253 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
AMERITERPENES LLC | 25-093 | CARBON UNIT #2 | 106000 | 2025-09-10 |  | FABRICATION | 31.6 | 325 | 222 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
RECO COMMERCIAL SYSTEMS | 25-069 | BUFFER TANK #14 | 102250 | 2025-06-13 |  | FABRICATION | 55.6 | 476 | 211 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
AMERITERPENES LLC | 25-092 | CARBON UNIT #1 | 106000 | 2025-09-10 |  | TESTING | 40.1 | 325 | 195 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
ENCHEM AMERICA, LLC | 23-042 | 300 M3 SS API TANK (FIELD KIT) | 208250 | 2023-06-02 |  | SHIPPING | 70.7 | 661 | 194 | 03/23: SHIPPING
KIMBERLY CLARK CORP | 25-013 | 340-TK-34001 | 116750 | 2025-01-28 |  | TESTING | 66.1 | 365 | 124 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
COASTAL TECHNOLOGIES, INC. | 25-098 | MIST ELIMINATOR W/FACE WASH | 71500 | 2025-09-24 |  | PRE-FAB | 0 | 108 | 108 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
RECO COMMERCIAL SYSTEMS | 25-068 | BUFFER TANK #13 | 102250 | 2025-06-13 |  | CLEANING | 83.1 | 476 | 81 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-268 | BUFFER TANK 145 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 0 | 74 | 74 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-272 | BUFFER TANK 149 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 0 | 74 | 74 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-269 | BUFFER TANK 146 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 0 | 74 | 74 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-271 | BUFFER TANK 148 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 0 | 74 | 74 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-273 | BUFFER TANK 150 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 0 | 74 | 74 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-347 | BUFFER TANK 224 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 0 | 74 | 74 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-270 | BUFFER TANK 147 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 0 | 74 | 74 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-306 | BUFFER TANK 183 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-297 | BUFFER TANK 174 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-307 | BUFFER TANK 184 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-305 | BUFFER TANK 182 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-298 | BUFFER TANK 175 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-303 | BUFFER TANK 180 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-299 | BUFFER TANK 176 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-300 | BUFFER TANK 177 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-301 | BUFFER TANK 178 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-241 | BUFFER TANK 118 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-242 | BUFFER TANK 119 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-224 | BUFFER TANK 101 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-235 | BUFFER TANK 112 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-215 | BUFFER TANK 92 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-304 | BUFFER TANK 181 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-239 | BUFFER TANK 116 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-240 | BUFFER TANK 117 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-278 | BUFFER TANK 155 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-279 | BUFFER TANK 156 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-280 | BUFFER TANK 157 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-281 | BUFFER TANK 158 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-282 | BUFFER TANK 159 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-283 | BUFFER TANK 160 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-290 | BUFFER TANK 167 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-291 | BUFFER TANK 168 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-292 | BUFFER TANK 169 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-293 | BUFFER TANK 170 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-294 | BUFFER TANK 171 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-295 | BUFFER TANK 172 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-274 | BUFFER TANK 151 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-296 | BUFFER TANK 173 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-230 | BUFFER TANK 107 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-231 | BUFFER TANK 108 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-232 | BUFFER TANK 109 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-233 | BUFFER TANK 110 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-234 | BUFFER TANK 111 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-236 | BUFFER TANK 113 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-237 | BUFFER TANK 114 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-238 | BUFFER TANK 115 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-221 | BUFFER TANK 98 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-222 | BUFFER TANK 99 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-223 | BUFFER TANK 100 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-225 | BUFFER TANK 102 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-226 | BUFFER TANK 103 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-227 | BUFFER TANK 104 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-228 | BUFFER TANK 105 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-229 | BUFFER TANK 106 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-276 | BUFFER TANK 153 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-277 | BUFFER TANK 154 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-259 | BUFFER TANK 136 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-258 | BUFFER TANK 135 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-257 | BUFFER TANK 134 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-255 | BUFFER TANK 132 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-254 | BUFFER TANK 131 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-313 | BUFFER TANK 190 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-312 | BUFFER TANK 189 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-311 | BUFFER TANK 188 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-310 | BUFFER TANK 187 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-309 | BUFFER TANK 186 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-289 | BUFFER TANK 166 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-288 | BUFFER TANK 165 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-287 | BUFFER TANK 164 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-286 | BUFFER TANK 163 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-285 | BUFFER TANK 162 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-284 | BUFFER TANK 161 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-315 | BUFFER TANK 192 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-314 | BUFFER TANK 191 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-275 | BUFFER TANK 152 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-260 | BUFFER TANK 137 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-246 | BUFFER TANK 123 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-261 | BUFFER TANK 138 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-262 | BUFFER TANK 139 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-245 | BUFFER TANK 122 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-250 | BUFFER TANK 127 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-251 | BUFFER TANK 128 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-252 | BUFFER TANK 129 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-324 | BUFFER TANK 201 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-325 | BUFFER TANK 202 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-247 | BUFFER TANK 124 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-248 | BUFFER TANK 125 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-249 | BUFFER TANK 126 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-217 | BUFFER TANK 94 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-216 | BUFFER TANK 93 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-214 | BUFFER TANK 91 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-343 | BUFFER TANK 220 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-342 | BUFFER TANK 219 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-323 | BUFFER TANK 200 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-322 | BUFFER TANK 199 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-321 | BUFFER TANK 198 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-320 | BUFFER TANK 197 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-319 | BUFFER TANK 196 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-318 | BUFFER TANK 195 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-317 | BUFFER TANK 194 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-316 | BUFFER TANK 193 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-244 | BUFFER TANK 121 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-243 | BUFFER TANK 120 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-329 | BUFFER TANK 206 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-328 | BUFFER TANK 205 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-327 | BUFFER TANK 204 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-326 | BUFFER TANK 203 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-256 | BUFFER TANK 133 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-267 | BUFFER TANK 144 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-266 | BUFFER TANK 143 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-265 | BUFFER TANK 142 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-341 | BUFFER TANK 218 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-218 | BUFFER TANK 95 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-219 | BUFFER TANK 96 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-220 | BUFFER TANK 97 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-340 | BUFFER TANK 217 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-253 | BUFFER TANK 130 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-264 | BUFFER TANK 141 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-263 | BUFFER TANK 140 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-308 | BUFFER TANK 185 OF 224 | 20500 | 2026-01-02 |  | PRE-FAB | 1.4 | 74 | 73 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-197 | BUFFER TANK 74 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-213 | BUFFER TANK 90 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-211 | BUFFER TANK 88 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-212 | BUFFER TANK 89 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-210 | BUFFER TANK 87 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-209 | BUFFER TANK 86 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-207 | BUFFER TANK 84 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-208 | BUFFER TANK 85 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-205 | BUFFER TANK 82 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-206 | BUFFER TANK 83 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-331 | BUFFER TANK 208 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-332 | BUFFER TANK 209 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-333 | BUFFER TANK 210 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-334 | BUFFER TANK 211 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-335 | BUFFER TANK 212 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-302 | BUFFER TANK 179 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-339 | BUFFER TANK 216 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-338 | BUFFER TANK 215 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-345 | BUFFER TANK 222 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-346 | BUFFER TANK 223 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-196 | BUFFER TANK 73 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-195 | BUFFER TANK 72 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-198 | BUFFER TANK 75 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-336 | BUFFER TANK 213 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-337 | BUFFER TANK 214 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-330 | BUFFER TANK 207 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-344 | BUFFER TANK 221 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 2.7 | 74 | 72 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-189 | BUFFER TANK 66 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-188 | BUFFER TANK 65 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-185 | BUFFER TANK 62 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-201 | BUFFER TANK 78 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.9 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-204 | BUFFER TANK 81 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.9 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-192 | BUFFER TANK 69 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-193 | BUFFER TANK 70 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-202 | BUFFER TANK 79 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.9 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-203 | BUFFER TANK 80 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.9 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-186 | BUFFER TANK 63 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-194 | BUFFER TANK 71 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-184 | BUFFER TANK 61 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-187 | BUFFER TANK 64 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-199 | BUFFER TANK 76 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.9 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-200 | BUFFER TANK 77 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.9 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-190 | BUFFER TANK 67 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-191 | BUFFER TANK 68 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 3.5 | 74 | 71 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-183 | BUFFER TANK 60 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 4.9 | 74 | 70 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-182 | BUFFER TANK 59 OF 224 | 20500 | 2025-12-15 |  | PRE-FAB | 7.6 | 74 | 68 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-178 | BUFFER TANK 55 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 10.3 | 74 | 66 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-180 | BUFFER TANK 57 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 10.3 | 74 | 66 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-181 | BUFFER TANK 58 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 10.3 | 74 | 66 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-177 | BUFFER TANK 54 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 11.7 | 74 | 65 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-176 | BUFFER TANK 53 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 11.7 | 74 | 65 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-173 | BUFFER TANK 50 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 13.9 | 74 | 64 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-175 | BUFFER TANK 52 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 13 | 74 | 64 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-179 | BUFFER TANK 56 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 13 | 74 | 64 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-172 | BUFFER TANK 49 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 14.5 | 74 | 63 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-171 | BUFFER TANK 48 OF 224 | 20500 | 2026-01-02 |  | FABRICATION | 14.5 | 74 | 63 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-170 | BUFFER TANK 47 OF 224 | 20500 | 2026-01-02 |  | FABRICATION | 14.5 | 74 | 63 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-168 | BUFFER TANK 45 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 22.6 | 74 | 57 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-165 | BUFFER TANK 42 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 24.3 | 74 | 56 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-167 | BUFFER TANK 44 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 24.3 | 74 | 56 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-166 | BUFFER TANK 43 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 24.3 | 74 | 56 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-163 | BUFFER TANK 40 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 25 | 74 | 56 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-162 | BUFFER TANK 39 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 25 | 74 | 56 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-160 | BUFFER TANK 37 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 27 | 74 | 54 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-158 | BUFFER TANK 35 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 27 | 74 | 54 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-161 | BUFFER TANK 38 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 27 | 74 | 54 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
ATLAS MINERALS & CHEMICALS | 25-084 | SULFUR HOLDING TANK | 140500 | 2025-07-18 |  | CLEANING | 89.4 | 513 | 54 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-157 | BUFFER TANK 34 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 27.7 | 74 | 54 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-174 | BUFFER TANK 51 OF 224 | 20500 | 2025-12-15 |  | TESTING | 32 | 74 | 50 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
VERTIV CORPORATION | 25-155 | BUFFER TANK 32 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 33.1 | 74 | 50 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-156 | BUFFER TANK 33 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 33.1 | 74 | 50 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-151 | BUFFER TANK 28 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 37.8 | 74 | 46 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-153 | BUFFER TANK 30 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 39.9 | 74 | 44 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-152 | BUFFER TANK 29 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 41.2 | 74 | 44 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
KIMBERLY CLARK CORP | 25-012 | 330-TK-3301 | 69850 | 2025-01-28 |  | CLEANING | 85.3 | 291 | 43 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-164 | BUFFER TANK 41 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 45.9 | 74 | 40 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-159 | BUFFER TANK 36 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 45.9 | 74 | 40 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-169 | BUFFER TANK 46 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 46.9 | 74 | 39 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
NAK KILN SERVICES, LLC | 25-040 | HR 120 SHELL | 1128000 | 2025-03-05 |  | FABRICATION | 84.5 | 234 | 36 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
BURKE INDUSTRIAL, INC. | 25-099 | CONE BOTTOM W/COIL | 34250 | 2025-10-02 |  | FABRICATION | 74.8 | 137 | 34 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-154 | BUFFER TANK 31 OF 224 | 20500 | 2025-12-15 |  | FABRICATION | 56.1 | 74 | 32 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
VERTIV CORPORATION | 25-149 | BUFFER TANK 26 OF 224 | 20500 | 2025-12-15 |  | TESTING | 60.8 | 74 | 29 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
VERTIV CORPORATION | 25-150 | BUFFER TANK 27 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 64.9 | 74 | 26 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-146 | BUFFER TANK 23 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 70.9 | 74 | 22
VERTIV CORPORATION | 25-138 | BUFFER TANK 15 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 71.6 | 74 | 21
VERTIV CORPORATION | 25-148 | BUFFER TANK 25 OF 224 | 20500 | 2025-12-15 |  | TESTING | 73.6 | 74 | 20
VERTIV CORPORATION | 25-144 | BUFFER TANK 21 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 72.3 | 74 | 20 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-139 | BUFFER TANK 16 OF 224 | 20500 | 2025-12-15 |  | TESTING | 75.7 | 74 | 18 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
MILLIKEN & CO | 22-017 | SS PROCESS TANK (TAT-17) | 73150 | 2022-03-10 | 2022-08-29 | SHIPPING | 89.3 | 159 | 17
SAVANNAH TANK AND EQUIPMENT, INC. | 26-023 | DEMO TANK | 1 | 2026-03-05 |  | PRE-FAB | 0 | 17 | 17 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING; 04/20: SHIPPING
VERTIV CORPORATION | 25-141 | BUFFER TANK 18 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 77 | 74 | 17
TELLUS PRODUCTS | 21-086 | 35,000 GAL SS STORAGE TANK | 103000 | 2021-09-08 | 2022-02-14 | PRE-FAB | 94.9 | 306 | 16 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING
VERTIV CORPORATION | 25-147 | BUFFER TANK 24 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 79.1 | 74 | 16
TELLUS PRODUCTS | 21-085 | 35,000 GAL SS STORAGE TANK | 103000 | 2021-09-08 | 2022-02-14 | PRE-FAB | 94.6 | 306 | 16 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: TESTING; 04/13: CLEANING
VERTIV CORPORATION | 25-145 | BUFFER TANK 22 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 79.1 | 74 | 16 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-136 | BUFFER TANK 13 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 80.9 | 74 | 14 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-134 | BUFFER TANK 11 OF 224 | 20500 | 2026-01-13 |  | TESTING | 80.4 | 74 | 14 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
VERTIV CORPORATION | 25-143 | BUFFER TANK 20 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 81.1 | 74 | 14
VERTIV CORPORATION | 25-142 | BUFFER TANK 19 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 82.4 | 74 | 13
VERTIV CORPORATION | 25-140 | BUFFER TANK 17 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 82.4 | 74 | 13
VERTIV CORPORATION | 25-135 | BUFFER TANK 12 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 83.1 | 74 | 12
ROSENBLAD DESIGN GROUP, INC. | 24-038 | Form (2) Cones per Customer Drawing | 2500 | 2024-06-11 |  | PRE-FAB | 0 | 12 | 12 | 03/23: PRE-FAB; 03/30: CLEANING; 04/06: SHIPPING
LF MULTICRAFT INC. | 24-059 | ROLL HANDRAIL & ANGLE | 1650 | 2024-10-30 |  | SHIPPING | 47.6 | 21 | 11 | 03/23: SHIPPING
SAVANNAH TANK AND EQUIPMENT, INC. | 23-022 | SAVANNAH TANK DEMO | 1 | 2023-03-16 |  | FABRICATION | 35.3 | 17 | 11 | 03/23: FABRICATION; 03/30: TESTING
ROSENBLAD DESIGN GROUP, INC. | 24-039 | FORM ELBOWS | 1750 | 2024-06-25 |  | PRE-FAB | 0 | 10 | 10 | 03/23: PRE-FAB
GARRETT MACHINE | 24-024 | 310 SS CYLINDER | 20000 | 2024-05-09 |  | FABRICATION | 78 | 46 | 10 | 03/23: FABRICATION; 03/30: TESTING; 04/06: CLEANING; 04/13: SHIPPING
NOAH INDUSTRIAL | 21-083 | 6' X 8' SS FEED TANK | 19500 | 2021-08-30 | 2021-11-17 | TESTING | 87 | 69 | 9 | 03/23: TESTING; 03/30: CLEANING; 04/06: SHIPPING
CON-CRET, LLC | 21-156 | 20,000 GAL SS ETHANOL STORAGE | 150000 | 2021-12-27 | 2022-07-15 | SHIPPING | 97.5 | 313 | 8
PRYSMIAN CABLES AND SYSTEMS USA LLC | 21-125 | SS HORIZONTAL PRESSURE VESSEL | 126250 | 2021-10-26 | 2022-06-14 | SHIPPING | 97 | 283 | 8
VERTIV CORPORATION | 25-132 | BUFFER TANK 9 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 89.2 | 74 | 8
VERTIV CORPORATION | 25-137 | BUFFER TANK 14 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 88.5 | 74 | 8
VERTIV CORPORATION | 25-127 | BUFFER TANK 4 OF 224 | 20500 | 2026-01-13 |  | CLEANING | 90.5 | 74 | 7 | 03/23: CLEANING; 03/30: SHIPPING
VERTIV CORPORATION | 25-133 | BUFFER TANK 10 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 90.5 | 74 | 7
ANDRITZ INC | 25-042 | FOUL CONDENSATE TANK | 20700 | 2025-03-19 | 2025-08-27 | CLEANING | 92.6 | 85 | 6
VERTIV CORPORATION | 25-124 | BUFFER TANK 1 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 91.9 | 74 | 6 | 03/23: CLEANING; 03/30: SHIPPING
US SUGAR REFINERY, LLC | 25-091 | API MANWAY | 5800 | 2025-09-04 |  | TESTING | 64.3 | 14 | 5 | 03/23: TESTING; 03/30: CLEANING
TELLUS PRODUCTS | 21-084 | 35,000 GAL SS STORAGE TANK | 103000 | 2021-09-08 | 2022-02-14 | FABRICATION | 98.6 | 306 | 4 | 03/23: FABRICATION
VERTIV CORPORATION | 25-130 | BUFFER TANK 7 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 94.6 | 74 | 4
US SUGAR REFINERY, LLC | 25-001 | 144" FLAT BOTTOM | 6100 | 2025-01-14 |  | PRE-FAB | 68.8 | 12 | 4 | 03/23: PRE-FAB; 03/30: FABRICATION; 04/06: CLEANING
VERTIV CORPORATION | 25-126 | BUFFER TANK 3 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 94.6 | 74 | 4
PISTOL'S INDUSTRIAL SERVICE | 24-045 | OIL/WATER SEPARATION TANK | 42400 | 2024-08-15 | 2024-12-03 | SHIPPING | 97.9 | 177 | 4
VERTIV CORPORATION | 25-129 | BUFFER TANK 6 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 94.6 | 74 | 4
VERTIV CORPORATION | 25-131 | BUFFER TANK 8 OF 224 | 20500 | 2025-12-15 |  | CLEANING | 94.6 | 74 | 4
ANDRITZ INC | 25-053 | VAPOR DUCTING 300122163 | 82000 | 2025-06-02 |  | SHIPPING | 97.5 | 120 | 3
VERTIV CORPORATION | 25-125 | BUFFER TANK 2 OF 224 | 20500 | 2025-12-15 |  | SHIPPING | 95.9 | 74 | 3
FIRST PLACE FABRICATION LLC | 24-040 | CUT AND BEND PLATES | 316 | 2024-07-12 |  | PRE-FAB | 0 | 2 | 2 | 03/23: PRE-FAB
R2T CONSTRUCTORS | 24-071 | TANGENTIAL NOZZLE CHARGES | 6800 | 2024-12-18 |  | SHIPPING | 0 | 1 | 1 | 03/23: SHIPPING
TELLUS PRODUCTS | 25-086 | SS FLANGE RING | 6075 | 2025-07-30 |  | CLEANING | 92.9 | 14 | 1
SAVANNAH TANK AND EQUIPMENT, INC. | OH-26 |  | 0 | 2026-01-02 |  | TESTING | 0 | 0 | 0
PRO PIPE INC | 25-081 | 20" ROLLED PIPE | 1800 | 2025-07-01 |  | PRE-FAB | 100 | 7 | 0
HOLBROOK METAL FABRICATION | 24-057 | FORM (2) CONES | 2800 | 2024-10-18 |  | PRE-FAB | 100 | 15 | 0
TOM HENLEY | 25-082 | ROLLED PLATE | 2300 | 2025-07-02 |  | PRE-FAB | 100 | 11 | 0
PRO PIPE INC | 25-045 | NOZZLES AND AGITATOR SUPPORTS | 38525 | 2025-04-05 |  | FABRICATION | 100 | 29 | 0
APPLIED INDUSTRIAL TECHNOLOGIES | 25-047 | (2) VIBE PADS | 950 | 2025-04-21 |  | PRE-FAB | 100 | 4 | 0
PINOVA INC | 22-087 | 24" API 650 ROOF MNWY CVR | 750 | 2022-09-22 |  | PRE-FAB | 100 | 4 | 0
LEAR WEST FABRICATION, LLC | 23-025 | (4) ROLLED RINGS | 4700 | 2023-03-29 |  | PRE-FAB | 100 | 5 | 0
CORROCOAT | 23-038 | REPLACEMENT PARTS | 5175 | 2023-05-25 |  | PRE-FAB | 100 | 2 | 0
LEAR WEST FABRICATION, LLC | 21-119 | 128 CST BURNED PLATES | 6650 | 2021-10-01 |  | SHIPPING | 100 | 8 | 0