## Build Plan w Hours
Job #: | 25-072 | Description: | SS STORAGE TANK #1 |  | Total Est Hours: | 395
Similar jobs used: | 25-073, 25-074, 25-054, 23-040, 25-032
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  | 1 | low | global:1.0-1.0
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | low | est:0.0-0.0
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4 | 4.5 | high | 3.0-7.5
PRE FAB |  | .105 | Build Nozzles-Weld | 8 | 12 | high | 6.5-14.5
PRE FAB |  | .115 | Make Manway Parts | 1 | 1.2 | high | 1.0-5.0
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1 | 1.8 | high | 1.0-2.0
PRE FAB |  | .125 | Roll Manway Neck | 2 | 2 | high | 2.0-3.0
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 2 | 5.2 | high | 4.0-7.0
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 1 | 3 | high | 2.0-4.0
PRE FAB |  | .140 | Build Hatch/Door | 1 | 3.5 | high | 1.5-7.0
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 28 | 26.5 | high | 14.0-39.5
PRE FAB |  | .156 | Clean & Prep Parts | 16 | 11.5 | high | 4.5-20.2
Supports
PRE FAB |  | .165 | Build Supports | 8 | 3.5 | high | 2.0-46.5
PRE FAB |  | .170 | Roll Repads-Drill & Tap | 2 | 2.5 | high | 2.0-3.0
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 2 | high | 2.0-2.0
PRE FAB |  | .205 | Roll Rim Angle | 2 | 3 | high | 2.0-3.0
Shells
INSPECTION |  | .QC3 | UT Shells |  |  | low | est:0.0-0.0
PRE FAB |  | .305 | BI, SQ, T&C Shells | 36 | 15 | high | 5.0-27.0
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 24 | 12 | high | 4.0-20.0
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 11 | 11 | high | 9.5-11.5
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  | 1 | low | global:1.0-2.0
PRE FAB |  | .355 | L/O Top, B&C Holes | 2 | 3.5 | high | 2.0-5.5
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2 | 3 | high | 2.0-6.0
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6 | 7.8 | high | 6.0-8.0
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 7 | 8 | high | 6.0-33.0
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 14 | 10 | high | 6.5-20.0
FIT |  | .605 | Tack Shell Courses | 14 | 5 | high | 4.0-15.0
FIT |  | .610 | Weld Inside Round Seams | 14 | 11.5 | high | 5.0-23.0
FIT |  | .615 | Install Rim Angle | 12 | 4 | high | 4.0-8.0
FIT |  | .616 | Weld Rim Angle | 12 | 8 | high | 4.0-10.0
FIT |  | .620 | L/O Shell, B&C Holes | 2 | 3 | high | 2.0-4.0
INSPECTION |  | .QC5 | QC Inspection - Internal |  | 1 | low | global:1.0-1.5
FIT |  | .640 | Fit Top to Shell | 9 | 6 | high | 4.5-12.0
FIT |  | .645 | Weld all Outside Seams | 14 | 18.5 | high | 8.0-24.0
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3 | 3 | high | 2.0-5.5
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 21 | 15 | high | 14.0-20.8
FIT |  | .717 | Install Lift Lugs on Shl | 5 | 4 | high | 2.0-4.5
FIT |  | .720 | Install Support Parts | 15 | 19.5 | high | 6.5-44.0
FIT |  | .725 | Set Nozzles in Shell | 6 | 6 | high | 2.5-7.5
FIT |  | .726 | Weld Shell Nozz & M/Ws | 12 | 10 | high | 7.0-32.0
FINISHING |  | .765 | Install Name Tag | 1 | 1 | high | 0.5-1.0
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1 | medium | 1.0-1.0
INSPECTION |  | .QC6 | QC Inspection - Fab |  | 3 | low | global:1.5-4.5
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 3 | 2 | high | 1.0-10.0
FINISHING |  | .910 | Test Tank | 14 | 21 | high | 7.0-33.0
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | low | est:0.0-0.0
FINISHING |  | .920 | Clean Tank Complete | 48 | 59 | high | 25.5-96.2
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | low | est:0.0-0.0
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 4 | 6.5 | high | 4.8-10.0
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | low | est:0.0-0.0
SHIPPING |  | .960 | Load on Truck | 5 | 8.5 | high | 7.0-10.5
|  |  | Total Predicted Hours |  | 371

## Build Plan - No Hours
Job #: | 25-072 | Description: | SS STORAGE TANK #1 |  | Total Est Hours: | 395
Similar jobs used: | 25-073, 25-074, 25-054, 23-040, 25-032
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4
PRE FAB |  | .105 | Build Nozzles-Weld | 8
PRE FAB |  | .115 | Make Manway Parts | 1
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1
PRE FAB |  | .125 | Roll Manway Neck | 2
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 2
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 1
PRE FAB |  | .140 | Build Hatch/Door | 1
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 28
PRE FAB |  | .156 | Clean & Prep Parts | 16
Supports
PRE FAB |  | .165 | Build Supports | 8
PRE FAB |  | .170 | Roll Repads-Drill & Tap | 2
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .205 | Roll Rim Angle | 2
Shells
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 36
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 24
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 11
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 2
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 7
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 14
FIT |  | .605 | Tack Shell Courses | 14
FIT |  | .610 | Weld Inside Round Seams | 14
FIT |  | .615 | Install Rim Angle | 12
FIT |  | .616 | Weld Rim Angle | 12
FIT |  | .620 | L/O Shell, B&C Holes | 2
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 9
FIT |  | .645 | Weld all Outside Seams | 14
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 21
FIT |  | .717 | Install Lift Lugs on Shl | 5
FIT |  | .720 | Install Support Parts | 15
FIT |  | .725 | Set Nozzles in Shell | 6
FIT |  | .726 | Weld Shell Nozz & M/Ws | 12
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 3
FINISHING |  | .910 | Test Tank | 14
INSPECTION |  | .QC7 | QC Inspection - Test
FINISHING |  | .920 | Clean Tank Complete | 48
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 4
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 5
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-073
25-074
25-054
23-040
25-032
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 1 | low | global:1.0-1.0 | global
.QC1 | UT Top & Bottom Heads | 0 | low | est:0.0-0.0 | 23-040, 25-032, 25-054, 25-073
.100 | Cut Nozzle Pipe and Clean | 4.5 | high | 3.0-7.5 | 25-074, 25-073, 25-054, 25-032, 23-040
.105 | Build Nozzles-Weld | 12 | high | 6.5-14.5 | 25-074, 25-073, 25-054, 25-032, 23-040
.115 | Make Manway Parts | 1.2 | high | 1.0-5.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.120 | Brn MW Neck, Clean, Bevel | 1.8 | high | 1.0-2.0 | 25-074, 25-073, 25-054, 23-040
.125 | Roll Manway Neck | 2 | high | 2.0-3.0 | 25-074, 25-073, 25-054, 23-040
.130 | S/U Weld MW Flg, Neck Sem | 5.2 | high | 4.0-7.0 | 25-074, 25-073, 25-054, 23-040
.135 | Bld Davit Arm Aby Cover | 3 | high | 2.0-4.0 | 25-074, 25-073, 25-054, 23-040
.140 | Build Hatch/Door | 3.5 | high | 1.5-7.0 | 25-073, 25-032, 23-040
.155 | Cut Parts on Burn Table | 26.5 | high | 14.0-39.5 | 25-074, 25-073, 25-054, 25-032, 23-040
.156 | Clean & Prep Parts | 11.5 | high | 4.5-20.2 | 25-074, 25-073, 25-054, 25-032
.165 | Build Supports | 3.5 | high | 2.0-46.5 | 25-074, 25-073, 25-054, 25-032, 23-040
.170 | Roll Repads-Drill & Tap | 2.5 | high | 2.0-3.0 | 25-074, 25-073, 25-032, 23-040
.200 | Bld Lift Lugs, Grd Lugs | 2 | high | 2.0-2.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.205 | Roll Rim Angle | 3 | high | 2.0-3.0 | 25-073, 25-032, 23-040
.QC3 | UT Shells | 0 | low | est:0.0-0.0 | 23-040, 25-032, 25-054, 25-073, 25-074
.305 | BI, SQ, T&C Shells | 15 | high | 5.0-27.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.315 | Roll Shell, Tack-Weld I/S | 12 | high | 4.0-20.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.350 | Build Top Head/Cone | 11 | high | 9.5-11.5 | 25-073, 25-032, 23-040
.QC4 | QC Inspection -Top/Bot/Co | 1 | low | global:1.0-2.0 | global
.355 | L/O Top, B&C Holes | 3.5 | high | 2.0-5.5 | 25-074, 25-073, 25-032, 23-040
.365 | Set Nozzles & Lugs - Top | 3 | high | 2.0-6.0 | 25-074, 25-073, 25-032, 23-040
.366 | Weld Nozzles - Top Head | 7.8 | high | 6.0-8.0 | 25-074, 25-073, 25-032, 23-040
.450 | Build Bottom Head/Cone | 8 | high | 6.0-33.0 | 25-073, 25-032, 23-040
.QC4 | QC Inspection -Top/Bot/Co | 1 | low | global:1.0-2.0 | global
.600 | Fit Bottom Head to Shell | 10 | high | 6.5-20.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.605 | Tack Shell Courses | 5 | high | 4.0-15.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.610 | Weld Inside Round Seams | 11.5 | high | 5.0-23.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.615 | Install Rim Angle | 4 | high | 4.0-8.0 | 25-073, 25-032, 23-040
.616 | Weld Rim Angle | 8 | high | 4.0-10.0 | 25-073, 25-032, 23-040
.620 | L/O Shell, B&C Holes | 3 | high | 2.0-4.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.QC5 | QC Inspection - Internal | 1 | low | global:1.0-1.5 | global
.640 | Fit Top to Shell | 6 | high | 4.5-12.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.645 | Weld all Outside Seams | 18.5 | high | 8.0-24.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.800 | Move Tank to Detail Rolls | 3 | high | 2.0-5.5 | 25-074, 25-073, 25-054, 25-032, 23-040
.715 | Install Insul/Vac Rings | 15 | high | 14.0-20.8 | 25-073, 25-054, 23-040
.717 | Install Lift Lugs on Shl | 4 | high | 2.0-4.5 | 25-073, 25-054, 25-032, 23-040
.720 | Install Support Parts | 19.5 | high | 6.5-44.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.725 | Set Nozzles in Shell | 6 | high | 2.5-7.5 | 25-074, 25-073, 25-054, 25-032, 23-040
.726 | Weld Shell Nozz & M/Ws | 10 | high | 7.0-32.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.765 | Install Name Tag | 1 | high | 0.5-1.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.770 | Inspect Tank, Make Repair | 1 | medium | 1.0-1.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.QC6 | QC Inspection - Fab | 3 | low | global:1.5-4.5 | global
.801 | Move to Shop Test Area | 2 | high | 1.0-10.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.910 | Test Tank | 21 | high | 7.0-33.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.QC7 | QC Inspection - Test | 0 | low | est:0.0-0.0 | 23-040, 25-032, 25-054, 25-073, 25-074
.920 | Clean Tank Complete | 59 | high | 25.5-96.2 | 25-074, 25-073, 25-054, 25-032, 23-040
.QC8 | QC Inspection - Clean | 0 | low | est:0.0-0.0 | 23-040, 25-032, 25-054, 25-073, 25-074
.940 | Prepare Tank for Shipment | 6.5 | high | 4.8-10.0 | 25-074, 25-073, 25-054, 25-032, 23-040
.QC95 | QC Inspection - Final & L | 0 | low | est:0.0-0.0 | 23-040, 25-032, 25-054, 25-073, 25-074
.960 | Load on Truck | 8.5 | high | 7.0-10.5 | 25-074, 25-073, 25-054, 25-032, 23-040