## Build Plan w Hours
Job #: | 25-083 | Description: | REACTOR 12 |  | Total Est Hours: | 511
Similar jobs used: | 24-062, 23-040, 25-074, 23-018, 25-085
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  | 1 | low | global:1.0-1.0
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | low | est:0.0-0.0
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12 | 4.2 | high | 3.0-5.5
PRE FAB |  | .105 | Build Nozzles-Weld | 18 | 8 | high | 4.0-21.5
PRE FAB |  | .107 | Build Repads for Nozzles | 4 | 4 | medium | 3.0-5.0
PRE FAB |  | .110 | Build Dip Tubes-Weld | 4 | 11 | low | global:3.0-31.8
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1 | 2 | high | 1.0-2.0
PRE FAB |  | .125 | Roll Manway Neck | 1 | 2 | high | 1.0-4.0
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 3 | 5 | high | 4.0-7.0
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 20 | 39.5 | high | 25.5-59.5
PRE FAB |  | .156 | Clean & Prep Parts | 12 | 16 | high | 9.5-20.5
Supports
PRE FAB |  | .165 | Build Supports | 20 | 6 | high | 3.5-46.5
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 2 | high | 2.0-2.0
PRE FAB |  | .252 | Fab Miscellaneous Parts | 3 | 3 | medium | 3.0-3.0
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2 | 1 | medium | 1.0-1.0
INSPECTION |  | .QC3 | UT Shells |  |  | low | est:0.0-0.0
PRE FAB |  | .305 | BI, SQ, T&C Shells | 6 | 15 | high | 3.0-33.0
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 5 | 12 | high | 4.0-17.0
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  | 1 | low | global:1.0-2.0
PRE FAB |  | .355 | L/O Top, B&C Holes | 2 | 4 | high | 3.0-12.0
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 14 | 4 | high | 2.0-8.2
PRE FAB |  | .366 | Weld Nozzles - Top Head | 24 | 7.5 | high | 6.5-26.0
PRE FAB |  | .370 | I&W Repads -Top | 12 | 7 | medium | 6.0-8.0
PRE FAB |  | .375 | Install Top Stiffeners | 5 | 5 | medium | 5.0-5.0
PRE FAB |  | .390 | Grind I/S Weld Smooth-Top | 8 | 4 | low | global:2.5-5.5
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 2 | 4 | medium | 3.0-5.0
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 2.5 | medium | 1.0-4.0
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2 | 1.5 | high | 1.0-2.0
FIT |  | .477 | Cut & Fit Btm Jacket | 20 | 39.2 | medium | 16.5-62.0
FIT |  | .478 | Weld Jacket to Bottom | 24 | 45 | medium | 28.5-61.5
FIT |  | .479 | Install Jacket Nozzle-Btm | 8 | 7 | medium | 7.0-7.0
PRE FAB |  | .490 | Grind I/S Weld Smooth-Btm | 1 | 1 | none | no data
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | low | est:0.0-0.0
FIT |  | .600 | Fit Bottom Head to Shell | 7 | 8.5 | high | 6.5-15.0
FIT |  | .620 | L/O Shell, B&C Holes | 1 | 3 | high | 1.5-5.0
FIT |  | .637 | Grind I/S Weld Smooth-Shl | 15 | 29 | low | global:6.0-52.0
INSPECTION |  | .QC5 | QC Inspection - Internal |  | 1 | low | global:1.0-1.5
FIT |  | .640 | Fit Top to Shell | 4 | 8 | high | 4.0-12.0
FIT |  | .641 | Weld top to shell | 8 | 6 | medium | 4.0-8.0
FIT |  | .645 | Weld all Outside Seams | 6 | 24 | high | 15.5-34.5
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2 | 4.5 | high | 2.0-7.0
Install Nozzles and Externals
FIT |  | .700 | Fit Jacket to Shell | 60 | 54.4 | medium | 53.8-55.0
FIT |  | .705 | Weld Jacket to Shell | 30 | 64.5 | medium | 56.2-72.8
FIT |  | .710 | Install Jacket Nozzles | 8 | 4 | medium | 2.0-6.0
FIT |  | .711 | Weld Jacket Nozzles | 8 | 2.8 | low | global:1.0-6.5
FIT |  | .715 | Install Insul/Vac Rings | 12 | 21.8 | high | 9.0-102.0
FIT |  | .720 | Install Support Parts | 20 | 25.2 | high | 17.0-44.0
FIT |  | .725 | Set Nozzles in Shell | 2 | 5 | high | 2.0-7.5
FIT |  | .726 | Weld Shell Nozz & M/Ws | 6 | 7.5 | high | 3.0-10.0
FIT |  | .735 | Install Dip Pipe Supports | 4 | 4.5 | low | global:0.5-24.0
FIT |  | .740 | Install Dip Pipes | 3 | 8.8 | low | global:2.5-118.8
FINISHING |  | .765 | Install Name Tag | 1 | 1 | high | 0.2-1.0
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1 | high | 1.0-25.0
INSPECTION |  | .QC6 | QC Inspection - Fab |  | 3 | low | global:1.5-4.5
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | low | est:0.0-0.0
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2 | 3 | high | 1.0-10.0
FINISHING |  | .910 | Test Tank | 30 | 21 | high | 7.0-42.0
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | low | est:0.0-0.0
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | low | est:0.0-0.0
FINISHING |  | .920 | Clean Tank Complete | 36 | 40 | high | 25.5-68.5
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | low | est:0.0-0.0
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 3 | 8 | high | 5.0-20.0
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | low | est:0.0-0.0
SHIPPING |  | .960 | Load on Truck | 6 | 9.2 | high | 7.5-17.0
|  |  | Total Predicted Hours |  | 633.1

## Build Plan - No Hours
Job #: | 25-083 | Description: | REACTOR 12 |  | Total Est Hours: | 511
Similar jobs used: | 24-062, 23-040, 25-074, 23-018, 25-085
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12
PRE FAB |  | .105 | Build Nozzles-Weld | 18
PRE FAB |  | .107 | Build Repads for Nozzles | 4
PRE FAB |  | .110 | Build Dip Tubes-Weld | 4
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1
PRE FAB |  | .125 | Roll Manway Neck | 1
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 3
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 20
PRE FAB |  | .156 | Clean & Prep Parts | 12
Supports
PRE FAB |  | .165 | Build Supports | 20
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .252 | Fab Miscellaneous Parts | 3
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 6
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 5
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 2
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 14
PRE FAB |  | .366 | Weld Nozzles - Top Head | 24
PRE FAB |  | .370 | I&W Repads -Top | 12
PRE FAB |  | .375 | Install Top Stiffeners | 5
PRE FAB |  | .390 | Grind I/S Weld Smooth-Top | 8
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 2
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2
FIT |  | .477 | Cut & Fit Btm Jacket | 20
FIT |  | .478 | Weld Jacket to Bottom | 24
FIT |  | .479 | Install Jacket Nozzle-Btm | 8
PRE FAB |  | .490 | Grind I/S Weld Smooth-Btm | 1
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 7
FIT |  | .620 | L/O Shell, B&C Holes | 1
FIT |  | .637 | Grind I/S Weld Smooth-Shl | 15
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 4
FIT |  | .641 | Weld top to shell | 8
FIT |  | .645 | Weld all Outside Seams | 6
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2
Install Nozzles and Externals
FIT |  | .700 | Fit Jacket to Shell | 60
FIT |  | .705 | Weld Jacket to Shell | 30
FIT |  | .710 | Install Jacket Nozzles | 8
FIT |  | .711 | Weld Jacket Nozzles | 8
FIT |  | .715 | Install Insul/Vac Rings | 12
FIT |  | .720 | Install Support Parts | 20
FIT |  | .725 | Set Nozzles in Shell | 2
FIT |  | .726 | Weld Shell Nozz & M/Ws | 6
FIT |  | .735 | Install Dip Pipe Supports | 4
FIT |  | .740 | Install Dip Pipes | 3
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2
FINISHING |  | .910 | Test Tank | 30
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 36
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 3
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 6
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
24-062
23-040
25-074
23-018
25-085
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 1 | low | global:1.0-1.0 | global
.QC1 | UT Top & Bottom Heads | 0 | low | est:0.0-0.0 | 23-018, 23-040, 24-062, 25-085
.100 | Cut Nozzle Pipe and Clean | 4.2 | high | 3.0-5.5 | 25-085, 25-074, 24-062, 23-040, 23-018
.105 | Build Nozzles-Weld | 8 | high | 4.0-21.5 | 25-085, 25-074, 24-062, 23-040, 23-018
.107 | Build Repads for Nozzles | 4 | medium | 3.0-5.0 | 25-085, 23-018
.110 | Build Dip Tubes-Weld | 11 | low | global:3.0-31.8 | global
.120 | Brn MW Neck, Clean, Bevel | 2 | high | 1.0-2.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.125 | Roll Manway Neck | 2 | high | 1.0-4.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.130 | S/U Weld MW Flg, Neck Sem | 5 | high | 4.0-7.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.155 | Cut Parts on Burn Table | 39.5 | high | 25.5-59.5 | 25-085, 25-074, 24-062, 23-040, 23-018
.156 | Clean & Prep Parts | 16 | high | 9.5-20.5 | 25-085, 25-074, 24-062
.165 | Build Supports | 6 | high | 3.5-46.5 | 25-085, 25-074, 24-062, 23-040, 23-018
.200 | Bld Lift Lugs, Grd Lugs | 2 | high | 2.0-2.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.252 | Fab Miscellaneous Parts | 3 | medium | 3.0-3.0 | 24-062
.300 | Wrap Top & Bottom Heads | 1 | medium | 1.0-1.0 | 25-074
.QC3 | UT Shells | 0 | low | est:0.0-0.0 | 23-018, 23-040, 24-062, 25-074, 25-085
.305 | BI, SQ, T&C Shells | 15 | high | 3.0-33.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.315 | Roll Shell, Tack-Weld I/S | 12 | high | 4.0-17.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.QC4 | QC Inspection -Top/Bot/Co | 1 | low | global:1.0-2.0 | global
.355 | L/O Top, B&C Holes | 4 | high | 3.0-12.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.365 | Set Nozzles & Lugs - Top | 4 | high | 2.0-8.2 | 25-085, 25-074, 24-062, 23-040, 23-018
.366 | Weld Nozzles - Top Head | 7.5 | high | 6.5-26.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.370 | I&W Repads -Top | 7 | medium | 6.0-8.0 | 25-085, 23-018
.375 | Install Top Stiffeners | 5 | medium | 5.0-5.0 | 23-018
.390 | Grind I/S Weld Smooth-Top | 4 | low | global:2.5-5.5 | global
.QC4 | QC Inspection -Top/Bot/Co | 1 | low | global:1.0-2.0 | global
.455 | L/O Bottom, B&C Holes | 4 | medium | 3.0-5.0 | 25-074, 24-062, 23-018
.465 | Set Nozzles - Bottom Head | 2.5 | medium | 1.0-4.0 | 25-074, 23-040, 23-018
.466 | Weld Nozzles - Bot. Head | 1.5 | high | 1.0-2.0 | 25-074, 23-040, 23-018
.477 | Cut & Fit Btm Jacket | 39.2 | medium | 16.5-62.0 | 23-040, 23-018
.478 | Weld Jacket to Bottom | 45 | medium | 28.5-61.5 | 23-040, 23-018
.479 | Install Jacket Nozzle-Btm | 7 | medium | 7.0-7.0 | 23-040, 23-018
.490 | Grind I/S Weld Smooth-Btm | 1 | none | no data
.OI1 | ASME Hold Point | 0 | low | est:0.0-0.0 | 23-018, 24-062, 25-085
.600 | Fit Bottom Head to Shell | 8.5 | high | 6.5-15.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.620 | L/O Shell, B&C Holes | 3 | high | 1.5-5.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.637 | Grind I/S Weld Smooth-Shl | 29 | low | global:6.0-52.0 | global
.QC5 | QC Inspection - Internal | 1 | low | global:1.0-1.5 | global
.640 | Fit Top to Shell | 8 | high | 4.0-12.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.641 | Weld top to shell | 6 | medium | 4.0-8.0 | 25-074, 23-018
.645 | Weld all Outside Seams | 24 | high | 15.5-34.5 | 25-085, 25-074, 24-062, 23-040, 23-018
.800 | Move Tank to Detail Rolls | 4.5 | high | 2.0-7.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.700 | Fit Jacket to Shell | 54.4 | medium | 53.8-55.0 | 23-040, 23-018
.705 | Weld Jacket to Shell | 64.5 | medium | 56.2-72.8 | 23-040, 23-018
.710 | Install Jacket Nozzles | 4 | medium | 2.0-6.0 | 23-040, 23-018
.711 | Weld Jacket Nozzles | 2.8 | low | global:1.0-6.5 | global
.715 | Install Insul/Vac Rings | 21.8 | high | 9.0-102.0 | 25-085, 24-062, 23-040, 23-018
.720 | Install Support Parts | 25.2 | high | 17.0-44.0 | 25-074, 24-062, 23-040, 23-018
.725 | Set Nozzles in Shell | 5 | high | 2.0-7.5 | 25-085, 25-074, 24-062, 23-040, 23-018
.726 | Weld Shell Nozz & M/Ws | 7.5 | high | 3.0-10.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.735 | Install Dip Pipe Supports | 4.5 | low | global:0.5-24.0 | global
.740 | Install Dip Pipes | 8.8 | low | global:2.5-118.8 | global
.765 | Install Name Tag | 1 | high | 0.2-1.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.770 | Inspect Tank, Make Repair | 1 | high | 1.0-25.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.QC6 | QC Inspection - Fab | 3 | low | global:1.5-4.5 | global
.OI2 | ASME Inspection Internal | 0 | low | est:0.0-0.0 | 23-018, 24-062, 25-085
.801 | Move to Shop Test Area | 3 | high | 1.0-10.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.910 | Test Tank | 21 | high | 7.0-42.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.QC7 | QC Inspection - Test | 0 | low | est:0.0-0.0 | 23-018, 23-040, 24-062, 25-074, 25-085
.OI3 | ASME Inspection Test | 0 | low | est:0.0-0.0 | 23-018, 24-062, 25-085
.920 | Clean Tank Complete | 40 | high | 25.5-68.5 | 25-085, 25-074, 24-062, 23-040, 23-018
.QC8 | QC Inspection - Clean | 0 | low | est:0.0-0.0 | 23-018, 23-040, 24-062, 25-074, 25-085
.940 | Prepare Tank for Shipment | 8 | high | 5.0-20.0 | 25-085, 25-074, 24-062, 23-040, 23-018
.QC95 | QC Inspection - Final & L | 0 | low | est:0.0-0.0 | 23-018, 23-040, 24-062, 25-074, 25-085
.960 | Load on Truck | 9.2 | high | 7.5-17.0 | 25-085, 25-074, 24-062, 23-040, 23-018