## Build Plan w Hours
Job #: | 25-088 | Description: | BALLAST TANK |  | Total Est Hours: | 58
Similar jobs used: | 25-034, 23-034, 25-002, 23-035, 25-036
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  | 1 | low | global:1.0-1.0
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | low | est:0.0-0.0
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 2 | 2 | high | 1.0-3.5
PRE FAB |  | .105 | Build Nozzles-Weld | 3 | 9 | high | 2.0-14.0
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 2 | 6.5 | high | 2.0-10.5
PRE FAB |  | .156 | Clean & Prep Parts | 1 | 2.5 | high | 2.0-6.5
Supports
PRE FAB |  | .165 | Build Supports | 5 | 3 | high | 2.0-4.0
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1 | 1 | high | 1.0-1.0
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  | 1 | low | global:1.0-2.0
PRE FAB |  | .355 | L/O Top, B&C Holes | 2 | 1.2 | medium | 1.0-1.5
PRE FAB |  | .360 | Bevel Top Head | 1 | 2 | low | global:1.0-14.0
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 1 | 2 | medium | 1.0-3.0
PRE FAB |  | .366 | Weld Nozzles - Top Head | 2 | 3 | medium | 2.0-4.0
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 2 | 1.5 | high | 0.5-1.5
PRE FAB |  | .460 | Bevel Bottom Head | 1 | 1 | low | global:0.5-8.0
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 1.5 | medium | 1.0-2.0
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 1 | 1.5 | medium | 1.0-2.0
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | low | est:0.0-0.0
FIT |  | .600 | Fit Bottom Head to Shell | 1 | 4 | high | 1.5-8.5
FIT |  | .620 | L/O Shell, B&C Holes | 3 | 1 | high | 1.0-3.0
INSPECTION |  | .QC5 | QC Inspection - Internal |  | 1 | low | global:1.0-1.5
FIT |  | .640 | Fit Top to Shell | 1 | 5.8 | medium | 1.5-10.0
FIT |  | .645 | Weld all Outside Seams | 3 | 4 | high | 2.5-9.5
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1 | 1.5 | high | 1.0-2.0
Install Nozzles and Externals
FIT |  | .720 | Install Support Parts | 5 | 5.5 | high | 4.0-8.5
FIT |  | .725 | Set Nozzles in Shell | 1 | 3.5 | high | 1.5-7.0
FIT |  | .726 | Weld Shell Nozz & M/Ws | 3 | 5 | high | 2.0-10.0
FINISHING |  | .765 | Install Name Tag | 1 | 0.8 | high | 0.5-1.0
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 0.8 | medium | 0.5-1.0
INSPECTION |  | .QC6 | QC Inspection - Fab |  | 3 | low | global:1.5-4.5
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | low | est:0.0-0.0
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1 | 2 | high | 1.0-2.0
FINISHING |  | .910 | Test Tank | 5 | 6 | high | 3.0-8.0
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | low | est:0.0-0.0
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | low | est:0.0-0.0
FINISHING |  | .920 | Clean Tank Complete | 5 | 6 | high | 1.5-7.0
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | low | est:0.0-0.0
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1 | 2.2 | high | 1.0-3.0
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | low | est:0.0-0.0
SHIPPING |  | .960 | Load on Truck | 1 | 2.5 | high | 2.0-3.0
|  |  | Total Predicted Hours |  | 94.3

## Build Plan - No Hours
Job #: | 25-088 | Description: | BALLAST TANK |  | Total Est Hours: | 58
Similar jobs used: | 25-034, 23-034, 25-002, 23-035, 25-036
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 2
PRE FAB |  | .105 | Build Nozzles-Weld | 3
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 2
PRE FAB |  | .156 | Clean & Prep Parts | 1
Supports
PRE FAB |  | .165 | Build Supports | 5
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 2
PRE FAB |  | .360 | Bevel Top Head | 1
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 1
PRE FAB |  | .366 | Weld Nozzles - Top Head | 2
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 2
PRE FAB |  | .460 | Bevel Bottom Head | 1
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 1
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 1
FIT |  | .620 | L/O Shell, B&C Holes | 3
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 1
FIT |  | .645 | Weld all Outside Seams | 3
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1
Install Nozzles and Externals
FIT |  | .720 | Install Support Parts | 5
FIT |  | .725 | Set Nozzles in Shell | 1
FIT |  | .726 | Weld Shell Nozz & M/Ws | 3
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1
FINISHING |  | .910 | Test Tank | 5
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 5
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 1
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-034
23-034
25-002
23-035
25-036
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 1 | low | global:1.0-1.0 | global
.QC1 | UT Top & Bottom Heads | 0 | low | est:0.0-0.0 | 23-034, 23-035, 25-002, 25-034, 25-036
.100 | Cut Nozzle Pipe and Clean | 2 | high | 1.0-3.5 | 25-036, 25-034, 25-002, 23-035, 23-034
.105 | Build Nozzles-Weld | 9 | high | 2.0-14.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.155 | Cut Parts on Burn Table | 6.5 | high | 2.0-10.5 | 25-036, 25-034, 25-002, 23-035, 23-034
.156 | Clean & Prep Parts | 2.5 | high | 2.0-6.5 | 25-036, 25-034, 25-002
.165 | Build Supports | 3 | high | 2.0-4.0 | 25-002, 23-035, 23-034
.200 | Bld Lift Lugs, Grd Lugs | 1 | high | 1.0-1.0 | 25-036, 25-034, 25-002, 23-035
.QC4 | QC Inspection -Top/Bot/Co | 1 | low | global:1.0-2.0 | global
.355 | L/O Top, B&C Holes | 1.2 | medium | 1.0-1.5 | 23-035, 23-034
.360 | Bevel Top Head | 2 | low | global:1.0-14.0 | global
.365 | Set Nozzles & Lugs - Top | 2 | medium | 1.0-3.0 | 23-035, 23-034
.366 | Weld Nozzles - Top Head | 3 | medium | 2.0-4.0 | 23-035, 23-034
.QC4 | QC Inspection -Top/Bot/Co | 1 | low | global:1.0-2.0 | global
.455 | L/O Bottom, B&C Holes | 1.5 | high | 0.5-1.5 | 25-036, 23-035, 23-034
.460 | Bevel Bottom Head | 1 | low | global:0.5-8.0 | global
.465 | Set Nozzles - Bottom Head | 1.5 | medium | 1.0-2.0 | 23-035, 23-034
.466 | Weld Nozzles - Bot. Head | 1.5 | medium | 1.0-2.0 | 23-035, 23-034
.OI1 | ASME Hold Point | 0 | low | est:0.0-0.0 | 23-034, 23-035
.600 | Fit Bottom Head to Shell | 4 | high | 1.5-8.5 | 25-036, 25-034, 25-002, 23-035, 23-034
.620 | L/O Shell, B&C Holes | 1 | high | 1.0-3.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.QC5 | QC Inspection - Internal | 1 | low | global:1.0-1.5 | global
.640 | Fit Top to Shell | 5.8 | medium | 1.5-10.0 | 23-035, 23-034
.645 | Weld all Outside Seams | 4 | high | 2.5-9.5 | 25-036, 25-034, 23-035, 23-034
.800 | Move Tank to Detail Rolls | 1.5 | high | 1.0-2.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.720 | Install Support Parts | 5.5 | high | 4.0-8.5 | 25-034, 25-002, 23-035, 23-034
.725 | Set Nozzles in Shell | 3.5 | high | 1.5-7.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.726 | Weld Shell Nozz & M/Ws | 5 | high | 2.0-10.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.765 | Install Name Tag | 0.8 | high | 0.5-1.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.770 | Inspect Tank, Make Repair | 0.8 | medium | 0.5-1.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.QC6 | QC Inspection - Fab | 3 | low | global:1.5-4.5 | global
.OI2 | ASME Inspection Internal | 0 | low | est:0.0-0.0 | 23-034, 23-035
.801 | Move to Shop Test Area | 2 | high | 1.0-2.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.910 | Test Tank | 6 | high | 3.0-8.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.QC7 | QC Inspection - Test | 0 | low | est:0.0-0.0 | 23-034, 23-035, 25-002, 25-034, 25-036
.OI3 | ASME Inspection Test | 0 | low | est:0.0-0.0 | 23-034, 23-035
.920 | Clean Tank Complete | 6 | high | 1.5-7.0 | 25-036, 25-034, 25-002, 23-035, 23-034
.QC8 | QC Inspection - Clean | 0 | low | est:0.0-0.0 | 23-034, 23-035, 25-002, 25-034, 25-036
.940 | Prepare Tank for Shipment | 2.2 | high | 1.0-3.0 | 25-036, 25-034, 23-035, 23-034
.QC95 | QC Inspection - Final & L | 0 | low | est:0.0-0.0 | 23-034, 23-035, 25-002, 25-034, 25-036
.960 | Load on Truck | 2.5 | high | 2.0-3.0 | 25-036, 25-034, 25-002, 23-035, 23-034