## Build Plan w Hours
Job #: | 25-094 | Description: | 420-TK-42003 |  | Total Est Hours: | 80
Similar jobs used: | 25-109, 24-028, 24-032, 24-030, 24-029
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  | 1 | low | global:1.0-1.0
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | low | est:0.0-0.0
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 6 | 1.5 | high | 1.0-9.2
PRE FAB |  | .105 | Build Nozzles-Weld | 12 | 2 | medium | 2.0-2.0
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 5 | 5 | high | 3.5-7.0
PRE FAB |  | .156 | Clean & Prep Parts | 2 | 2.5 | high | 0.8-7.5
Supports
PRE FAB |  | .165 | Build Supports | 3 | 5.5 | low | global:1.0-46.5
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1 | 1 | high | 1.0-1.0
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 5 | 2 | high | 2.0-7.0
FIT |  | .620 | L/O Shell, B&C Holes | 6 | 3 | low | global:0.5-49.5
INSPECTION |  | .QC5 | QC Inspection - Internal |  | 1 | low | global:1.0-1.5
Install Nozzles and Externals
FIT |  | .717 | Install Lift Lugs on Shl | 1 | 2.5 | low | global:0.5-12.0
FIT |  | .720 | Install Support Parts | 6 | 3 | high | 2.5-3.0
FIT |  | .725 | Set Nozzles in Shell | 6 | 1 | high | 1.0-1.5
FIT |  | .726 | Weld Shell Nozz & M/Ws | 12 | 2 | high | 1.5-2.0
FINISHING |  | .765 | Install Name Tag | 1 | 0.8 | high | 0.5-1.0
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1.5 | low | global:0.5-25.0
INSPECTION |  | .QC6 | QC Inspection - Fab |  | 3 | low | global:1.5-4.5
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1 | 0.5 | high | 0.5-1.0
FINISHING |  | .910 | Test Tank | 5 | 7.2 | high | 6.0-7.5
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | low | est:0.0-0.0
FINISHING |  | .920 | Clean Tank Complete | 5 | 3 | high | 3.0-3.0
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | low | est:0.0-0.0
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1 | 4 | low | global:1.0-24.0
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | low | est:0.0-0.0
SHIPPING |  | .960 | Load on Truck | 1 | 6 | low | global:1.0-25.0
|  |  | Total Predicted Hours |  | 59

## Build Plan - No Hours
Job #: | 25-094 | Description: | 420-TK-42003 |  | Total Est Hours: | 80
Similar jobs used: | 25-109, 24-028, 24-032, 24-030, 24-029
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 6
PRE FAB |  | .105 | Build Nozzles-Weld | 12
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 5
PRE FAB |  | .156 | Clean & Prep Parts | 2
Supports
PRE FAB |  | .165 | Build Supports | 3
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 5
FIT |  | .620 | L/O Shell, B&C Holes | 6
INSPECTION |  | .QC5 | QC Inspection - Internal
Install Nozzles and Externals
FIT |  | .717 | Install Lift Lugs on Shl | 1
FIT |  | .720 | Install Support Parts | 6
FIT |  | .725 | Set Nozzles in Shell | 6
FIT |  | .726 | Weld Shell Nozz & M/Ws | 12
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1
FINISHING |  | .910 | Test Tank | 5
INSPECTION |  | .QC7 | QC Inspection - Test
FINISHING |  | .920 | Clean Tank Complete | 5
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 1
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-109
24-028
24-032
24-030
24-029
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 1 | low | global:1.0-1.0 | global
.QC1 | UT Top & Bottom Heads | 0 | low | est:0.0-0.0 | 24-028, 24-029, 24-030, 24-032, 25-109
.100 | Cut Nozzle Pipe and Clean | 1.5 | high | 1.0-9.2 | 25-109, 24-032, 24-030, 24-029, 24-028
.105 | Build Nozzles-Weld | 2 | medium | 2.0-2.0 | 25-109
.155 | Cut Parts on Burn Table | 5 | high | 3.5-7.0 | 25-109, 24-032, 24-030, 24-029, 24-028
.156 | Clean & Prep Parts | 2.5 | high | 0.8-7.5 | 25-109, 24-032, 24-030, 24-029, 24-028
.165 | Build Supports | 5.5 | low | global:1.0-46.5 | global
.200 | Bld Lift Lugs, Grd Lugs | 1 | high | 1.0-1.0 | 24-032, 24-030, 24-029, 24-028
.600 | Fit Bottom Head to Shell | 2 | high | 2.0-7.0 | 25-109, 24-032, 24-030, 24-029, 24-028
.620 | L/O Shell, B&C Holes | 3 | low | global:0.5-49.5 | global
.QC5 | QC Inspection - Internal | 1 | low | global:1.0-1.5 | global
.717 | Install Lift Lugs on Shl | 2.5 | low | global:0.5-12.0 | global
.720 | Install Support Parts | 3 | high | 2.5-3.0 | 25-109, 24-032, 24-030, 24-029, 24-028
.725 | Set Nozzles in Shell | 1 | high | 1.0-1.5 | 25-109, 24-032, 24-030, 24-029, 24-028
.726 | Weld Shell Nozz & M/Ws | 2 | high | 1.5-2.0 | 25-109, 24-032, 24-030, 24-029, 24-028
.765 | Install Name Tag | 0.8 | high | 0.5-1.0 | 25-109, 24-032, 24-030, 24-029, 24-028
.770 | Inspect Tank, Make Repair | 1.5 | low | global:0.5-25.0 | global
.QC6 | QC Inspection - Fab | 3 | low | global:1.5-4.5 | global
.801 | Move to Shop Test Area | 0.5 | high | 0.5-1.0 | 25-109, 24-032, 24-030, 24-029, 24-028
.910 | Test Tank | 7.2 | high | 6.0-7.5 | 25-109, 24-032, 24-030, 24-029, 24-028
.QC7 | QC Inspection - Test | 0 | low | est:0.0-0.0 | 24-028, 24-029, 24-030, 24-032, 25-109
.920 | Clean Tank Complete | 3 | high | 3.0-3.0 | 25-109, 24-032, 24-030, 24-029, 24-028
.QC8 | QC Inspection - Clean | 0 | low | est:0.0-0.0 | 24-028, 24-029, 24-030, 24-032, 25-109
.940 | Prepare Tank for Shipment | 4 | low | global:1.0-24.0 | global
.QC95 | QC Inspection - Final & L | 0 | low | est:0.0-0.0 | 24-028, 24-029, 24-030, 24-032, 25-109
.960 | Load on Truck | 6 | low | global:1.0-25.0 | global