## Build Plan w Hours
Job #: | 25-069 | Description: | BUFFER TANK #14 |  | Total Est Hours: | 476
Similar jobs used: | 25-071, 25-070, 25-065, 25-063, 25-062
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12 | 2.5 | high | ratio=0.21 (0.20-0.25)
PRE FAB |  | .105 | Build Nozzles-Weld | 6 | 3 | high | ratio=0.50 (0.20-0.50)
PRE FAB |  | .107 | Build Repads for Nozzles | 3 | 3 | high | ratio=1.00 (0.83-1.00)
PRE FAB |  | .110 | Build Dip Tubes-Weld | 30 | 24.5 | high | ratio=0.82 (0.48-0.94)
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 40 | 17.5 | high | ratio=0.44 (0.41-0.54)
PRE FAB |  | .156 | Clean & Prep Parts | 20 | 15 | high | ratio=0.75 (0.55-0.95)
Supports
PRE FAB |  | .175 | B&W Base Ring, Skirt | 8 | 11 | high | ratio=1.38 (1.00-1.75)
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 2 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .255 | Drill/Punch holes | 10 | 8 | high | ratio=0.80 (0.50-1.00)
PRE FAB |  | .261 | Misc Fabrication | 2 | 2 | high | ratio=1.00 (1.00-1.00)
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2 | 2 | high | ratio=1.00 (1.00-1.00)
INSPECTION |  | .QC3 | UT Shells |  |  | skip | 0h estimate
PRE FAB |  | .305 | BI, SQ, T&C Shells | 9 | 6 | high | ratio=0.67 (0.50-1.11)
PRE FAB |  | .310 | Bevel Shell Plates | 12 | 6.5 | high | ratio=0.54 (0.25-0.83)
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 18 | 8 | high | ratio=0.44 (0.20-0.89)
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | skip | 0h estimate
PRE FAB |  | .355 | L/O Top, B&C Holes | 1 | 3 | high | ratio=3.00 (2.00-3.50)
PRE FAB |  | .360 | Bevel Top Head | 1 | 1 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 1 | 1 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6 | 6 | high | ratio=1.00 (0.67-1.33)
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1 | 2 | high | ratio=2.00 (1.00-5.00)
PRE FAB |  | .460 | Bevel Bottom Head | 1 | 1 | medium | ratio=1.00 (n=1)
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 1 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2 | 2 | medium | ratio=1.00 (n=2)
Skirt
PRE FAB |  | .500 | Bld Skirt, Roll & Tack | 5 | 5 | high | ratio=1.00 (0.60-1.00)
PRE FAB |  | .510 | Bld Skirt, F&T to Base | 5 | 3.5 | high | ratio=0.70 (0.40-1.10)
FIT |  | .515 | Weld Skirt | 8 | 6.5 | high | ratio=0.81 (0.38-1.00)
FIT |  | .530 | Bld Skirt, Fit Anchor/Gst | 3 | 2.8 | high | ratio=0.92 (0.67-1.00)
FIT |  | .545 | Weld Skirt Nozzles, Etc. | 6 | 2 | high | ratio=0.33 (0.29-0.67)
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | skip | 0h estimate
FIT |  | .600 | Fit Bottom Head to Shell | 4 | 6.5 | high | ratio=1.62 (0.75-2.75)
FIT |  | .605 | Tack Shell Courses | 8 | 9.8 | high | ratio=1.22 (0.94-1.50)
FIT |  | .610 | Weld Inside Round Seams | 18 | 13.8 | high | ratio=0.76 (0.67-1.64)
FIT |  | .620 | L/O Shell, B&C Holes | 6 | 4.8 | high | ratio=0.79 (0.50-1.00)
FIT |  | .630 | Install Internal Parts | 36 | 24.5 | high | ratio=0.68 (0.20-0.72)
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
FIT |  | .640 | Fit Top to Shell | 5 | 7 | high | ratio=1.40 (0.80-2.20)
FIT |  | .641 | Weld top to shell | 12 | 10.5 | high | ratio=0.88 (0.50-1.17)
FIT |  | .645 | Weld all Outside Seams | 20 | 35 | high | ratio=1.75 (1.30-2.02)
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3 | 1 | high | ratio=0.33 (0.33-0.33)
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 48 | 49.8 | high | ratio=1.04 (0.88-1.23)
FIT |  | .720 | Install Support Parts | 32 | 21 | high | ratio=0.66 (0.34-0.78)
FIT |  | .725 | Set Nozzles in Shell | 8 | 9 | high | ratio=1.12 (0.44-2.00)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 30 | 14 | high | ratio=0.47 (0.30-1.03)
FIT |  | .730 | Add Repads-Weld | 5 | 5 | high | ratio=1.00 (0.80-2.20)
FINISHING |  | .765 | Install Name Tag | 1 | 1.2 | high | ratio=1.25 (0.50-1.50)
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 2 | high | ratio=2.00 (2.00-5.00)
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
INSPECTION |  | .OI4 | Customer Inspection |  |  | skip | 0h estimate
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2 | 1.5 | medium | ratio=0.75 (n=2)
FINISHING |  | .910 | Test Tank | 12 | 14.8 | high | ratio=1.23 (0.20-1.56)
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | skip | 0h estimate
MOVE TANK |  | .802 | Move to Paint Area | 2 | 2 | high | ratio=1.00 (0.25-1.50)
INSPECTION |  | .QC9 | QC Inspection - Sandblast |  |  | skip | 0h estimate
INSPECTION |  | .QC90 | QC Inspection - Paint |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 3 | 6.5 | medium | ratio=2.17 (n=2)
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 5 | 8 | high | ratio=1.60 (1.60-1.60)
|  |  | Total Predicted Hours |  | 395.5

## Build Plan - No Hours
Job #: | 25-069 | Description: | BUFFER TANK #14 |  | Total Est Hours: | 476
Similar jobs used: | 25-071, 25-070, 25-065, 25-063, 25-062
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12
PRE FAB |  | .105 | Build Nozzles-Weld | 6
PRE FAB |  | .107 | Build Repads for Nozzles | 3
PRE FAB |  | .110 | Build Dip Tubes-Weld | 30
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 40
PRE FAB |  | .156 | Clean & Prep Parts | 20
Supports
PRE FAB |  | .175 | B&W Base Ring, Skirt | 8
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .255 | Drill/Punch holes | 10
PRE FAB |  | .261 | Misc Fabrication | 2
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 9
PRE FAB |  | .310 | Bevel Shell Plates | 12
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 18
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 1
PRE FAB |  | .360 | Bevel Top Head | 1
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 1
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1
PRE FAB |  | .460 | Bevel Bottom Head | 1
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2
Skirt
PRE FAB |  | .500 | Bld Skirt, Roll & Tack | 5
PRE FAB |  | .510 | Bld Skirt, F&T to Base | 5
FIT |  | .515 | Weld Skirt | 8
FIT |  | .530 | Bld Skirt, Fit Anchor/Gst | 3
FIT |  | .545 | Weld Skirt Nozzles, Etc. | 6
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 4
FIT |  | .605 | Tack Shell Courses | 8
FIT |  | .610 | Weld Inside Round Seams | 18
FIT |  | .620 | L/O Shell, B&C Holes | 6
FIT |  | .630 | Install Internal Parts | 36
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 5
FIT |  | .641 | Weld top to shell | 12
FIT |  | .645 | Weld all Outside Seams | 20
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 48
FIT |  | .720 | Install Support Parts | 32
FIT |  | .725 | Set Nozzles in Shell | 8
FIT |  | .726 | Weld Shell Nozz & M/Ws | 30
FIT |  | .730 | Add Repads-Weld | 5
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI4 | Customer Inspection
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2
FINISHING |  | .910 | Test Tank | 12
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
MOVE TANK |  | .802 | Move to Paint Area | 2
INSPECTION |  | .QC9 | QC Inspection - Sandblast
INSPECTION |  | .QC90 | QC Inspection - Paint
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 3
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 5
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-071
25-070
25-065
25-063
25-062
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 2.5 | high | ratio=0.21 (0.20-0.25) | 25-071, 25-070, 25-065, 25-063, 25-062
.105 | Build Nozzles-Weld | 3 | high | ratio=0.50 (0.20-0.50) | 25-071, 25-070, 25-065, 25-063, 25-062
.107 | Build Repads for Nozzles | 3 | high | ratio=1.00 (0.83-1.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.110 | Build Dip Tubes-Weld | 24.5 | high | ratio=0.82 (0.48-0.94) | 25-071, 25-070, 25-065, 25-063, 25-062
.155 | Cut Parts on Burn Table | 17.5 | high | ratio=0.44 (0.41-0.54) | 25-071, 25-070, 25-065, 25-063, 25-062
.156 | Clean & Prep Parts | 15 | high | ratio=0.75 (0.55-0.95) | 25-071, 25-070, 25-065, 25-063, 25-062
.175 | B&W Base Ring, Skirt | 11 | high | ratio=1.38 (1.00-1.75) | 25-071, 25-070, 25-065, 25-063, 25-062
.200 | Bld Lift Lugs, Grd Lugs | 2 | high | ratio=1.00 (1.00-1.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.255 | Drill/Punch holes | 8 | high | ratio=0.80 (0.50-1.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.261 | Misc Fabrication | 2 | high | ratio=1.00 (1.00-1.00) | 25-070, 25-063, 25-062
.300 | Wrap Top & Bottom Heads | 2 | high | ratio=1.00 (1.00-1.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.QC3 | UT Shells | 0 | skip | 0h estimate
.305 | BI, SQ, T&C Shells | 6 | high | ratio=0.67 (0.50-1.11) | 25-071, 25-070, 25-065, 25-063, 25-062
.310 | Bevel Shell Plates | 6.5 | high | ratio=0.54 (0.25-0.83) | 25-071, 25-065, 25-063, 25-062
.315 | Roll Shell, Tack-Weld I/S | 8 | high | ratio=0.44 (0.20-0.89) | 25-071, 25-070, 25-065, 25-063, 25-062
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.355 | L/O Top, B&C Holes | 3 | high | ratio=3.00 (2.00-3.50) | 25-071, 25-065, 25-063, 25-062
.360 | Bevel Top Head | 1 | high | ratio=1.00 (1.00-1.00) | 25-071, 25-070, 25-063
.365 | Set Nozzles & Lugs - Top | 1 | high | ratio=1.00 (1.00-1.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.366 | Weld Nozzles - Top Head | 6 | high | ratio=1.00 (0.67-1.33) | 25-071, 25-070, 25-065, 25-063, 25-062
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.455 | L/O Bottom, B&C Holes | 2 | high | ratio=2.00 (1.00-5.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.460 | Bevel Bottom Head | 1 | medium | ratio=1.00 (n=1) | 25-062
.465 | Set Nozzles - Bottom Head | 1 | high | ratio=1.00 (1.00-1.00) | 25-071, 25-070, 25-063, 25-062
.466 | Weld Nozzles - Bot. Head | 2 | medium | ratio=1.00 (n=2) | 25-063, 25-062
.500 | Bld Skirt, Roll & Tack | 5 | high | ratio=1.00 (0.60-1.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.510 | Bld Skirt, F&T to Base | 3.5 | high | ratio=0.70 (0.40-1.10) | 25-071, 25-070, 25-065, 25-063, 25-062
.515 | Weld Skirt | 6.5 | high | ratio=0.81 (0.38-1.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.530 | Bld Skirt, Fit Anchor/Gst | 2.8 | high | ratio=0.92 (0.67-1.00) | 25-071, 25-065, 25-063, 25-062
.545 | Weld Skirt Nozzles, Etc. | 2 | high | ratio=0.33 (0.29-0.67) | 25-071, 25-070, 25-063
.OI1 | ASME Hold Point | 0 | skip | 0h estimate
.600 | Fit Bottom Head to Shell | 6.5 | high | ratio=1.62 (0.75-2.75) | 25-071, 25-070, 25-065, 25-063, 25-062
.605 | Tack Shell Courses | 9.8 | high | ratio=1.22 (0.94-1.50) | 25-070, 25-065, 25-063, 25-062
.610 | Weld Inside Round Seams | 13.8 | high | ratio=0.76 (0.67-1.64) | 25-071, 25-070, 25-065, 25-063, 25-062
.620 | L/O Shell, B&C Holes | 4.8 | high | ratio=0.79 (0.50-1.00) | 25-071, 25-070, 25-065, 25-063
.630 | Install Internal Parts | 24.5 | high | ratio=0.68 (0.20-0.72) | 25-071, 25-070, 25-065, 25-063, 25-062
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.640 | Fit Top to Shell | 7 | high | ratio=1.40 (0.80-2.20) | 25-071, 25-070, 25-065, 25-063, 25-062
.641 | Weld top to shell | 10.5 | high | ratio=0.88 (0.50-1.17) | 25-071, 25-070, 25-065, 25-063, 25-062
.645 | Weld all Outside Seams | 35 | high | ratio=1.75 (1.30-2.02) | 25-071, 25-070, 25-065, 25-063, 25-062
.800 | Move Tank to Detail Rolls | 1 | high | ratio=0.33 (0.33-0.33) | 25-071, 25-070, 25-062
.715 | Install Insul/Vac Rings | 49.8 | high | ratio=1.04 (0.88-1.23) | 25-071, 25-070, 25-065, 25-063, 25-062
.720 | Install Support Parts | 21 | high | ratio=0.66 (0.34-0.78) | 25-071, 25-070, 25-065, 25-063, 25-062
.725 | Set Nozzles in Shell | 9 | high | ratio=1.12 (0.44-2.00) | 25-071, 25-070, 25-065, 25-063, 25-062
.726 | Weld Shell Nozz & M/Ws | 14 | high | ratio=0.47 (0.30-1.03) | 25-071, 25-070, 25-065, 25-063, 25-062
.730 | Add Repads-Weld | 5 | high | ratio=1.00 (0.80-2.20) | 25-071, 25-065, 25-063, 25-062
.765 | Install Name Tag | 1.2 | high | ratio=1.25 (0.50-1.50) | 25-071, 25-065, 25-063, 25-062
.770 | Inspect Tank, Make Repair | 2 | high | ratio=2.00 (2.00-5.00) | 25-071, 25-065, 25-063
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.OI4 | Customer Inspection | 0 | skip | 0h estimate
.OI2 | ASME Inspection Internal | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 1.5 | medium | ratio=0.75 (n=2) | 25-071, 25-062
.910 | Test Tank | 14.8 | high | ratio=1.23 (0.20-1.56) | 25-071, 25-065, 25-063, 25-062
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.OI3 | ASME Inspection Test | 0 | skip | 0h estimate
.802 | Move to Paint Area | 2 | high | ratio=1.00 (0.25-1.50) | 25-071, 25-065, 25-063, 25-062
.QC9 | QC Inspection - Sandblast | 0 | skip | 0h estimate
.QC90 | QC Inspection - Paint | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 6.5 | medium | ratio=2.17 (n=2) | 25-063, 25-062
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 8 | high | ratio=1.60 (1.60-1.60) | 25-065, 25-063, 25-062