## Build Plan w Hours
Job #: | 25-073 | Description: | SS STORAGE TANK #2 |  | Total Est Hours: | 395
Similar jobs used: | 25-072, 23-032, 23-040, 23-045, 23-047
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4 | 3 | high | ratio=0.75 (0.33-1.17)
PRE FAB |  | .105 | Build Nozzles-Weld | 8 | 7.2 | high | ratio=0.90 (0.33-1.10)
PRE FAB |  | .115 | Make Manway Parts | 1 | 1 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1 | 1 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .125 | Roll Manway Neck | 2 | 2 | high | ratio=1.00 (0.75-1.00)
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 2 | 2.5 | high | ratio=1.25 (1.00-2.00)
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 1 | 1 | high | ratio=1.00 (0.67-2.00)
PRE FAB |  | .140 | Build Hatch/Door | 1 | 1.3 | medium | ratio=1.33 (n=2)
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 28 | 33.6 | high | ratio=1.20 (0.80-1.32)
PRE FAB |  | .156 | Clean & Prep Parts | 16 | 3.5 | medium | ratio=0.22 (n=1)
Supports
PRE FAB |  | .165 | Build Supports | 8 | 7.4 | high | ratio=0.93 (0.25-1.17)
PRE FAB |  | .170 | Roll Repads-Drill & Tap | 2 | 2 | high | ratio=1.00 (1.00-2.00)
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 2 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .205 | Roll Rim Angle | 2 | 2 | medium | ratio=1.00 (n=2)
Shells
INSPECTION |  | .QC3 | UT Shells |  |  | skip | 0h estimate
PRE FAB |  | .305 | BI, SQ, T&C Shells | 36 | 28.5 | high | ratio=0.79 (0.61-1.80)
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 24 | 24 | high | ratio=1.00 (0.62-1.33)
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 11 | 14.3 | medium | ratio=1.30 (n=2)
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | skip | 0h estimate
PRE FAB |  | .355 | L/O Top, B&C Holes | 2 | 3.6 | high | ratio=1.78 (1.00-2.50)
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2 | 2 | high | ratio=1.00 (0.50-4.38)
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6 | 9.6 | high | ratio=1.60 (1.00-1.98)
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 7 | 7.7 | high | ratio=1.10 (0.89-1.32)
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 14 | 19 | high | ratio=1.36 (0.93-1.71)
FIT |  | .605 | Tack Shell Courses | 14 | 20.6 | high | ratio=1.47 (1.19-1.56)
FIT |  | .610 | Weld Inside Round Seams | 14 | 15.1 | high | ratio=1.08 (0.50-1.67)
FIT |  | .615 | Install Rim Angle | 12 | 8.8 | medium | ratio=0.73 (n=2)
FIT |  | .616 | Weld Rim Angle | 12 | 14.7 | medium | ratio=1.23 (n=2)
FIT |  | .620 | L/O Shell, B&C Holes | 2 | 3.8 | medium | ratio=1.88 (n=2)
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
FIT |  | .640 | Fit Top to Shell | 9 | 13 | high | ratio=1.44 (1.00-2.50)
FIT |  | .645 | Weld all Outside Seams | 14 | 19.7 | high | ratio=1.41 (0.80-2.25)
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3 | 10.5 | high | ratio=3.50 (0.92-5.00)
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 21 | 20 | high | ratio=0.95 (0.73-1.30)
FIT |  | .717 | Install Lift Lugs on Shl | 5 | 4.5 | high | ratio=0.90 (0.80-1.00)
FIT |  | .720 | Install Support Parts | 15 | 10 | high | ratio=0.67 (0.50-0.97)
FIT |  | .725 | Set Nozzles in Shell | 6 | 5.2 | high | ratio=0.88 (0.42-1.25)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 12 | 9.4 | high | ratio=0.78 (0.58-1.75)
FINISHING |  | .765 | Install Name Tag | 1 | 1 | high | ratio=1.00 (1.00-1.50)
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 2.5 | high | ratio=2.50 (1.00-5.00)
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 3 | 6.8 | high | ratio=2.25 (0.50-4.00)
FINISHING |  | .910 | Test Tank | 14 | 16.3 | high | ratio=1.17 (0.64-1.28)
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
FINISHING |  | .920 | Clean Tank Complete | 48 | 64 | high | ratio=1.33 (0.31-1.88)
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 4 | 9.4 | high | ratio=2.34 (1.33-3.67)
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 5 | 9.8 | high | ratio=1.96 (0.75-3.20)
|  |  | Total Predicted Hours |  | 443.3

## Build Plan - No Hours
Job #: | 25-073 | Description: | SS STORAGE TANK #2 |  | Total Est Hours: | 395
Similar jobs used: | 25-072, 23-032, 23-040, 23-045, 23-047
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4
PRE FAB |  | .105 | Build Nozzles-Weld | 8
PRE FAB |  | .115 | Make Manway Parts | 1
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1
PRE FAB |  | .125 | Roll Manway Neck | 2
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 2
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 1
PRE FAB |  | .140 | Build Hatch/Door | 1
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 28
PRE FAB |  | .156 | Clean & Prep Parts | 16
Supports
PRE FAB |  | .165 | Build Supports | 8
PRE FAB |  | .170 | Roll Repads-Drill & Tap | 2
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .205 | Roll Rim Angle | 2
Shells
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 36
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 24
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 11
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 2
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 7
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 14
FIT |  | .605 | Tack Shell Courses | 14
FIT |  | .610 | Weld Inside Round Seams | 14
FIT |  | .615 | Install Rim Angle | 12
FIT |  | .616 | Weld Rim Angle | 12
FIT |  | .620 | L/O Shell, B&C Holes | 2
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 9
FIT |  | .645 | Weld all Outside Seams | 14
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 21
FIT |  | .717 | Install Lift Lugs on Shl | 5
FIT |  | .720 | Install Support Parts | 15
FIT |  | .725 | Set Nozzles in Shell | 6
FIT |  | .726 | Weld Shell Nozz & M/Ws | 12
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 3
FINISHING |  | .910 | Test Tank | 14
INSPECTION |  | .QC7 | QC Inspection - Test
FINISHING |  | .920 | Clean Tank Complete | 48
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 4
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 5
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-072
23-032
23-040
23-045
23-047
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 3 | high | ratio=0.75 (0.33-1.17) | 25-072, 23-047, 23-045, 23-032
.105 | Build Nozzles-Weld | 7.2 | high | ratio=0.90 (0.33-1.10) | 25-072, 23-047, 23-045, 23-040, 23-032
.115 | Make Manway Parts | 1 | high | ratio=1.00 (1.00-1.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.120 | Brn MW Neck, Clean, Bevel | 1 | high | ratio=1.00 (1.00-1.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.125 | Roll Manway Neck | 2 | high | ratio=1.00 (0.75-1.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.130 | S/U Weld MW Flg, Neck Sem | 2.5 | high | ratio=1.25 (1.00-2.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.135 | Bld Davit Arm Aby Cover | 1 | high | ratio=1.00 (0.67-2.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.140 | Build Hatch/Door | 1.3 | medium | ratio=1.33 (n=2) | 25-072, 23-040
.155 | Cut Parts on Burn Table | 33.6 | high | ratio=1.20 (0.80-1.32) | 25-072, 23-047, 23-045, 23-040, 23-032
.156 | Clean & Prep Parts | 3.5 | medium | ratio=0.22 (n=1) | 25-072
.165 | Build Supports | 7.4 | high | ratio=0.93 (0.25-1.17) | 25-072, 23-047, 23-045, 23-040, 23-032
.170 | Roll Repads-Drill & Tap | 2 | high | ratio=1.00 (1.00-2.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.200 | Bld Lift Lugs, Grd Lugs | 2 | high | ratio=1.00 (1.00-1.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.205 | Roll Rim Angle | 2 | medium | ratio=1.00 (n=2) | 25-072, 23-040
.QC3 | UT Shells | 0 | skip | 0h estimate
.305 | BI, SQ, T&C Shells | 28.5 | high | ratio=0.79 (0.61-1.80) | 25-072, 23-047, 23-045, 23-040, 23-032
.315 | Roll Shell, Tack-Weld I/S | 24 | high | ratio=1.00 (0.62-1.33) | 25-072, 23-047, 23-045, 23-040, 23-032
.350 | Build Top Head/Cone | 14.3 | medium | ratio=1.30 (n=2) | 25-072, 23-040
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.355 | L/O Top, B&C Holes | 3.6 | high | ratio=1.78 (1.00-2.50) | 25-072, 23-047, 23-045, 23-040, 23-032
.365 | Set Nozzles & Lugs - Top | 2 | high | ratio=1.00 (0.50-4.38) | 25-072, 23-047, 23-045, 23-040, 23-032
.366 | Weld Nozzles - Top Head | 9.6 | high | ratio=1.60 (1.00-1.98) | 25-072, 23-047, 23-045, 23-040, 23-032
.450 | Build Bottom Head/Cone | 7.7 | high | ratio=1.10 (0.89-1.32) | 25-072, 23-047, 23-045, 23-040
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.600 | Fit Bottom Head to Shell | 19 | high | ratio=1.36 (0.93-1.71) | 25-072, 23-047, 23-045, 23-040, 23-032
.605 | Tack Shell Courses | 20.6 | high | ratio=1.47 (1.19-1.56) | 25-072, 23-047, 23-045, 23-040
.610 | Weld Inside Round Seams | 15.1 | high | ratio=1.08 (0.50-1.67) | 25-072, 23-047, 23-045, 23-040
.615 | Install Rim Angle | 8.8 | medium | ratio=0.73 (n=2) | 25-072, 23-040
.616 | Weld Rim Angle | 14.7 | medium | ratio=1.23 (n=2) | 25-072, 23-040
.620 | L/O Shell, B&C Holes | 3.8 | medium | ratio=1.88 (n=2) | 23-047, 23-040
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.640 | Fit Top to Shell | 13 | high | ratio=1.44 (1.00-2.50) | 25-072, 23-047, 23-045, 23-040, 23-032
.645 | Weld all Outside Seams | 19.7 | high | ratio=1.41 (0.80-2.25) | 25-072, 23-047, 23-045, 23-040, 23-032
.800 | Move Tank to Detail Rolls | 10.5 | high | ratio=3.50 (0.92-5.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.715 | Install Insul/Vac Rings | 20 | high | ratio=0.95 (0.73-1.30) | 25-072, 23-047, 23-045, 23-040
.717 | Install Lift Lugs on Shl | 4.5 | high | ratio=0.90 (0.80-1.00) | 25-072, 23-040, 23-032
.720 | Install Support Parts | 10 | high | ratio=0.67 (0.50-0.97) | 25-072, 23-047, 23-045, 23-040, 23-032
.725 | Set Nozzles in Shell | 5.2 | high | ratio=0.88 (0.42-1.25) | 25-072, 23-047, 23-045, 23-040, 23-032
.726 | Weld Shell Nozz & M/Ws | 9.4 | high | ratio=0.78 (0.58-1.75) | 25-072, 23-047, 23-045, 23-040, 23-032
.765 | Install Name Tag | 1 | high | ratio=1.00 (1.00-1.50) | 25-072, 23-047, 23-045, 23-040, 23-032
.770 | Inspect Tank, Make Repair | 2.5 | high | ratio=2.50 (1.00-5.00) | 25-072, 23-045, 23-040, 23-032
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 6.8 | high | ratio=2.25 (0.50-4.00) | 25-072, 23-047, 23-045, 23-040, 23-032
.910 | Test Tank | 16.3 | high | ratio=1.17 (0.64-1.28) | 25-072, 23-047, 23-045, 23-040, 23-032
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.920 | Clean Tank Complete | 64 | high | ratio=1.33 (0.31-1.88) | 25-072, 23-047, 23-045, 23-040, 23-032
.QC8 | QC Inspection - Clean | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 9.4 | high | ratio=2.34 (1.33-3.67) | 25-072, 23-047, 23-045, 23-032
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 9.8 | high | ratio=1.96 (0.75-3.20) | 25-072, 23-047, 23-045, 23-032