## Build Plan w Hours
Job #: | 25-076 | Description: | GLUE CONTAINMENT DROPLET SEAL POT |  | Total Est Hours: | 38
Similar jobs used: | 23-057, 23-059, 25-010, 23-061, 23-058
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 1 | 1 | high | ratio=1.00 (0.50-1.33)
PRE FAB |  | .105 | Build Nozzles-Weld | 2 | 2 | high | ratio=1.00 (0.71-1.50)
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 2 | 1.6 | high | ratio=0.80 (0.62-1.21)
PRE FAB |  | .156 | Clean & Prep Parts | 1 | 1 | low | wc_ratio=1.00
Supports
PRE FAB |  | .165 | Build Supports | 2 | 2 | high | ratio=1.00 (1.00-1.10)
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1 | 1 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .261 | Misc Fabrication | 2 | 2 | medium | ratio=1.00 (n=1)
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | skip | 0h estimate
FIT |  | .605 | Tack Shell Courses | 3 | 3 | low | wc_ratio=1.00
FIT |  | .610 | Weld Inside Round Seams | 2 | 2 | low | wc_ratio=1.00
FIT |  | .620 | L/O Shell, B&C Holes | 1 | 1 | high | ratio=1.00 (0.50-1.00)
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
FIT |  | .645 | Weld all Outside Seams | 2 | 2.3 | high | ratio=1.17 (1.00-1.17)
Install Nozzles and Externals
FIT |  | .717 | Install Lift Lugs on Shl | 1 | 0.8 | high | ratio=0.83 (0.50-1.00)
FIT |  | .720 | Install Support Parts | 1 | 0.7 | high | ratio=0.69 (0.44-1.25)
FIT |  | .725 | Set Nozzles in Shell | 2 | 1.8 | high | ratio=0.88 (0.75-1.67)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 3 | 2.4 | high | ratio=0.79 (0.61-1.06)
INSPECTION |  | .QC51 | UT Components |  |  | skip | 0h estimate
FINISHING |  | .765 | Install Name Tag | 1 | 1 | high | ratio=1.00 (0.50-2.00)
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1 | low | wc_ratio=1.00
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
INSPECTION |  | .OI4 | Customer Inspection |  |  | skip | 0h estimate
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1 | 3 | high | ratio=3.00 (0.50-5.00)
FINISHING |  | .910 | Test Tank | 2 | 1.5 | high | ratio=0.75 (0.50-1.71)
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | skip | 0h estimate
FINISHING |  | .920 | Clean Tank Complete | 5 | 5 | high | ratio=1.00 (1.00-1.25)
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | skip | 0h estimate
INSPECTION |  | .QC9 | QC Inspection - Sandblast |  |  | skip | 0h estimate
INSPECTION |  | .QC90 | QC Inspection - Paint |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1 | 3 | high | ratio=3.00 (2.00-4.00)
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 1 | 2.5 | high | ratio=2.50 (1.50-4.00)
|  |  | Total Predicted Hours |  | 41.6

## Build Plan - No Hours
Job #: | 25-076 | Description: | GLUE CONTAINMENT DROPLET SEAL POT |  | Total Est Hours: | 38
Similar jobs used: | 23-057, 23-059, 25-010, 23-061, 23-058
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 1
PRE FAB |  | .105 | Build Nozzles-Weld | 2
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 2
PRE FAB |  | .156 | Clean & Prep Parts | 1
Supports
PRE FAB |  | .165 | Build Supports | 2
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1
PRE FAB |  | .261 | Misc Fabrication | 2
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .605 | Tack Shell Courses | 3
FIT |  | .610 | Weld Inside Round Seams | 2
FIT |  | .620 | L/O Shell, B&C Holes | 1
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .645 | Weld all Outside Seams | 2
Install Nozzles and Externals
FIT |  | .717 | Install Lift Lugs on Shl | 1
FIT |  | .720 | Install Support Parts | 1
FIT |  | .725 | Set Nozzles in Shell | 2
FIT |  | .726 | Weld Shell Nozz & M/Ws | 3
INSPECTION |  | .QC51 | UT Components
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI4 | Customer Inspection
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1
FINISHING |  | .910 | Test Tank | 2
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 5
INSPECTION |  | .QC8 | QC Inspection - Clean
INSPECTION |  | .QC9 | QC Inspection - Sandblast
INSPECTION |  | .QC90 | QC Inspection - Paint
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 1
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
23-057
23-059
25-010
23-061
23-058
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 1 | high | ratio=1.00 (0.50-1.33) | 25-010, 23-061, 23-059, 23-058, 23-057
.105 | Build Nozzles-Weld | 2 | high | ratio=1.00 (0.71-1.50) | 25-010, 23-061, 23-059, 23-058, 23-057
.155 | Cut Parts on Burn Table | 1.6 | high | ratio=0.80 (0.62-1.21) | 25-010, 23-061, 23-059, 23-058, 23-057
.156 | Clean & Prep Parts | 1 | low | wc_ratio=1.00 | wc_avg
.165 | Build Supports | 2 | high | ratio=1.00 (1.00-1.10) | 23-061, 23-059, 23-058, 23-057
.200 | Bld Lift Lugs, Grd Lugs | 1 | high | ratio=1.00 (1.00-1.00) | 23-061, 23-059, 23-058, 23-057
.261 | Misc Fabrication | 2 | medium | ratio=1.00 (n=1) | 23-061
.OI1 | ASME Hold Point | 0 | skip | 0h estimate
.605 | Tack Shell Courses | 3 | low | wc_ratio=1.00 | wc_avg
.610 | Weld Inside Round Seams | 2 | low | wc_ratio=1.00 | wc_avg
.620 | L/O Shell, B&C Holes | 1 | high | ratio=1.00 (0.50-1.00) | 23-059, 23-058, 23-057
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.645 | Weld all Outside Seams | 2.3 | high | ratio=1.17 (1.00-1.17) | 23-061, 23-059, 23-058
.717 | Install Lift Lugs on Shl | 0.8 | high | ratio=0.83 (0.50-1.00) | 25-010, 23-059, 23-058, 23-057
.720 | Install Support Parts | 0.7 | high | ratio=0.69 (0.44-1.25) | 23-061, 23-059, 23-058, 23-057
.725 | Set Nozzles in Shell | 1.8 | high | ratio=0.88 (0.75-1.67) | 25-010, 23-061, 23-059, 23-058, 23-057
.726 | Weld Shell Nozz & M/Ws | 2.4 | high | ratio=0.79 (0.61-1.06) | 25-010, 23-061, 23-059, 23-058, 23-057
.QC51 | UT Components | 0 | skip | 0h estimate
.765 | Install Name Tag | 1 | high | ratio=1.00 (0.50-2.00) | 25-010, 23-061, 23-059, 23-058, 23-057
.770 | Inspect Tank, Make Repair | 1 | low | wc_ratio=1.00 | wc_avg
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.OI4 | Customer Inspection | 0 | skip | 0h estimate
.OI2 | ASME Inspection Internal | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 3 | high | ratio=3.00 (0.50-5.00) | 23-061, 23-059, 23-058, 23-057
.910 | Test Tank | 1.5 | high | ratio=0.75 (0.50-1.71) | 25-010, 23-061, 23-059, 23-058, 23-057
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.OI3 | ASME Inspection Test | 0 | skip | 0h estimate
.920 | Clean Tank Complete | 5 | high | ratio=1.00 (1.00-1.25) | 25-010, 23-061, 23-059, 23-058, 23-057
.QC8 | QC Inspection - Clean | 0 | skip | 0h estimate
.QC9 | QC Inspection - Sandblast | 0 | skip | 0h estimate
.QC90 | QC Inspection - Paint | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 3 | high | ratio=3.00 (2.00-4.00) | 25-010, 23-061, 23-059, 23-058, 23-057
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 2.5 | high | ratio=2.50 (1.50-4.00) | 25-010, 23-061, 23-059, 23-058, 23-057