## Build Plan w Hours
Job #: | 25-077 | Description: | R-301 DMN CSTR |  | Total Est Hours: | 141
Similar jobs used: | 23-055, 25-083, 25-055, 23-029, 25-042
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12 | 12 | high | ratio=1.00 (0.67-2.20)
PRE FAB |  | .105 | Build Nozzles-Weld | 12 | 9.3 | high | ratio=0.78 (0.42-2.31)
PRE FAB |  | .107 | Build Repads for Nozzles | 1 | 1 | high | ratio=1.00 (0.40-1.50)
PRE FAB |  | .110 | Build Dip Tubes-Weld | 2 | 1.5 | medium | ratio=0.75 (n=1)
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 6 | 6.2 | high | ratio=1.04 (0.60-2.44)
PRE FAB |  | .156 | Clean & Prep Parts | 2 | 1.8 | high | ratio=0.92 (0.50-1.55)
Supports
PRE FAB |  | .165 | Build Supports | 6 | 6 | high | ratio=1.00 (0.58-1.38)
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 2 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .230 | Build Baffles-Weld | 3 | 3 | medium | ratio=1.00 (n=1)
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | skip | 0h estimate
PRE FAB |  | .355 | L/O Top, B&C Holes | 2 | 2.3 | high | ratio=1.14 (0.88-5.00)
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2 | 1.8 | high | ratio=0.92 (0.64-1.83)
PRE FAB |  | .366 | Weld Nozzles - Top Head | 5 | 1.5 | high | ratio=0.31 (0.25-1.05)
PRE FAB |  | .370 | I&W Repads -Top | 4 | 2.8 | medium | ratio=0.69 (n=2)
FIT |  | .382 | Install Body Flange - Top | 1 | 1 | low | wc_ratio=1.00
FIT |  | .383 | Weld Body Flg-Top W/C | 3 | 3 | low | wc_ratio=1.00
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1 | 1 | high | ratio=1.00 (1.00-1.75)
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 1 | high | ratio=1.00 (1.00-1.50)
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 1 | 1 | high | ratio=1.00 (0.75-1.00)
FIT |  | .477 | Cut & Fit Btm Jacket | 3 | 2.5 | high | ratio=0.83 (0.78-1.50)
FIT |  | .478 | Weld Jacket to Bottom | 5 | 4.5 | high | ratio=0.91 (0.58-2.57)
FIT |  | .479 | Install Jacket Nozzle-Btm | 3 | 1.6 | medium | ratio=0.55 (n=2)
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | skip | 0h estimate
FIT |  | .600 | Fit Bottom Head to Shell | 4 | 3.2 | high | ratio=0.81 (0.57-0.92)
FIT |  | .620 | L/O Shell, B&C Holes | 5 | 5 | medium | ratio=1.00 (n=1)
FIT |  | .625 | Install Baffles-Weld | 3 | 4.8 | medium | ratio=1.58 (n=1)
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
FIT |  | .640 | Fit Top to Shell | 1 | 1.2 | high | ratio=1.25 (1.00-2.50)
FIT |  | .641 | Weld top to shell | 3 | 1.3 | high | ratio=0.44 (0.42-0.50)
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1 | 2.8 | high | ratio=2.75 (2.38-3.00)
Install Nozzles and Externals
FIT |  | .700 | Fit Jacket to Shell | 4 | 2.6 | medium | ratio=0.65 (n=2)
FIT |  | .705 | Weld Jacket to Shell | 5 | 10.8 | medium | ratio=2.15 (n=2)
FIT |  | .710 | Install Jacket Nozzles | 2 | 1.5 | medium | ratio=0.75 (n=2)
FIT |  | .711 | Weld Jacket Nozzles | 2 | 1.2 | medium | ratio=0.59 (n=2)
FIT |  | .715 | Install Insul/Vac Rings | 5 | 7.3 | medium | ratio=1.47 (n=2)
FIT |  | .720 | Install Support Parts | 5 | 4.6 | high | ratio=0.93 (0.62-1.44)
FIT |  | .725 | Set Nozzles in Shell | 3 | 4.5 | high | ratio=1.50 (1.33-1.50)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 5 | 5 | high | ratio=1.00 (0.20-1.00)
FINISHING |  | .765 | Install Name Tag | 1 | 1 | medium | ratio=1.00 (n=2)
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1 | medium | ratio=1.00 (n=1)
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1 | 1.5 | high | ratio=1.50 (1.00-2.25)
FINISHING |  | .910 | Test Tank | 6 | 6.3 | high | ratio=1.05 (0.77-1.71)
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | skip | 0h estimate
FINISHING |  | .920 | Clean Tank Complete | 5 | 4 | high | ratio=0.80 (0.25-1.00)
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1 | 3 | high | ratio=3.00 (2.00-4.00)
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 1 | 1.2 | high | ratio=1.25 (0.83-1.50)
|  |  | Total Predicted Hours |  | 140.6

## Build Plan - No Hours
Job #: | 25-077 | Description: | R-301 DMN CSTR |  | Total Est Hours: | 141
Similar jobs used: | 23-055, 25-083, 25-055, 23-029, 25-042
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12
PRE FAB |  | .105 | Build Nozzles-Weld | 12
PRE FAB |  | .107 | Build Repads for Nozzles | 1
PRE FAB |  | .110 | Build Dip Tubes-Weld | 2
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 6
PRE FAB |  | .156 | Clean & Prep Parts | 2
Supports
PRE FAB |  | .165 | Build Supports | 6
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .230 | Build Baffles-Weld | 3
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 2
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2
PRE FAB |  | .366 | Weld Nozzles - Top Head | 5
PRE FAB |  | .370 | I&W Repads -Top | 4
FIT |  | .382 | Install Body Flange - Top | 1
FIT |  | .383 | Weld Body Flg-Top W/C | 3
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 1
FIT |  | .477 | Cut & Fit Btm Jacket | 3
FIT |  | .478 | Weld Jacket to Bottom | 5
FIT |  | .479 | Install Jacket Nozzle-Btm | 3
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 4
FIT |  | .620 | L/O Shell, B&C Holes | 5
FIT |  | .625 | Install Baffles-Weld | 3
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 1
FIT |  | .641 | Weld top to shell | 3
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1
Install Nozzles and Externals
FIT |  | .700 | Fit Jacket to Shell | 4
FIT |  | .705 | Weld Jacket to Shell | 5
FIT |  | .710 | Install Jacket Nozzles | 2
FIT |  | .711 | Weld Jacket Nozzles | 2
FIT |  | .715 | Install Insul/Vac Rings | 5
FIT |  | .720 | Install Support Parts | 5
FIT |  | .725 | Set Nozzles in Shell | 3
FIT |  | .726 | Weld Shell Nozz & M/Ws | 5
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1
FINISHING |  | .910 | Test Tank | 6
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 5
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 1
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
23-055
25-083
25-055
23-029
25-042
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 12 | high | ratio=1.00 (0.67-2.20) | 25-083, 25-055, 25-042, 23-055, 23-029
.105 | Build Nozzles-Weld | 9.3 | high | ratio=0.78 (0.42-2.31) | 25-083, 25-055, 25-042, 23-055, 23-029
.107 | Build Repads for Nozzles | 1 | high | ratio=1.00 (0.40-1.50) | 25-083, 25-055, 23-055, 23-029
.110 | Build Dip Tubes-Weld | 1.5 | medium | ratio=0.75 (n=1) | 25-083
.155 | Cut Parts on Burn Table | 6.2 | high | ratio=1.04 (0.60-2.44) | 25-083, 25-055, 25-042, 23-055, 23-029
.156 | Clean & Prep Parts | 1.8 | high | ratio=0.92 (0.50-1.55) | 25-083, 25-055, 25-042
.165 | Build Supports | 6 | high | ratio=1.00 (0.58-1.38) | 25-083, 25-055, 25-042, 23-055, 23-029
.200 | Bld Lift Lugs, Grd Lugs | 2 | high | ratio=1.00 (1.00-1.00) | 25-083, 25-055, 25-042, 23-055, 23-029
.230 | Build Baffles-Weld | 3 | medium | ratio=1.00 (n=1) | 23-055
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.355 | L/O Top, B&C Holes | 2.3 | high | ratio=1.14 (0.88-5.00) | 25-083, 25-055, 25-042, 23-055, 23-029
.365 | Set Nozzles & Lugs - Top | 1.8 | high | ratio=0.92 (0.64-1.83) | 25-083, 25-042, 23-055, 23-029
.366 | Weld Nozzles - Top Head | 1.5 | high | ratio=0.31 (0.25-1.05) | 25-083, 25-055, 25-042, 23-055, 23-029
.370 | I&W Repads -Top | 2.8 | medium | ratio=0.69 (n=2) | 25-083, 23-055
.382 | Install Body Flange - Top | 1 | low | wc_ratio=1.00 | wc_avg
.383 | Weld Body Flg-Top W/C | 3 | low | wc_ratio=1.00 | wc_avg
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.455 | L/O Bottom, B&C Holes | 1 | high | ratio=1.00 (1.00-1.75) | 25-083, 25-042, 23-029
.465 | Set Nozzles - Bottom Head | 1 | high | ratio=1.00 (1.00-1.50) | 25-083, 25-042, 23-055, 23-029
.466 | Weld Nozzles - Bot. Head | 1 | high | ratio=1.00 (0.75-1.00) | 25-083, 25-042, 23-055, 23-029
.477 | Cut & Fit Btm Jacket | 2.5 | high | ratio=0.83 (0.78-1.50) | 25-083, 23-055, 23-029
.478 | Weld Jacket to Bottom | 4.5 | high | ratio=0.91 (0.58-2.57) | 25-083, 23-055, 23-029
.479 | Install Jacket Nozzle-Btm | 1.6 | medium | ratio=0.55 (n=2) | 25-083, 23-029
.OI1 | ASME Hold Point | 0 | skip | 0h estimate
.600 | Fit Bottom Head to Shell | 3.2 | high | ratio=0.81 (0.57-0.92) | 25-083, 25-042, 23-055, 23-029
.620 | L/O Shell, B&C Holes | 5 | medium | ratio=1.00 (n=1) | 23-055
.625 | Install Baffles-Weld | 4.8 | medium | ratio=1.58 (n=1) | 23-055
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.640 | Fit Top to Shell | 1.2 | high | ratio=1.25 (1.00-2.50) | 25-083, 25-042, 23-055, 23-029
.641 | Weld top to shell | 1.3 | high | ratio=0.44 (0.42-0.50) | 25-083, 23-055, 23-029
.800 | Move Tank to Detail Rolls | 2.8 | high | ratio=2.75 (2.38-3.00) | 25-083, 25-042, 23-055, 23-029
.700 | Fit Jacket to Shell | 2.6 | medium | ratio=0.65 (n=2) | 25-083, 23-055
.705 | Weld Jacket to Shell | 10.8 | medium | ratio=2.15 (n=2) | 25-083, 23-055
.710 | Install Jacket Nozzles | 1.5 | medium | ratio=0.75 (n=2) | 25-083, 23-055
.711 | Weld Jacket Nozzles | 1.2 | medium | ratio=0.59 (n=2) | 25-083, 23-055
.715 | Install Insul/Vac Rings | 7.3 | medium | ratio=1.47 (n=2) | 25-083, 23-029
.720 | Install Support Parts | 4.6 | high | ratio=0.93 (0.62-1.44) | 25-083, 25-042, 23-055, 23-029
.725 | Set Nozzles in Shell | 4.5 | high | ratio=1.50 (1.33-1.50) | 25-083, 25-042, 23-029
.726 | Weld Shell Nozz & M/Ws | 5 | high | ratio=1.00 (0.20-1.00) | 25-083, 25-042, 23-029
.765 | Install Name Tag | 1 | medium | ratio=1.00 (n=2) | 25-042, 23-055
.770 | Inspect Tank, Make Repair | 1 | medium | ratio=1.00 (n=1) | 23-029
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.OI2 | ASME Inspection Internal | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 1.5 | high | ratio=1.50 (1.00-2.25) | 25-042, 23-055, 23-029
.910 | Test Tank | 6.3 | high | ratio=1.05 (0.77-1.71) | 25-083, 25-042, 23-055, 23-029
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.OI3 | ASME Inspection Test | 0 | skip | 0h estimate
.920 | Clean Tank Complete | 4 | high | ratio=0.80 (0.25-1.00) | 25-083, 25-042, 23-029
.QC8 | QC Inspection - Clean | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 3 | high | ratio=3.00 (2.00-4.00) | 25-083, 25-042, 23-055, 23-029
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 1.2 | high | ratio=1.25 (0.83-1.50) | 25-083, 23-055, 23-029