## Build Plan w Hours
Job #: | 25-089 | Description: | DISSOLVING TANK |  | Total Est Hours: | 1700
Similar jobs used: | 24-004, 24-005, 23-016, 25-101, 23-015
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 10 | 10.6 | high | ratio=1.06 (0.80-1.57)
PRE FAB |  | .105 | Build Nozzles-Weld | 14 | 26.6 | high | ratio=1.90 (0.80-3.25)
PRE FAB |  | .107 | Build Repads for Nozzles | 12 | 18 | high | ratio=1.50 (0.25-2.00)
PRE FAB |  | .115 | Make Manway Parts | 6 | 6 | high | ratio=1.00 (1.00-2.00)
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2 | 2 | high | ratio=1.00 (0.50-2.00)
PRE FAB |  | .125 | Roll Manway Neck | 4 | 4 | high | ratio=1.00 (0.70-3.50)
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 6 | 10.9 | high | ratio=1.81 (1.50-2.25)
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 5 | 16.2 | high | ratio=3.25 (1.00-4.88)
PRE FAB |  | .145 | Install Cladding on Flng | 10 | 10 | low | wc_ratio=1.00
PRE FAB |  | .147 | Install Clad on Blind/Cov | 20 | 20 | low | wc_ratio=1.00
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 70 | 126 | high | ratio=1.80 (0.88-3.88)
PRE FAB |  | .156 | Clean & Prep Parts | 35 | 22.6 | high | ratio=0.65 (0.40-0.73)
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 4 | 3 | high | ratio=0.75 (0.40-1.00)
PRE FAB |  | .235 | Bld T-B Stiffeners | 65 | 65 | low | wc_ratio=1.00
PRE FAB |  | .252 | Fab Miscellaneous Parts | 48 | 59.3 | high | ratio=1.24 (1.00-2.50)
PRE FAB |  | .261 | Misc Fabrication | 48 | 42 | medium | ratio=0.88 (n=2)
Ladders, Handrails and Platforms
INSPECTION |  | .QC2 | QC Inspection - Pre Sub C |  |  | skip | 0h estimate
Shells
INSPECTION |  | .QC3 | UT Shells |  |  | skip | 0h estimate
PRE FAB |  | .305 | BI, SQ, T&C Shells | 24 | 28.5 | high | ratio=1.19 (1.06-2.60)
PRE FAB |  | .310 | Bevel Shell Plates | 48 | 48 | high | ratio=1.00 (0.39-1.00)
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 40 | 55.6 | high | ratio=1.39 (0.50-3.70)
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 40 | 41 | medium | ratio=1.02 (n=2)
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | skip | 0h estimate
PRE FAB |  | .355 | L/O Top, B&C Holes | 1 | 2.7 | high | ratio=2.69 (0.96-4.50)
PRE FAB |  | .360 | Bevel Top Head | 30 | 36.5 | medium | ratio=1.22 (n=2)
PRE FAB |  | .375 | Install Top Stiffeners | 20 | 13.4 | medium | ratio=0.67 (n=2)
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 20 | 24 | medium | ratio=1.20 (n=2)
PRE FAB |  | .460 | Bevel Bottom Head | 30 | 20 | medium | ratio=0.67 (n=2)
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 100 | 112.7 | high | ratio=1.13 (0.33-2.38)
FIT |  | .605 | Tack Shell Courses | 80 | 122.7 | high | ratio=1.53 (0.53-2.00)
FIT |  | .610 | Weld Inside Round Seams | 50 | 50 | high | ratio=1.00 (0.71-2.57)
FIT |  | .620 | L/O Shell, B&C Holes | 40 | 55 | high | ratio=1.38 (0.67-2.42)
FIT |  | .630 | Install Internal Parts | 60 | 42 | medium | ratio=0.70 (n=2)
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
FIT |  | .640 | Fit Top to Shell | 80 | 147.7 | high | ratio=1.85 (0.80-3.00)
FIT |  | .641 | Weld top to shell | 50 | 52.5 | medium | ratio=1.05 (n=2)
FIT |  | .645 | Weld all Outside Seams | 120 | 150.6 | high | ratio=1.25 (0.57-1.42)
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 60 | 47.4 | medium | ratio=0.79 (n=2)
FIT |  | .720 | Install Support Parts | 28 | 29.1 | high | ratio=1.04 (0.69-1.60)
FIT |  | .725 | Set Nozzles in Shell | 56 | 38 | high | ratio=0.68 (0.53-0.81)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 120 | 72.2 | high | ratio=0.60 (0.24-0.77)
FIT |  | .730 | Add Repads-Weld | 40 | 40 | high | ratio=1.00 (1.00-1.58)
FIT |  | .750 | Fit Handrail, I&W Clips | 60 | 101.2 | medium | ratio=1.69 (n=2)
FINISHING |  | .765 | Install Name Tag | 1 | 1 | medium | ratio=1.00 (n=2)
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1 | high | ratio=1.00 (1.00-5.00)
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
INSPECTION |  | .OI4 | Customer Inspection |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 20 | 28.3 | high | ratio=1.42 (0.65-4.25)
FINISHING |  | .900 | Dye Pen Test | 20 | 24 | low | wc_ratio=1.20
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
FINISHING |  | .920 | Clean Tank Complete | 50 | 91.4 | high | ratio=1.83 (0.35-2.51)
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | skip | 0h estimate
MOVE TANK |  | .802 | Move to Paint Area | 4 | 3.7 | low | wc_ratio=0.92
INSPECTION |  | .QC9 | QC Inspection - Sandblast |  |  | skip | 0h estimate
INSPECTION |  | .QC90 | QC Inspection - Paint |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 10 | 12.2 | high | ratio=1.22 (0.20-1.75)
FINISHING |  | .950 | Check BOM, Pack Parts | 5 | 5 | high | ratio=1.00 (0.80-1.00)
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 25 | 32.5 | high | ratio=1.30 (0.73-1.75)
SHIPPING |  | .971 | Take Parts - Machine Shop | 4 | 3.6 | low | wc_ratio=0.91
SHIPPING |  | .973 | P/U Parts - Machine Shop | 4 | 3.6 | low | wc_ratio=0.91
|  |  | Total Predicted Hours |  | 1979.3

## Build Plan - No Hours
Job #: | 25-089 | Description: | DISSOLVING TANK |  | Total Est Hours: | 1700
Similar jobs used: | 24-004, 24-005, 23-016, 25-101, 23-015
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 10
PRE FAB |  | .105 | Build Nozzles-Weld | 14
PRE FAB |  | .107 | Build Repads for Nozzles | 12
PRE FAB |  | .115 | Make Manway Parts | 6
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2
PRE FAB |  | .125 | Roll Manway Neck | 4
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 6
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 5
PRE FAB |  | .145 | Install Cladding on Flng | 10
PRE FAB |  | .147 | Install Clad on Blind/Cov | 20
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 70
PRE FAB |  | .156 | Clean & Prep Parts | 35
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 4
PRE FAB |  | .235 | Bld T-B Stiffeners | 65
PRE FAB |  | .252 | Fab Miscellaneous Parts | 48
PRE FAB |  | .261 | Misc Fabrication | 48
Ladders, Handrails and Platforms
INSPECTION |  | .QC2 | QC Inspection - Pre Sub C
Shells
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 24
PRE FAB |  | .310 | Bevel Shell Plates | 48
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 40
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 40
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 1
PRE FAB |  | .360 | Bevel Top Head | 30
PRE FAB |  | .375 | Install Top Stiffeners | 20
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 20
PRE FAB |  | .460 | Bevel Bottom Head | 30
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 100
FIT |  | .605 | Tack Shell Courses | 80
FIT |  | .610 | Weld Inside Round Seams | 50
FIT |  | .620 | L/O Shell, B&C Holes | 40
FIT |  | .630 | Install Internal Parts | 60
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 80
FIT |  | .641 | Weld top to shell | 50
FIT |  | .645 | Weld all Outside Seams | 120
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 60
FIT |  | .720 | Install Support Parts | 28
FIT |  | .725 | Set Nozzles in Shell | 56
FIT |  | .726 | Weld Shell Nozz & M/Ws | 120
FIT |  | .730 | Add Repads-Weld | 40
FIT |  | .750 | Fit Handrail, I&W Clips | 60
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI4 | Customer Inspection
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 20
FINISHING |  | .900 | Dye Pen Test | 20
INSPECTION |  | .QC7 | QC Inspection - Test
FINISHING |  | .920 | Clean Tank Complete | 50
INSPECTION |  | .QC8 | QC Inspection - Clean
MOVE TANK |  | .802 | Move to Paint Area | 4
INSPECTION |  | .QC9 | QC Inspection - Sandblast
INSPECTION |  | .QC90 | QC Inspection - Paint
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 10
FINISHING |  | .950 | Check BOM, Pack Parts | 5
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 25
SHIPPING |  | .971 | Take Parts - Machine Shop | 4
SHIPPING |  | .973 | P/U Parts - Machine Shop | 4
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
24-004
24-005
23-016
25-101
23-015
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 10.6 | high | ratio=1.06 (0.80-1.57) | 25-101, 24-005, 24-004, 23-016, 23-015
.105 | Build Nozzles-Weld | 26.6 | high | ratio=1.90 (0.80-3.25) | 25-101, 24-005, 24-004, 23-016, 23-015
.107 | Build Repads for Nozzles | 18 | high | ratio=1.50 (0.25-2.00) | 25-101, 24-005, 24-004, 23-016, 23-015
.115 | Make Manway Parts | 6 | high | ratio=1.00 (1.00-2.00) | 25-101, 24-005, 24-004, 23-016, 23-015
.120 | Brn MW Neck, Clean, Bevel | 2 | high | ratio=1.00 (0.50-2.00) | 25-101, 24-005, 24-004, 23-016, 23-015
.125 | Roll Manway Neck | 4 | high | ratio=1.00 (0.70-3.50) | 25-101, 24-005, 24-004, 23-016, 23-015
.130 | S/U Weld MW Flg, Neck Sem | 10.9 | high | ratio=1.81 (1.50-2.25) | 25-101, 24-005, 24-004, 23-016, 23-015
.135 | Bld Davit Arm Aby Cover | 16.2 | high | ratio=3.25 (1.00-4.88) | 25-101, 24-005, 24-004, 23-016, 23-015
.145 | Install Cladding on Flng | 10 | low | wc_ratio=1.00 | wc_avg
.147 | Install Clad on Blind/Cov | 20 | low | wc_ratio=1.00 | wc_avg
.155 | Cut Parts on Burn Table | 126 | high | ratio=1.80 (0.88-3.88) | 25-101, 24-005, 24-004, 23-016, 23-015
.156 | Clean & Prep Parts | 22.6 | high | ratio=0.65 (0.40-0.73) | 25-101, 24-005, 24-004
.200 | Bld Lift Lugs, Grd Lugs | 3 | high | ratio=0.75 (0.40-1.00) | 24-005, 24-004, 23-016, 23-015
.235 | Bld T-B Stiffeners | 65 | low | wc_ratio=1.00 | wc_avg
.252 | Fab Miscellaneous Parts | 59.3 | high | ratio=1.24 (1.00-2.50) | 25-101, 24-005, 23-016, 23-015
.261 | Misc Fabrication | 42 | medium | ratio=0.88 (n=2) | 24-005, 23-015
.QC2 | QC Inspection - Pre Sub C | 0 | skip | 0h estimate
.QC3 | UT Shells | 0 | skip | 0h estimate
.305 | BI, SQ, T&C Shells | 28.5 | high | ratio=1.19 (1.06-2.60) | 25-101, 24-005, 24-004, 23-016, 23-015
.310 | Bevel Shell Plates | 48 | high | ratio=1.00 (0.39-1.00) | 25-101, 24-005, 23-016
.315 | Roll Shell, Tack-Weld I/S | 55.6 | high | ratio=1.39 (0.50-3.70) | 25-101, 24-005, 24-004, 23-016, 23-015
.350 | Build Top Head/Cone | 41 | medium | ratio=1.02 (n=2) | 24-004, 23-015
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.355 | L/O Top, B&C Holes | 2.7 | high | ratio=2.69 (0.96-4.50) | 24-005, 24-004, 23-016, 23-015
.360 | Bevel Top Head | 36.5 | medium | ratio=1.22 (n=2) | 24-005, 24-004
.375 | Install Top Stiffeners | 13.4 | medium | ratio=0.67 (n=2) | 24-004, 23-016
.450 | Build Bottom Head/Cone | 24 | medium | ratio=1.20 (n=2) | 24-004, 23-015
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.460 | Bevel Bottom Head | 20 | medium | ratio=0.67 (n=2) | 25-101, 24-005
.600 | Fit Bottom Head to Shell | 112.7 | high | ratio=1.13 (0.33-2.38) | 24-005, 24-004, 23-016, 23-015
.605 | Tack Shell Courses | 122.7 | high | ratio=1.53 (0.53-2.00) | 24-005, 24-004, 23-016, 23-015
.610 | Weld Inside Round Seams | 50 | high | ratio=1.00 (0.71-2.57) | 24-005, 24-004, 23-016, 23-015
.620 | L/O Shell, B&C Holes | 55 | high | ratio=1.38 (0.67-2.42) | 24-005, 24-004, 23-016, 23-015
.630 | Install Internal Parts | 42 | medium | ratio=0.70 (n=2) | 25-101, 23-016
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.640 | Fit Top to Shell | 147.7 | high | ratio=1.85 (0.80-3.00) | 24-005, 24-004, 23-016, 23-015
.641 | Weld top to shell | 52.5 | medium | ratio=1.05 (n=2) | 24-005, 23-016
.645 | Weld all Outside Seams | 150.6 | high | ratio=1.25 (0.57-1.42) | 24-005, 24-004, 23-016, 23-015
.715 | Install Insul/Vac Rings | 47.4 | medium | ratio=0.79 (n=2) | 23-016, 23-015
.720 | Install Support Parts | 29.1 | high | ratio=1.04 (0.69-1.60) | 24-005, 24-004, 23-016, 23-015
.725 | Set Nozzles in Shell | 38 | high | ratio=0.68 (0.53-0.81) | 24-005, 24-004, 23-016, 23-015
.726 | Weld Shell Nozz & M/Ws | 72.2 | high | ratio=0.60 (0.24-0.77) | 24-005, 24-004, 23-016, 23-015
.730 | Add Repads-Weld | 40 | high | ratio=1.00 (1.00-1.58) | 24-005, 24-004, 23-016, 23-015
.750 | Fit Handrail, I&W Clips | 101.2 | medium | ratio=1.69 (n=2) | 24-005, 23-015
.765 | Install Name Tag | 1 | medium | ratio=1.00 (n=2) | 24-004, 23-015
.770 | Inspect Tank, Make Repair | 1 | high | ratio=1.00 (1.00-5.00) | 24-005, 24-004, 23-016, 23-015
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.OI4 | Customer Inspection | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 28.3 | high | ratio=1.42 (0.65-4.25) | 24-005, 24-004, 23-016, 23-015
.900 | Dye Pen Test | 24 | low | wc_ratio=1.20 | wc_avg
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.920 | Clean Tank Complete | 91.4 | high | ratio=1.83 (0.35-2.51) | 25-101, 24-005, 24-004, 23-016, 23-015
.QC8 | QC Inspection - Clean | 0 | skip | 0h estimate
.802 | Move to Paint Area | 3.7 | low | wc_ratio=0.92 | wc_avg
.QC9 | QC Inspection - Sandblast | 0 | skip | 0h estimate
.QC90 | QC Inspection - Paint | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 12.2 | high | ratio=1.22 (0.20-1.75) | 24-005, 24-004, 23-016, 23-015
.950 | Check BOM, Pack Parts | 5 | high | ratio=1.00 (0.80-1.00) | 24-005, 24-004, 23-015
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 32.5 | high | ratio=1.30 (0.73-1.75) | 24-005, 24-004, 23-016, 23-015
.971 | Take Parts - Machine Shop | 3.6 | low | wc_ratio=0.91 | wc_avg
.973 | P/U Parts - Machine Shop | 3.6 | low | wc_ratio=0.91 | wc_avg