## Drawing Submittal
Drawing Submittal
On Track
At Risk
[5 empty] | Late |  | No Y | No Y
Job # | Customer | Rev. | Target | Actual | Days +/- | Status | Submitted | Approved | 0 | 1 | 2 | 3 | 4
24-046 | SYMS Engineering | 4 | 2024-08-29 | 2025-08-14 | -350 |  | Y | y | 2024-09-05 | 2025-05-12 | 2025-07-15 | 2025-08-06 | 2024-08-29 | 1900-01-03 | 2024-08-29 | 2024-08-29
25-010 | Kimberly Clark | 3 | 2025-09-11 | 2025-08-28 | 14 | 46076 | Y | y | 2025-03-04 | 2025-07-03 | 2025-08-28 | 2025-09-11 | 2025-02-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 0
25-011 | Kimberly Clark | 3 | 2025-09-18 | 2025-09-04 | 14 | 46057 | Y | y | 2025-03-04 | 2025-06-05 | 2025-09-04 | 2025-09-18 | 2025-02-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 0
25-012 | Kimberly Clark | 3 | 2025-09-18 | 2025-09-04 | 14 |  | Y | y | 2025-03-04 | 2025-06-05 | 2025-09-04 | 2025-09-18 | 2025-02-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 46023
25-013 | Kimberly Clark | 2 | 2025-06-18 | 2025-09-04 | -78 |  | Y | y | 2025-03-04 | 2025-06-05 | 2025-06-18 | 2025-07-02 | 2025-02-11 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 45932
25-014 | Kimberly Clark | 2 | 2025-06-11 | 2025-05-28 | 14 | 45967 | Y | y | 2025-03-04 | 2025-05-21 | 2025-06-11 | 2025-06-25 | 2025-02-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-015 | Kimberly Clark | 2 | 2025-06-11 | 2025-05-28 | 14 | 45967 | Y | y | 2025-03-04 | 2025-05-21 | 2025-06-11 | 2025-06-25 | 2025-02-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-016 | Kimberly Clark | 2 | 2025-06-11 | 2025-05-28 | 14 | 46076 | Y | y | 2025-03-04 | 2025-05-21 | 2025-06-11 | 2025-06-25 | 2025-02-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-017 | Kimberly Clark | 2 | 2025-05-06 | 2025-04-22 | 14 | 46043 | Y | y | 2025-03-04 | 2025-04-14 | 2025-05-06 | 2025-05-20 | 2025-02-11 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 0
25-018 | Kimberly Clark | 3 | 2025-09-19 | 2025-09-05 | 14 |  | Y | y | 2025-03-04 | 2025-07-21 | 2025-08-28 | 2025-09-19 | 2025-02-11 | 2025-09-19 | 2025-09-19 | 2025-09-19 | 46044
25-019 | Kimberly Clark | 3 | 2025-09-19 | 2025-09-05 | 14 | 46076 | Y | y | 2025-03-04 | 2025-06-25 | 2025-09-04 | 2025-09-19 | 2025-02-11 | 2025-09-19 | 2025-09-19 | 2025-09-19 | 0
25-020 | Kimberly Clark | 4 | 2025-02-11 | 2025-08-26 | -196 | 46058 | Y | y | 2025-03-04 | 2025-06-05 | 2025-07-31 | 2025-08-28 | 2025-02-11 | 1900-01-03 | 2025-02-11 | 2025-02-11 | 0
25-021 | Kimberly Clark | 3 | 2025-09-16 | 2025-09-02 | 14 | 46073 | Y | y | 2025-03-04 | 2025-06-25 | 2025-09-04 | 2025-09-16 | 2025-02-11 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 0
25-023 | Andritz | 3 | 2025-03-24 | 2025-03-10 | 14 | 45804 | Y | y | 2025-02-13 | 2025-03-05 | 2025-03-17 | 2025-03-24 | 2025-02-13 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 0
25-024 | Andritz | 3 | 2025-03-24 | 2025-03-10 | 14 | 45804 | Y | y | 2025-02-13 | 2025-03-05 | 2025-03-17 | 2025-03-24 | 2025-02-13 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 0
25-025 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45904 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-29 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-026 | Irving Tissue | 3 | 2025-06-03 | 2025-05-20 | 14 | 45904 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-20 | 2025-06-03 | 2025-02-19 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 0
25-027 | Irving Tissue | 3 | 2025-06-03 | 2025-05-20 | 14 | 45932 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-20 | 2025-06-03 | 2025-02-19 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 0
25-028 | Irving Tissue | 3 | 2025-06-03 | 2025-05-20 | 14 | 45932 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-20 | 2025-06-03 | 2025-02-19 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 0
25-029 | Irving Tissue | 3 | 2025-06-03 | 2025-05-20 | 14 | 45930 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-20 | 2025-06-03 | 2025-02-19 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 0
25-030 | Irving Tissue | 3 | 2025-06-03 | 2025-05-20 | 14 | 45930 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-20 | 2025-06-03 | 2025-02-19 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 0
25-031 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45958 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-28 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-032 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45958 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-28 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-033 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45958 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-28 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-034 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45896 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-28 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-035 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45896 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-28 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-036 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45896 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-28 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-037 | Irving Tissue | 3 | 2025-06-11 | 2025-05-28 | 14 | 45904 | Y | y | 2025-03-05 | 2025-04-14 | 2025-05-28 | 2025-06-11 | 2025-02-19 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 0
25-039 | Zachry | 2 | 2025-05-20 | 2025-05-06 | 14 | 45884 | Y | y | 2025-03-19 | 2025-05-08 | 2025-05-20 | 2025-06-03 | 2025-03-12 | 2025-05-20 | 2025-05-20 | 2025-05-20 | 0
25-040 | NAK Kiln | 2 | 2025-03-27 | 2025-03-13 | 14 |  | Y | y | 2025-03-19 | 2025-03-04 | 2025-03-27 | 2025-04-10 | 2025-03-19 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 45867
25-042 | Andritz | 3 | 2025-06-05 | 2025-05-22 | 14 | 45896 | Y | y | 2025-04-09 | 2025-04-21 | 2025-05-26 | 2025-06-05 | 2025-04-02 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 0
25-044 | Noah Industrial | 3 | 2025-06-13 | 2025-05-30 | 14 | 45883 | Y | y | 2025-04-29 | 2025-05-28 | 2025-06-05 | 2025-06-13 | 2025-04-15 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 0
25-045 | ProPipe | 4 | 2025-04-19 | 2026-03-16 | -331 | 46022 | Y |  | 2025-04-12 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-04-19 | 1900-01-03 | 2025-04-19 | 2025-04-19 | 0
25-052 | Kraton | 4 | 2025-06-02 | 2025-07-29 | -57 | 46020 | Y | y | 2025-06-09 | 2025-07-08 | 2025-07-21 | 2025-07-29 | 2025-06-02 | 1900-01-03 | 2025-06-02 | 2025-06-02 | 0
25-053 | Andritz | 0 | 2026-04-27 | 2026-03-16 | 42 | 45926 | N |  | 2026-01-05 | 2026-01-26 | 2026-02-09 | 2026-02-23 | 2025-06-16 | 2026-01-05 | 2026-01-05 | 2026-04-27 | 0
25-054 | Chromascape | 3 | 2025-07-31 | 2025-07-17 | 14 | 45985 | Y | y | 2025-07-01 | 2025-07-07 | 2025-07-17 | 2025-07-31 | 2025-06-17 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 0
25-055 | Airgas | 2 | 2025-12-31 | 2025-12-17 | 14 |  | Y | y | 2025-10-02 | 2025-12-17 | 2025-12-31 | 2026-01-14 | 2025-06-26 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 46183
25-056 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 45972 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-057 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 45972 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-058 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46009 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-059 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46007 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-060 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46035 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-061 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46035 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-062 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46055 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-063 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46055 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-064 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46069 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-065 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 | 46069 | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 0
25-066 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 |  | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 46104
25-067 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 |  | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 46104
25-068 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 |  | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 46132
25-069 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 |  | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 46132
25-070 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 |  | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 46160
25-071 | Reco | 3 | 2025-08-18 | 2025-08-04 | 14 |  | Y | y | 2025-07-04 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-06-27 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 46160
25-072 | Burke Industrial | 2 | 2025-07-28 | 2025-07-14 | 14 | 45922 | Y | y | 2025-07-07 | 2025-07-14 | 2025-07-28 | 2025-08-11 | 2025-06-30 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 0
25-073 | Burke Industrial | 2 | 2025-07-28 | 2025-07-14 | 14 | 45925 | Y | y | 2025-07-07 | 2025-07-14 | 2025-07-28 | 2025-08-11 | 2025-06-30 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 0
25-074 | Kemira | 2 | 2025-08-05 | 2025-07-22 | 14 | 46008 | Y | y | 2025-07-07 | 2025-07-24 | 2025-08-05 | 2025-08-19 | 2025-06-30 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 0
25-075 | Kemira | 3 | 2025-09-02 | 2025-08-19 | 14 | 45994 | Y | y | 2025-07-07 | 2025-07-28 | 2025-08-22 | 2025-09-02 | 2025-06-30 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 0
25-076 | Irving tissue | 2 | 2025-09-02 | 2025-08-19 | 14 | 45930 | Y | y | 2025-07-15 | 2025-08-19 | 2025-09-02 | 2025-09-16 | 2025-07-01 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 0
25-077 | Epic Systems | 3 | 2025-09-08 | 2025-08-25 | 14 | 46028 | Y | y | 2025-07-16 | 2025-08-13 | 2025-08-25 | 2025-09-08 | 2025-07-09 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 0
25-078 | Epic Systems | 3 | 2025-09-08 | 2025-08-25 | 14 | 46028 | Y | y | 2025-07-16 | 2025-08-08 | 2025-08-25 | 2025-09-08 | 2025-07-09 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 0
25-079 | Epic Systems | 3 | 2025-09-08 | 2025-08-25 | 14 | 46028 | Y | y | 2025-07-16 | 2025-08-08 | 2025-08-25 | 2025-09-08 | 2025-07-09 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 0
25-080 | Domtar | 2 | 2025-09-04 | 2025-08-21 | 14 | 46029 | Y | y | 2025-07-18 | 2025-08-07 | 2025-09-04 | 2025-09-18 | 2025-07-11 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 0
25-083 | Synthomer | 3 | 2026-02-09 | 2025-11-04 | 97 |  | N | y | 2025-08-05 | 2025-10-21 | 2025-11-06 | 2026-02-09 | 2025-07-29 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 46237
25-084 | Atlas Minerals | 4 | 2025-08-01 | 2025-11-04 | -95 |  | Y | y | 2025-08-08 | 2025-08-18 | 2025-10-22 | 2025-10-31 | 2025-08-01 | 1900-01-03 | 2025-08-01 | 2025-08-01 | 46070
25-085 | Noah Industrial | 2 | 2025-09-02 | 2025-08-19 | 14 | 45999 | Y | y | 2025-08-12 | 2025-08-21 | 2025-09-02 | 2025-09-16 | 2025-08-05 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 0
25-086 | Tellus | 4 | 2025-08-13 | 2026-03-16 | -215 | 46022 | Y |  | 2025-07-30 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-08-13 | 1900-01-03 | 2025-08-13 | 2025-08-13 | 0
25-087 | Solvay | 2 | 2025-09-29 | 2025-09-15 | 14 | 45952 | Y | y | 2025-08-28 | 2025-09-15 | 2025-09-29 | 2025-10-13 | 2025-08-21 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 0
25-088 | CIL Isotopes | 2 | 2025-09-29 | 2025-09-15 | 14 | 45979 | Y | y | 2025-09-03 | 2025-09-16 | 2025-09-29 | 2025-10-13 | 2025-08-27 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 0
25-089 | Valmet | 2 | 2025-12-18 | 2025-12-04 | 14 | 46090 | Y | y | 2025-09-22 12:00 | 2025-11-28 | 2025-12-18 | 2026-01-01 | 2025-09-05 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 0
25-090 | GAF | 1 | 2025-09-12 | 2025-08-22 | 21 | 45912 | Y | y | 2025-08-25 | 2025-09-12 | 2025-09-26 | 2025-10-10 | 2025-09-01 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 0
25-091 | US Sugar | 4 | 2025-09-18 | 2026-03-16 | -179 | 46022 | Y |  | 2025-09-11 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-09-18 | 1900-01-03 | 2025-09-18 | 2025-09-18 | 0
25-092 | Symrise | 3 | 2025-11-10 | 2025-10-27 | 14 |  | Y | y | 2025-10-08 | 2025-10-14 | 2025-10-30 | 2025-11-10 | 2025-09-24 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 46079
25-093 | Symrise | 3 | 2025-11-10 | 2025-10-27 | 14 |  | Y | y | 2025-10-08 | 2025-10-14 | 2025-10-30 | 2025-11-10 | 2025-09-24 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 46079
25-094 | Kimberly Clark | 2 | 2025-12-02 | 2025-11-18 | 14 | 45678 | Y | y | 2025-10-06 | 2025-10-27 | 2025-12-02 | 2025-12-16 | 2025-09-29 | 2025-12-02 | 2025-12-02 | 2025-12-02 | 0
25-095 | Andritz | 3 | 2026-02-27 | 2026-03-16 | -17 | 46022 | Y |  | 2025-10-17 | 2025-11-19 | 2026-02-09 | 2026-02-27 | 2025-10-03 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 0
25-096 | Milliken | 2 | 2025-11-06 | 2025-10-23 | 14 | 46029 | Y | y | 2025-10-13 | 2025-10-23 | 2025-11-06 | 2025-11-20 | 2025-10-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 0
25-097 | Milliken | 2 | 2025-11-06 | 2025-10-23 | 14 | 46029 | Y | y | 2025-10-13 | 2025-10-23 | 2025-11-06 | 2025-11-20 | 2025-10-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 0
25-098 | Coastal Technologies | 2 | 2025-11-13 | 2025-10-30 | 14 |  | Y | y | 2025-10-22 | 2025-10-31 | 2025-11-13 | 2025-11-27 | 2025-10-08 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 46080
25-099 | Burke Industrial | 2 | 2025-11-19 | 2025-11-05 | 14 |  | Y | y | 2025-10-30 | 2025-11-05 | 2025-11-19 | 2025-12-03 | 2025-10-16 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 46071
25-101 | Harper Love | 2 | 2025-12-22 | 2025-12-08 | 14 |  | Y | y | 2025-11-21 | 2025-12-08 | 2025-12-22 | 2026-01-05 | 2025-11-07 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 46118
25-102 | Epic Systems | 3 | 2026-02-26 | 2026-02-24 | 2 |  | N | y | 2025-12-12 | 2026-01-19 | 2026-02-09 | 2026-02-26 | 2025-11-21 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 46198
25-103 | Epic Systems | 3 | 2026-02-26 | 2026-02-19 | 7 |  | N | y | 2025-12-12 | 2026-01-19 | 2026-02-09 | 2026-02-26 | 2025-11-21 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 46198
25-104 | Epic Systems | 3 | 2026-02-26 | 2026-02-19 | 7 |  | N | y | 2025-12-12 | 2026-01-19 | 2026-02-09 | 2026-02-26 | 2025-11-21 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 46198
25-105 | Epic Systems | 3 | 2026-02-26 | 2026-02-19 | 7 |  | N | y | 2025-12-12 | 2026-01-19 | 2026-02-09 | 2026-02-26 | 2025-11-21 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 46198
25-106 | Epic Systems | 3 | 2026-02-26 | 2026-02-24 | 2 |  | N | y | 2025-12-12 | 2026-01-19 | 2026-02-09 | 2026-02-26 | 2025-11-21 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 46198
25-107 | Epic Systems | 2 | 2026-03-26 | 2026-03-16 | 10 |  | N |  | 2026-03-02 | 2026-02-09 | 2026-03-19 | 2026-04-02 | 2026-02-16 | 2026-03-19 | 2026-03-19 | 2026-03-26 | 46226
25-108 | Epic Systems | 2 | 2026-03-19 | 2026-03-16 | 3 |  | N |  | 2025-11-27 | 2026-02-09 | 2026-03-19 | 2026-04-02 | 2025-11-13 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 46219
25-109 | Epic Systems | 4 | 2025-11-13 | 2026-02-19 | -98 |  | Y | y | 2025-11-27 | 2025-12-19 | 2026-01-19 | 2026-01-30 | 2025-11-13 | 1900-01-03 | 2025-11-13 | 2025-11-13 | 46198
25-110 | Epic Systems | 4 | 2025-11-13 | 2026-02-24 | -103 |  | Y | y | 2025-11-27 | 2025-12-19 | 2026-01-19 | 2026-01-30 | 2025-11-13 | 1900-01-03 | 2025-11-13 | 2025-11-13 | 46171
25-111 | Epic Systems | 4 | 2025-11-13 | 2026-02-24 | -103 |  | Y | y | 2025-11-27 | 2025-12-19 | 2026-01-19 | 2026-01-30 | 2025-11-13 | 1900-01-03 | 2025-11-13 | 2025-11-13 | 46171
25-112 | Epic Systems | 4 | 2025-11-13 | 2026-02-24 | -103 |  | Y | y | 2025-11-27 | 2025-12-19 | 2026-01-19 | 2026-01-30 | 2025-11-13 | 1900-01-03 | 2025-11-13 | 2025-11-13 | 46171
25-113 | Epic Systems | 3 | 2026-02-19 | 2026-03-16 | -25 |  | Y |  | 2025-12-12 | 2026-01-19 | 2026-02-09 | 2026-02-19 | 2025-11-28 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 46181
25-115 | Epic Systems | 3 | 2026-02-26 | 2026-02-19 | 7 |  | N | y | 2025-11-27 | 2026-01-19 | 2026-01-30 | 2026-02-26 | 2025-11-13 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 46198
25-116 | Polynt | 3 | 2026-03-05 | 2026-03-16 | -11 |  | Y |  | 2025-12-02 | 2026-01-09 | 2026-02-19 | 2026-03-05 | 2025-11-18 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 46191
25-117 | Merrick | 3 | 2026-02-24 | 2026-02-10 | 14 |  | Y | y | 2026-01-09 | 2026-01-28 | 2026-02-09 | 2026-02-24 | 2025-11-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 46195
25-118 | Merrick | 3 | 2026-03-02 | 2026-02-16 | 14 |  | Y | y | 2026-01-09 | 2026-01-28 | 2026-02-16 | 2026-03-02 | 2025-11-21 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 46202
25-119 | Vertiv | 2 | 2025-12-17 | 2025-12-03 | 14 | 46022 | Y | y | 2025-11-28 | 2025-12-10 | 2025-12-17 | 2025-12-31 | 2025-11-28 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 0
25-120 | Andritz | 4 | 2025-12-05 | 2026-03-16 | -101 |  | Y |  | 2025-11-21 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-12-05 | 1900-01-03 | 2025-12-05 | 2025-12-05 | 46204
25-121 | Kimberly Clark | 1 | 2026-03-17 | 2026-03-16 | 1 |  | N |  | 2026-01-01 | 2026-02-24 | 2026-03-10 | 2026-03-24 | 2025-12-18 | 2026-02-24 | 2026-02-24 | 2026-03-17 | 2026-07-14
25-122 | Kimberly Clark | 1 | 2026-03-17 | 2026-03-16 | 1 |  | N |  | 2026-01-01 | 2026-02-24 | 2026-03-10 | 2026-03-24 | 2025-12-18 | 2026-02-24 | 2026-02-24 | 2026-03-17 | 2026-07-14
25-123 | Kimberly Clark | 1 | 2026-01-29 | 2026-03-16 | -46 |  | Y |  | 2026-01-01 | 2026-01-29 | 2026-02-12 | 2026-02-26 | 2025-12-18 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 46170
25-124 | Vertiv | 4 | 2025-12-29 | 2026-03-16 | -77 |  | Y |  | 2025-12-15 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-12-29 | 1900-01-03 | 2025-12-29 | 2025-12-29 | 46246
25-356 | Synthomer | 3 | 2026-03-12 | 2026-02-26 | 14 |  | Y | y | 2026-01-26 | 2026-02-09 | 2026-02-28 | 2026-03-12 | 2026-01-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 46200
25-357 | Sylvamo | 2 | 2026-03-13 | 2026-03-16 | -3 |  | Y |  | 2026-01-27 | 2026-02-18 | 2026-03-13 | 2026-03-27 | 2026-01-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 46176
25-358 | Sylvamo | 2 | 2026-03-13 | 2026-03-16 | -3 |  | Y |  | 2026-01-27 | 2026-02-18 | 2026-03-13 | 2026-03-27 | 2026-01-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 46176
26-002 | SNF | 1 | 2026-02-27 | 2026-03-16 | -17 |  | Y |  | 2026-02-06 | 2026-02-27 | 2026-03-13 | 2026-03-27 | 2026-01-23 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 46199
26-003 | SNF | 1 | 2026-02-27 | 2026-03-16 | -17 |  | Y |  | 2026-02-06 | 2026-02-27 | 2026-03-13 | 2026-03-27 | 2026-01-23 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 46199
26-004 | SNF | 1 | 2026-02-27 | 2026-03-16 | -17 |  | Y |  | 2026-02-06 | 2026-02-27 | 2026-03-13 | 2026-03-27 | 2026-01-23 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 46199
26-005 | US Sugar | 2 | 2026-03-18 | 2026-03-04 | 14 |  | Y | y | 2026-02-09 | 2026-02-18 | 2026-03-18 | 2026-04-01 | 2026-01-26 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 46183
26-014 | SNF | 1 | 2026-03-04 | 2026-03-16 | -12 |  | Y |  | 2026-02-09 | 2026-03-04 | 2026-03-18 | 2026-04-01 | 2026-01-26 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 46085
26-015 | SNF | 1 | 2026-04-01 | 2026-03-16 | 16 |  | Y |  | 2026-03-11 | 2026-04-01 | 2026-04-15 | 2026-04-29 | 2026-02-25 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 46090
26-016 | SNF | 1 | 2026-03-30 | 2026-03-16 | 14 |  | Y |  | 2026-03-11 | 2026-03-30 | 2026-04-13 | 2026-04-27 | 2026-02-25 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 46090
26-017 | SNF | 1 | 2026-03-04 | 2026-03-16 | -12 |  | Y |  | 2026-02-09 | 2026-03-04 | 2026-03-18 | 2026-04-01 | 2026-01-26 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 46085
26-018 | SNF | 1 | 2026-03-04 | 2026-03-16 | -12 |  | Y |  | 2026-02-09 | 2026-03-04 | 2026-03-18 | 2026-04-01 | 2026-01-26 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 46085
26-020 | US Sugar | 2 | 2026-03-20 | 2026-03-16 | 4 |  | N |  | 2026-03-06 | 2026-03-16 | 2026-03-20 | 2026-04-03 | 2026-02-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-07-17
26-021 | US Sugar | 2 | 2026-03-20 | 2026-03-16 | 4 |  | N |  | 2026-03-06 | 2026-03-16 | 2026-03-20 | 2026-04-03 | 2026-02-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-07-17
26-022 | Andritz | 1 | 2026-03-27 | 2026-03-16 | 11 |  | Y |  | 2026-03-03 | 2026-03-27 | 2026-04-10 | 2026-04-24 | 2026-02-24 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 46090
26-024 | Polynt | 0 | 2026-04-01 | 2026-03-16 | 16 |  | N |  | 2026-03-25 | 2026-04-15 | 2026-04-29 | 2026-05-13 | 2026-03-11 | 2026-03-25 | 2026-03-25 | 2026-04-01 | 2026-03-10
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16
0 |  | 0 | 2026-03-16 | 2026-03-16 | 0 |  | Y |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16

## Cust Dwg Return
Drawing Return From Customer
On Track
At Risk
[5 empty] | Late |  | Blanks only | Blanks only
Job # | Customer | Rev. | Target | Actual | Days +/- | Status | Returned | Approved
24-046 | SYMS Engineering | 3 | 2025-08-13 | 2025-08-14 | -215 |  | 1 | y
25-010 | Kimberly Clark | 2 | 2025-09-04 | 2025-08-28 | -193 |  |  | y
25-011 | Kimberly Clark | 2 | 2025-09-11 | 2025-09-04 | -186 |  |  | y
25-012 | Kimberly Clark | 2 | 2025-09-11 | 2025-09-04 | -186 |  |  | y
25-013 | Kimberly Clark | 1 | 2025-06-11 | 2025-09-04 | -278 |  |  | y
25-014 | Kimberly Clark | 1 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-015 | Kimberly Clark | 1 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-016 | Kimberly Clark | 1 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-017 | Kimberly Clark | 1 | 2025-04-29 | 2025-04-22 | -321 |  |  | y
25-018 | Kimberly Clark | 2 | 2025-09-12 | 2025-09-05 | -185 |  |  | y
25-019 | Kimberly Clark | 2 | 2025-09-12 | 2025-09-05 | -185 |  |  | y
25-020 | Kimberly Clark | 3 | 2025-09-02 | 2025-08-26 | -195 |  |  | y
25-021 | Kimberly Clark | 2 | 2025-09-09 | 2025-09-02 | -188 |  |  | y
25-023 | Andritz | 2 | 2025-03-17 | 2025-03-10 | -364 |  |  | y
25-024 | Andritz | 2 | 2025-03-17 | 2025-03-10 | -364 |  |  | y
25-025 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-026 | Irving Tissue | 2 | 2025-05-27 | 2025-05-20 | -293 |  |  | y
25-027 | Irving Tissue | 2 | 2025-05-27 | 2025-05-20 | -293 |  |  | y
25-028 | Irving Tissue | 2 | 2025-05-27 | 2025-05-20 | -293 |  |  | y
25-029 | Irving Tissue | 2 | 2025-05-27 | 2025-05-20 | -293 |  |  | y
25-030 | Irving Tissue | 2 | 2025-05-27 | 2025-05-20 | -293 |  |  | y
25-031 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-032 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-033 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-034 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-035 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-036 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-037 | Irving Tissue | 2 | 2025-06-04 | 2025-05-28 | -285 |  |  | y
25-039 | Zachry | 1 | 2025-05-13 | 2025-05-06 | -307 |  |  | y
25-040 | NAK Kiln | 1 | 2025-03-20 | 2025-03-13 | -361 |  |  | Y
25-042 | Andritz | 2 | 2025-05-29 | 2025-05-22 | -291 |  |  | Y
25-044 | Noah Industrial | 2 | 2025-06-06 | 2025-05-30 | -283 |  |  | Y
25-045 | ProPipe | 3 | 2026-01-07 | - | -68 |  | 1 | Y
25-052 | Kraton | 3 | 2025-08-05 | 2025-07-29 | -223 |  |  | Y
25-053 | Andritz | [5 empty] | FALSE
25-054 | Chromascape | 2 | 2025-07-24 | 2025-07-17 | -235 |  |  | y
25-055 | Airgas | 1 | 2025-12-24 | 2025-12-17 | -82 |  |  | Y
25-056 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-057 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-058 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-059 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-060 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | Y
25-061 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-062 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-063 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-064 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-065 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-066 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-067 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-068 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-069 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-070 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-071 | Reco | 2 | 2025-08-11 | 2025-08-04 | -217 |  |  | y
25-072 | Burke Industrial | 1 | 2025-07-21 | 2025-07-14 | -238 |  |  | y
25-073 | Burke Industrial | 1 | 2025-07-21 | 2025-07-14 | -238 |  |  | y
25-074 | Kemira | 1 | 2025-07-29 | 2025-07-22 | -230 |  |  | y
25-075 | Kemira | 2 | 2025-08-26 | 2025-08-19 | -202 |  |  | y
25-076 | Irving tissue | 1 | 2025-08-26 | 2025-08-19 | -202 |  |  | y
25-077 | Epic Systems | 2 | 2025-09-01 | 2025-08-25 | -196 |  |  | y
25-078 | Epic Systems | 2 | 2025-09-01 | 2025-08-25 | -196 |  |  | y
25-079 | Epic Systems | 2 | 2025-09-01 | 2025-08-25 | -196 |  |  | y
25-080 | Domtar | 1 | 2025-08-28 | 2025-08-21 | -200 |  |  | y
25-083 | Synthomer | 2 | 2025-11-11 | 2025-11-04 | -125 |  | 1 | y
25-084 | Atlas Minerals | 3 | 2025-11-07 | 2025-11-04 | -129 |  | 1 | y
25-085 | Noah Industrial | 1 | 2025-08-26 | 2025-08-19 | -202 |  |  | y
25-086 | Tellus | 3 | 2026-01-07 | - | -68 |  | 1
25-087 | Solvay | 1 | 2025-09-22 | 2025-09-15 | -175 |  |  | y
25-088 | CIL Isotopes | 1 | 2025-09-22 | 2025-09-15 | -175 |  |  | y
25-089 | Valmet | 1 | 2025-12-11 | 2025-12-04 | -95 |  |  | y
25-090 | GAF | 0 | 2025-09-05 | 2025-08-22 | -192 |  |  | y
25-091 | US Sugar | 3 | 2026-01-07 | - | -68 |  | 1
25-092 | Symrise | 2 | 2025-11-03 | 2025-10-27 | -133 |  |  | y
25-093 | Symrise | 2 | 2025-11-03 | 2025-10-27 | -133 |  |  | y
25-094 | Kimberly Clark | 1 | 2025-11-25 | 2025-11-18 | -111 |  |  | y
25-095 | Andritz | 2 | 2026-02-20 | - | -24
25-096 | Milliken | 1 | 2025-10-30 | 2025-10-23 | -137 |  |  | y
25-097 | Milliken | 1 | 2025-10-30 | 2025-10-23 | -137 |  |  | y
25-098 | Coastal Technologies | 1 | 2025-11-06 | 2025-10-30 | -130 |  |  | y
25-099 | Burke Industrial | 1 | 2025-11-12 | 2025-11-05 | -124 |  |  | y
25-101 | Harper Love | 1 | 2025-12-15 | 2025-12-08 | -91 |  |  | y
25-102 | Epic Systems | 2 | 2026-02-11 | 2026-02-24 | -33 |  | 1 | y
25-103 | Epic Systems | 2 | 2026-02-11 | 2026-02-19 | -33 |  | 1 | y
25-104 | Epic Systems | 2 | 2026-02-11 | 2026-02-19 | -33 |  | 1 | y
25-105 | Epic Systems | 2 | 2026-02-11 | 2026-02-19 | -33 |  | 1 | y
25-106 | Epic Systems | 2 | 2026-02-12 | 2026-02-24 | -32 |  | 1 | y
25-107 | Epic Systems | 1 | 2026-03-04 | - | -12 |  | 1
25-108 | Epic Systems | 1 | 2026-02-18 | - | -26 |  | 1
25-109 | Epic Systems | 3 | 2026-02-06 | 2026-02-19 | -38 |  | 1 | y
25-110 | Epic Systems | 3 | 2026-02-06 | 2026-02-24 | -38 |  |  | y
25-111 | Epic Systems | 3 | 2026-02-06 | 2026-02-24 | -38 |  |  | y
25-112 | Epic Systems | 3 | 2026-02-06 | 2026-02-24 | -38 |  |  | y
25-113 | Epic Systems | 2 | 2026-02-12 | - | -32
25-115 | Epic Systems | 2 | 2026-02-06 | 2026-02-19 | -38 |  | 1 | y
25-116 | Polynt | 2 | 2026-02-26 | - | -18
25-117 | Merrick | 2 | 2026-02-17 | 2026-02-10 | -27 |  |  | y
25-118 | Merrick | 2 | 2026-02-23 | 2026-02-16 | -21 |  |  | y
25-119 | Vertiv | 1 | 2025-12-10 | 2025-12-03 | -96 |  |  | y
25-120 | Andritz | 3 | 2026-01-07 | - | -68 |  | 1
25-121 | Kimberly Clark | 0 | 2026-01-22 | - | -53 |  | 1
25-122 | Kimberly Clark | 0 | 2026-01-22 | - | -53 |  | 1
25-123 | Kimberly Clark | 0 | 2026-01-22 | - | -53
25-124 | Vertiv | 3 | 2026-01-07 | - | -68 |  | 1
25-356 | Synthomer | 2 | 2026-03-05 | 2026-02-26 | -11 |  |  | y
25-357 | Sylvamo | 1 | 2026-03-06 | - | -10
25-358 | Sylvamo | 1 | 2026-03-06 | - | -10
26-002 | SNF | 0 | 2026-02-20 | - | -24
26-003 | SNF | 0 | 2026-02-20 | - | -24
26-004 | SNF | 0 | 2026-02-20 | - | -24
26-005 | US Sugar | 1 | 2026-03-11 | 2026-03-04 | -5 |  |  | y
26-014 | SNF | 0 | 2026-02-25 | - | -19
26-015 | SNF | 0 | 2026-03-25 | - | 9
26-016 | SNF | 0 | 2026-03-23 | - | 7
26-017 | SNF | 0 | 2026-02-25 | - | -19
26-018 | SNF | 0 | 2026-02-25 | - | -19
26-020 | US Sugar | 1 | 2026-03-20 | - | 4 |  | 1
26-021 | US Sugar | 1 | 2026-03-20 | - | 4 |  | 1
26-022 | Andritz | 0 | 2026-03-20 | - | 4
26-024 | Polynt | [5 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
0 | [6 empty] | FALSE
Formulas:
Target = IF([Rev.]=" "," ",IF([Rev.]=0,VLOOKUP([Job #],'Date Calcs'!A:AG,9,),IF([Rev.]=1,VLOOKUP([Job #],'Date Calcs'!A:AG,11,),IF([Rev.]=2,VLOOKUP([Job #],'Date Calcs'!A:AG,13,),IF([Rev.]=3,VLOOKUP([Job #],'Date Calcs'!A:AG,15,),4)))))
Actual = IF(IFNA(IF([Target]=" "," ",VLOOKUP([Job #],'Actual Dates'!A:AE,20,0)),"")<1,"-",IFNA(IF([Target]=" "," ",VLOOKUP([Job #],'Actual Dates'!A:AE,20,0)),""))

## RTR v2
Shop Release Readiness
|  | Pre-Approval | [5 empty] | After Return of Approval Drawings | [22 empty] | Release to Shop By Ship Date
Job # | Customer | App. Prints |  | Long lead time |  | Prelim BOM |  | Final Calcs |  |  | Cert Dwgs |  | Update BOM |  | Stock Check |  | Purch Recvd |  | Final BOM |  | Build Plan |  | Burn File |  | QC Checklist |  | Released |  | Drop Dead Date Week of | Drawings Certified | Build Plan | Days to go | QC Checklist | days to go | Burn File | days to go | All MAT. On hand | Purchase vs Release | Release to Shop | days to go | Ship Date Week Of | Difference drop dead to ship | UDR1 Form (ASME Only) | Logistics Confirmed | Actual Ship Date | COMMENTS
24-046 | SYMS Engineering | Y | 4 | Y | -2 | Y | 6 | Y | 4 | 3 | Y | 209 | Y | -276 | Y | 76 | Y | 69 | Y | 87 | Y | 81 | Y | 85 | Y | 97 | Y |  | 2026-03-12 | 2025-08-14 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-13 | -32 | 2026-03-06
25-010 | Kimberly Clark | Y | 85 | Y | 8 | Y | 6 | Y | 5 | 4 | Y | 98 | Y | -132 | Y | -38 | Y | -45 | Y | 88 | Y | 127 | Y | -238 | Y | 127 | Y | 172 | 2025-12-04 | 2025-08-28 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 |  |  |  |  | 2026-02-23
25-011 | Kimberly Clark | Y | 52 | Y | 7 | Y | 6 | Y | 5 | 4 | Y | 126 | Y | -196 | Y | -76 |  | -83 | Y | 43 | Y | [6 empty] | 146 | 2026-01-08 | 2025-09-04 | DONE | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 2026-02-04
25-012 | Kimberly Clark | Y | 52 | Y | 7 | Y | 6 | Y | 5 | 4 | Y | 126 | Y | -192 | Y | -72 | Y | -79 | Y | -254 | Y | 82 | Y | 111 | Y | 111 | Y |  | 2026-01-08 | 2025-09-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-12 | -63 | 2026-01-01 | 2026-03-12
25-013 | Kimberly Clark | Y | 21 | Y | 7 | Y | 6 | Y | 96 | 95 | Y | 217 | Y | -101 | Y | 20 | Y | 13 | Y | 125 | Y | 126 | Y | 128 | Y | 129 | Y |  | 2026-01-08 | 2025-09-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-12 | -63 | 2025-10-02 | 2026-03-12
25-014 | Kimberly Clark | Y | 29 | Y | 7 | Y | 6 | Y | 12 | 11 | Y | 133 | Y | -85 | Y | 35 |  | 28 | Y | 91 | Y |  |  |  |  | 90 | Y | 162 | 2025-10-01 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-11-06
25-015 | Kimberly Clark | Y | 29 | Y | 7 | Y | 6 | Y | 12 | 11 | Y | 161 | Y | -98 | Y | 50 |  | 43 | Y | 84 | Y |  |  |  |  | 83 | Y | 162 | 2025-10-29 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-11-06
25-016 | Kimberly Clark | Y | 29 | Y | 7 | Y | -2 | Y | 12 | 11 | Y | 161 | Y | -93 | Y | 55 | Y | 48 | Y | 167 | Y | 182 | Y | 182 | Y | 182 | Y | 271 | 2025-10-29 | 2025-05-28 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 |  |  |  |  | 2026-02-23
25-017 | Kimberly Clark | Y | 6 | Y | 7 | Y | -2 | Y | 13 | 12 | Y | 162 | Y | -55 | Y | 93 |  | 86 | Y | 155 | Y |  |  |  |  | 154 | Y | 275 | 2025-09-23 | 2025-04-22 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-21
25-018 | Kimberly Clark | Y | 78 | Y | 7 | Y | 0 | Y | 13 | 12 | Y | 162 | Y | -134 | Y | 15 | Y | 8 | Y | 41 | Y | 140 | Y | 139 | Y | 42 | Y |  | 2026-02-06 | 2025-09-05 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 |  |  | 2026-01-22 | 2026-03-10
25-019 | Kimberly Clark | Y | 70 | Y | 7 | Y | 0 | Y | 6 | 5 | Y | 183 | Y | -171 | Y | 6 | Y | -1 | Y | 61 | Y | 84 | Y | 81 | Y | 76 | Y | 165 | 2026-03-06 | 2025-09-05 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 |  |  |  |  | 2026-02-23
25-020 | Kimberly Clark | Y | 21 | Y | 7 | Y | 0 | Y | 3 | 2 | Y | 180 | Y | -224 | Y | -16 |  | -23 | Y | -7 | Y |  |  |  |  | -8 | Y | 154 | 2026-02-24 | 2025-08-26 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-02-05
25-021 | Kimberly Clark | Y | 70 | Y | 7 | Y | 0 | Y | 3 | 2 | Y | 180 | Y | -176 | Y | 0 | Y | -7 | Y | -2 | Y | 32 | Y | 0 | Y | -1 | Y | 162 | 2026-03-03 | 2025-09-02 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 |  |  |  |  | 2026-02-20
25-023 | Andritz | Y | -1 | Y | -2 | Y | 0 | Y | -2 | -3 | Y | 77 | Y | -87 | Y | -6 |  | -13 | Y | -19 | Y |  |  |  |  | -13 | Y | 64 | 2025-06-02 | 2025-03-10 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-05-27
25-024 | Andritz | Y | -1 | Y | -2 | Y | 0 | Y | -2 | -3 | Y | 77 | Y | -87 | Y | -6 |  | -13 | Y | -19 | Y |  |  |  |  | -13 | Y | 64 | 2025-06-02 | 2025-03-10 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-05-27
25-025 | Irving Tissue | Y | -7 | Y | -1 | Y | 0 | Y | 4 | 3 | Y | 167 | Y | -169 | Y | -8 |  | -15 | Y | -9 | Y |  |  |  |  | 0 | Y | 91 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-04
25-026 | Irving Tissue | Y | -7 | Y | -1 | Y | 0 | Y | 5 | 4 | Y | 168 | Y | -173 | Y | -11 |  | -18 | Y | -1 | Y |  |  |  |  | 9 | Y | 100 | 2025-11-04 | 2025-05-20 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-04
25-027 | Irving Tissue | Y | -7 | Y | -1 | Y | 0 | Y | 5 | 4 | Y | 168 | Y | -168 | Y | -6 |  | -12 | Y | 0 | Y |  |  |  |  | 63 | Y | 128 | 2025-11-04 | 2025-05-20 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-10-02
25-028 | Irving Tissue | Y | -2 | Y | -1 | Y | 0 | Y | 5 | 4 | Y | 168 | Y | -168 | Y | -6 |  | -12 | Y | 0 | Y |  |  |  |  | 63 | Y | 128 | 2025-11-04 | 2025-05-20 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-10-02
25-029 | Irving Tissue | Y | -2 | Y | -1 | Y | 0 | Y | 5 | 4 | Y | 168 | Y | -168 | Y | -6 |  | -12 | Y | 6 | Y |  |  |  |  | 65 | Y | 126 | 2025-11-04 | 2025-05-20 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-30
25-030 | Irving Tissue | Y | 0 | Y | -1 | Y | 0 | Y | 5 | 4 | Y | 168 | Y | -166 | Y | -4 |  | -11 | Y | 6 | Y |  |  |  |  | 65 | Y | 126 | 2025-11-04 | 2025-05-20 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-30
25-031 | Irving Tissue | Y | -6 | Y | -1 | Y | 0 | Y | 5 | 4 | Y | 168 | Y | 182455 | Y | -2 |  | -9 | Y | 1 | Y |  |  |  |  | 62 | Y | 146 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-10-28
25-032 | Irving Tissue | Y | -6 | Y | -1 | Y | -7 | Y | 5 | 4 | Y | 168 | Y | 182455 | Y | -2 |  | -9 | Y | 1 | Y |  |  |  |  | 64 | Y | 146 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-10-28
25-033 | Irving Tissue | Y | 0 | Y | -1 | Y | -14 | Y | 5 | 4 | Y | 168 | Y | -161 | Y | 0 |  | -7 | Y | 5 | Y |  |  |  |  | 69 | Y | 146 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-10-28
25-034 | Irving Tissue | Y | -7 | Y | -1 | Y | -6 | Y | 5 | 4 | Y | 168 | Y | -160 | Y | 2 |  | -5 | Y | 5 | Y |  |  |  |  | 20 | Y | 84 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-08-27
25-035 | Irving Tissue | Y | 0 | Y | -1 | Y | 3 | Y | 5 | 4 | Y | 168 | Y | -160 | Y | 1 |  | -6 | Y | 5 | Y |  |  |  |  | 20 | Y | 84 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-08-27
25-036 | Irving Tissue | Y | -7 | Y | -1 | Y | -10 | Y | 5 | 4 | Y | 168 | Y | -160 | Y | 2 |  | -5 | Y | 5 | Y |  |  |  |  | 20 | Y | 84 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-08-27
25-037 | Irving Tissue | Y | -5 | Y | -1 | Y | -10 | Y | 5 | 4 | Y | 168 | Y | -168 | Y | -6 |  | -13 | Y | 5 | Y |  |  |  |  | 6 | Y | 92 | 2025-11-12 | 2025-05-28 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-04
25-039 | Zachry | Y | 1 | Y | -6 | Y | 57 | Y | 3 | 2 | Y | 110 | Y | -108 | Y | -2 |  | -8 | Y | -14 | Y |  |  |  |  | 6 | Y | 92 | 2025-08-26 | 2025-05-06 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-08-15
25-040 | NAK Kiln | Y | -29 | Y | -14 | Y | -8 | Y | 14 | 13 | Y | 163 | Y | -161 | Y | 189 | Y | 182 | Y | 182 | Y | 183 | Y | 182 | Y | 182 | Y |  | 2025-08-14 | 2025-03-13 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-03 | -232 | 2025-07-29
25-042 | Andritz | Y | -15 | Y | -6 | Y | 165 | Y | 1 | 0 | Y | 66 | Y | -68 | Y | -4 |  | -11 | Y | 11 | Y |  |  |  |  | 21 | Y | 86 | 2025-07-31 | 2025-05-22 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-08-27
25-044 | Noah Industrial | Y | 15 | Y | 8 | Y |  | Y | -1 | -2 | Y | 78 | Y | -77 | Y | 5 |  | -2 | Y | -1 | Y |  |  |  |  | 5 | Y | 63 | 2025-08-22 | 2025-05-30 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-08-14
25-045 | ProPipe | Y | 263 | Y | -10 | Y |  | Y |  |  |  |  | Y |  | Y |  |  |  | Y | [8 empty] | -14 | 2026-03-30 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 2025-12-31
25-052 | Kraton | Y | 2 | Y | -10 | Y |  | Y | 5 | 4 | Y | 98 | Y | -56 | Y | 38 |  | 31 | Y | 36 | Y |  |  |  |  | 41 | Y | 146 | 2025-11-04 | 2025-07-29 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-29
25-053 | Andritz | Y |  | Y | 58 | Y |  | Y |  |  |  |  | Y | -348 | Y | -273 | Y | -280 | Y | -277 | Y | -250 | Y |  |  | -278 | Y | -241 | 2026-05-25 |  |  | 0 |  | 0 |  | 0 | DONE | 0 | DONE | 0 | 2026-06-01 | -7 |  |  | 2025-09-26
25-054 | Chromascape | Y | -4 | Y | -8 | Y |  | Y | 5 | 4 | Y | 105 | Y | -93 | Y | 6 |  | -1 | Y | 48 | Y |  |  |  |  | 53 | Y | 123 | 2025-10-30 | 2025-07-17 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-11-24
25-055 | Airgas | Y | 54 | Y | 166 | Y |  | Y | 5 | 4 | Y | 182 | Y | -163 | Y | 14 |  | 7 | Y | 70 | Y | 41 | Y | 39 | Y |  |  |  | 2026-06-17 | 2025-12-17 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-14 | 7 | 2026-04-21 | 36 | 2026-05-26 | 22 | 2026-06-10
25-056 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 98 | Y | -97 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 1 | Y | 92 | 2025-11-10 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-11-11
25-057 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 98 | Y | -97 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 1 | Y | 92 | 2025-11-10 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-11-11
25-058 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 126 | Y | -125 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 15 | Y | 129 | 2025-12-08 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-18
25-059 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 126 | Y | -125 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 15 | Y | 127 | 2025-12-08 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-16
25-060 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 154 | Y | -153 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 38 | Y | 155 | 2026-01-05 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-13
25-061 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 154 | Y | -153 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 38 | Y | 155 | 2026-01-05 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-13
25-062 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 182 | Y | -181 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 83 | Y | 175 | 2026-02-02 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-02-02
25-063 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 182 | Y | -181 | Y | -5 |  | -12 | Y | -17 | Y |  |  |  |  | 83 | Y | 175 | 2026-02-02 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-02-02
25-064 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 210 | Y | -209 | Y | -5 | Y | -12 | Y | -17 | Y |  |  |  |  | 112 | Y | 189 | 2026-03-02 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 | DONE | 0 | DONE | 0 |  |  |  |  | 2026-02-16
25-065 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 210 | Y | -209 | Y | -5 | Y | -12 | Y | -17 | Y |  |  |  |  | 112 | Y | 189 | 2026-03-02 | 2025-08-04 | DONE | 0 |  | 0 |  | 0 | DONE | 0 | DONE | 0 |  |  |  |  | 2026-02-16
25-066 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 238 | Y | -237 | Y | -5 | Y | -12 | Y | -17 | Y | 186 | Y | -17 | Y | 146 | Y |  | 2026-03-30 | 2025-08-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-17 | 13 | 2026-03-23 | 2026-03-16
25-067 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 238 | Y | -237 | Y | -5 | Y | -12 | Y | -17 | Y | 186 | Y | -17 | Y | 146 | Y |  | 2026-03-30 | 2025-08-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-17 | 13 | 2026-03-23 | 2026-03-16
25-068 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 266 | Y | -265 | Y | -5 | Y | -12 | Y | -17 | Y | 186 | Y | -17 | Y | 174 | Y |  | 2026-04-27 | 2025-08-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-06 | 21 | 2026-04-20
25-069 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 266 | Y | -265 | Y | -5 | Y | -12 | Y | -17 | Y | 186 | Y | -17 | Y | 174 | Y |  | 2026-04-27 | 2025-08-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-06 | 21 | 2026-04-20
25-070 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 294 | Y | -293 | Y | -5 | Y | -12 | Y | -17 | Y | 186 | Y | -17 | Y | 183 | Y |  | 2026-05-25 | 2025-08-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-27 | 28 | 2026-05-18
25-071 | Reco | Y | 5 | Y |  | Y |  | Y | 5 | 4 | Y | 294 | Y | -293 | Y | -5 | Y | -12 | Y | -17 | Y | 186 | Y | -17 | Y | 183 | Y |  | 2026-05-25 | 2025-08-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-27 | 28 | 2026-05-18
25-072 | Burke Industrial | Y | -4 | Y |  | Y |  | Y | 5 | 4 | Y | 91 | Y | -87 | Y | 0 |  | -7 | Y | -5 | Y |  |  |  |  | 1 | Y | 63 | 2025-10-13 | 2025-07-14 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-22
25-073 | Burke Industrial | Y | -4 | Y |  | Y |  | Y | 5 | 4 | Y | 91 | Y | -87 | Y | 0 |  | -7 | Y | -5 | Y |  |  |  |  | 1 | Y | 66 | 2025-10-13 | 2025-07-14 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-25
25-074 | Kemira | Y | 9 | Y |  | Y |  | Y | 3 | 2 | Y | 96 | Y | -92 | Y | 1 |  | -6 | Y | 34 | Y |  |  |  |  | 34 | Y | 139 | 2025-10-28 | 2025-07-22 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-17
25-075 | Kemira | Y | 9 | Y |  | Y | -5 | Y | 2 | 1 | Y | 95 | Y | -92 | Y | 0 |  | -7 | Y | 47 | Y |  |  |  |  | 54 | Y | 96 | 2025-11-25 | 2025-08-19 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-03
25-076 | Irving tissue | Y | 13 | Y |  | Y | -8 | Y | 5 | 4 | Y | 182 | Y | -181 | Y | -5 |  | -12 | Y | -5 | Y |  |  |  |  | -6 | Y | 35 | 2026-02-17 | 2025-08-19 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-09-30
25-077 | Epic Systems | Y | 7 | Y |  | Y | -12 | Y | 5 | 4 | Y | 182 | Y | -174 | Y | 3 |  | -96 | Y | 45 | Y |  |  |  |  | 52 | Y | 127 | 2026-02-23 | 2025-08-25 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-06
25-078 | Epic Systems | Y | 5 | Y |  | Y | 0 | Y | 5 | 4 | Y | 182 | Y | -174 | Y | 2 |  | -5 | Y | 45 | Y |  |  |  |  | 57 | Y | 127 | 2026-02-23 | 2025-08-25 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-06
25-079 | Epic Systems | Y | 5 | Y |  | Y | -7 | Y | 5 | 4 | Y | 182 | Y | -174 | Y | 2 |  | -5 | Y | 45 | Y |  |  |  |  | 57 | Y | 127 | 2026-02-23 | 2025-08-25 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-06
25-080 | Domtar | Y | 0 | Y |  |  |  | Y | 19 | 18 | Y | 196 | Y | -153 | Y | 27 |  | 20 | Y | 33 | Y |  |  |  |  | 69 | Y | 146 | 2026-02-19 | 2025-08-21 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-07
25-083 | Synthomer | Y | 10 | Y | -5 | Y | 7 | Y | -92 | -93 | Y | 85 | Y | -273 | Y | -97 | Y | -104 | Y | -91 | Y | -41 | Y | -91 | Y | -92 | Y |  | 2026-05-05 | 2025-11-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-09 | 26 | 2026-08-03
25-084 | Atlas Minerals | Y | 0 | Y | -8 | Y |  | Y | -2 | -3 | Y | 98 | Y | -179 | Y | -13 | Y | -20 | Y | -1 | Y | 35 | Y | -1 | Y | -2 | Y |  | 2026-02-17 | 2025-11-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-14 | -56 | 2026-02-17 | HOLD |  | Customer needs time to Prep Site
25-085 | Noah Industrial | Y | 0 | Y | -11 | Y |  | Y | 3 | 2 | Y | 110 | Y | -112 | Y | -1 |  | -8 | Y | 18 | Y |  |  |  |  | 25 | Y | 102 | 2025-12-09 | 2025-08-19 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-08
25-086 | Tellus | Y | 154 | Y | 0 | Y | -7 | Y |  |  |  |  | Y | -320 | Y | -140 |  | -147 | Y | -149 | Y |  |  |  |  | -149 | Y | -14 | 2026-09-14 |  |  | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-31
25-087 | Solvay | Y | 0 | Y | -3 | Y | -7 | Y | 5 | 4 | Y | 84 | Y | -80 | Y | 0 |  | -7 | Y | -7 | Y |  |  |  |  | -6 | Y | 30 | 2025-12-08 | 2025-09-15 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-10-22
25-088 | CIL Isotopes | Y | 0 |  |  | Y |  | Y | 4 | 3 | Y | 48 | Y | -47 | Y | -1 |  | -8 | Y | -8 | Y |  |  |  |  | 22 | Y | 56 | 2025-11-03 | 2025-09-15 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-11-18
25-089 | Valmet | Y | -0.5 | Y | 12 | Y |  | Y | 11 | 10 | Y | 174 | Y | -158 | Y | 4 | Y | -3 | Y | -1 | Y | 69 | Y | -1 | Y | 3 | Y | 94 | 2026-05-21 | 2025-12-04 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 |  |  |  | 2026-03-05 | 2026-03-09
25-090 | GAF | Y | -3 | Y |  | Y | -11 | Y | -16 | -17 | Y | 0 | Y |  | Y |  |  |  | Y | [8 empty] | -7 | 2025-09-12 | 2025-08-22 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 2025-09-12
25-091 | US Sugar | Y | 111 | Y |  | Y | -11 | Y |  |  |  |  | Y | -113 | Y | -113 |  | -120 | Y | -121 | Y |  |  |  |  | -121 | Y | -14 | 2026-03-23 |  |  | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-12-31
25-092 | Symrise | Y | -7 | Y | -6 | Y | -1 | Y | 2 | 1 | Y | 123 | Y | -107 | Y | 12 | Y | 5 | Y | 57 | Y | 60 | Y | 57 | Y | 60 | Y |  | 2026-03-02 | 2025-10-27 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-02 | -31 | 2026-02-26
25-093 | Symrise | Y | -7 | Y | -6 | Y | -6 | Y | 2 | 1 | Y | 123 | Y | -107 | Y | 12 | Y | 5 | Y | 57 | Y | 63 | Y | 57 | Y | 60 | Y |  | 2026-03-02 | 2025-10-27 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-02 | -31 | 2026-02-26
25-094 | Kimberly Clark | Y | 0 | Y |  | Y | -8 | Y | 27 | 26 | Y | 120 | Y | -73 | Y | 18 |  | 11 | Y | 21 | Y |  |  |  |  | 28 | Y | -286 | 2026-02-24 | 2025-11-18 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2025-01-21
25-095 | Andritz | Y | -1 | Y |  | Y | 3 | Y |  |  |  |  | Y |  | Y |  |  |  | Y | [8 empty] | -47 | 2026-03-23 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 2025-12-31
25-096 | Milliken | Y | 2 | Y | -11 | Y | 3 | Y | 5 | 4 | Y | 77 | Y | 182555 | Y | 5 |  | -2 | Y | 25 | Y |  |  |  |  | 31 | Y | 69 | 2026-01-08 | 2025-10-23 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-07
25-097 | Milliken | Y | 2 | Y | -11 | Y | 3 | Y | 5 | 4 | Y | 77 | Y | 182555 | Y | 5 |  | -2 | Y | 25 | Y |  |  |  |  | 31 | Y | 69 | 2026-01-08 | 2025-10-23 | DONE | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  |  |  | 2026-01-07
25-098 | Coastal Technologies | Y | 0 | Y | 2 | Y | 3 | Y | 4 | 3 | Y | 125 | Y | -143 | Y | 6 | Y | -1 | Y | -42 | Y | -44 | Y | 62 | Y | -37 | Y |  | 2026-03-05 | 2025-10-30 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-30 | -25 | 2026-02-27 | HOLD
25-099 | Burke Industrial | Y | -1 | Y | -3 | Y | 3 | Y | 5 | 4 | Y | 112 | Y | -104 | Y | 1 | Y | -6 | Y | 58 | Y | 64 | Y | 64 | Y | 64 | Y |  | 2026-02-25 | 2025-11-05 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-19 | -22 | 2026-02-18
25-101 | Harper Love | Y | -1 | Y | -7 | Y | -36 | Y | 5 | 4 | Y | 126 | Y | -124 | Y | 1 | Y | -6 | Y | 28 | Y | 25 | Y | 28 | Y | 29 | Y |  | 2026-04-13 | 2025-12-08 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-05-11 | -28 | 2026-04-06
25-102 | Epic Systems | Y | 0 | Y | 4 | Y | 59 | Y | 3 | 2 | Y | 124 | Y | -125 | Y | -3 |  | -10 | Y | [9 empty] | 2026-06-30 | 2026-02-24 | 2026-03-16 | 0 | 2026-03-16 | 0 | 2026-03-16 | 0 | 2026-03-16 | 7 | 2026-03-23 | 7 | 2026-04-27 | 64 | 2026-06-25
25-103 | Epic Systems | Y | 0 | Y | 4 | Y | -7 | Y | -2 | -3 | Y | 119 | Y | -132 | Y | -10 |  | -17 | Y |  |  |  |  | -8 | Y |  |  |  | 2026-06-25 | 2026-02-19 | 2026-03-16 | 0 | DONE | 0 | 2026-03-16 | 0 | 2026-03-16 | 7 | 2026-03-23 | 7 | 2026-04-27 | 59 | 2026-06-25
25-104 | Epic Systems | Y | 0 | Y | 4 | Y | -7 | Y | -2 | -3 | Y | 119 | Y | -129 | Y | -10 |  | -17 | Y |  |  |  |  | -8 | Y |  |  |  | 2026-06-25 | 2026-02-19 | 2026-03-16 | 0 | DONE | 0 | 2026-03-16 | 0 | 2026-03-16 | 7 | 2026-03-23 | 7 | 2026-04-27 | 59 | 2026-06-25
25-105 | Epic Systems | Y | 0 | Y | 4 | Y | -3 | Y | -2 | -3 | Y | 119 | Y | -127 | Y | -7 |  | -14 | Y |  |  |  |  | -8 | Y |  |  |  | 2026-06-25 | 2026-02-19 | 2026-04-20 | 35 | DONE | 0 | 2026-04-20 | 35 | 2026-04-20 | 7 | 2026-04-27 | 42 | 2026-06-01 | 24 | 2026-06-25
25-106 | Epic Systems | Y | 0 | Y | 4 | Y | -3 | Y | 3 | 2 | Y | 124 | Y | -120 | Y | -1 |  | -8 | Y | [9 empty] | 2026-06-30 | 2026-02-24 | 2026-04-20 | 35 | 2026-04-20 | 35 | 2026-04-20 | 35 | 2026-04-20 | 7 | 2026-04-27 | 42 | 2026-06-01 | 29 | 2026-06-25
25-107 | Epic Systems | Y | -96 | Y | -4 | Y | -18 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-04-20 | 7 | 2026-04-27 | 42 | 2026-06-01 | 49 | 2026-07-23
25-108 | Epic Systems | Y | -1 | Y | 91 | Y | -3 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-04-20 | 7 | 2026-04-27 | 42 | 2026-06-01 | 49 | 2026-07-16
25-109 | Epic Systems | Y | -1 | Y | -2 | Y | -8 | Y | -2 | -3 | Y | 119 | Y | -163 | Y | -43 | Y | -50 | Y |  |  |  |  | -8 | Y |  |  |  | 2026-06-25 | 2026-02-19 | 2026-03-16 | 0 | DONE | 0 | 2026-03-16 | 0 | DONE | 0 | 2026-03-23 | 7 | 2026-04-27 | 59 | 2026-06-25
25-110 | Epic Systems | Y | -1 | Y | -6 | Y | 55 | Y | 30 | 29 | Y | 151 | Y | -135 | Y | -4 | Y | -11 | Y |  |  |  |  | 19 | Y |  |  |  | 2026-06-30 | 2026-02-24 | 2026-03-16 | 0 | DONE | 0 | 2026-03-16 | 0 | DONE | 0 | 2026-03-23 | 7 | 2026-04-27 | 64 | 2026-05-29
25-111 | Epic Systems | Y | -1 | Y | 18 | Y | 55 | Y | 30 | 29 | Y | 151 | Y | -93 | Y | 31 |  | 24 | Y |  |  |  |  | 19 | Y |  |  |  | 2026-06-30 | 2026-02-24 | 2026-03-16 | 0 | DONE | 0 | 2026-03-16 | 0 | 2026-03-16 | 7 | 2026-03-23 | 7 | 2026-04-27 | 64 | 2026-05-29
25-112 | Epic Systems | Y | -1 | Y | 18 | Y |  | Y | 30 | 29 | Y | 151 | Y | -93 | Y | 31 |  | 24 | Y |  |  |  |  | 19 | Y |  |  |  | 2026-06-30 | 2026-02-24 | 2026-03-16 | 0 | DONE | 0 | 2026-03-16 | 0 | 2026-03-16 | 7 | 2026-03-23 | 7 | 2026-04-27 | 64 | 2026-05-29
25-113 | Epic Systems | Y | 0 | Y | 3 | Y | -4 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-03-30 | 7 | 2026-04-06 | 21 | 2026-05-11 | 70 | 2026-06-08
25-115 | Epic Systems | Y | -1 | Y | -2 | Y | -2 | Y | -2 | -3 | Y | 119 | Y | -127 | Y | -7 |  | -14 | Y | [9 empty] | 2026-06-25 | 2026-02-19 | 2026-03-30 | 14 | 2026-03-30 | 14 | 2026-03-30 | 14 | 2026-03-30 | 7 | 2026-04-06 | 21 | 2026-05-11 | 45 | 2026-06-25
25-116 | Polynt | Y | 17 | Y | -8 | Y | -2 | Y |  |  |  | 126 | Y | -162 | Y | -41 | Y | -48 | Y |  |  |  |  | -1 | Y |  |  |  | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | DONE | 0 | 2026-05-12 | 57 | 2026-06-16 | 34 | 2026-06-18
25-117 | Merrick | Y | 5 | Y | 55 | Y | -2 | Y | 6 | 5 | Y | 141 | Y | -137 | Y | 0 | Y | -7 | Y | -11 | Y | -5 | Y | -5 | Y | -5 | Y |  | 2026-06-30 | 2026-02-10 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-13 | 78 | 2026-06-22
25-118 | Merrick | Y | 5 | Y | 55 | Y | -18 | Y | 5 | 4 | Y | 140 |  |  |  |  | Y | -10 | Y | -13 | Y |  |  | 2 | Y | 9 | Y |  | 2026-07-06 | 2026-02-16 | DONE | 0 | DONE | 0 | 2026-03-30 | 14 | DONE | 0 | DONE | 0 | 2026-05-11 | 56 | 2026-06-29
25-119 | Vertiv | Y | -4 | Y |  | Y | 7 | Y | -2 | -3 | Y | -7 | [15 empty] | 14 | 2025-12-03 | 2025-12-03 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 2025-12-31
25-120 | Andritz | Y | 40 | Y | 55 | Y | 6 | Y |  |  |  | 182 | [16 empty] | 2026-09-14 |  |  | 0 |  | 0 |  | 0 | 2026-05-18 | 7 | 2026-05-25 | 70 | 2026-07-06 | 70 | 2026-07-01
25-121 | Kimberly Clark | Y | 7 | Y | -1 | Y | 6 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-04-06 | 7 | 2026-04-13 | 28 | 2026-05-18 | 63 | 2026-07-14 | HOLD
25-122 | Kimberly Clark | Y | 7 | Y | -1 | Y | -1 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-04-06 | 7 | 2026-04-13 | 28 | 2026-05-18 | 63 | 2026-07-14 | HOLD
25-123 | Kimberly Clark | Y | 7 | Y | -1 | Y | -1 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-04-06 | 7 | 2026-04-13 | 28 | 2026-05-18 | 63 | 2026-05-28
25-124 | Vertiv | Y | 16 | Y | -14 | Y | -1 | Y |  |  |  | 224 | Y | -225 | Y | -7 |  | -14 | Y | -12 | Y | -11 | Y | 42 | Y | 12 | Y |  | 2026-10-26 |  |  | 0 |  | 0 |  | 0 |  | 0 | DONE | 0 |  |  | 2026-08-12 | 2026-03-16 |  | FIRST 24 TO SHIP
25-356 | Synthomer | Y | 2 | Y | 42 | Y | -4 | Y | 3 | 2 | Y | 131 | Y | -115 | Y | -1 |  | -8 | Y | [9 empty] | 2026-07-02 | 2026-02-26 | 2026-04-27 | 42 | 2026-04-27 | 42 | 2026-04-27 | 42 | 2026-04-27 | 7 | 2026-05-04 | 49 | 2026-06-08 | 24 | 2026-06-27 |  |  | 4/29-(2) Head & 5/11-24" Quick Open T-Bolt Manway
25-357 | Sylvamo | Y | 2 | Y | 6 | Y | 1 | Y |  |  |  | 112 | [16 empty] | 2026-07-06 |  |  | 0 |  | 0 |  | 0 | 2026-04-06 | 7 | 2026-04-13 | 28 | 2026-05-18 | 49 | 2026-06-03
25-358 | Sylvamo | Y | 3 | Y | 6 | Y | -29 | Y |  |  |  | 112 | [16 empty] | 2026-07-06 |  |  | 0 |  | 0 |  | 0 | 2026-04-06 | 7 | 2026-04-13 | 28 | 2026-05-18 | 49 | 2026-06-03
26-002 | SNF | Y | 0 | Y | 3 | Y | -29 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-05-20 | 7 | 2026-05-27 | 72 | 2026-07-01 | 19 | 2026-06-26
26-003 | SNF | Y | 0 | Y | 3 | Y | 1 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-05-20 | 7 | 2026-05-27 | 72 | 2026-07-01 | 19 | 2026-06-26
26-004 | SNF | Y | 0 | Y | 3 | Y | 1 | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-05-20 | 7 | 2026-05-27 | 72 | 2026-07-01 | 19 | 2026-06-26
26-005 | US Sugar | Y | -4 | Y | -4 | Y | -3 | Y | 19 | 18 | Y | 133 | [16 empty] | 2026-07-01 | 2026-03-04 | 2026-03-30 | 14 | 2026-03-30 | 14 | 2026-03-30 | 14 | 2026-03-30 | 7 | 2026-04-06 | 21 | 2026-05-18 | 44 | 2026-06-10
26-014 | SNF | Y | 2 | Y | 1 | Y | -3 | Y |  |  |  | 112 | [16 empty] | 2026-07-06 |  |  | 0 |  | 0 |  | 0 | 2026-04-13 | 7 | 2026-04-20 | 35 | 2026-06-01 | 35 | 2026-03-04
26-015 | SNF | Y | 0 | Y | -1 | Y | -6 | Y |  |  |  | 112 | [16 empty] | 2026-07-06 |  |  | 0 |  | 0 |  | 0 | 2026-05-19 | 7 | 2026-05-26 | 71 | 2026-06-23 | 13 | 2026-03-09
26-016 | SNF | Y | -2 | Y | -13 | Y | -6 | Y |  |  |  | 112 | [16 empty] | 2026-07-06 |  |  | 0 |  | 0 |  | 0 | 2026-05-05 | 7 | 2026-05-12 | 57 | 2026-06-23 | 13 | 2026-03-09
26-017 | SNF | Y | 2 | Y | 1 |  |  | Y |  |  |  | 140 | [16 empty] | 2026-08-03 |  |  | 0 |  | 0 |  | 0 | 2026-05-20 | 7 | 2026-05-27 | 72 | 2026-07-08 | 26 | 2026-03-04
26-018 | SNF | Y | 2 | Y | 1 |  |  | Y |  |  |  | 140 | [16 empty] | 2026-08-03 |  |  | 0 |  | 0 |  | 0 | 2026-05-20 | 7 | 2026-05-27 | 72 | 2026-07-08 | 26 | 2026-03-04
26-020 | US Sugar | Y | 0 | Y | -3 |  |  | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-05-27 | 7 | 2026-06-03 | 79 | 2026-07-15 | 5 | 2026-07-17
26-021 | US Sugar | Y | 0 | Y | -3 |  |  | Y |  |  |  | 126 | [16 empty] | 2026-07-20 |  |  | 0 |  | 0 |  | 0 | 2026-05-27 | 7 | 2026-06-03 | 79 | 2026-07-15 | 5 | 2026-07-17
26-022 | Andritz | Y | 3 | Y | -5 |  |  | Y |  |  |  | 112 | [16 empty] | 2026-07-06 |  |  | 0 |  | 0 |  | 0 | 2026-04-23 | 7 | 2026-04-30 | 45 | 2026-06-04 | 32 | 2026-03-09
26-024 | Polynt | Y |  | Y | -6 |  |  | Y |  |  |  | 112 | [16 empty] | 2026-07-06 |  |  | 0 |  | 0 |  | 0 | 2026-06-22 | 7 | 2026-06-29 | 105 | 2026-07-20 | -14 | 2026-03-10
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
0 | [7 empty] | Y | [23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
Formulas:
Drop Dead Date Week of = IF([Drawings Certified]="",TODAY()+(VLOOKUP([Job #],'Date Calcs'!A:G,7,0)*7),VLOOKUP([Job #],'Actual Dates'!A:AE,21,FALSE))
Drop Dead Date Week of = IFNA(IF([Drawings Certified]="",TODAY()+(VLOOKUP([Job #],'Date Calcs'!A:G,7,0)*7),VLOOKUP([Job #],'Actual Dates'!A:AE,21,FALSE)),"")
Drawings Certified = IF(VLOOKUP([Job #],'Actual Dates'!A:AE,20,0)="","",VLOOKUP([Job #],'Actual Dates'!A:AE,20,0))
Drawings Certified = IFNA(IF(VLOOKUP([Job #],'Actual Dates'!A:AE,20,0)="","",VLOOKUP([Job #],'Actual Dates'!A:AE,20,0)+(VLOOKUP([Job #],'Date Calcs'!A:X,22,0)*7)),"")
Days to go = IFERROR([Release to Shop By Ship Date]-TODAY(),0)
days to go = IFERROR([QC Checklist]-TODAY(),0)
days to go = IFERROR([Burn File]-TODAY(),0)
Ship Date Week Of = IFNA(VLOOKUP([Job #],'Ship Date'!A:C,3,0),"")
Ship Date Week Of = IFERROR(IFNA(VLOOKUP([Job #],'Ship Date'!A:C,3,0),""),"")
UDR1 Form (ASME Only) = IFNA(IF(VLOOKUP([Job #],'Actual Dates'!A:AF,32,0)="N/A"," ",VLOOKUP([Job #],'Actual Dates'!A:AF,32,0))," ")
Actual Ship Date = IFNA(IF(VLOOKUP([Job #],'Actual Dates'!A:AE,31,0)="","",VLOOKUP([Job #],'Actual Dates'!A:AE,31,0)),"")
All MAT. On hand = IFNA(IF([Purch Recvd]="Y","DONE",VLOOKUP([Job #],'Ship Date'!A:AE,25,0)),"")
Release to Shop = IFNA(IF([Released]="Y","DONE",VLOOKUP([Job #],'Ship Date'!A:AE,30,0)),"")
Release to Shop By Ship Date = IFNA(IF([Drawings Certified]="","",IF([Build Plan]="Y","DONE",VLOOKUP([Job #],'Ship Date'!A:AE,27,0))),"")
QC Checklist = IFNA(IF([Drawings Certified]="","",IF([QC Checklist]="Y","DONE",VLOOKUP([Job #],'Ship Date'!A:AG,29,0))),"")
Burn File = IFNA(IF([Drawings Certified]="","",IF([Burn File]="Y","DONE",VLOOKUP([Job #],'Ship Date'!A:AI,28,0))),"")

## Actual Dates
Actual Dates
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Job | Submitted 0 | Submitted 1 | Submitted 2 | Submitted 3 | Rev | Approved | App. Prints Submitted | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Long lead time | Prelim BOM | Rev | Final Calcs | Cert Dwgs | Customer Drop Dead Date | Update BOM | Stock Check | Order Balance | All Purchased Parts Recv'd | Final BOM | Build Plan | Burn File | QC Checklist | Release | Delivery Date | U-DR-1 Form (ASME ONLY) | Due Date | Date Complete
24-046 | Y | Y | Y | Y | 3 | y | 2024-09-09 | 2025-05-05 | 2025-05-24 | 2025-07-08 | 2025-07-16 | 2025-07-30 | 2025-08-06 | 2025-08-08 | 2024-08-27 | 2024-08-26 | 4 | 2025-08-14 | 2025-08-14 | 2026-03-12 | 2025-08-19 | 2025-08-19 | 2025-11-06 | 2024-12-03 | 2025-11-06 | 2025-11-24 | 2025-11-18 | 2025-11-24 | 2025-12-05 |  | 2026-03-06
25-010 | Y | Y | Y | Y | 2 | y | 2025-05-28 | 2025-06-26 | 2025-07-03 | 2025-08-21 | 2025-08-28 |  |  |  | 2025-02-19 | 2025-02-17 | 3 | 2025-08-28 | 2025-08-28 | 2025-12-04 | 2025-07-25 | 2025-07-25 | 2025-07-28 | 2025-08-04 | 2025-07-28 | 2025-12-08 | 2026-01-16 | 2025-01-16 | 2026-01-17 | 2026-02-23 | 2025-11-27
25-011 | Y | Y | Y | Y | 2 | y | 2025-04-25 | 2025-05-29 | 2025-06-04 | 2025-08-28 | 2025-09-04 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-04 | 2025-09-04 | 2026-01-08 | 2025-06-26 | 2025-06-26 | 2025-06-27 |  | 2025-06-27 | 2025-10-31 |  |  |  | 2026-02-04 | 2026-01-01
25-012 | Y | Y | Y | Y | 2 | y | 2025-04-25 | 2025-05-29 | 2025-06-04 | 2025-08-28 | 2025-09-04 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-04 | 2025-09-04 | 2026-01-08 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-12-11 | 2025-07-01 | 2025-01-07 | 2025-12-09 | 2026-01-07 | 2026-01-08 |  | 2026-01-01
25-013 | Y | Y | Y | Y | 1 | y | 2025-03-25 | 2025-05-29 | 2025-06-04 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-09-04 | 2025-09-04 | 2026-01-08 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-08-18 | 2025-07-02 | 2025-10-22 | 2025-10-23 | 2025-10-25 | 2025-10-27 |  | 2025-10-02
25-014 | Y | Y | Y | Y | 1 | y | 2025-04-02 | 2025-05-14 | 2025-05-28 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-05-28 | 2025-05-28 | 2025-10-01 | 2025-07-01 | 2025-07-01 | 2025-07-02 |  | 2025-07-02 | 2025-09-03 |  |  | 2025-09-03 | 2025-11-06 | 2025-09-17
25-015 | Y | Y | Y | Y | 1 | y | 2025-04-02 | 2025-05-14 | 2025-05-28 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-05-28 | 2025-05-28 | 2025-10-29 | 2025-07-16 | 2025-07-16 | 2025-07-17 |  | 2025-07-17 | 2025-08-27 |  |  | 2025-08-27 | 2025-11-06 | 2025-10-15
25-016 | Y | Y | Y | Y | 1 | y | 2025-04-02 | 2025-05-14 | 2025-05-28 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-05-28 | 2025-05-28 | 2025-10-29 | 2025-07-21 | 2025-07-21 | 2025-07-22 | 2025-09-15 | 2025-07-22 | 2025-11-18 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2026-02-23 | 2025-10-15
25-017 | Y | Y | Y | Y | 1 | y | 2025-03-10 | 2025-04-07 | 2025-04-22 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-04-22 | 2025-04-22 | 2025-09-23 | 2025-07-22 | 2025-07-22 | 2025-07-23 |  | 2025-07-23 | 2025-09-30 |  |  | 2025-09-30 | 2026-01-21 | 2025-09-08
25-018 | Y | Y | Y | Y | 2 | y | 2025-05-21 | 2025-07-14 | 2025-08-05 | 2025-08-21 | 2025-09-05 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-05 | 2025-09-05 | 2026-02-06 | 2025-09-15 | 2025-09-17 | 2025-09-19 | 2026-02-13 | 2025-09-19 | 2025-10-22 | 2026-01-29 | 2026-01-28 | 2025-10-24 |  | 2026-01-22
25-019 | Y | Y | Y | Y | 2 | y | 2025-05-13 | 2025-06-18 | 2025-06-26 | 2025-08-28 | 2025-09-05 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-05 | 2025-09-05 | 2026-03-06 | 2025-09-13 | 2025-09-15 | 2025-09-17 | 2025-09-23 | 2025-09-17 | 2025-11-18 | 2025-12-11 | 2025-12-08 | 2025-12-04 | 2026-02-23 | 2026-02-26
25-020 | Y | Y | Y | Y | 3 | y | 2025-03-25 | 2025-05-29 | 2025-06-04 | 2025-07-24 | 2025-08-04 | 2025-08-21 | 2025-08-26 |  | 2025-02-18 | 2025-02-17 | 4 | 2025-08-26 | 2025-08-26 | 2026-02-24 | 2025-07-17 | 2025-07-17 | 2025-08-19 |  | 2025-08-19 | 2025-09-04 |  |  | 2025-09-04 | 2026-02-05 | 2026-02-19
25-021 | Y | Y | Y | Y | 2 | y | 2025-05-13 | 2025-06-18 | 2025-08-22 | 2025-08-28 | 2025-09-02 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-02 | 2025-09-02 | 2026-03-03 | 2025-09-10 | 2025-09-10 | 2025-09-11 | 2025-09-15 | 2025-09-11 | 2025-09-16 | 2025-10-20 | 2025-09-18 | 2025-09-18 | 2026-02-20 | 2026-02-26
25-023 | Y | Y | Y | Y | 2 | y | 2025-02-12 | 2025-02-26 | 2025-03-05 | 2025-03-10 | 2025-03-10 |  |  |  | 2025-02-11 | 2025-02-11 | 3 | 2025-03-10 | 2025-03-10 | 2025-06-02 | 2025-03-13 | 2025-03-14 | 2025-03-18 |  | 2025-03-18 | 2025-03-12 |  |  | 2025-03-19 | 2025-05-27 | 2025-06-02
25-024 | Y | Y | Y | Y | 2 | y | 2025-02-12 | 2025-02-26 | 2025-03-05 | 2025-03-10 | 2025-03-10 |  |  |  | 2025-02-11 | 2025-02-11 | 3 | 2025-03-10 | 2025-03-10 | 2025-06-02 | 2025-03-13 | 2025-03-14 | 2025-03-18 |  | 2025-03-18 | 2025-03-12 |  |  | 2025-03-19 | 2025-05-27 | 2025-06-02
25-025 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-22 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-05-28 | 2025-05-28 | 2025-05-28 |  | 2025-05-28 | 2025-06-03 |  |  | 2025-06-13 | 2025-09-04 | 2025-11-06
25-026 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 | 2025-05-20 | 2025-11-04 | 2025-05-15 | 2025-05-15 | 2025-05-16 |  | 2025-05-16 | 2025-06-02 |  |  | 2025-06-13 | 2025-09-04 | 2025-10-28
25-027 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 | 2025-05-20 | 2025-11-04 | 2025-05-19 | 2025-05-20 | 2025-05-21 |  | 2025-05-22 | 2025-06-03 |  |  | 2025-08-06 | 2025-10-02 | 2025-10-28
25-028 | Y | Y | Y | Y | 2 | y | 2025-03-03 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 | 2025-05-20 | 2025-11-04 | 2025-05-19 | 2025-05-20 | 2025-05-21 |  | 2025-05-22 | 2025-06-03 |  |  | 2025-08-06 | 2025-10-02 | 2025-10-28
25-029 | Y | Y | Y | Y | 2 | y | 2025-03-03 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 | 2025-05-20 | 2025-11-04 | 2025-05-19 | 2025-05-20 | 2025-05-21 |  | 2025-05-22 | 2025-06-09 |  |  | 2025-08-08 | 2025-09-30 | 2025-10-28
25-030 | Y | Y | Y | Y | 2 | y | 2025-03-05 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 | 2025-05-20 | 2025-11-04 | 2025-05-22 | 2025-05-22 | 2025-05-23 |  | 2025-05-23 | 2025-06-09 |  |  | 2025-08-08 | 2025-09-30 | 2025-10-28
25-031 | Y | Y | Y | Y | 2 | y | 2025-02-27 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-05-30 | 228428 | 2025-06-02 |  | 2025-06-02 | 2025-06-12 |  |  | 2025-08-13 | 2025-10-28 | 2025-11-05
25-032 | Y | Y | Y | Y | 2 | y | 2025-02-27 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-05-30 | 228428 | 2025-06-02 |  | 2025-06-02 | 2025-06-12 |  |  | 2025-08-15 | 2025-10-28 | 2025-11-05
25-033 | Y | Y | Y | Y | 2 | y | 2025-03-05 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-06-04 | 2025-06-04 | 2025-06-04 |  | 2025-06-04 | 2025-06-16 |  |  | 2025-08-20 | 2025-10-28 | 2025-11-05
25-034 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-06-05 | 2025-06-05 | 2025-06-06 |  | 2025-06-06 | 2025-06-16 |  |  | 2025-07-02 | 2025-08-27 | 2025-11-05
25-035 | Y | Y | Y | Y | 2 | y | 2025-03-05 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-06-05 | 2025-06-05 | 2025-06-05 |  | 2025-06-05 | 2025-06-16 |  |  | 2025-07-02 | 2025-08-27 | 2025-11-05
25-036 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-06-05 | 2025-06-05 | 2025-06-06 |  | 2025-06-06 | 2025-06-16 |  |  | 2025-07-02 | 2025-08-27 | 2025-11-05
25-037 | Y | Y | Y | Y | 2 | y | 2025-02-28 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 | 2025-05-28 | 2025-11-12 | 2025-05-28 | 2025-05-28 | 2025-05-29 |  | 2025-05-29 | 2025-06-16 |  |  | 2025-06-18 | 2025-09-04 | 2025-11-05
25-039 | Y | Y | Y | Y | 1 | y | 2025-03-20 | 2025-05-01 | 2025-05-06 | [5 empty] | 2025-03-06 | 2025-03-05 | 2 | 2025-05-06 | 2025-05-06 | 2025-08-26 | 2025-05-09 | 2025-05-12 | 2025-05-13 |  | 2025-05-14 | 2025-05-08 |  |  | 2025-05-29 | 2025-08-15 | 2025-08-21
25-040 | Y | Y | Y | Y | 1 | y | 2025-02-18 | 2025-02-25 | 2025-03-13 | [5 empty] | 2025-03-05 | 2025-03-05 | 2 | 2025-03-13 | 2025-03-13 | 2025-08-14 | 2025-03-27 | 2025-09-16 | 2025-09-16 | 2025-07-01 | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-17 |  | 2025-07-29
25-042 | Y | Y | Y | Y | 2 | y | 2025-03-25 | 2025-04-14 | 2025-04-15 | 2025-05-19 | 2025-05-22 |  |  |  | 2025-03-27 | 2025-03-27 | 3 | 2025-05-22 | 2025-05-22 | 2025-07-31 | 2025-05-27 | 2025-05-28 | 2025-05-29 |  | 2025-05-29 | 2025-06-20 |  |  | 2025-07-01 | 2025-08-27 | 2025-07-28
25-044 | Y | Y | Y | Y | 2 | y | 2025-05-14 | 2025-05-21 | 2025-05-27 | 2025-05-29 | 2025-05-30 |  |  |  | 2025-04-23 | 2025-04-18 | 3 | 2025-05-30 | 2025-05-30 | 2025-08-22 | 2025-06-12 | 2025-06-12 | 2025-06-17 |  | 2025-06-17 | 2025-06-18 |  |  | 2025-06-25 | 2025-08-14 | 2025-08-21
25-045 | Y | Y | Y | Y | 3 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-04-09 | 2025-04-09 | 4 | - |  | 0 | NA | NA | NA |  | NA |  |  |  |  | 2025-12-31 | 2026-01-14
25-052 | Y | Y | Y | Y | 3 | y | 2025-06-11 | 2025-07-01 | 2025-07-08 | 2025-07-14 | 2025-07-21 | 2025-07-22 | 2025-07-29 |  | 2025-05-23 | 2025-05-23 | 4 | 2025-07-29 | 2025-07-29 | 2025-11-04 | 2025-09-08 | 2025-09-09 | 2025-09-12 |  | 2025-09-12 | 2025-09-17 |  |  | 2025-09-23 | 2025-12-29 | 2025-10-28
25-053 | N | Y | Y | Y | [10 empty] | 2025-08-13 | 2025-08-12 | 0 | - |  | 0 | 2025-08-13 | 2025-08-13 | 2025-08-25 | 2025-09-02 | 2025-08-25 | 2025-08-28 | 2025-09-24 |  | 2025-08-28 | 2025-09-26 | 2026-07-20
25-054 | Y | Y | Y | Y | 2 | y | 2025-06-27 | 2025-06-30 | 2025-07-10 | 2025-07-10 | 2025-07-17 |  |  |  | 2025-06-09 | 2025-06-09 | 3 | 2025-07-17 | 2025-07-17 | 2025-10-30 | 2025-07-29 | 2025-07-29 | 2025-07-30 |  | 2025-07-30 | 2025-09-17 |  |  | 2025-09-23 | 2025-11-24 | 2025-10-23
25-055 | Y | Y | Y | Y | 1 | y | 2025-11-25 | 2025-12-10 | 2025-12-17 | [5 empty] | 2025-12-09 | 2025-12-08 | 2 | 2025-12-17 | 2025-12-17 | 2026-06-17 | 2026-01-02 | 2026-01-05 | 2026-01-07 |  | 2026-01-07 | 2026-03-11 | 2026-02-10 | 2026-02-08 |  |  | 2026-06-10
25-056 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2025-11-10 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-08-20 | 2025-11-11 | 2025-11-03
25-057 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2025-11-10 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-08-20 | 2025-11-11 | 2025-11-03
25-058 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2025-12-08 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-03 | 2025-12-18 | 2025-12-01
25-059 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2025-12-08 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-03 | 2025-12-16 | 2025-12-01
25-060 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2026-01-05 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-26 | 2026-01-13 | 2025-12-29
25-061 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2026-01-05 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-26 | 2026-01-13 | 2025-12-29
25-062 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2026-02-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-11-10 | 2026-02-02 | 2026-01-26
25-063 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 | 2025-08-04 | 2026-02-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-11-10 | 2026-02-02 | 2026-01-26
25-064 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-03-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 |  |  | 2025-12-09 | 2026-02-16 | 2026-02-23
25-065 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-03-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 |  |  | 2025-12-09 | 2026-02-16 | 2026-02-23
25-066 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-03-30 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-01-12 |  | 2026-03-23
25-067 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-03-30 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-01-12 |  | 2026-03-23
25-068 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-04-27 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-09 |  | 2026-04-20
25-069 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-04-27 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-09 |  | 2026-04-20
25-070 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-05-25 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-18 |  | 2026-05-18
25-071 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | n/a | n/a | 3 | 2025-08-04 | 2025-08-04 | 2026-05-25 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-18 |  | 2026-05-18
25-072 | Y | Y | Y | Y | 1 | y | 2025-07-03 | 2025-07-07 | 2025-07-14 | [5 empty] | n/a | n/a | 2 | 2025-07-14 | 2025-07-14 | 2025-10-13 | 2025-07-18 | 2025-07-18 | 2025-07-21 |  | 2025-07-21 | 2025-07-23 |  |  | 2025-07-30 | 2025-09-22 | 2025-10-06
25-073 | Y | Y | Y | Y | 1 | y | 2025-07-03 | 2025-07-07 | 2025-07-14 | [5 empty] | n/a | n/a | 2 | 2025-07-14 | 2025-07-14 | 2025-10-13 | 2025-07-18 | 2025-07-18 | 2025-07-21 |  | 2025-07-21 | 2025-07-23 |  |  | 2025-07-30 | 2025-09-25 | 2025-10-06
25-074 | Y | Y | Y | Y | 1 | y | 2025-07-16 | 2025-07-17 | 2025-07-22 | [5 empty] | n/a | n/a | 2 | 2025-07-22 | 2025-07-22 | 2025-10-28 | 2025-07-30 | 2025-07-30 | 2025-08-01 |  | 2025-08-01 | 2025-09-10 |  |  | 2025-09-11 | 2025-12-17 | 2025-10-23
25-075 | Y | Y | Y | Y | 2 | y | 2025-07-16 | 2025-07-21 | 2025-07-30 | 2025-08-15 | 2025-08-19 |  |  |  | n/a | n/a | 3 | 2025-08-19 | 2025-08-19 | 2025-11-25 | 2025-08-28 | 2025-08-28 | 2025-08-29 |  | 2025-08-29 | 2025-10-22 |  |  | 2025-10-30 | 2025-12-03 | 2025-11-21
25-076 | Y | Y | Y | Y | 1 | y | 2025-07-28 | 2025-08-12 | 2025-08-19 | [5 empty] | n/a | n/a | 2 | 2025-08-19 | 2025-08-19 | 2026-02-17 | 2025-08-20 | 2025-08-20 | 2025-08-21 |  | 2025-08-21 | 2025-08-28 |  |  | 2025-08-28 | 2025-09-30 | 2026-02-10
25-077 | Y | Y | Y | Y | 2 | y | 2025-07-23 | 2025-08-06 | 2025-08-14 | 2025-08-18 | 2025-08-25 |  |  |  | n/a | n/a | 3 | 2025-08-25 | 2025-08-25 | 2026-02-23 | 2025-09-02 | 2025-09-02 | 2025-09-04 |  | 2025-06-04 | 2025-10-23 |  |  | 2025-10-31 | 2026-01-06 | 2026-02-16
25-078 | Y | Y | Y | Y | 2 | y | 2025-07-21 | 2025-08-01 | 2025-08-11 | 2025-08-18 | 2025-08-25 |  |  |  | n/a | n/a | 3 | 2025-08-25 | 2025-08-25 | 2026-02-23 | 2025-09-02 | 2025-09-02 | 2025-09-03 |  | 2025-09-03 | 2025-10-23 |  |  | 2025-11-05 | 2026-01-06 | 2026-02-16
25-079 | Y | Y | Y | Y | 2 | y | 2025-07-21 | 2025-08-01 | 2025-08-11 | 2025-08-18 | 2025-08-25 |  |  |  | n/a | n/a | 3 | 2025-08-25 | 2025-08-25 | 2026-02-23 | 2025-09-02 | 2025-09-02 | 2025-09-03 |  | 2025-09-03 | 2025-10-23 |  |  | 2025-11-05 | 2026-01-06 | 2026-02-16
25-080 | Y | Y | Y | Y | 1 | y | 2025-07-18 | 2025-07-31 | 2025-08-21 | [5 empty] | n/a | n/a | 2 | 2025-08-21 | 2025-08-21 | 2026-02-19 | 2025-09-05 | 2025-09-05 | 2025-09-10 |  | 2025-09-10 | 2025-09-23 |  |  | 2025-10-30 | 2026-01-07 | 2026-01-29
25-083 | Y | Y | Y | N | 2 | y | 2025-08-15 | 2025-10-14 | 2025-10-29 | 2025-10-30 | 2025-11-04 | 2026-02-02 |  |  | 2025-07-24 | 2025-07-24 | 3 | 2025-11-04 | 2025-11-04 | 2026-05-05 | 2025-11-10 | 2025-11-10 | 2025-11-11 | 2026-01-08 | 2025-11-11 | 2025-11-24 | 2026-01-13 | 2025-11-24 | 2025-11-24 |  | 2026-08-03
25-084 | Y | Y | Y | Y | 3 | y | 2025-08-08 | 2025-08-11 | 2025-08-18 | 2025-10-15 | 2025-10-21 | 2025-10-24 | 2025-10-31 | 2025-11-04 | 2025-07-24 | 2025-07-24 | 4 | 2025-11-04 | 2025-11-04 | 2026-02-17 | 2025-10-24 | 2025-10-24 | 2025-11-05 | 2025-11-17 | 2025-11-05 | 2025-11-24 | 2025-12-30 | 2025-11-24 | 2025-11-24 |  | 2026-02-17
25-085 | Y | Y | Y | Y | 1 | y | 2025-08-12 | 2025-08-14 | 2025-08-19 | [5 empty] | 2025-07-25 | 2025-07-24 | 2 | 2025-08-19 | 2025-08-19 | 2025-12-09 | 2025-08-21 | 2025-08-21 | 2025-08-27 |  | 2025-08-27 | 2025-09-22 |  |  | 2025-09-30 | 2025-12-08 | 2025-12-04
25-086 | Y | Y | Y | Y | 3 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-08-13 | 2025-08-13 | 4 | - |  | 0 | 2025-08-22 | 2025-08-22 | 2025-08-27 |  | 2025-08-27 | 2025-08-25 |  |  | 2025-08-26 | 2025-12-31 | 2026-07-01
25-087 | Y | Y | Y | Y | 1 | y | 2025-08-28 | 2025-09-08 | 2025-09-15 | [5 empty] | 2025-08-18 | 2025-08-14 | 2 | 2025-09-15 | 2025-09-15 | 2025-12-08 | 2005-09-19 | 2025-09-19 | 2025-09-22 |  | 2025-09-22 | 2025-09-22 |  |  | 2025-09-24 | 2025-10-22 | 2025-12-01
25-088 | Y | Y | Y | Y | 1 | y | 2025-09-03 | 2025-09-09 | 2025-09-15 | [7 empty] | 2 | 2025-09-15 | 2025-09-15 | 2025-11-03 | 2025-09-18 | 2025-09-18 | 2025-09-22 |  | 2025-09-22 | 2025-09-22 |  |  | 2025-10-23 | 2025-11-18 | 2025-10-28
25-089 | Y | Y | Y | Y | 1 | y | 2025-09-22 | 2025-11-21 | 2025-12-04 | [5 empty] | 2025-09-17 | 2025-09-12 | 2 | 2025-12-04 | 2025-12-04 | 2026-05-21 | 2025-12-08 | 2025-12-08 | 2025-12-09 | 2026-01-21 | 2025-12-09 | 2025-12-11 | 2026-02-19 | 2025-12-11 | 2025-12-16 | 2026-03-09 | 2026-05-08
25-090 | Y | Y | Y | Y | 0 | y | 2025-08-22 | [7 empty] | NA | NA | 1 | 2025-08-22 | 2025-08-22 | 2025-09-12 | NA | NA | NA |  | NA |  |  |  |  | 2025-09-12 | 2025-09-26
25-091 | Y | Y | Y | Y | 3 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | NA | NA | 4 | - |  | 0 | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-22 |  |  | 2025-09-23 | 2025-12-31 | 2026-01-07
25-092 | Y | Y | Y | Y | 2 | y | 2025-10-01 | 2025-10-07 | 2025-10-14 | 2025-10-23 | 2025-10-27 |  |  |  | 2025-09-18 | 2025-09-17 | 3 | 2025-10-27 | 2025-10-27 | 2026-03-02 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-12-01 | 2025-11-18 | 2026-01-09 | 2026-01-12 | 2026-01-09 | 2026-01-13 |  | 2026-02-26
25-093 | Y | Y | Y | Y | 2 | y | 2025-10-01 | 2025-10-07 | 2025-10-14 | 2025-10-23 | 2025-10-27 |  |  |  | 2025-09-18 | 2025-09-17 | 3 | 2025-10-27 | 2025-10-27 | 2026-03-02 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-12-01 | 2025-11-18 | 2026-01-09 | 2026-01-15 | 2026-01-09 | 2026-01-13 |  | 2026-02-26
25-094 | Y | Y | Y | Y | 1 | y | 2025-10-06 |  | 2025-11-18 | [5 empty] | NA | NA | 2 | 2025-11-18 | 2025-11-18 | 2026-02-24 | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2025-11-21 | 2025-12-01 |  |  | 2025-12-09 | 2025-01-21 | 2026-01-26
25-095 | Y | Y | Y | Y | 2 |  | 2025-10-16 | 2025-11-12 | 2025-11-19 | 2026-02-02 | 2026-02-13 |  |  |  | NA | NA | 3 | - |  | 0 | NA | NA | NA |  | NA |  |  |  |  | 2025-12-31 | 2026-02-09
25-096 | Y | Y | Y | Y | 1 | y | 2025-10-15 | 2025-10-16 | 2025-10-23 | [5 empty] | 2025-09-25 | 2025-09-25 | 2 | 2025-10-23 | 2025-10-23 | 2026-01-08 | 2025-11-03 | 228585 | 2025-11-04 |  | 2025-11-04 | 2025-12-01 |  |  | 2025-12-08 | 2026-01-07 | 2026-01-01
25-097 | Y | Y | Y | Y | 1 | y | 2025-10-15 | 2025-10-16 | 2025-10-23 | [5 empty] | 2025-09-25 | 2025-09-25 | 2 | 2025-10-23 | 2025-10-23 | 2026-01-08 | 2025-11-03 | 228585 | 2025-11-04 |  | 2025-11-04 | 2025-12-01 |  |  | 2025-12-08 | 2026-01-07 | 2026-01-01
25-098 | Y | Y | Y | Y | 1 | y | 2025-10-22 | 2025-10-24 | 2025-10-30 | [5 empty] | 2025-10-10 | 2025-10-07 | 2 | 2025-10-30 | 2025-10-30 | 2026-03-05 | 2025-11-11 | 2025-11-11 | 2025-11-13 | 2026-03-03 | 2025-11-13 | 2026-01-15 | 2026-01-13 | 2026-01-15 | 2026-01-21 |  | 2026-02-27
25-099 | Y | Y | Y | Y | 1 | y | 2025-10-29 | 2025-10-29 | 2025-11-05 | [5 empty] | 2025-10-13 | 2025-10-10 | 2 | 2025-11-05 | 2025-11-05 | 2026-02-25 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-19 | 2025-11-13 | 2026-01-16 | 2026-01-22 | 2026-01-22 | 2026-01-23 |  | 2026-02-18
25-101 | Y | Y | Y | Y | 1 | y | 2025-11-20 | 2025-12-01 | 2025-12-08 | [5 empty] | 2025-10-31 | 2025-10-30 | 2 | 2025-12-08 | 2025-12-08 | 2026-04-13 | 2025-12-10 | 2025-12-10 | 2025-12-16 | 2026-02-10 | 2025-12-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | 2026-01-21 |  | 2026-04-06
25-102 | Y | Y | Y | N | 2 | y | 2025-12-12 | 2026-01-12 | 2026-01-19 | 2026-02-02 | 2026-02-04 | 2026-02-19 |  |  | 2025-11-25 | 2025-11-24 | 3 | 2026-02-24 | 2026-02-24 | 2026-06-30 | 2026-02-27 | 2026-02-27 | 2026-03-02 |  | 2026-03-02 | [5 empty] | 2026-06-25
25-103 | Y | Y | Y | N | 2 | y | 2025-12-12 | 2026-01-12 | 2026-01-22 | 2026-02-02 | 2026-02-04 | 2026-02-19 |  |  | 2025-11-25 | 2025-11-24 | 3 | 2026-02-19 | 2026-02-19 | 2026-06-25 | 2026-02-20 | 2026-02-20 | 2026-02-23 |  | 2026-02-23 |  |  | 2026-03-04 |  |  | 2026-06-25
25-104 | Y | Y | Y | N | 2 | y | 2025-12-12 | 2026-01-12 | 2026-01-22 | 2026-02-02 | 2026-02-04 | 2026-02-19 |  |  | 2025-11-25 | 2025-11-24 | 3 | 2026-02-19 | 2026-02-19 | 2026-06-25 | 2026-02-23 | 2026-02-23 | 2026-02-23 |  | 2026-02-23 |  |  | 2026-03-04 |  |  | 2026-06-25
25-105 | Y | Y | Y | N | 2 | y | 2025-12-12 | 2026-01-12 | 2026-01-28 | 2026-02-02 | 2026-02-04 | 2026-02-19 |  |  | 2025-11-25 | 2025-11-24 | 3 | 2026-02-19 | 2026-02-19 | 2026-06-25 | 2026-02-25 | 2026-02-25 | 2026-02-26 |  | 2026-02-26 |  |  | 2026-03-04 |  |  | 2026-06-25
25-106 | Y | Y | Y | N | 2 | y | 2025-12-12 | 2026-01-12 | 2026-01-28 | 2026-02-02 | 2026-02-05 | 2026-02-19 |  |  | 2025-11-25 | 2025-11-24 | 3 | 2026-02-24 | 2026-02-24 | 2026-06-30 | 2026-03-04 | 2026-03-04 | 2026-03-04 |  | 2026-03-04 | [5 empty] | 2026-06-25
25-107 | Y | Y | N | Y | 1 |  | 2025-11-26 | 2026-02-02 | 2026-02-25 | 2026-03-12 |  |  |  |  | 2026-02-12 | 2026-01-11 | 2 | - |  | 2026-07-30 | [10 empty] | 2026-07-23
25-108 | Y | Y | N | Y | 1 |  | 2025-11-26 | 2026-02-02 | 2026-02-11 | 2026-03-12 |  |  |  |  | 2026-02-12 | 2026-01-11 | 2 | - |  | 2026-07-23 | [10 empty] | 2026-07-16
25-109 | Y | Y | Y | Y | 3 | y | 2025-11-26 | 2025-12-12 | 2025-12-19 | 2026-01-12 | 2026-01-19 | 2026-01-23 | 2026-01-30 | 2026-02-19 | 2025-11-11 | 2025-11-06 | 4 | 2026-02-19 | 2026-02-19 | 2026-06-25 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-02-16 | 2026-01-21 |  |  | 2026-03-04 |  |  | 2026-06-25
25-110 | Y | Y | Y | Y | 3 | y | 2025-11-26 | 2025-12-12 | 2025-12-22 | 2026-01-12 | 2026-01-19 | 2026-01-23 | 2026-01-30 |  | 2025-11-07 | 2025-11-06 | 4 | 2026-02-24 | 2026-02-24 | 2026-06-30 | 2026-01-21 | 2026-01-21 | 2026-02-02 | 2026-02-16 | 2026-02-02 |  |  | 2026-03-04 |  |  | 2026-05-29
25-111 | Y | Y | Y | Y | 3 | y | 2025-11-26 | 2025-12-12 | 2025-12-19 | 2026-01-12 | 2026-01-21 | 2026-01-23 | 2026-01-30 |  | 2025-12-01 | 2025-11-10 | 4 | 2026-02-24 | 2026-02-24 | 2026-06-30 | 2026-03-04 | 2026-03-04 | 2026-03-09 |  | 2026-03-09 |  |  | 2026-03-04 |  |  | 2026-05-29
25-112 | Y | Y | Y | Y | 3 | y | 2025-11-26 | 2025-12-12 | 2025-12-19 | 2026-01-12 | 2026-01-21 | 2026-01-23 | 2026-01-30 |  | 2025-12-01 | 2025-11-10 | 4 | 2026-02-24 | 2026-02-24 | 2026-06-30 | 2026-03-04 | 2026-03-04 | 2026-03-09 |  | 2026-03-09 |  |  | 2026-03-04 |  |  | 2026-05-29
25-113 | Y | Y | Y | Y | 2 |  | 2025-12-12 | 2026-01-12 | 2026-01-19 | 2026-02-02 | 2026-02-05 |  |  |  | 2025-12-01 | 2025-11-10 | 3 | - |  | 2026-06-15 | [10 empty] | 2026-06-08
25-115 | Y | Y | Y | N | 2 | y | 2025-11-26 | 2026-01-12 | 2026-01-21 | 2026-01-23 | 2026-01-30 | 2026-02-19 |  |  | 2025-11-11 | 2025-11-10 | 3 | 2026-02-19 | 2026-02-19 | 2026-06-25 | 2026-02-25 | 2026-02-25 | 2026-02-26 |  | 2026-02-26 | [5 empty] | 2026-06-25
25-116 | Y | Y | Y | Y | 2 |  | 2025-12-19 | 2026-01-02 | 2026-01-09 | 2026-02-12 | 2026-02-19 |  |  |  | 2025-11-10 | 2025-11-10 | 3 | - |  | 2026-06-25 | 2026-01-14 | 2026-01-14 | 2026-01-16 | 2026-02-26 | 2026-01-16 |  |  | 2026-03-04 |  |  | 2026-06-18
25-117 | Y | Y | Y | Y | 2 | y | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-02 | 2026-02-10 |  |  |  | 2026-01-15 | 2026-01-15 | 3 | 2026-02-10 | 2026-02-10 | 2026-06-30 | 2026-02-12 | 2026-02-12 | 2026-02-16 | 2026-03-11 | 2026-02-16 | 2026-02-12 | 2026-02-18 | 2026-02-18 | 2026-02-19 |  | 2026-06-22
25-118 | Y | Y | Y | Y | 2 | y | 2026-01-14 | 2026-01-21 | 2026-02-02 | 2026-02-09 | 2026-02-16 |  |  |  | 2026-01-15 | 2026-01-15 | 3 | 2026-02-16 | 2026-02-16 | 2026-07-06 |  |  |  | 2026-03-11 | 2026-02-20 | 2026-02-17 |  | 2026-03-04 | 2026-03-12 |  | 2026-06-29
25-119 | Y | Y | Y | Y | 1 | y | 2025-11-24 | 2025-12-03 | 2025-12-03 | [5 empty] | NA | NA | 2 | 2025-12-03 | 2025-12-03 | 2025-12-03 | [9 empty] | 2025-12-31 | 2025-12-03
25-120 | Y | Y | Y | Y | 3 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-29 | 2025-12-01 | 4 | - |  | 2026-07-08 | [10 empty] | 2026-07-01
25-121 | Y | N | Y | Y | 0 |  | 2026-01-08 | 2026-02-17 | [6 empty] | 2025-12-17 | 2025-12-16 | 1 | - |  | 2026-07-21 | [10 empty] | 2026-07-14
25-122 | Y | N | Y | Y | 0 |  | 2026-01-08 | 2026-02-17 | [6 empty] | 2025-12-17 | 2025-12-16 | 1 | - |  | 2026-07-21 | [10 empty] | 2026-07-14
25-123 | Y | Y | Y | Y | 0 |  | 2026-01-08 | [7 empty] | 2025-12-17 | 2025-12-16 | 1 | - |  | 2026-06-04 | [10 empty] | 2026-05-28
25-124 | Y | Y | Y | Y | 3 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-15 | 2025-12-11 | 4 | - |  | 2026-08-19 | 2026-01-06 | 2026-01-06 | 2026-01-07 |  | 2026-01-07 | 2026-01-09 | 2026-01-10 | 2026-03-04 | 2026-02-03 |  | 2026-08-12
25-356 | Y | Y | Y | Y | 2 | y | 2026-01-28 | 2026-02-02 | 2026-02-16 | 2026-02-21 | 2026-02-26 |  |  |  | 2026-02-23 | 2026-01-19 | 3 | 2026-02-26 | 2026-02-26 | 2026-07-02 | 2026-03-04 | 2026-03-04 | 2026-03-06 |  | 2026-03-06 | [5 empty] | 2026-06-27
25-357 | Y | Y | Y | Y | 1 |  | 2026-01-29 | 2026-02-11 | 2026-02-27 | [5 empty] | 2026-01-19 | 2026-01-19 | 2 | - |  | 2026-06-10 | [10 empty] | 2026-06-03
25-358 | Y | Y | Y | Y | 1 |  | 2026-01-30 | 2026-02-11 | 2026-02-27 | [5 empty] | 2026-01-19 | 2026-01-19 | 2 | - |  | 2026-06-10 | [10 empty] | 2026-06-03
26-002 | Y | Y | Y | Y | 0 |  | 2026-02-06 | [7 empty] | 2026-01-26 | 2026-01-22 | 1 | - |  | 2026-07-03 | [10 empty] | 2026-06-26
26-003 | Y | Y | Y | Y | 0 |  | 2026-02-06 | [7 empty] | 2026-01-26 | 2026-01-22 | 1 | - |  | 2026-07-03 | [10 empty] | 2026-06-26
26-004 | Y | Y | Y | Y | 0 |  | 2026-02-06 | [7 empty] | 2026-01-26 | 2026-01-22 | 1 | - |  | 2026-07-03 | [10 empty] | 2026-06-26
26-005 | Y | Y | Y | Y | 1 | y | 2026-02-05 | 2026-02-11 | 2026-03-04 | [5 empty] | 2026-01-22 | 2026-01-22 | 2 | 2026-03-04 | 2026-03-04 | 2026-07-01 | [10 empty] | 2026-06-10
26-014 | Y | Y | Y | Y | 0 |  | 2026-02-11 | [7 empty] | 2026-01-27 | 2026-01-27 | 1 | - |  | 2026-06-24 | [10 empty] | 2026-03-04
26-015 | Y | Y | Y | Y | 0 |  | 2026-03-11 | [7 empty] | 2026-02-24 | 2026-01-27 | 1 | - |  | 2026-07-22 | [10 empty] | 2026-03-09
26-016 | Y | Y | Y | Y | 0 |  | 2026-03-09 | [7 empty] | 2026-02-12 | 2026-01-27 | 1 | - |  | 2026-07-20 | [10 empty] | 2026-03-09
26-017 | Y | Y | Y | Y | 0 |  | 2026-02-11 | [7 empty] | 2026-01-27 | 2026-01-27 | 1 | - |  | 2026-07-22 | [10 empty] | 2026-03-04
26-018 | Y | Y | Y | Y | 0 |  | 2026-02-11 | [7 empty] | 2026-01-27 | 2026-01-27 | 1 | - |  | 2026-07-22 | [10 empty] | 2026-03-04
26-020 | Y | Y | N | Y | 1 |  | 2026-03-06 | 2026-03-09 | 2026-03-13 | 2026-03-13 |  |  |  |  | 2026-02-17 | 2026-02-17 | 2 | - |  | 2026-07-24 | [10 empty] | 2026-07-17
26-021 | Y | Y | N | Y | 1 |  | 2026-03-06 | 2026-03-09 | 2026-03-13 | 2026-03-13 |  |  |  |  | 2026-02-17 | 2026-02-17 | 2 | - |  | 2026-07-24 | [10 empty] | 2026-07-17
26-022 | Y | Y | Y | Y | 0 |  | 2026-03-06 | [7 empty] | 2026-02-19 | 2026-02-18 | 1 | - |  | 2026-07-17 | [10 empty] | 2026-03-09
26-024 | N | Y | Y | Y | [10 empty] | 2026-03-05 | 2026-03-05 | 0 | - |  | 2026-08-12 | [10 empty] | 2026-03-10
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
0 | N | Y | Y | Y | [12 empty] | 0 | - | [12 empty] | #N/A
Formulas:
Final Calcs = IF([Cert Dwgs]="","-",[Cert Dwgs])
Customer Drop Dead Date = IFNA(IF([Cert Dwgs]="",VLOOKUP([Job],Jobs,23,0),[Cert Dwgs]+(VLOOKUP([Job],Jobs,7,FALSE)*7)+(VLOOKUP([Job],Jobs,22,FALSE)*7)),"")
U-DR-1 Form (ASME ONLY) = IF(VLOOKUP([Job],'Date Calcs'!A:AH,33,0)="","N/A",VLOOKUP([Job],'Date Calcs'!A:AH,33,0))

## Change Order (3) (hidden)
Change Order Status
|  | Status | [5 empty] | After Return of Approval Drawings | [15 empty] | Release to Shop
Job # | Customer | Project Scope |  | Material Escalation |  | Prelim BOM |  | Final Calcs |  | A.I. |  | Cert Dwgs |  | Update BOM |  | Stock Check |  | Order Balance |  | Final BOM |  | Build Plan |  | Target | Actual | Days +/- | Status
16-073 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16-074 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16-075 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16-076 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-132 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-133 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-134 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-135 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-136 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-137 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-141 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-142 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-143 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-144 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-145 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-146 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-147 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-148 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-149 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-150 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-151 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-152 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-153 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-154 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-155 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-156 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-001 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-002 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-003 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-004 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-005 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-006 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-007 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-008 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-009 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-010 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-011 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-012 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-015 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-016 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-017 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-018 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-019 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-020 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-021 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-022 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-023 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-024 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-025 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-026 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-027 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-028 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-029 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-030 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-031 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-032 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-033 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-034 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-035 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-036 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-037 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-038 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-040 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-041 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-042 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-043 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-044 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-045 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-046 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-047 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-048 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-049 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-050 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-051 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-052 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-053 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-054 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-055 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-056 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-058 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-059 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-061 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-062 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-063 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-064 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-065 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-066 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-067 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-068 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-069 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-070 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-071 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-072 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-074 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-075 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-076 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Date (hidden)
Today | 2026-03-16
|  | Dates | ='Actual Dates'!$A$4:$AB$350
|  | Jobs | ='Date Calcs'!$A$4:$AB$350
|  | Ship | ='Date Calcs from Ship Date'!$A$4:$AB$351

## Date Calcs
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
|  | Dates | # of weeks per quote |  |  |  | # of Days---> | 14 | 7 | 7 | 7 | 7 | 7 | 7 | 14 | 14 |  | 2 | 1 | 7 |  |  |  | 14 | 21 | 21 | 21 | 14 | 1 | 7 | 2
[7 empty] | from c | From h | From I | From J | From k | From L | From M | From N | from C | from C |  | From I,K,L or N | From S | From I,K,L or N |  |  |  | From I,K,L or N | From I,K,L or N | From I,K,L or N | From I,K,L or N | From I,K,L or N |  |  | From Z | From I,K,L or N
Job | Customer | Order Date | min design | max design | min build | max build | App. Prints Submitted | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Long lead time | Prelim BOM |  | Final Calcs | A.I. | Cert Dwgs | Weeks Drawings on Hold by Customer | Weeks Fabrication on Hold by Customer | Customer Ship Date | Update BOM | Stock Check | Order Balance | Final BOM | Build Plan | Burn File | QC Checklist | Release Target | Delivery Date | U-DR-1 Form (ASME ONLY)
24-046 | SYMS Engineering | 2024-08-15 | 2 | 3 | 18 | 30 | 2024-09-05 | 2024-09-23 | 2025-05-12 | 2025-05-31 | 2025-07-15 | 2025-07-23 | 2025-08-06 | 2025-08-13 | 2024-08-29 | 2024-08-29 |  | 2025-08-10 | 2025-08-11 | 2025-08-15 | 0 | 10 | 2026-05-22 | 2025-08-22 | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-31 | 2025-08-30 | 2025-08-22 | 2025-09-01 | 2026-03-06
25-010 | Kimberly Clark | 2025-01-28 | 4 | 5 | 12 | 14 | 2025-03-04 | 2025-06-11 | 2025-07-03 | 2025-07-10 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-02-11 | 2025-02-11 |  | 2025-08-23 | 2025-08-24 | 2025-08-28 | 0 | 0 | 2025-12-04 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-04 | 2025-09-14 | 2025-11-27
25-011 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-05-09 | 2025-06-05 | 2025-06-11 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 | 0 | 0 | 2026-01-08 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-01-01
25-012 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-05-09 | 2025-06-05 | 2025-06-11 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 | 0 | 0 | 2026-01-08 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-01-01
25-013 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-04-08 | 2025-06-05 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-02-11 | 2025-02-11 |  | 2025-05-31 | 2025-06-01 | 2025-06-05 | 0 | 0 | 2025-10-09 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-06-12 | 2025-06-22 | 2025-10-02
25-014 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-04-16 | 2025-05-21 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-02-11 | 2025-02-11 |  | 2025-05-16 | 2025-05-17 | 2025-05-21 | 0 | 0 | 2025-09-24 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-05-28 | 2025-06-07 | 2025-09-17
25-015 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-04-16 | 2025-05-21 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-02-11 | 2025-02-11 |  | 2025-05-16 | 2025-05-17 | 2025-05-21 | 0 | 0 | 2025-10-22 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-05-28 | 2025-06-07 | 2025-10-15
25-016 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-04-16 | 2025-05-21 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-02-11 | 2025-02-11 |  | 2025-05-16 | 2025-05-17 | 2025-05-21 | 0 | 0 | 2025-10-22 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-05-28 | 2025-06-07 | 2025-10-15
25-017 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-03-24 | 2025-04-14 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-02-11 | 2025-02-11 |  | 2025-04-09 | 2025-04-10 | 2025-04-14 | 0 | 0 | 2025-09-15 | 2025-04-21 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-29 | 2025-04-21 | 2025-05-01 | 2025-09-08
25-018 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-06-04 | 2025-07-21 | 2025-08-12 | 2025-08-28 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-02-11 | 2025-02-11 |  | 2025-08-23 | 2025-08-24 | 2025-08-28 | 0 | 0 | 2026-01-29 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-04 | 2025-09-14 | 2026-01-22
25-019 | Kimberly Clark | 2025-01-28 | 4 | 5 | 24 | 26 | 2025-03-04 | 2025-05-27 | 2025-06-25 | 2025-07-03 | 2025-09-04 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 | 0 | 0 | 2026-03-05 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-02-26
25-020 | Kimberly Clark | 2025-01-28 | 4 | 5 | 24 | 26 | 2025-03-04 | 2025-04-08 | 2025-06-05 | 2025-06-11 | 2025-07-31 | 2025-08-11 | 2025-08-28 | 2025-09-02 | 2025-02-11 | 2025-02-11 |  | 2025-08-23 | 2025-08-24 | 2025-08-28 | 0 | 0 | 2026-02-26 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-04 | 2025-09-14 | 2026-02-19
25-021 | Kimberly Clark | 2025-01-28 | 4 | 5 | 24 | 26 | 2025-03-04 | 2025-05-27 | 2025-06-25 | 2025-08-29 | 2025-09-04 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 | 0 | 0 | 2026-03-05 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-02-26
25-023 | Andritz | 2025-01-30 | 1 | 2 | 10 | 12 | 2025-02-13 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-17 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-02-13 | 2025-02-13 |  | 2025-03-12 | 2025-03-13 | 2025-03-17 | 0 | 0 | 2025-06-09 | 2025-03-24 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-03-24 | 2025-04-03 | 2025-06-02
25-024 | Andritz | 2025-01-30 | 1 | 2 | 10 | 12 | 2025-02-13 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-17 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-02-13 | 2025-02-13 |  | 2025-03-12 | 2025-03-13 | 2025-03-17 | 0 | 0 | 2025-06-09 | 2025-03-24 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-03-24 | 2025-04-03 | 2025-06-02
25-025 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-29 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-24 | 2025-05-25 | 2025-05-29 | 0 | 0 | 2025-11-13 | 2025-06-05 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-13 | 2025-06-05 | 2025-06-15 | 2025-11-06
25-026 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 | 0 | 0 | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-027 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 | 0 | 0 | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-028 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-17 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 | 0 | 0 | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-029 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-17 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 | 0 | 0 | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-030 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-19 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 | 0 | 0 | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-031 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-13 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 | 0 | 0 | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-032 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-13 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 | 0 | 0 | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-033 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-19 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 | 0 | 0 | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-034 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 | 0 | 0 | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-035 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-19 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 | 0 | 0 | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-036 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 | 0 | 0 | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-037 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-14 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 | 0 | 0 | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-039 | Zachry | 2025-02-26 | 2 | 3 | 14 | 16 | 2025-03-19 | 2025-04-03 | 2025-05-08 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-03-12 | 2025-03-12 |  | 2025-05-03 | 2025-05-04 | 2025-05-08 | 0 | 0 | 2025-08-28 | 2025-05-15 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-23 | 2025-05-15 | 2025-05-25 | 2025-08-21
25-040 | NAK Kiln | 2025-03-05 | 1 | 2 | 20 | 22 | 2025-03-19 | 2025-03-04 | 2025-03-04 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-03-19 | 2025-03-19 |  | 2025-02-27 | 2025-02-28 | 2025-03-04 | 0 | 29 | 2026-02-24 | 2025-03-11 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-19 | 2025-03-11 | 2025-03-21 | 2025-07-29
25-042 | Andritz | 2025-03-19 | 2 | 3 | 8 | 10 | 2025-04-09 | 2025-04-08 | 2025-04-21 | 2025-04-22 | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-04-02 | 2025-04-02 |  | 2025-05-21 | 2025-05-22 | 2025-05-26 | 0 | 0 | 2025-08-04 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-10 | 2025-06-02 | 2025-06-12 | 2025-07-28
25-044 | Noah Industrial | 2025-04-01 | 3 | 4 | 10 | 12 | 2025-04-29 | 2025-05-28 | 2025-05-28 | 2025-06-03 | 2025-06-05 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-04-15 | 2025-04-15 |  | 2025-05-31 | 2025-06-01 | 2025-06-05 | 0 | 0 | 2025-08-28 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-06-12 | 2025-06-22 | 2025-08-21
25-045 | ProPipe | 2025-04-05 | 1 | 1 | 1 | 2 | 2025-04-12 | 2026-01-14 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-04-19 | 2025-04-19 |  | 2026-01-02 | 2026-01-03 | 2026-01-07 | 0 | 0 | 2026-01-21 | 2026-01-14 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-22 | 2026-01-14 | 2026-01-24 | 2026-01-14
25-052 | Kraton | 2025-05-19 | 2 | 3 | 12 | 14 | 2025-06-09 | 2025-06-25 | 2025-07-08 | 2025-07-15 | 2025-07-21 | 2025-07-28 | 2025-07-29 | 2025-08-05 | 2025-06-02 | 2025-06-02 |  | 2025-07-24 | 2025-07-25 | 2025-07-29 | 0 | 0 | 2025-11-04 | 2025-08-05 | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-13 | 2025-08-05 | 2025-08-15 | 2025-10-28
25-053 | Andritz | 2025-06-02 | 2 | 31 | 8 | 10 | 2026-01-05 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2025-06-16 | 2025-06-16 |  | 2026-05-13 | 2026-05-14 | 2026-05-18 | 16 | 0 | 2026-07-27 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-02 | 2026-05-25 | 2026-06-04 | 2026-07-20
25-054 | Chromascape | 2025-06-03 | 3 | 4 | 13 | 15 | 2025-07-01 | 2025-07-11 | 2025-07-07 | 2025-07-17 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-06-17 | 2025-06-17 |  | 2025-07-12 | 2025-07-13 | 2025-07-17 | 0 | 0 | 2025-10-30 | 2025-07-24 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-08-01 | 2025-07-24 | 2025-08-03 | 2025-10-23
25-055 | Airgas | 2025-06-12 | 3 | 16 | 22 | 26 | 2025-10-02 | 2025-12-09 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2025-06-26 | 2025-06-26 |  | 2025-12-12 | 2025-12-13 | 2025-12-17 | 0 | 0 | 2026-06-17 | 2025-12-24 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-01 | 2025-12-24 | 2026-01-03 | 2026-06-10
25-056 | Reco | 2025-06-13 | 2 | 3 | 12 | 14 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2025-11-10 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-11-03
25-057 | Reco | 2025-06-13 | 2 | 3 | 12 | 14 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2025-11-10 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-11-03
25-058 | Reco | 2025-06-13 | 2 | 3 | 16 | 18 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2025-12-08 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-01
25-059 | Reco | 2025-06-13 | 2 | 3 | 16 | 18 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2025-12-08 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-01
25-060 | Reco | 2025-06-13 | 2 | 3 | 20 | 22 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-01-05 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-29
25-061 | Reco | 2025-06-13 | 2 | 3 | 20 | 22 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-01-05 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-29
25-062 | Reco | 2025-06-13 | 2 | 3 | 24 | 26 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-02-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-01-26
25-063 | Reco | 2025-06-13 | 2 | 3 | 24 | 26 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-02-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-01-26
25-064 | Reco | 2025-06-13 | 2 | 3 | 28 | 30 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-03-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-02-23
25-065 | Reco | 2025-06-13 | 2 | 3 | 28 | 30 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-03-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-02-23
25-066 | Reco | 2025-06-13 | 2 | 3 | 32 | 34 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-03-30 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-03-23
25-067 | Reco | 2025-06-13 | 2 | 3 | 32 | 34 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-03-30 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-03-23
25-068 | Reco | 2025-06-13 | 2 | 3 | 36 | 38 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-04-27 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-04-20
25-069 | Reco | 2025-06-13 | 2 | 3 | 36 | 38 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-04-27 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-04-20
25-070 | Reco | 2025-06-13 | 2 | 3 | 40 | 42 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-05-25 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-05-18
25-071 | Reco | 2025-06-13 | 2 | 3 | 40 | 42 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 | 0 | 0 | 2026-05-25 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-05-18
25-072 | Burke Industrial | 2025-06-16 | 2 | 3 | 11 | 13 | 2025-07-07 | 2025-07-17 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-06-30 | 2025-06-30 |  | 2025-07-09 | 2025-07-10 | 2025-07-14 | 0 | 0 | 2025-10-13 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-29 | 2025-07-21 | 2025-07-31 | 2025-10-06
25-073 | Burke Industrial | 2025-06-16 | 2 | 3 | 11 | 13 | 2025-07-07 | 2025-07-17 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-06-30 | 2025-06-30 |  | 2025-07-09 | 2025-07-10 | 2025-07-14 | 0 | 0 | 2025-10-13 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-29 | 2025-07-21 | 2025-07-31 | 2025-10-06
25-074 | Kemira | 2025-06-16 | 2 | 3 | 12 | 14 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-06-30 | 2025-06-30 |  | 2025-07-19 | 2025-07-20 | 2025-07-24 | 0 | 0 | 2025-10-30 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-08 | 2025-07-31 | 2025-08-10 | 2025-10-23
25-075 | Kemira | 2025-06-16 | 2 | 3 | 12 | 14 | 2025-07-07 | 2025-07-30 | 2025-07-28 | 2025-08-06 | 2025-08-22 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-06-30 | 2025-06-30 |  | 2025-08-17 | 2025-08-18 | 2025-08-22 | 0 | 0 | 2025-11-28 | 2025-08-29 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-06 | 2025-08-29 | 2025-09-08 | 2025-11-21
25-076 | Irving tissue | 2025-06-17 | 2 | 4 | 22 | 26 | 2025-07-15 | 2025-08-11 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-07-01 | 2025-07-01 |  | 2025-08-14 | 2025-08-15 | 2025-08-19 | 0 | 0 | 2026-02-17 | 2025-08-26 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-03 | 2025-08-26 | 2025-09-05 | 2026-02-10
25-077 | Epic Systems | 2025-06-25 | 2 | 3 | 22 | 26 | 2025-07-16 | 2025-08-06 | 2025-08-13 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-07-09 | 2025-07-09 |  | 2025-08-20 | 2025-08-21 | 2025-08-25 | 0 | 0 | 2026-02-23 | 2025-09-01 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 2025-09-01 | 2025-09-11 | 2026-02-16
25-078 | Epic Systems | 2025-06-25 | 2 | 3 | 22 | 26 | 2025-07-16 | 2025-08-04 | 2025-08-08 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-07-09 | 2025-07-09 |  | 2025-08-20 | 2025-08-21 | 2025-08-25 | 0 | 0 | 2026-02-23 | 2025-09-01 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 2025-09-01 | 2025-09-11 | 2026-02-16
25-079 | Epic Systems | 2025-06-25 | 2 | 3 | 22 | 26 | 2025-07-16 | 2025-08-04 | 2025-08-08 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-07-09 | 2025-07-09 |  | 2025-08-20 | 2025-08-21 | 2025-08-25 | 0 | 0 | 2026-02-23 | 2025-09-01 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 2025-09-01 | 2025-09-11 | 2026-02-16
25-080 | Domtar | 2025-06-27 | 2 | 3 | 22 | 26 | 2025-07-18 | 2025-08-01 | 2025-08-07 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-07-11 | 2025-07-11 |  | 2025-08-02 | 2025-08-03 | 2025-08-07 | 0 | 0 | 2026-02-05 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-22 | 2025-08-14 | 2025-08-24 | 2026-01-29
25-083 | Synthomer | 2025-07-15 | 2 | 3 | 22 | 26 | 2025-08-05 | 2025-08-29 | 2025-10-21 | 2025-11-05 | 2025-11-06 | 2025-11-11 | 2026-02-09 | 2026-02-16 | 2025-07-29 | 2025-07-29 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 | 0 | 0 | 2026-08-10 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-08-03
25-084 | Atlas Minerals | 2025-07-18 | 2 | 3 | 13 | 15 | 2025-08-08 | 2025-08-22 | 2025-08-18 | 2025-08-25 | 2025-10-22 | 2025-10-28 | 2025-10-31 | 2025-11-07 | 2025-08-01 | 2025-08-01 |  | 2025-11-06 | 2025-11-07 | 2025-11-11 | 0 | 8 | 2026-04-21 | 2025-11-18 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-26 | 2025-11-18 | 2025-11-28 | 2026-02-17
25-085 | Noah Industrial | 2025-07-22 | 2 | 3 | 14 | 16 | 2025-08-12 | 2025-08-26 | 2025-08-21 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-08-05 | 2025-08-05 |  | 2025-08-16 | 2025-08-17 | 2025-08-21 | 0 | 0 | 2025-12-11 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-08-28 | 2025-09-07 | 2025-12-04
25-086 | Tellus | 2025-07-30 | 0 | 0 | 22 | 26 | 2025-07-30 | 2026-01-14 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-08-13 | 2025-08-13 |  | 2026-01-02 | 2026-01-03 | 2026-01-07 | 0 | 0 | 2026-07-08 | 2026-01-14 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-22 | 2026-01-14 | 2026-01-24 | 2026-07-01
25-087 | Solvay | 2025-08-07 | 2 | 3 | 10 | 12 | 2025-08-28 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-08-21 | 2025-08-21 |  | 2025-09-10 | 2025-09-11 | 2025-09-15 | 0 | 0 | 2025-12-08 | 2025-09-22 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-30 | 2025-09-22 | 2025-10-02 | 2025-12-01
25-088 | CIL Isotopes | 2025-08-13 | 2 | 3 | 6 | 7 | 2025-09-03 | 2025-09-17 | 2025-09-16 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-08-27 | 2025-08-27 |  | 2025-09-11 | 2025-09-12 | 2025-09-16 | 0 | 0 | 2025-11-04 | 2025-09-23 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-01 | 2025-09-23 | 2025-10-03 | 2025-10-28
25-089 | Valmet | 2025-08-22 | 3 | 4.5 | 20 | 24 | 2025-09-22 12:00 | 2025-10-06 | 2025-11-28 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2025-09-05 | 2025-09-05 |  | 2025-11-23 | 2025-11-24 | 2025-11-28 | 0 | 0 | 2026-05-15 | 2025-12-05 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-05 | 2025-12-15 | 2026-05-08
25-090 | GAF | 2025-08-18 | 1 | 1 | 2 | 3 | 2025-08-25 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-09-01 | 2025-09-01 |  | 2025-09-07 | 2025-09-08 | 2025-09-12 | 0 | 0 | 2025-10-03 | 2025-09-19 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-27 | 2025-09-19 | 2025-09-29 | 2025-09-26
25-091 | US Sugar | 2025-09-04 | 1 | 1 | 1 | 1 | 2025-09-11 | 2026-01-14 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-09-18 | 2025-09-18 |  | 2026-01-02 | 2026-01-03 | 2026-01-07 | 0 | 0 | 2026-01-14 | 2026-01-14 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-22 | 2026-01-14 | 2026-01-24 | 2026-01-07
25-092 | Symrise | 2025-09-10 | 3 | 4 | 16 | 18 | 2025-10-08 | 2025-10-15 | 2025-10-14 | 2025-10-21 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-09-24 | 2025-09-24 |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 0 | 0 | 2026-03-05 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-06 | 2025-11-16 | 2026-02-26
25-093 | Symrise | 2025-09-10 | 3 | 4 | 16 | 18 | 2025-10-08 | 2025-10-15 | 2025-10-14 | 2025-10-21 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-09-24 | 2025-09-24 |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 0 | 0 | 2026-03-05 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-06 | 2025-11-16 | 2026-02-26
25-094 | Kimberly Clark | 2025-09-15 | 2 | 3 | 12 | 14 | 2025-10-06 | 2025-10-20 | 2025-10-27 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-09-29 | 2025-09-29 |  | 2025-10-22 | 2025-10-23 | 2025-10-27 | 0 | 0 | 2026-02-02 | 2025-11-03 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-11 | 2025-11-03 | 2025-11-13 | 2026-01-26
25-095 | Andritz | 2025-09-19 | 3 | 4 | 1 | 1 | 2025-10-17 | 2025-10-30 | 2025-11-19 | 2025-11-26 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2025-10-03 | 2025-10-03 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 | 0 | 0 | 2026-02-16 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-02-09
25-096 | Milliken | 2025-09-22 | 2 | 3 | 10 | 11 | 2025-10-13 | 2025-10-29 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-10-06 | 2025-10-06 |  | 2025-10-18 | 2025-10-19 | 2025-10-23 | 0 | 0 | 2026-01-08 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-07 | 2025-10-30 | 2025-11-09 | 2026-01-01
25-097 | Milliken | 2025-09-22 | 2 | 3 | 10 | 11 | 2025-10-13 | 2025-10-29 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-10-06 | 2025-10-06 |  | 2025-10-18 | 2025-10-19 | 2025-10-23 | 0 | 0 | 2026-01-08 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-07 | 2025-10-30 | 2025-11-09 | 2026-01-01
25-098 | Coastal Technologies | 2025-09-24 | 3 | 4 | 16 | 18 | 2025-10-22 | 2025-11-05 | 2025-10-31 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-10-08 | 2025-10-08 |  | 2025-10-26 | 2025-10-27 | 2025-10-31 | 0 | 4 | 2026-04-03 | 2025-11-07 | 2025-11-14 | 2026-02-26 | 2026-02-26 | 2025-11-14 | 2026-02-27 | 2025-11-07 | 2026-03-01 | 2026-02-27
25-099 | Burke Industrial | 2025-10-02 | 3 | 4 | 14 | 16 | 2025-10-30 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-10-16 | 2025-10-16 |  | 2025-10-31 | 2025-11-01 | 2025-11-05 | 0 | 0 | 2026-02-25 | 2025-11-12 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-11-12 | 2025-11-22 | 2026-02-18
25-101 | Harper Love | 2025-10-24 | 3 | 4 | 16 | 18 | 2025-11-21 | 2025-12-04 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2025-11-07 | 2025-11-07 |  | 2025-12-03 | 2025-12-04 | 2025-12-08 | 0 | 0 | 2026-04-13 | 2025-12-15 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-23 | 2025-12-15 | 2025-12-25 | 2026-04-06
25-102 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-26 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 0 | 0 | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-103 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-29 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 0 | 0 | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-104 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-29 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 0 | 0 | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-105 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-02-04 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 0 | 0 | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-106 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-02-04 | 2026-02-09 | 2026-02-12 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 0 | 0 | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-107 | Epic Systems | 2026-02-02 | 3 | 4 | 16 | 18 | 2026-03-02 | 2025-12-10 | 2026-02-09 | 2026-03-04 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-02-16 | 2026-02-16 |  | 2026-03-21 | 2026-03-22 | 2026-03-26 | 1 | 0 | 2026-07-30 | 2026-04-02 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-02 | 2026-04-12 | 2026-07-23
25-108 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2026-02-09 | 2026-02-18 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2025-11-13 | 2025-11-13 |  | 2026-03-14 | 2026-03-15 | 2026-03-19 | 0 | 0 | 2026-07-23 | 2026-03-26 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-03 | 2026-03-26 | 2026-04-05 | 2026-07-16
25-109 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-26 | 2026-01-19 | 2026-01-26 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 0 | 0 | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-110 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-29 | 2026-01-19 | 2026-01-26 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-01-25 | 2026-01-26 | 2026-01-30 | 0 | 0 | 2026-06-05 | 2026-02-06 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-06 | 2026-02-16 | 2026-05-29
25-111 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-26 | 2026-01-19 | 2026-01-28 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-01-25 | 2026-01-26 | 2026-01-30 | 0 | 0 | 2026-06-05 | 2026-02-06 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-06 | 2026-02-16 | 2026-05-29
25-112 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-26 | 2026-01-19 | 2026-01-28 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-01-25 | 2026-01-26 | 2026-01-30 | 0 | 0 | 2026-06-05 | 2026-02-06 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-06 | 2026-02-16 | 2026-05-29
25-113 | Epic Systems | 2025-11-14 | 3 | 4 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-26 | 2026-02-09 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2025-11-28 | 2025-11-28 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 | 0 | 0 | 2026-06-15 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-06-08
25-115 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2026-01-19 | 2026-01-28 | 2026-01-30 | 2026-02-06 | 2026-02-26 | 2026-03-05 | 2025-11-13 | 2025-11-13 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 0 | 0 | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-116 | Polynt | 2025-11-04 | 3 | 4 | 16 | 18 | 2025-12-02 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2025-11-18 | 2025-11-18 |  | 2026-02-14 | 2026-02-15 | 2026-02-19 | 0 | 0 | 2026-06-25 | 2026-02-26 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-02-26 | 2026-03-08 | 2026-06-18
25-117 | Merrick | 2025-11-07 | 3 | 9 | 18 | 20 | 2026-01-09 | 2026-01-28 | 2026-01-28 | 2026-02-04 | 2026-02-09 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2025-11-21 | 2025-11-21 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 | 0 | 0 | 2026-06-29 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-06-22
25-118 | Merrick | 2025-11-07 | 3 | 9 | 18 | 20 | 2026-01-09 | 2026-01-28 | 2026-01-28 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2025-11-21 | 2025-11-21 |  | 2026-02-11 | 2026-02-12 | 2026-02-16 | 0 | 0 | 2026-07-06 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-03 | 2026-02-23 | 2026-03-05 | 2026-06-29
25-119 | Vertiv | 2025-11-14 | 1 | 2 |  |  | 2025-11-28 | 2025-12-08 | 2025-12-10 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2025-11-28 | 2025-11-28 |  | 2025-12-05 | 2025-12-06 | 2025-12-10 | 0 | 0 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-17 | 2025-12-27 | 2025-12-03
25-120 | Andritz | 2025-11-21 | 0 | 0 | 22 | 26 | 2025-11-21 | 2026-01-14 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-12-05 | 2025-12-05 |  | 2026-01-02 | 2026-01-03 | 2026-01-07 | 0 | 0 | 2026-07-08 | 2026-01-14 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-22 | 2026-01-14 | 2026-01-24 | 2026-07-01
25-121 | Kimberly Clark | 2025-12-04 | 3 | 4 | 16 | 18 | 2026-01-01 | 2026-01-22 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2025-12-18 | 2025-12-18 |  | 2026-03-12 | 2026-03-13 | 2026-03-17 | 3 | 0 | 2026-07-21 | 2026-03-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-03-24 | 2026-04-03 | 2026-07-14
25-122 | Kimberly Clark | 2025-12-04 | 3 | 4 | 16 | 18 | 2026-01-01 | 2026-01-22 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2025-12-18 | 2025-12-18 |  | 2026-03-12 | 2026-03-13 | 2026-03-17 | 3 | 0 | 2026-07-21 | 2026-03-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-03-24 | 2026-04-03 | 2026-07-14
25-123 | Kimberly Clark | 2025-12-04 | 3 | 4 | 16 | 18 | 2026-01-01 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2025-12-18 | 2025-12-18 |  | 2026-01-24 | 2026-01-25 | 2026-01-29 | 0 | 0 | 2026-06-04 | 2026-02-05 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-05 | 2026-02-15 | 2026-05-28
25-124 | Vertiv | 2025-12-15 | 0 | 0 | 16 | 32 | 2025-12-15 | 2026-01-14 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2025-12-29 | 2025-12-29 |  | 2026-01-02 | 2026-01-03 | 2026-01-07 | 0 | 0 | 2026-08-19 | 2026-01-14 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-22 | 2026-01-14 | 2026-01-24 | 2026-08-12
25-356 | Synthomer | 2025-12-29 | 3 | 4 | 16 | 18 | 2026-01-26 | 2026-02-11 | 2026-02-09 | 2026-02-23 | 2026-02-28 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-01-12 | 2026-01-12 |  | 2026-02-23 | 2026-02-24 | 2026-02-21 | 0 | 0 | 2026-06-27 | 2026-03-07 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-07 | 2026-03-15 | 2026-02-28 | 2026-03-17 | 2026-06-27
25-357 | Sylvamo | 2025-12-30 | 3 | 4 | 14 | 16 | 2026-01-27 | 2026-02-12 | 2026-02-18 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-13 | 2026-01-13 |  | 2026-02-13 | 2026-02-14 | 2026-02-18 | 0 | 0 | 2026-06-10 | 2026-02-25 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-02-25 | 2026-03-07 | 2026-06-03
25-358 | Sylvamo | 2025-12-30 | 3 | 4 | 14 | 16 | 2026-01-27 | 2026-02-13 | 2026-02-18 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-13 | 2026-01-13 |  | 2026-02-13 | 2026-02-14 | 2026-02-18 | 0 | 0 | 2026-06-10 | 2026-02-25 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-02-25 | 2026-03-07 | 2026-06-03
26-002 | SNF | 2026-01-09 | 3 | 4 | 16 | 18 | 2026-02-06 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-23 | 2026-01-23 |  | 2026-02-22 | 2026-02-23 | 2026-02-27 | 0 | 0 | 2026-07-03 | 2026-03-06 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-06 | 2026-03-16 | 2026-06-26
26-003 | SNF | 2026-01-09 | 3 | 4 | 16 | 18 | 2026-02-06 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-23 | 2026-01-23 |  | 2026-02-22 | 2026-02-23 | 2026-02-27 | 0 | 0 | 2026-07-03 | 2026-03-06 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-06 | 2026-03-16 | 2026-06-26
26-004 | SNF | 2026-01-09 | 3 | 4 | 16 | 18 | 2026-02-06 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-23 | 2026-01-23 |  | 2026-02-22 | 2026-02-23 | 2026-02-27 | 0 | 0 | 2026-07-03 | 2026-03-06 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-06 | 2026-03-16 | 2026-06-26
26-005 | US Sugar | 2026-01-12 | 3 | 4 | 15 | 17 | 2026-02-09 | 2026-02-19 | 2026-02-18 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-01-26 | 2026-01-26 |  | 2026-02-13 | 2026-02-14 | 2026-02-18 | 0 | 0 | 2026-06-17 | 2026-02-25 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-02-25 | 2026-03-07 | 2026-06-10
26-014 | SNF | 2026-01-12 | 3 | 4 | 14 | 16 | 2026-02-09 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-01-26 | 2026-01-26 |  | 2026-02-27 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2026-06-24 | 2026-03-11 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-11 | 2026-03-21 | 2026-06-17 | 2026-03-06
26-015 | SNF | 2026-02-11 | 3 | 4 | 14 | 16 | 2026-03-11 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-02-25 | 2026-02-25 |  | 2026-03-27 | 2026-03-28 | 2026-04-01 | 0 | 0 | 2026-07-22 | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-08 | 2026-04-18 | 2026-07-15 | 2026-04-03
26-016 | SNF | 2026-02-11 | 3 | 4 | 14 | 16 | 2026-03-11 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-02-25 | 2026-02-25 |  | 2026-03-25 | 2026-03-26 | 2026-03-30 | 0 | 0 | 2026-07-20 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-06 | 2026-04-16 | 2026-07-13 | 2026-04-01
26-017 | SNF | 2026-01-12 | 3 | 4 | 18 | 20 | 2026-02-09 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-01-26 | 2026-01-26 |  | 2026-02-27 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2026-07-22 | 2026-03-11 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-11 | 2026-03-21 | 2026-07-15 | 2026-03-06
26-018 | SNF | 2026-01-12 | 3 | 4 | 18 | 20 | 2026-02-09 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-01-26 | 2026-01-26 |  | 2026-02-27 | 2026-02-28 | 2026-03-04 | 0 | 0 | 2026-07-22 | 2026-03-11 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-11 | 2026-03-21 | 2026-07-15 | 2026-03-06
26-020 | US Sugar | 2026-02-06 | 3 | 4 | 16 | 18 | 2026-03-06 | 2026-03-20 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-02-20 | 2026-02-20 |  | 2026-03-15 | 2026-03-16 | 2026-03-20 | 0 | 0 | 2026-07-24 | 2026-03-27 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-04 | 2026-03-27 | 2026-04-06 | 2026-07-17
26-021 | US Sugar | 2026-02-06 | 3 | 4 | 16 | 18 | 2026-03-06 | 2026-03-20 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-02-20 | 2026-02-20 |  | 2026-03-15 | 2026-03-16 | 2026-03-20 | 0 | 0 | 2026-07-24 | 2026-03-27 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-04 | 2026-03-27 | 2026-04-06 | 2026-07-17
26-022 | Andritz | 2026-02-10 | 2 | 3 | 14 | 16 | 2026-03-03 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-02-24 | 2026-02-24 |  | 2026-03-22 | 2026-03-23 | 2026-03-27 | 0 | 0 | 2026-07-17 | 2026-04-03 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-03 | 2026-04-13 | 2026-07-10 | 2026-03-29
26-024 | Polynt | 2026-02-25 | 3 | 4 | 14 | 16 | 2026-03-25 | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-03-11 | 2026-03-11 |  | 2026-04-17 | 2026-04-18 | 2026-04-22 | 1 | 0 | 2026-08-12 | 2026-04-29 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-04-29 | 2026-05-09 | 2026-08-05 | 2026-04-24
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
Formulas:
from c = [Order Date]+[max design]*7
From h = IF(VLOOKUP([Job],Dates,8,)=0,[from c]+I2,VLOOKUP([Job],Dates,8,)+I2)
From I = IF(VLOOKUP([Job],Dates,9,)=0,[From h]+J2,VLOOKUP([Job],Dates,9,)+J2)
From J = IF(VLOOKUP([Job],Dates,10,)=0,[From I]+K2,VLOOKUP([Job],Dates,10,)+K2)
From k = IF(VLOOKUP([Job],Dates,11,)=0,[From J]+L2,VLOOKUP([Job],Dates,11,)+L2)
From L = IF(VLOOKUP([Job],Dates,12,)=0,[From k]+M2,VLOOKUP([Job],Dates,12,)+M2)
From M = IF(VLOOKUP([Job],Dates,13,)=0,[From L]+N2,VLOOKUP([Job],Dates,13,)+N2)
From N = IF(VLOOKUP([Job],Dates,14,)=0,[From M]+O2,VLOOKUP([Job],Dates,14,)+O2)
from C = [Order Date]+P2
From S = [From I,K,L or N]+T2
From I,K,L or N = [From I,K,L or N]+U2-S2
From I,K,L or N = [From I,K,L or N]+Y2-S2
Customer Ship Date = ([max build]*7)+([Weeks Fabrication on Hold by Customer]*7)+[From I,K,L or N]
Burn File = [From I,K,L or N]+AD2
QC Checklist = [From I,K,L or N]+AE2
From Z = IF([from C]>[Burn File],[from C]+AD2,[Burn File]+AF2)
U-DR-1 Form (ASME ONLY) = +[From I,K,L or N]+2

## Ship Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  | Dates | # of weeks per schedule |  |  |  |  | # of Days---> | 14 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 2 |  | 5 | 1 | 7 | 7 | 7 | 14 | 5 | 7 | 7 | 7 | 2
to c
Job | Customer | Ship Date | Fabrication | Testing | Painting / Sandblasting | Cleaning | Shipping Prep | App. Prints Submitted | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Last Possible Resubmit | Last Possible Customer Response | Long lead time order by | Prelim BOM complete by |  | Final Calcs | A.I. | Cert Dwgs | Update BOM | Stock Check | Parts to Arrive | Final BOM | Build Plan | Burn File | QC Checklist | Release Target | Ship Date | ALT JOB #
24-046 | SYMS Engineering | 2026-04-13 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2024-06-02 | 2024-06-23 | 2024-07-07 | 2024-07-14 | 2024-07-21 | 2024-07-28 | 2024-08-04 | 2024-08-11 | 2024-08-15 | 2024-08-13 |  | 2026-02-04 | 2026-04-06 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-04-13 | 046-24
25-010 | Kimberly Clark |  | 4 | 0.25 | 0 | 0.25 | 0.5 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 010-25
25-011 | Kimberly Clark |  | 0 | 0.25 | 0 | 0 | 0 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 011-25
25-012 | Kimberly Clark | 2026-03-12 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | 2026-01-03 | 2026-03-05 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-01-31 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-02-05 | 2026-03-12 | 012-25
25-013 | Kimberly Clark | 2026-03-12 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | 2026-01-03 | 2026-03-05 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-01-31 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-02-05 | 2026-03-12 | 013-25
25-014 | Kimberly Clark |  | 0 | 0 | 0 | 0 | 0 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 014-25
25-015 | Kimberly Clark |  | 0 | 0 | 0 | 0 | 0 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 015-25
25-016 | Kimberly Clark |  | 4 | 0.25 | 0 | 0.25 | 0.5 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 016-25
25-017 | Kimberly Clark |  | 0 | 0 | 0 | 0 | 0 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 017-25
25-018 | Kimberly Clark |  | 1 | 0 | 0 | 0.25 | 0.5 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 018-25
25-019 | Kimberly Clark |  | 4 | 0.25 | 0 | 0.25 | 0.5 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 019-25
25-020 | Kimberly Clark |  | 0 | 0 | 0 | 0 | 0 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 020-25
25-021 | Kimberly Clark |  | 4 | 0.25 | 0 | 0.25 | 0.5 | 2024-11-15 | 2024-12-06 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-28 | 2025-01-26 |  | #VALUE! | #VALUE! | [10 empty] | 021-25
25-023 | Andritz |  | 0 | 0 | 0 | 0 | 0 | 2024-11-17 | 2024-12-08 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-01-30 | 2025-01-28 |  | #VALUE! | #VALUE! | [10 empty] | 023-25
25-024 | Andritz |  | 0 | 0 | 0 | 0 | 0 | 2024-11-17 | 2024-12-08 | 2024-12-22 | 2024-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-01-30 | 2025-01-28 |  | #VALUE! | #VALUE! | [10 empty] | 024-25
25-025 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 025-25
25-026 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 026-25
25-027 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 027-25
25-028 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 028-25
25-029 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 029-25
25-030 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 030-25
25-031 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 031-25
25-032 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 032-25
25-033 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 033-25
25-034 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 034-25
25-035 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 035-25
25-036 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 036-25
25-037 | Irving Tissue |  | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 2024-12-14 | 2024-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-05 | 2025-02-03 |  | #VALUE! | #VALUE! | [10 empty] | 037-25
25-039 | Zachry |  | 0 | 0 | 0 | 0 | 0 | 2024-12-14 | 2025-01-04 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-02-26 | 2025-02-24 |  | #VALUE! | #VALUE! | [10 empty] | 039-25
25-040 | NAK Kiln | 2026-04-03 | 3 | 0.25 | 0 | 0.25 | 0.5 | 2024-12-21 | 2025-01-11 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-05 | 2025-03-03 |  | 2026-02-01 | 2026-03-27 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-01 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-06 | 2026-04-03 | 040-25
25-042 | Andritz |  | 0 | 0 | 0 | 0 | 0 | 2025-01-04 | 2025-01-25 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-19 | 2025-03-17 |  | #VALUE! | #VALUE! | [10 empty] | 042-25
25-044 | Noah Industrial |  | 0 | 0 | 0 | 0 | 0 | 2025-01-17 | 2025-02-07 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-01 | 2025-03-30 |  | #VALUE! | #VALUE! | [10 empty] | 044-25
25-045 | ProPipe |  | 0 | 0 | 0 | 0 | 0 | 2025-01-21 | 2025-02-11 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-05 | 2025-04-03 |  | #VALUE! | #VALUE! | [10 empty] | 045-25
25-052 | Kraton |  | 0 | 0 | 0 | 0 | 0 | 2025-03-06 | 2025-03-27 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-19 | 2025-05-17 |  | #VALUE! | #VALUE! | [10 empty] | 052-25
25-053 | Andritz | 2026-06-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-03-20 | 2025-04-10 | 2025-04-24 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-02 | 2025-05-31 |  | 2026-03-25 | 2026-05-25 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-06-01 | 053-25
25-054 | Chromascape |  | 0 | 0 | 0 | 0 | 0 | 2025-03-21 | 2025-04-11 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-03 | 2025-06-01 |  | #VALUE! | #VALUE! | [10 empty] | 054-25
25-055 | Airgas | 2026-05-26 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-03-30 | 2025-04-20 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-12 | 2025-06-10 |  | 2026-03-19 | 2026-05-19 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-16 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-21 | 2026-05-26 | 055-25
25-056 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 056-25
25-057 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 057-25
25-058 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 058-25
25-059 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 059-25
25-060 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 060-25
25-061 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 061-25
25-062 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 062-25
25-063 | Reco |  | 0 | 0 | 0 | 0 | 0 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 063-25
25-064 | Reco |  | 4 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 064-25
25-065 | Reco |  | 4 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | #VALUE! | #VALUE! | [10 empty] | 065-25
25-066 | Reco | 2026-03-17 | 4 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | 2026-01-02 18:00 | 2026-03-04 18:00 | 2026-01-07 18:00 | 2026-01-14 18:00 | 2026-01-21 18:00 | 2026-01-28 18:00 | 2026-01-30 18:00 | 2026-01-28 18:00 | 2026-01-28 18:00 | 2026-01-28 18:00 | 2026-02-04 18:00 | 2026-03-17 | 066-25
25-067 | Reco | 2026-03-17 | 4 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | 2026-01-02 18:00 | 2026-03-04 18:00 | 2026-01-07 18:00 | 2026-01-14 18:00 | 2026-01-21 18:00 | 2026-01-28 18:00 | 2026-01-30 18:00 | 2026-01-28 18:00 | 2026-01-28 18:00 | 2026-01-28 18:00 | 2026-02-04 18:00 | 2026-03-17 | 067-25
25-068 | Reco | 2026-04-06 | 5 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | 2026-01-15 18:00 | 2026-03-24 18:00 | 2026-01-20 18:00 | 2026-01-27 18:00 | 2026-02-03 18:00 | 2026-02-10 18:00 | 2026-02-12 18:00 | 2026-02-10 18:00 | 2026-02-10 18:00 | 2026-02-10 18:00 | 2026-02-17 18:00 | 2026-04-06 | 068-25
25-069 | Reco | 2026-04-06 | 5 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | 2026-01-15 18:00 | 2026-03-24 18:00 | 2026-01-20 18:00 | 2026-01-27 18:00 | 2026-02-03 18:00 | 2026-02-10 18:00 | 2026-02-12 18:00 | 2026-02-10 18:00 | 2026-02-10 18:00 | 2026-02-10 18:00 | 2026-02-17 18:00 | 2026-04-06 | 069-25
25-070 | Reco | 2026-04-27 | 6 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | 2026-01-29 18:00 | 2026-04-14 18:00 | 2026-02-03 18:00 | 2026-02-10 18:00 | 2026-02-17 18:00 | 2026-02-24 18:00 | 2026-02-26 18:00 | 2026-02-24 18:00 | 2026-02-24 18:00 | 2026-02-24 18:00 | 2026-03-03 18:00 | 2026-04-27 | 070-25
25-071 | Reco | 2026-04-27 | 6 | 0.25 | 1 | 0 | 0.5 | 2025-03-31 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-13 | 2025-06-11 |  | 2026-01-29 18:00 | 2026-04-14 18:00 | 2026-02-03 18:00 | 2026-02-10 18:00 | 2026-02-17 18:00 | 2026-02-24 18:00 | 2026-02-26 18:00 | 2026-02-24 18:00 | 2026-02-24 18:00 | 2026-02-24 18:00 | 2026-03-03 18:00 | 2026-04-27 | 071-25
25-072 | Burke Industrial |  | 0 | 0 | 0 | 0 | 0 | 2025-04-03 | 2025-04-24 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-16 | 2025-06-14 |  | #VALUE! | #VALUE! | [10 empty] | 072-25
25-073 | Burke Industrial |  | 0 | 0 | 0 | 0 | 0 | 2025-04-03 | 2025-04-24 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-16 | 2025-06-14 |  | #VALUE! | #VALUE! | [10 empty] | 073-25
25-074 | Kemira |  | 0 | 0 | 0 | 0 | 0 | 2025-04-03 | 2025-04-24 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-16 | 2025-06-14 |  | #VALUE! | #VALUE! | [10 empty] | 074-25
25-075 | Kemira |  | 0 | 0 | 0 | 0 | 0 | 2025-04-03 | 2025-04-24 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-06-16 | 2025-06-14 |  | #VALUE! | #VALUE! | [10 empty] | 075-25
25-076 | Irving tissue |  | 0 | 0 | 0 | 0 | 0 | 2025-04-04 | 2025-04-25 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-17 | 2025-06-15 |  | #VALUE! | #VALUE! | [10 empty] | 076-25
25-077 | Epic Systems |  | 0 | 0 | 0 | 0 | 0 | 2025-04-12 | 2025-05-03 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-25 | 2025-06-23 |  | #VALUE! | #VALUE! | [10 empty] | 077-25
25-078 | Epic Systems |  | 0 | 0 | 0 | 0 | 0 | 2025-04-12 | 2025-05-03 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-25 | 2025-06-23 |  | #VALUE! | #VALUE! | [10 empty] | 078-25
25-079 | Epic Systems |  | 0 | 0 | 0 | 0 | 0 | 2025-04-12 | 2025-05-03 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-06-14 | 2025-06-21 | 2025-06-25 | 2025-06-23 |  | #VALUE! | #VALUE! | [10 empty] | 079-25
25-080 | Domtar |  | 0 | 0 | 0 | 0 | 0 | 2025-04-14 | 2025-05-05 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-27 | 2025-06-25 |  | #VALUE! | #VALUE! | [10 empty] | 080-25
25-083 | Synthomer | 2026-04-09 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-05-02 | 2025-05-23 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-15 | 2025-07-13 |  | 2026-01-31 | 2026-04-02 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-02-28 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-03-05 | 2026-04-09 | 083-25
25-084 | Atlas Minerals | 2026-04-14 | 2 | 0.25 | 1 | 0 | 0.5 | 2025-05-05 | 2025-05-26 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-18 | 2025-07-16 |  | 2026-02-13 18:00 | 2026-04-01 18:00 | 2026-02-18 18:00 | 2026-02-25 18:00 | 2026-03-04 18:00 | 2026-03-11 18:00 | 2026-03-13 18:00 | 2026-03-11 18:00 | 2026-03-11 18:00 | 2026-03-11 18:00 | 2026-03-18 18:00 | 2026-04-14 | 084-25
25-085 | Noah Industrial |  | 0 | 0 | 0 | 0 | 0 | 2025-05-09 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-22 | 2025-07-20 |  | #VALUE! | #VALUE! | [10 empty] | 085-25
25-086 | Tellus |  | 0 | 0 | 0 | 0 | 0 | 2025-05-17 | 2025-06-07 | 2025-06-21 | 2025-06-28 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-07-30 | 2025-07-28 |  | #VALUE! | #VALUE! | [10 empty] | 086-25
25-087 | Solvay |  | 0 | 0 | 0 | 0 | 0 | 2025-05-25 | 2025-06-15 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-07 | 2025-08-05 |  | #VALUE! | #VALUE! | [10 empty] | 087-25
25-088 | CIL Isotopes |  | 0 | 0 | 0 | 0 | 0 | 2025-05-31 | 2025-06-21 | 2025-07-05 | 2025-07-12 | 2025-07-19 | 2025-07-26 | 2025-08-02 | 2025-08-09 | 2025-08-13 | 2025-08-11 |  | #VALUE! | #VALUE! | [10 empty] | 088-25
25-089 | Valmet |  | 4 | 0 | 0 | 0.25 | 0.5 | 2025-06-09 | 2025-06-30 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-22 | 2025-08-20 |  | #VALUE! | #VALUE! | [10 empty] | 089-25
25-090 | GAF |  | 0 | 0 | 0 | 0 | 0 | 2025-06-05 | 2025-06-26 | 2025-07-10 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-14 | 2025-08-18 | 2025-08-16 |  | #VALUE! | #VALUE! | [10 empty] | 090-25
25-091 | US Sugar |  | 0 | 0 | 0 | 0 | 0 | 2025-06-22 | 2025-07-13 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-04 | 2025-09-02 |  | #VALUE! | #VALUE! | [10 empty] | 091-25
25-092 | Symrise | 2026-04-02 | 3 | 0.25 | 0 | 0 | 0.5 | 2025-06-28 | 2025-07-19 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-10 | 2025-09-08 |  | 2026-02-01 18:00 | 2026-03-27 18:00 | 2026-02-06 18:00 | 2026-02-13 18:00 | 2026-02-20 18:00 | 2026-02-27 18:00 | 2026-03-01 18:00 | 2026-02-27 18:00 | 2026-02-27 18:00 | 2026-02-27 18:00 | 2026-03-06 18:00 | 2026-04-02 | 092-25
25-093 | Symrise | 2026-04-02 | 3 | 0.25 | 0 | 0 | 0.5 | 2025-06-28 | 2025-07-19 | 2025-08-02 | 2025-08-09 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-10 | 2025-09-08 |  | 2026-02-01 18:00 | 2026-03-27 18:00 | 2026-02-06 18:00 | 2026-02-13 18:00 | 2026-02-20 18:00 | 2026-02-27 18:00 | 2026-03-01 18:00 | 2026-02-27 18:00 | 2026-02-27 18:00 | 2026-02-27 18:00 | 2026-03-06 18:00 | 2026-04-02 | 093-25
25-094 | Kimberly Clark |  | 0 | 0 | 0 | 0 | 0 | 2025-07-03 | 2025-07-24 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-15 | 2025-09-13 |  | #VALUE! | #VALUE! | [10 empty] | 094-25
25-095 | Andritz |  | 0 | 0 | 0 | 0 | 0 | 2025-07-07 | 2025-07-28 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-19 | 2025-09-17 |  | #VALUE! | #VALUE! | [10 empty] | 095-25
25-096 | Milliken |  | 0 | 0 | 0 | 0 | 0 | 2025-07-10 | 2025-07-31 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-22 | 2025-09-20 |  | #VALUE! | #VALUE! | [10 empty] | 096-25
25-097 | Milliken |  | 0 | 0 | 0 | 0 | 0 | 2025-07-10 | 2025-07-31 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-22 | 2025-09-20 |  | #VALUE! | #VALUE! | [10 empty] | 097-25
25-098 | Coastal Technologies | 2026-03-30 | 3 | 0.25 | 0 | 0.25 | 0.5 | 2025-07-12 | 2025-08-02 | 2025-08-16 | 2025-08-23 | 2025-08-30 | 2025-09-06 | 2025-09-13 | 2025-09-20 | 2025-09-24 | 2025-09-22 |  | 2026-01-28 | 2026-03-23 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-02-25 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-03-02 | 2026-03-30 | 098-25
25-099 | Burke Industrial | 2026-03-19 | 3 | 0.25 | 0 | 0.25 | 0.5 | 2025-07-20 | 2025-08-10 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-02 | 2025-09-30 |  | 2026-01-17 | 2026-03-12 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-14 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-19 | 2026-03-19 | 099-25
25-101 | Harper Love | 2026-05-11 | 5 | 0.25 | 1 | 0 | 0.5 | 2025-08-11 | 2025-09-01 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-24 | 2025-10-22 |  | 2026-02-19 18:00 | 2026-04-28 18:00 | 2026-02-24 18:00 | 2026-03-03 18:00 | 2026-03-10 18:00 | 2026-03-17 18:00 | 2026-03-19 18:00 | 2026-03-17 18:00 | 2026-03-17 18:00 | 2026-03-17 18:00 | 2026-03-24 18:00 | 2026-05-11 | 101-25
25-102 | Epic Systems | 2026-04-27 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-25 | 2025-09-15 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 |  | 2026-02-18 | 2026-04-20 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-04-27 | 102-25
25-103 | Epic Systems | 2026-04-27 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-25 | 2025-09-15 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 |  | 2026-02-18 | 2026-04-20 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-04-27 | 103-25
25-104 | Epic Systems | 2026-04-27 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-25 | 2025-09-15 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 |  | 2026-02-18 | 2026-04-20 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-04-27 | 104-25
25-105 | Epic Systems | 2026-06-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-25 | 2025-09-15 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 |  | 2026-03-25 | 2026-05-25 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-06-01 | 105-25
25-106 | Epic Systems | 2026-06-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-25 | 2025-09-15 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 |  | 2026-03-25 | 2026-05-25 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-06-01 | 106-25
25-107 | Epic Systems | 2026-06-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-11-20 | 2025-12-11 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-02 | 2026-01-31 |  | 2026-03-25 | 2026-05-25 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-06-01 | 107-25
25-108 | Epic Systems | 2026-06-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-17 | 2025-09-07 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-10-30 | 2025-10-28 |  | 2026-03-25 | 2026-05-25 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-06-01 | 108-25
25-109 | Epic Systems | 2026-04-27 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-17 | 2025-09-07 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-10-30 | 2025-10-28 |  | 2026-02-18 | 2026-04-20 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-04-27 | 109-25
25-110 | Epic Systems | 2026-04-27 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-17 | 2025-09-07 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-10-30 | 2025-10-28 |  | 2026-02-18 | 2026-04-20 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-04-27 | 110-25
25-111 | Epic Systems | 2026-04-27 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-17 | 2025-09-07 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-10-30 | 2025-10-28 |  | 2026-02-18 | 2026-04-20 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-04-27 | 111-25
25-112 | Epic Systems | 2026-04-27 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-17 | 2025-09-07 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-10-30 | 2025-10-28 |  | 2026-02-18 | 2026-04-20 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-18 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-04-27 | 112-25
25-113 | Epic Systems | 2026-05-11 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-09-01 | 2025-09-22 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-14 | 2025-11-12 |  | 2026-03-04 | 2026-05-04 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-05-11 | 113-25
25-115 | Epic Systems | 2026-05-11 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-17 | 2025-09-07 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-10-30 | 2025-10-28 |  | 2026-03-04 | 2026-05-04 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-05-11 | 115-25
25-116 | Polynt | 2026-06-16 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-22 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-04 | 2025-11-02 |  | 2026-04-09 | 2026-06-09 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-07 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-12 | 2026-06-16 | 116-25
25-117 | Merrick | 2026-04-13 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-25 | 2025-09-15 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 |  | 2026-02-04 | 2026-04-06 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-04-13 | 117-25
25-118 | Merrick | 2026-05-11 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-08-25 | 2025-09-15 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 |  | 2026-03-04 | 2026-05-04 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-05-11 | 118-25
25-119 | Vertiv |  | 0 | 0 | 0 | 0 | 0 | 2025-09-01 | 2025-09-22 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-14 | 2025-11-12 |  | #VALUE! | #VALUE! | [10 empty] | 119-25
25-120 | Andritz | 2026-07-06 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-09-08 | 2025-09-29 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-21 | 2025-11-19 |  | 2026-04-22 | 2026-06-29 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-20 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-07-06 | 120-25
25-121 | Kimberly Clark | 2026-05-18 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-09-21 | 2025-10-12 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-04 | 2025-12-02 |  | 2026-03-11 | 2026-05-11 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-05-18 | 121-25
25-122 | Kimberly Clark | 2026-05-18 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-09-21 | 2025-10-12 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-04 | 2025-12-02 |  | 2026-03-11 | 2026-05-11 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-05-18 | 122-25
25-123 | Kimberly Clark | 2026-05-18 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-09-21 | 2025-10-12 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-04 | 2025-12-02 |  | 2026-03-11 | 2026-05-11 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-05-18 | 123-25
25-124 | Vertiv |  | 0 | 0 | 0 | 0 | 0 | 2025-10-02 | 2025-10-23 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-15 | 2025-12-13 |  | #VALUE! | #VALUE! | [10 empty] | 124-25
25-356 | Synthomer | 2026-06-08 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-16 | 2025-11-06 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2025-12-29 | 2025-12-27 |  | 2026-04-01 | 2026-06-01 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 | 2026-06-08 | 356-25
25-357 | Sylvamo | 2026-05-18 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-17 | 2025-11-07 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2025-12-30 | 2025-12-28 |  | 2026-03-11 | 2026-05-11 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-05-18 | 357-25
25-358 | Sylvamo | 2026-05-18 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-17 | 2025-11-07 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2025-12-30 | 2025-12-28 |  | 2026-03-11 | 2026-05-11 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-05-18 | 358-25
26-002 | SNF | 2026-07-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-27 | 2025-11-17 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-09 | 2026-01-07 |  | 2026-04-24 | 2026-06-24 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-22 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-27 | 2026-07-01 | 002-26
26-003 | SNF | 2026-07-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-27 | 2025-11-17 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-09 | 2026-01-07 |  | 2026-04-24 | 2026-06-24 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-22 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-27 | 2026-07-01 | 003-26
26-004 | SNF | 2026-07-01 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-27 | 2025-11-17 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-09 | 2026-01-07 |  | 2026-04-24 | 2026-06-24 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-22 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-27 | 2026-07-01 | 004-26
26-005 | US Sugar | 2026-05-18 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-30 | 2025-11-20 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-12 | 2026-01-10 |  | 2026-03-04 | 2026-05-11 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-05-18 | 005-26
26-014 | SNF | 2026-06-01 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-30 | 2025-11-20 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-12 | 2026-01-10 |  | 2026-03-18 | 2026-05-25 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-20 | 2026-06-01 | 014-26
26-015 | SNF | 2026-06-23 | 3 | 0.25 | 0 | 0.25 | 0.5 | 2025-11-29 | 2025-12-20 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-11 | 2026-02-09 |  | 2026-04-23 | 2026-06-16 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-21 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-26 | 2026-06-23 | 015-26
26-016 | SNF | 2026-06-23 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-11-29 | 2025-12-20 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-11 | 2026-02-09 |  | 2026-04-09 | 2026-06-16 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-07 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-12 | 2026-06-23 | 016-26
26-017 | SNF | 2026-07-08 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-30 | 2025-11-20 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-12 | 2026-01-10 |  | 2026-04-24 | 2026-07-01 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-22 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-27 | 2026-07-08 | 017-26
26-018 | SNF | 2026-07-08 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-10-30 | 2025-11-20 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-12 | 2026-01-10 |  | 2026-04-24 | 2026-07-01 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-22 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-27 | 2026-07-08 | 018-26
26-020 | US Sugar | 2026-07-15 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-11-24 | 2025-12-15 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-06 | 2026-02-04 |  | 2026-05-01 | 2026-07-08 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-27 | 2026-05-29 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-06-03 | 2026-07-15 | 020-26
26-021 | US Sugar | 2026-07-15 | 5 | 0.25 | 0 | 0.25 | 0.5 | 2025-11-24 | 2025-12-15 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-06 | 2026-02-04 |  | 2026-05-01 | 2026-07-08 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-27 | 2026-05-29 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-06-03 | 2026-07-15 | 021-26
26-022 | Andritz | 2026-06-04 | 4 | 0.25 | 0 | 0.25 | 0.5 | 2025-11-28 | 2025-12-19 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-10 | 2026-02-08 |  | 2026-03-28 | 2026-05-28 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-25 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-30 | 2026-06-04 | 022-26
26-024 | Polynt | 2026-07-20 | 2 | 0.25 | 0 | 0.25 | 0.5 | 2025-12-13 | 2026-01-03 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-25 | 2026-02-23 |  | 2026-05-27 | 2026-07-13 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-24 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-07-20 | 024-26
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | #VALUE! | #VALUE! | [10 empty] | 0-0
Formulas:
Ship Date = IFNA(IFNA(VLOOKUP([ALT JOB #],'[1]Schedule Not Certified'!$C:$F,3,0),VLOOKUP([ALT JOB #],[1]CERTIFIED!$C:$E,3,0)),"")
Ship Date = [Ship Date]
App. Prints Submitted = IFERROR([Customer Response]-21,"")
Customer Response = [Resubmit]-J2
Customer Response = [Resubmit]-L2
Resubmit = [Customer Response]-K2
Resubmit = [Customer Response]-M2
Last Possible Resubmit = IFERROR([Last Possible Customer Response]-O2,"")
Last Possible Customer Response = IFERROR([Prelim BOM complete by]-2,"")
Long lead time order by = IFERROR(VLOOKUP([Job],'Date Calcs'!A:C,3,0),"")
Prelim BOM complete by = IFERROR([Long lead time order by]-R2,"")
Final Calcs = [Cert Dwgs]-T2
A.I. = [Release Target]+([Fabrication]*7)
Cert Dwgs = IFERROR(IF(VLOOKUP([Job],'Actual Dates'!A:AE,21,0)>"",VLOOKUP([Job],'Actual Dates'!A:AE,21,0),[Update BOM]-V2),"")
Update BOM = IFERROR([Stock Check]-W2,"")
Stock Check = IFERROR([Parts to Arrive]-X2,"")
Parts to Arrive = IFERROR(IF([Final BOM]+Y2+5>[Release Target],[Release Target]-7,[Final BOM]+Y2+5),"")
Final BOM = IFERROR([Release Target]-Z2,"")
Build Plan = IFERROR([Release Target]-AA2,"")
Burn File = IFERROR([Release Target]-AB2,"")
QC Checklist = IFERROR([Release Target]-AC2,"")
Release Target = IFERROR([Ship Date]-(SUM([Fabrication]:[Shipping Prep])*7),"")

## Shipment Checklist
Shipped
Job # | Customer | Actual Ship Date | QC Document Created | Customer Notified of ETA | As Built Drawings | QC Documents | Shipping Photographs | Ship Loose Verified | Other Requested | Sent Survey Email | Comments
24-046 | SYMS Engineering |  | Yes | Yes |  |  | Yes | Yes | N/A
25-010 | Kimberly Clark | 2026-02-23 | Yes | Yes | Yes |  | Yes | Yes | N/A |  | Wait for end of Project
25-011 | Kimberly Clark | 2026-02-04 | Yes | Yes | Yes |  | Yes | Yes | N/A |  | Wait for end of Project
25-012 | Kimberly Clark
25-013 | Kimberly Clark
25-014 | Kimberly Clark | 2025-11-06
25-015 | Kimberly Clark | 2025-11-06
25-016 | Kimberly Clark | 2026-02-23 | Yes | Yes | Yes |  | Yes | Yes | N/A |  | Wait for end of Project
25-017 | Kimberly Clark | 2026-01-21 | Yes | Yes |  | Yes | Yes | N/A | N/A
25-018 | Kimberly Clark
25-019 | Kimberly Clark | 2026-02-23 | Yes | Yes | Yes |  | Yes | N/A | N/A |  | Wait for end of Project
25-020 | Kimberly Clark | 2026-02-05 | Yes | Yes | Yes |  | Yes | N/A | N/A |  | Wait for end of Project
25-021 | Kimberly Clark | 2026-02-20 | Yes | Yes | Yes |  | Yes | N/A | N/A |  | Wait for end of Project
25-023 | Andritz | 2025-05-27
25-024 | Andritz | 2025-05-27
25-025 | Irving Tissue | 2025-09-04
25-026 | Irving Tissue | 2025-09-04
25-027 | Irving Tissue | 2025-10-02
25-028 | Irving Tissue | 2025-10-02
25-029 | Irving Tissue | 2025-09-30
25-030 | Irving Tissue | 2025-09-30
25-031 | Irving Tissue | 2025-10-28
25-032 | Irving Tissue | 2025-10-28
25-033 | Irving Tissue | 2025-10-28
25-034 | Irving Tissue | 2025-08-27
25-035 | Irving Tissue | 2025-08-27
25-036 | Irving Tissue | 2025-08-27
25-037 | Irving Tissue | 2025-09-04
25-039 | Zachry | 2025-08-15
25-040 | NAK Kiln
25-042 | Andritz | 2025-08-27
25-044 | Noah Industrial | 2025-08-14
25-045 | ProPipe | 2025-12-31
25-052 | Kraton | 2025-12-29
25-053 | Andritz | 2025-09-26
25-054 | Chromascape | 2025-11-24
25-055 | Airgas
25-056 | Reco | 2025-11-11
25-057 | Reco | 2025-11-11
25-058 | Reco | 2025-12-18
25-059 | Reco | 2025-12-16
25-060 | Reco | 2026-01-13
25-061 | Reco | 2026-01-13
25-062 | Reco | 2026-02-02 | Yes | Yes | Yes | Yes | Yes | N/A | N/A |  | Wait for end of Project
25-063 | Reco | 2026-02-02 | Yes | Yes | Yes | Yes | Yes | N/A | N/A |  | Wait for end of Project
25-064 | Reco | 2026-02-16 | Yes | Yes | Yes | Yes | Yes | N/A | N/A |  | Wait for end of Project
25-065 | Reco | 2026-02-16 | Yes | Yes | Yes | Yes | Yes | N/A | N/A |  | Wait for end of Project
25-066 | Reco
25-067 | Reco
25-068 | Reco
25-069 | Reco
25-070 | Reco
25-071 | Reco
25-072 | Burke Industrial | 2025-09-22
25-073 | Burke Industrial | 2025-09-25
25-074 | Kemira | 2025-12-17
25-075 | Kemira | 2025-12-03
25-076 | Irving tissue | 2025-09-30
25-077 | Epic Systems | 2026-01-06
25-078 | Epic Systems | 2026-01-06
25-079 | Epic Systems | 2026-01-06
25-080 | Domtar | 2026-01-07
25-083 | Synthomer
25-084 | Atlas Minerals
25-085 | Noah Industrial | 2025-12-08
25-086 | Tellus | 2025-12-31
25-087 | Solvay | 2025-10-22
25-088 | CIL Isotopes | 2025-11-18
25-089 | Valmet | 2026-03-09 | Yes | Yes | Yes |  | Yes | Yes | N/A
25-090 | GAF | 2025-09-12
25-091 | US Sugar | 2025-12-31
25-092 | Symrise
25-093 | Symrise
25-094 | Kimberly Clark | 2025-01-21
25-095 | Andritz | 2025-12-31
25-096 | Milliken | 2026-01-07
25-097 | Milliken | 2026-01-07
25-098 | Coastal Technologies
25-099 | Burke Industrial
25-101 | Harper Love
25-102 | Epic Systems
25-103 | Epic Systems
25-104 | Epic Systems
25-105 | Epic Systems
25-106 | Epic Systems
25-107 | Epic Systems
25-108 | Epic Systems
25-109 | Epic Systems
25-110 | Epic Systems
25-111 | Epic Systems
25-112 | Epic Systems
25-113 | Epic Systems
25-115 | Epic Systems
25-116 | Polynt
25-117 | Merrick
25-118 | Merrick
25-119 | Vertiv | 2025-12-31
25-120 | Andritz
25-121 | Kimberly Clark
25-122 | Kimberly Clark
25-123 | Kimberly Clark
25-124 | Vertiv
25-356 | Synthomer
25-357 | Sylvamo
25-358 | Sylvamo
26-002 | SNF
26-003 | SNF
26-004 | SNF
26-005 | US Sugar
26-014 | SNF
26-015 | SNF
26-016 | SNF
26-017 | SNF
26-018 | SNF
26-020 | US Sugar
26-021 | US Sugar
26-022 | Andritz
26-024 | Polynt
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0 | 0
0 | 0
0 | 0

## OGSM 2019 (hidden)
OGSM 2019 (EFFICIENCY MEASURE)
JOB | CUSTOMER | PO RECEIVING | KICK-OFF MEETING |  | INITIAL DWG SUBMISSION |  | BILL OF MATERIAL |  | BUILT PLAN |  | CERTIFIED DWG | SHOP RELEASE |  | CYCLE TIME | DWG DELAY | RELEASE DELAY | REMARK |  | TIME PERIOD | DWG DUE | DWG ON TIME | EFFICIENCY
|  |  | EXPECTED | ACTUAL | EXPECTED | ACTUAL | EXPECTED | ACTUAL | EXPECTED | ACTUAL |  | EXPECTED | ACTUAL
#REF! | #REF! | #REF! | #REF! | 2019-02-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | NP ON VACATION
#REF! | #REF! | #REF! | #REF! | 2019-02-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | NP ON VACATION
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | N/A | N/A | #VALUE! | N/A | N/A | #REF! | #VALUE!
#REF! | #REF! | #REF! | #REF! | 2019-03-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | APPROVAL ON LEG
#REF! | #REF! | #REF! | #REF! | 2019-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Customer changes
#REF! | #REF! | #REF! | #REF! | 2019-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Customer changes
#REF! | #REF! | #REF! | #REF! | 2019-03-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | AI dwg CHECK
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #VALUE! | N/A | #VALUE! | #REF! | #VALUE! | TOE plate JN 071-18
#REF! | #REF! | #REF! | #REF! | 2019-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-05-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | CRN APPROVAL
#REF! | #REF! | #REF! | #REF! | 2019-05-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | CRN APPROVAL
#REF! | #REF! | #REF! | #REF! | 2019-05-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | NO SCALED DWG
#REF! | #REF! | #REF! | #REF! | 2019-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Hurricane Dorian
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | AI dwg CHECK
#REF! | #REF! | #REF! | #REF! | 2019-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | YATES JOB WAS PRIORITY
#REF! | #REF! | #REF! | #REF! | 2019-09-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | [13 empty] | 0
#REF! | #REF! | #REF! | #REF! | 2019-12-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | N/A | N/A | N/A | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-11-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | JAN' 2021 | #REF! | 6 | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | FAB'2021 | #REF! | 2 | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | FAB'2021
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | MAR'21 | #REF! | 1 | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | FAB'2021
#REF! | #REF! | #REF! | #REF! | 2021-03-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | MAR'21 | 1 | 1
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24-046 | SYMS Engineering | 2024-08-15 | 2024-09-04 | 2022-03-23 | 2024-09-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-01 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25-010 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-18 | 2025-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-14 | #REF! | #REF! | #REF! | #REF!
25-011 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-19 | 2025-03-04 | #REF! | #REF! |  | #REF! | #REF! | #REF! | 2025-09-21 | #REF! | #REF! | #REF! | #REF!
25-012 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-20 | 2025-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-21 | #REF! | #REF! | #REF! | #REF!
25-013 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-21 | 2025-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-06-22 | #REF! | #REF! | #REF! | #REF!
25-014 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-22 | 2025-03-04 | 2025-05-28 | 2025-09-02 |  | 2025-09-03 | 2025-12-08 | 2025-08-28 | 2025-06-07 | 2026-01-17 | 354 | -85 | -224
25-015 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-23 | 2025-03-04 | 2025-04-25 | 2025-09-09 |  | 2025-09-10 | 2025-10-31 | 2025-09-04 | 2025-06-07 | 0 | -45685 | -52 | 45815
25-016 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-24 | 2025-03-04 | 2025-04-25 | 2025-09-09 | 2025-07-01 | 2025-09-10 | 2025-01-07 | 2025-09-04 | 2025-06-07 | 2026-01-08 | 345 | -52 | -215
25-017 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-25 | 2025-03-04 | 2025-03-25 | 2025-09-09 |  | 2025-09-10 | 2025-10-22 | 2025-09-04 | 2025-05-01 | 2025-10-27 | 272 | -21 | -179
25-018 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-26 | 2025-03-04 | 2025-04-02 | 2025-06-02 | 2025-07-02 | 2025-06-03 | 2025-09-03 | 2025-05-28 | 2025-09-14 | 2025-09-03 | 218 | -29 | 11
25-019 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-27 | 2025-03-04 | 2025-04-02 | 2025-06-02 | 2025-07-17 | 2025-06-03 | 2025-08-27 | 2025-05-28 | 2025-09-21 | 2025-08-27 | 211 | -29 | 25
25-020 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-28 | 2025-03-04 | 2025-04-02 | 2025-06-02 |  | 2025-06-03 | 2025-11-18 | 2025-05-28 | 2025-09-14 | 2025-12-04 | 310 | -29 | -81
25-021 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-29 | 2025-03-04 | 2025-03-10 | 2025-04-25 | 2025-07-23 | 2025-04-28 | 2025-09-30 | 2025-04-22 | 2025-09-21 | 2025-09-30 | 245 | -6 | -9
25-023 | Andritz | 2025-01-30 | 2025-02-12 | 2022-04-30 | 2025-02-13 | 2025-05-21 | 2025-09-10 |  | 2025-09-11 | 2025-10-22 | 2025-09-05 | 2025-04-03 | 2025-10-24 | 267 | -97 | -204
25-024 | Andritz | 2025-01-30 | 2025-02-12 | 2022-05-01 | 2025-02-13 | 2025-05-13 | 2025-09-10 |  | 2025-09-11 | 2025-11-18 | 2025-09-05 | 2025-04-03 | 2025-12-04 | 308 | -89 | -245
25-025 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-02 | 2025-03-05 | 2025-03-25 | 2025-08-29 |  | 2025-09-01 | 2025-09-04 | 2025-08-26 | 2025-06-15 | 2025-09-04 | 211 | -20 | -81
25-026 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-03 | 2025-03-05 | 2025-05-13 | 2025-09-05 |  | 2025-09-08 | 2025-09-16 | 2025-09-02 | 2025-06-06 | 2025-09-18 | 225 | -69 | -104
25-027 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-04 | 2025-03-05 | 2025-02-12 | 2025-03-13 |  | 2025-03-14 | 2025-03-12 | 2025-03-10 | 2025-06-06 | 2025-03-19 | 42 | 21 | 79
25-028 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-05 | 2025-03-05 | 2025-02-12 | 2025-03-13 |  | 2025-03-14 | 2025-03-12 | 2025-03-10 | 2025-06-06 | 2025-03-19 | 42 | 21 | 79
25-029 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-06 | 2025-03-05 | 2025-02-26 | 2025-06-02 |  | 2025-06-03 | 2025-06-03 | 2025-05-28 | 2025-06-06 | 2025-06-13 | 128 | 7 | -7
25-030 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-07 | 2025-03-05 | 2025-02-26 | 2025-05-23 |  | 2025-05-26 | 2025-06-02 | 2025-05-20 | 2025-06-06 | 2025-06-13 | 128 | 7 | -7
25-031 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-08 | 2025-03-05 | 2025-02-26 | 2025-05-23 |  | 2025-05-26 | 2025-06-03 | 2025-05-20 | 2025-06-14 | 2025-08-06 | 182 | 7 | -53
25-032 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-09 | 2025-03-05 | 2025-03-03 | 2025-05-23 |  | 2025-05-26 | 2025-06-03 | 2025-05-20 | 2025-06-14 | 2025-08-06 | 182 | 2 | -53
25-033 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-10 | 2025-03-05 | 2025-03-03 | 2025-05-23 |  | 2025-05-26 | 2025-06-09 | 2025-05-20 | 2025-06-14 | 2025-08-08 | 184 | 2 | -55
25-034 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-11 | 2025-03-05 | 2025-03-05 | 2025-05-23 |  | 2025-05-26 | 2025-06-09 | 2025-05-20 | 2025-06-14 | 2025-08-08 | 184 | 0 | -55
25-035 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-12 | 2025-03-05 | 2025-02-27 | 2025-06-02 |  | 2025-06-03 | 2025-06-12 | 2025-05-28 | 2025-06-14 | 2025-08-13 | 189 | 6 | -60
25-036 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-13 | 2025-03-05 | 2025-02-27 | 2025-06-02 |  | 2025-06-03 | 2025-06-12 | 2025-05-28 | 2025-06-14 | 2025-08-15 | 191 | 6 | -62
25-037 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-14 | 2025-03-05 | 2025-03-05 | 2025-06-02 |  | 2025-06-03 | 2025-06-16 | 2025-05-28 | 2025-06-14 | 2025-08-20 | 196 | 0 | -67
25-039 | Zachry | 2025-02-26 | 2025-03-18 | 2022-05-15 | 2025-03-19 | 2025-02-26 | 2025-06-02 |  | 2025-06-03 | 2025-06-16 | 2025-05-28 | 2025-05-25 | 2025-07-02 | 126 | 21 | -38
25-040 | NAK Kiln | 2025-03-05 | 2025-03-18 | 2022-05-16 | 2025-03-19 | 2025-03-05 | 2025-06-02 | 2025-06-05 | 2025-06-03 | 2025-06-16 | 2025-05-28 | 2025-03-21 | 2025-07-02 | 119 | 14 | -103
25-042 | Andritz | 2025-03-19 | 2025-04-08 | 2022-05-17 | 2025-04-09 | 2025-02-26 | 2025-06-02 |  | 2025-06-03 | 2025-06-16 | 2025-05-28 | 2025-06-12 | 2025-07-02 | 105 | 42 | -20
25-044 | Noah Industrial | 2025-04-01 | 2025-04-28 | 2022-05-18 | 2025-04-29 | 2025-02-28 | 2025-06-02 |  | 2025-06-03 | 2025-06-16 | 2025-05-28 | 2025-06-22 | 2025-06-18 | 78 | 60 | 4
25-045 | ProPipe | 2025-04-05 | 2025-04-11 | 2022-05-19 | 2025-04-12 | 2025-03-20 | #VALUE! |  | #VALUE! | #VALUE! |  | 2026-01-24 |  | #VALUE! | 23 | #VALUE!
25-052 | Kraton | 2025-05-19 | 2025-06-06 | 2022-05-20 | 2025-06-09 | 2025-02-18 | 2025-03-18 |  | 2025-03-19 | 2025-09-16 | 2025-03-13 | 2025-08-15 | 2025-09-17 | 121 | 111 | -33
25-053 | Andritz | 2025-06-02 | 2026-01-02 | 2022-05-21 | 2026-01-05 |  | #VALUE! | 2025-05-29 | #VALUE! | 2025-06-20 |  | 2026-06-04 | 2025-07-01 | 29 | #VALUE! | 338
25-054 | Chromascape | 2025-06-03 | 2025-06-30 | 2022-05-22 | 2025-07-01 | 2025-05-14 | 2025-06-04 |  | 2025-06-05 | 2025-06-18 | 2025-05-30 | 2025-08-03 | 2025-06-25 | 22 | 48 | 39
25-055 | Airgas | 2025-06-12 | 2025-10-01 | 2022-05-23 | 2025-10-02 | 2025-12-31 | 1900-01-03 |  | 1900-01-04 | 0 | 0 | 2026-01-03 | 0 | -45820 | -90 | 46025
25-056 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-24 | 2025-07-04 | 2025-06-11 | 2025-08-01 |  | 2025-08-04 | 2025-09-17 | 2025-07-29 | 2025-08-21 | 2025-09-23 | 102 | 23 | -33
25-057 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-25 | 2025-07-04 | 0 | 1900-01-03 |  | 1900-01-04 | 2025-08-28 | 0 | 2025-08-21 | 2025-08-28 | 76 | 45842 | -7
25-058 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-26 | 2025-07-04 | 2025-06-27 | 2025-07-22 |  | 2025-07-23 | 2025-09-17 | 2025-07-17 | 2025-08-21 | 2025-09-23 | 102 | 7 | -33
25-059 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-27 | 2025-07-04 | 2025-11-25 | 2025-12-22 |  | 2025-12-23 | 2026-03-11 | 2025-12-17 | 2025-08-21 | 2025-09-23 | 102 | -144 | -33
25-060 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-28 | 2025-07-04 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-08-20 | 68 | -5 | 1
25-061 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-29 | 2025-07-04 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-08-20 | 68 | -5 | 1
25-062 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-30 | 2025-07-04 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-09-03 | 82 | -5 | -13
25-063 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-31 | 2025-07-04 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-09-03 | 82 | -5 | -13
25-064 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-01 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-09-26 | 105 | -5 | -36
25-065 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-02 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-09-26 | 105 | -5 | -36
25-066 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-03 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-11-10 | 150 | -5 | -81
25-067 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-04 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-11-10 | 150 | -5 | -81
25-068 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-05 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-12-09 | 179 | -5 | -110
25-069 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-06 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-12-09 | 179 | -5 | -110
25-070 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-07 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2026-01-12 | 213 | -5 | -144
25-071 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-08 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2026-01-12 | 213 | -5 | -144
25-072 | Burke Industrial | 2025-06-16 | 2025-07-04 | 2022-06-09 | 2025-07-07 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-07-31 | 2026-02-09 | 238 | -2 | -193
25-073 | Burke Industrial | 2025-06-16 | 2025-07-04 | 2022-06-10 | 2025-07-07 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-07-31 | 2026-02-09 | 238 | -2 | -193
25-074 | Kemira | 2025-06-16 | 2025-07-04 | 2022-06-11 | 2025-07-07 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-10 | 2026-02-18 | 247 | -2 | -192
25-075 | Kemira | 2025-06-16 | 2025-07-04 | 2022-06-12 | 2025-07-07 | 2025-07-09 | 2025-08-07 |  | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-09-08 | 2026-02-18 | 247 | -2 | -163
25-076 | Irving tissue | 2025-06-17 | 2025-07-14 | 2022-06-13 | 2025-07-15 | 2025-07-03 | 2025-07-17 |  | 2025-07-18 | 2025-07-23 | 2025-07-14 | 2025-09-05 | 2025-07-30 | 43 | 12 | 37
25-077 | Epic Systems | 2025-06-25 | 2025-07-15 | 2022-06-14 | 2025-07-16 | 2025-07-03 | 2025-07-17 |  | 2025-07-18 | 2025-07-23 | 2025-07-14 | 2025-09-11 | 2025-07-30 | 35 | 13 | 43
25-078 | Epic Systems | 2025-06-25 | 2025-07-15 | 2022-06-15 | 2025-07-16 | 2025-07-16 | 2025-07-25 |  | 2025-07-28 | 2025-09-10 | 2025-07-22 | 2025-09-11 | 2025-09-11 | 78 | 0 | 0
25-079 | Epic Systems | 2025-06-25 | 2025-07-15 | 2022-06-16 | 2025-07-16 | 2025-07-16 | 2025-08-22 |  | 2025-08-25 | 2025-10-22 | 2025-08-19 | 2025-09-11 | 2025-10-30 | 127 | 0 | -49
25-080 | Domtar | 2025-06-27 | 2025-07-17 | 2022-06-17 | 2025-07-18 | 2025-07-28 | 2025-08-22 |  | 2025-08-25 | 2025-08-28 | 2025-08-19 | 2025-08-24 | 2025-08-28 | 62 | -10 | -4
25-083 | Synthomer | 2025-07-15 | 2025-08-04 | 2022-06-18 | 2025-08-05 | 2025-07-23 | 2025-08-28 | 2025-06-04 | 2025-08-29 | 2025-10-23 | 2025-08-25 | 2026-02-26 | 2025-10-31 | 108 | 13 | 118
25-084 | Atlas Minerals | 2025-07-18 | 2025-08-07 | 2022-06-19 | 2025-08-08 | 2025-07-21 | 2025-08-28 | 2025-09-03 | 2025-08-29 | 2025-10-23 | 2025-08-25 | 2025-11-28 | 2025-11-05 | 110 | 18 | 23
25-085 | Noah Industrial | 2025-07-22 | 2025-08-11 | 2022-06-20 | 2025-08-12 | 2025-07-21 | 2025-08-28 |  | 2025-08-29 | 2025-10-23 | 2025-08-25 | 2025-09-07 | 2025-11-05 | 106 | 22 | -59
25-086 | Tellus | 2025-07-30 | 2025-07-29 | 2022-06-21 | 2025-07-30 | 2025-07-18 | #VALUE! |  | #VALUE! | 2025-09-23 |  | 2026-01-24 | 2025-10-30 | 92 | 12 | 86
25-087 | Solvay | 2025-08-07 | 2025-08-27 | 2022-06-22 | 2025-08-28 | #REF! | #REF! |  | #REF! | #REF! | #REF! | 2025-10-02 | #REF! | #REF! | #REF! | #REF!
25-088 | CIL Isotopes | 2025-08-13 | 2025-09-02 | 2022-06-23 | 2025-09-03 | 2025-08-15 | 2025-11-07 |  | 2025-11-10 | 2025-11-24 | 2025-11-04 | 2025-10-03 | 2025-11-24 | 103 | 19 | -52
25-089 | Valmet | 2025-08-22 | 2025-09-19 | 2022-06-24 | 2025-09-22 12:00 | 2025-08-08 | 2025-11-07 | 2025-11-05 | 2025-11-10 | 2025-11-24 | 2025-11-04 | 2025-12-15 | 2025-11-24 | 94 | 45.5 | 21
25-090 | GAF | 2025-08-18 | 2025-08-22 | 2022-06-25 | 2025-08-25 | 2025-08-12 | 2025-08-22 |  | 2025-08-25 | #VALUE! | 2025-08-19 | 2025-09-29 |  | #VALUE! | 13 | #VALUE!
25-091 | US Sugar | 2025-09-04 | 2025-09-10 | 2022-06-26 | 2025-09-11 | 2025-12-31 | #VALUE! |  | #VALUE! | 2025-08-25 |  | 2026-01-24 | 2025-08-26 | -9 | -111 | 151
25-092 | Symrise | 2025-09-10 | 2025-10-07 | 2022-06-27 | 2025-10-08 | 2025-08-28 | 2025-09-18 | 2025-09-22 | 2025-09-19 | 2025-09-22 | 2025-09-15 | 2025-11-16 | 2025-09-24 | 14 | 41 | 53
25-093 | Symrise | 2025-09-10 | 2025-10-07 | 2022-06-28 | 2025-10-08 | 2025-09-03 | 2025-09-18 | 2025-09-22 | 2025-09-19 | 2025-09-22 | 2025-09-15 | 2025-11-16 | 2025-10-23 | 43 | 35 | 24
25-094 | Kimberly Clark | 2025-09-15 | 2025-10-03 | 2022-06-29 | 2025-10-06 | 2025-09-22 | 2025-12-09 |  | 2025-12-10 | 2025-12-11 | 2025-12-04 | 2025-11-13 | 2025-12-16 | 92 | 14 | -33
25-095 | Andritz | 2025-09-19 | 2025-10-16 | 2022-06-30 | 2025-10-17 | 2025-08-22 | #VALUE! |  | #VALUE! | #VALUE! |  | 2026-02-26 |  | #VALUE! | 56 | #VALUE!
25-096 | Milliken | 2025-09-22 | 2025-10-10 | 2022-07-01 | 2025-10-13 | 2025-12-31 | 1900-01-03 |  | 1900-01-04 | 2025-09-22 | 0 | 2025-11-09 | 2025-09-23 | 1 | -79 | 47
25-097 | Milliken | 2025-09-22 | 2025-10-10 | 2022-07-02 | 2025-10-13 | 2025-10-01 | 2025-10-30 |  | 2025-10-31 | 2026-01-09 | 2025-10-27 | 2025-11-09 | 2026-01-13 | 113 | 12 | -65
25-098 | Coastal Technologies | 2025-09-24 | 2025-10-21 | 2022-07-03 | 2025-10-22 | 2025-10-01 | 2025-10-30 | 2025-11-18 | 2025-10-31 | 2026-01-09 | 2025-10-27 | 2026-03-01 | 2026-01-13 | 111 | 21 | 47
25-099 | Burke Industrial | 2025-10-02 | 2025-10-29 | 2022-07-04 | 2025-10-30 | 2025-10-06 | 2025-11-21 | 2025-11-21 | 2025-11-24 | 2025-12-01 | 2025-11-18 | 2025-11-22 | 2025-12-09 | 68 | 24 | -17
25-101 | Harper Love | 2025-10-24 | 2025-11-20 | 2022-07-05 | 2025-11-21 | 2025-10-16 | 1900-01-03 | NA | 1900-01-04 | 0 | 0 | 2025-12-25 | 0 | -45954 | 36 | 46016
25-102 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-06 | 2025-12-12 | 2025-10-15 | 2025-10-28 |  | 2025-10-29 | 2025-12-01 | 2025-10-23 | 2026-03-15 |  | #VALUE! | 58 | #VALUE!
25-103 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-07 | 2025-12-12 | 2025-10-15 | 2025-10-28 |  | 2025-10-29 | 2025-12-01 | 2025-10-23 | 2026-03-15 |  | #VALUE! | 58 | #VALUE!
25-104 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-08 | 2025-12-12 | 2025-10-22 | 2025-11-04 |  | 2025-11-05 | 2026-01-15 | 2025-10-30 | 2026-03-15 |  | #VALUE! | 51 | #VALUE!
25-105 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-09 | 2025-12-12 | 2025-10-29 | 2025-11-10 |  | 2025-11-11 | 2026-01-16 | 2025-11-05 | 2026-03-15 |  | #VALUE! | 44 | #VALUE!
25-106 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-10 | 2025-12-12 | 2025-11-20 | 2025-12-11 |  | 2025-12-12 | 2026-01-19 | 2025-12-08 | 2026-03-15 |  | #VALUE! | 22 | #VALUE!
25-107 | Epic Systems | 2026-02-02 | 2026-02-27 | 2022-07-11 | 2026-03-02 | 2025-12-12 | 2026-02-27 |  | 2026-03-02 |  | 2026-02-24 | 2026-04-12 |  | #VALUE! | 80 | #VALUE!
25-108 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-12 | 2025-11-27 | 2025-12-12 | 2026-02-24 |  | 2026-02-25 |  | 2026-02-19 | 2026-04-05 |  | #VALUE! | -15 | #VALUE!
25-109 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-13 | 2025-11-27 | 2025-12-12 | 2026-02-24 | 2026-02-23 | 2026-02-25 | 0 | 2026-02-19 | 2026-03-15 |  | #VALUE! | -15 | #VALUE!
25-110 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-14 | 2025-11-27 | 2025-12-12 | 2026-02-24 | 2026-02-26 | 2026-02-25 | 0 | 2026-02-19 | 2026-02-16 |  | #VALUE! | -15 | #VALUE!
25-111 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-15 | 2025-11-27 | 2025-12-12 | 2026-02-27 |  | 2026-03-02 | 0 | 2026-02-24 | 2026-02-16 |  | #VALUE! | -15 | #VALUE!
25-112 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-16 | 2025-11-27 | 2025-11-26 | 1900-01-03 |  | 1900-01-04 | 0 | 0 | 2026-02-16 |  | #VALUE! | 1 | #VALUE!
25-113 | Epic Systems | 2025-11-14 | 2025-12-11 | 2022-07-17 | 2025-12-12 | 2025-11-26 | 1900-01-03 |  | 1900-01-04 |  | 0 | 2026-02-26 |  | #VALUE! | 16 | #VALUE!
25-115 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-18 | 2025-11-27 | 2025-11-26 | 2026-02-24 |  | 2026-02-25 | 0 | 2026-02-19 | 2026-03-15 |  | #VALUE! | 1 | #VALUE!
25-116 | Polynt | 2025-11-04 | 2025-12-01 | 2022-07-19 | 2025-12-02 | 2025-11-26 | 2026-02-27 | 2026-02-02 | 2026-03-02 | 0 | 2026-02-24 | 2026-03-08 |  | #VALUE! | 6 | #VALUE!
25-117 | Merrick | 2025-11-07 | 2026-01-08 | 2022-07-20 | 2026-01-09 | 2025-11-26 | 2026-02-27 | 2026-03-09 | 2026-03-02 | 0 | 2026-02-24 | 2026-02-26 | 0 | -45968 | 44 | 46079
25-118 | Merrick | 2025-11-07 | 2026-01-08 | 2022-07-21 | 2026-01-09 | 2025-11-26 | 2026-02-27 | 2026-03-09 | 2026-03-02 | 0 | 2026-02-24 | 2026-03-05 | 0 | -45968 | 44 | 46086
25-119 | Vertiv | 2025-11-14 | 2025-11-27 | 2022-07-22 | 2025-11-28 | 2025-12-12 | 1900-01-03 |  | 1900-01-04 |  | 0 | 2025-12-27 |  | #VALUE! | -14 | #VALUE!
25-120 | Andritz | 2025-11-21 | 2025-11-20 | 2022-07-23 | 2025-11-21 | 2025-11-26 | 2026-02-24 |  | 2026-02-25 |  | 2026-02-19 | 2026-01-24 |  | #VALUE! | -5 | #VALUE!
25-121 | Kimberly Clark | 2025-12-04 | 2025-12-31 | 2022-07-24 | 2026-01-01 | 2025-12-19 | 1900-01-03 |  | 1900-01-04 |  | 0 | 2026-04-03 |  | #VALUE! | 13 | #VALUE!
25-122 | Kimberly Clark | 2025-12-04 | 2025-12-31 | 2022-07-25 | 2026-01-01 | 2026-01-14 | 2026-02-13 |  | 2026-02-16 |  | 2026-02-10 | 2026-04-03 |  | #VALUE! | -13 | #VALUE!
25-123 | Kimberly Clark | 2025-12-04 | 2025-12-31 | 2022-07-26 | 2026-01-01 | 2026-01-14 | 2026-02-19 |  | 2026-02-20 |  | 2026-02-16 | 2026-02-15 |  | #VALUE! | -13 | #VALUE!
25-124 | Vertiv | 2025-12-15 | 2025-12-12 | 2022-07-27 | 2025-12-15 | 2025-11-24 | 2025-12-08 |  | 2025-12-09 | 0 | 2025-12-03 | 2026-01-24 | 0 | -46006 | 21 | 46046
25-356 | Synthomer | 2025-12-29 | 2026-01-23 | 2022-07-28 | 2026-01-26 | 2025-12-31 | 1900-01-03 |  | 1900-01-04 | 0 | 0 | 2026-03-17 |  | #VALUE! | 26 | #VALUE!
25-357 | Sylvamo | 2025-12-30 | 2026-01-26 | 2022-07-29 | 2026-01-27 | 2026-01-08 | 1900-01-03 |  | 1900-01-04 |  | 0 | 2026-03-07 |  | #VALUE! | 19 | #VALUE!
25-358 | Sylvamo | 2025-12-30 | 2026-01-26 | 2022-07-30 | 2026-01-27 | 2026-01-08 | 1900-01-03 |  | 1900-01-04 |  | 0 | 2026-03-07 |  | #VALUE! | 19 | #VALUE!
Formulas:
KICK-OFF MEETING = WORKDAY([INITIAL DWG SUBMISSION],-1,)
BILL OF MATERIAL = WORKDAY([CERTIFIED DWG],3,)
BUILT PLAN = WORKDAY([CERTIFIED DWG],4,)
ACTUAL = IF(VLOOKUP([JOB],'Actual Dates'!A4:AE777,8,),'Actual Dates'!H5,"")
ACTUAL = IF(VLOOKUP([JOB],'Actual Dates'!A4:AE800,26,),'Actual Dates'!AA5,"")
CERTIFIED DWG = IF(VLOOKUP([JOB],'Actual Dates'!A4:AE800,21,),'Actual Dates'!T5,"")

## DRAWING EFFICIENCY (hidden)
| TIME PERIOD | DWG DUE | DWG ON TIME | EFFICIENCY | TARGET
2021 | JANUARY | #REF! | 6 | #REF! | 95%
| FEBRUARY | #REF! | 2 | #REF! | 95%
| MARCH | 2 | 2 | 100% | 95%
| APRIL | 2 | 2 |  | 95%
| MAY | 2 | 2 |  | 95%
| JUNE |  |  |  | 95%
| JULY |  |  |  | 95%
| AUGUST |  |  |  | 95%
| SEPTEMBER |  |  |  | 95%
| OCTOBER |  |  |  | 95%
| NOVEMBER |  |  |  | 95%
| DECEMBER |  |  |  | 95%
2022 | JANUARY |  |  |  | 95%
| FEBRUARY |  |  |  | 95%
| MARCH |  |  |  | 95%
| APRIL |  |  |  | 95%
| MAY |  |  |  | 95%
| JUNE |  |  |  | 95%
| JULY |  |  |  | 95%
| AUGUST |  |  |  | 95%
| SEPTEMBER |  |  |  | 95%
| OCTOBER |  |  |  | 95%
| NOVEMBER |  |  |  | 95%
| DECEMBER |  |  |  | 95%