## Schedule
Savannah Tank and Equipment |  |  |  |  | PLAN | ACT |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[5 empty] | 2026-02-23 | 2026-02-23 | time axis 2026-03-02 to 2026-12-21
[5 empty] | 22 | 22 |  |  | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
OVERHEAD | 431 | REL |  |  | 55 | 55 |  |  | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 40
| DUE | JOB # | QTE | PRE |  |  | WK | WK% | [43 empty] | REQ | BAL | JOB #
SYMS (Lansing) |  | 046-24 | 705 | 253 |  |  | 253 | 35.89% | 2026-03-16: 150; 2026-03-23: 130; 2026-03-30: 100; 2026-04-06: 72 | 452 | 452 | 046-24 | 0
Kimberly Clark 220-TK-22112 | 2026-01-05 | 010-25 | 174 | 88 |  | 3 | 91 | 52.3% | [43 empty] | 0 | 83 | 010-25 | 83
Kimberly Clark 330-TK-33001 | 2026-01-05 | 012-25 | 314 | 223 |  | 75 | 298 | 94.9% | [43 empty] | 0 | 16 | 012-25 | 16
Kimberly Clark 340-TK-34001 | 2026-01-05 | 013-25 | 513 | 113 | 80 | 34 | 147 | 28.65% | [43 empty] | 0 | 366 | 013-25 | 366 | bar: 2026-03-02
Kimberly Clark 370-TK-37001 | 2026-01-05 | 016-25 | 316 | 192 |  | 3 | 195 | 61.71% | [43 empty] | 0 | 121 | 016-25 | 121
Kimberly Clark 420-BT-42001 | 2025-12-01 | 018-25 | 518 | 433 |  |  | 433 | 83.59% | [43 empty] | 0 | 85 | 018-25 | 85
Kimberly Clark 520-TK-52001 | 2026-01-05 | 019-25 | 287 | 155 |  | 5 | 160 | 55.75% | [43 empty] | 0 | 127 | 019-25 | 127
Nak Kiln | 2025-09-03 | 040-25 | 190 | 258 |  | 1 | 259 | 136.3% | 2026-03-09: 50; 2026-03-16: 40; 2026-03-23: 40 | 130 | -69 | 040-25 | -199
Andritz | 2025-08-15 | 053-25 | 244 | 171 |  |  | 171 | 70.08% | 2026-05-18: 50; 2026-05-25: 23 | 73 | 73 | 053-25 | 0
Nudyne Tank 11 | 2026-03-09 | 066-25 | 520 | 394 | 12 | 43 | 437 | 84.04% | [43 empty] | 0 | 83 | 066-25 | 83 | bar: 2026-03-09
Nudyne Tank 12 | 2026-03-09 | 067-25 | 520 | 298 | 45 | 72 | 370 | 71.15% | [43 empty] | 0 | 150 | 067-25 | 150 | bar: 2026-03-09
Nudyne Tank 13 | 2026-04-06 | 068-25 | 520 | 196 | 50 | 16 | 212 | 40.77% | 2026-03-02: 50; 2026-03-09: 50; 2026-03-16: 50; 2026-03-23: 10 | 160 | 308 | 068-25 | 148
Nudyne Tank 14 | 2026-04-06 | 069-25 | 520 | 153 | 75 |  | 153 | 29.42% | 2026-03-02: 75; 2026-03-09: 50; 2026-03-16: 40; 2026-03-23: 15 | 180 | 367 | 069-25 | 187
Nudyne Tank 15 | 2026-04-20 | 070-25 | 520 | 93 |  | 1 | 94 | 18.08% | 2026-03-09: 50; 2026-03-16: 50; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 42 | 292 | 426 | 070-25 | 134
Nudyne Tank 16 | 2026-04-20 | 071-25 | 520 | 95 |  | 13 | 108 | 20.77% | 2026-03-09: 50; 2026-03-16: 50; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 51 | 301 | 412 | 071-25 | 111
Synthomer | 2026-02-18 | 083-25 | 597 | 177 |  |  | 177 | 29.65% | 2026-03-09: 80; 2026-03-16: 80; 2026-03-23: 80; 2026-03-30: 80 | 320 | 420 | 083-25 | 100
Atlas | 2025-11-27 | 084-25 | 392 | 514 |  |  | 514 | 131.1% | [43 empty] | 0 | -122 | 084-25 | -122
Valmet | 2025-02-23 | 089-25 | 1975 | 1381 | 200 | 252 | 1633 | 82.68% | 2026-03-02: 280 | 280 | 342 | 089-25 | 62
Symrise | 2026-02-16 | 092-25 | 373 | 74 |  |  | 74 | 19.84% | 2026-03-16: 80; 2026-03-23: 84 | 164 | 299 | 092-25 | 135
Symrise | 2026-02-16 | 093-25 | 373 | 81 |  |  | 81 | 21.72% | 2026-03-16: 80; 2026-03-23: 82 | 162 | 292 | 093-25 | 130
Coastal Tech. | 2026-01-16 | 098-25 | 198 |  | 60 |  | 0 | 0% | 2026-03-02: 90; 2026-03-09: 108 | 198 | 198 | 098-25 | 0
Burke | 2026-02-16 | 099-25 | 162 | 7 | 50 |  | 7 | 4.321% | 2026-03-02: 75; 2026-03-09: 80 | 155 | 155 | 099-25 | 0
Harper Love | 2026-04-09 | 101-25 | 781 | 61 |  | 8 | 69 | 8.835% | 2026-03-23: 40; 2026-03-30: 100; 2026-04-06: 120; 2026-04-13: 120; 2026-04-20: 120; 2026-04-27: 100; 2026-05-04: 80 | 680 | 712 | 101-25 | 32
Merrick | 2026-05-07 | 117-25 | 526 |  | 30 |  | 0 | 0% | 2026-03-02: 70; 2026-03-09: 70; 2026-03-16: 100; 2026-03-23: 100; 2026-03-30: 100; 2026-04-06: 86 | 526 | 526 | 117-25 | 0
Vertiv Tanks |  |  | 2240 | 489 | 50 | 492 | 981 | 43.79% | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 9 | [17 empty] | 1259 | 1259 | 0 | 0
Work Order | [6 empty] | 0 | [44 empty] | 0 | 0 | 0 | 0
|  |  |  | TOT | 652 | 1015 | 6573 | PRO | 690 | 638 | 770 | 731 | 530 | 428 | 263 | 170 | 150 | 130 | 50 | 100 | 73 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4880
|  |  |  | PCT | 53.88% | 83.88% |  | PCT | 57.02% | 52.73% | 63.64% | 60.41% | 43.8% | 35.37% | 21.74% | 14.05% | 12.4% | 10.74% | 4.132% | 8.264% | 8.295% | 4.132% | 4.132% | 4.132% | 4.132% | 4.132% | 5.682% | 4.132% | 4.132% | 4.132% | 4.132% | 4.132% | 4.132% | 0.7438% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  |  | BAL | 558 | 195 |  | BAL | 520 | 572 | 440 | 479 | 680 | 782 | 947 | 1040 | 1060 | 1080 | 1160 | 1110 | 807 | 1160 | 1160 | 1160 | 1160 | 1160 | 830 | 1160 | 1160 | 1160 | 1160 | 1160 | 1160 | 1201 | 1210 | 880 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 880 | 1210 | 1210 | 1210 | 880
| DUE | JOB # | QTE | PRE | PLAN | ACT | SUB | SUB% | [43 empty] | REQ | BAL | JOB # | time axis 2026-03-02 to 2026-12-21
Air Gas | 2025-11-16 | 055-25 | 665 |  |  |  | 0 | 0% | 2026-03-23: 50; 2026-03-30: 80; 2026-04-06: 80; 2026-04-13: 70; 2026-04-20: 70; 2026-04-27: 60; 2026-05-04: 60; 2026-05-11: 50; 2026-05-18: 45 | 565 | 665 | 055-25 | 100
Epic | 2026-04-20 | 102-25 | 290 |  |  |  | 0 | 0% | 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 46 | 246 | 290 | 102-25 | 44
Epic | 2026-04-20 | 103-25 | 322 |  |  |  | 0 | 0% | 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 74 | 274 | 322 | 103-25 | 48
Epic | 2026-04-20 | 104-25 | 316 |  |  |  | 0 | 0% | 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 69 | 269 | 316 | 104-25 | 47
Epic | 2026-04-20 | 105-25 | 303 |  |  |  | 0 | 0% | 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 58 | 258 | 303 | 105-25 | 45
Epic | 2026-04-20 | 106-25 | 215 |  |  |  | 0 | 0% | 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 33 | 183 | 215 | 106-25 | 32
Epic | 2026-04-20 | 107-25 | 114 |  |  |  | 0 | 0% | 2026-05-11: 40; 2026-05-18: 40; 2026-05-25: 17 | 97 | 114 | 107-25 | 17
Epic | 2026-04-20 | 108-25 | 86 |  |  |  | 0 | 0% | 2026-05-18: 40; 2026-05-25: 33 | 73 | 86 | 108-25 | 13
Epic | 2026-04-20 | 109-25 | 99 |  |  |  | 0 | 0% | 2026-03-30: 20; 2026-04-06: 40; 2026-04-13: 24 | 84 | 99 | 109-25 | 15
Epic | 2026-04-20 | 110-25 | 184 |  |  |  | 0 | 0% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 6 | 156 | 184 | 110-25 | 28
Epic | 2026-04-20 | 111-25 | 180 |  |  |  | 0 | 0% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 3 | 153 | 180 | 111-25 | 27
Epic | 2026-04-20 | 112-25 | 180 |  |  |  | 0 | 0% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 3 | 153 | 180 | 112-25 | 27
Epic | 2026-04-20 | 113-25 | 189 |  |  |  | 0 | 0% | 2026-04-13: 50; 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 11 | 161 | 189 | 113-25 | 28
Epic | 2026-04-20 | 115-25 | 86 |  |  |  | 0 | 0% | 2026-04-27: 50; 2026-05-04: 23 | 73 | 86 | 115-25 | 13
Polynt | 2026-04-30 | 116-25 | 522 |  |  |  | 0 | 0% | 2026-04-20: 25; 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 75; 2026-05-18: 75; 2026-05-25: 75; 2026-06-01: 44 | 444 | 522 | 116-25 | 78
Merrick | 2026-05-07 | 118-25 | 526 |  |  |  | 0 | 0% | 2026-03-23: 30; 2026-03-30: 70; 2026-04-06: 70; 2026-04-13: 100; 2026-04-20: 70; 2026-04-27: 60; 2026-05-04: 47 | 447 | 526 | 118-25 | 79
Andritz - Dis Tank | 2026-06-01 | 120-25 | 1842 |  |  |  | 0 | 0% | 2026-04-27: 150; 2026-05-04: 180; 2026-05-11: 180; 2026-05-18: 180; 2026-05-25: 56; 2026-06-01: 180; 2026-06-08: 180; 2026-06-15: 180; 2026-06-22: 180; 2026-06-29: 100 | 1566 | 1842 | 120-25 | 276
Kimberly Clark | 2026-05-19 | 121-25 | 528 |  |  |  | 0 | 0% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 75; 2026-04-20: 75; 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 49 | 449 | 528 | 121-25 | 79
Kimberly Clark | 2026-05-19 | 122-25 | 466 |  |  |  | 0 | 0% | 2026-03-30: 30; 2026-04-06: 75; 2026-04-13: 75; 2026-04-20: 75; 2026-04-27: 75; 2026-05-04: 40; 2026-05-11: 26 | 396 | 466 | 122-25 | 70
Kimberly Clark | 2026-05-19 | 123-25 | 413 |  |  |  | 0 | 0% | 2026-04-13: 75; 2026-04-20: 75; 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 51 | 351 | 413 | 123-25 | 62
Synthomer | 2026-06-15 | 356-25 | 461 |  |  |  | 0 | 0% | 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 75; 2026-05-18: 75; 2026-05-25: 25; 2026-06-01: 40; 2026-06-08: 27 | 392 | 461 | 356-25 | 69
Sylvamo | 2026-06-02 | 357-25 | 214 |  |  |  | 0 | 0% | 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 32 | 182 | 214 | 357-25 | 32
Sylvamo | 2026-06-02 | 358-25 | 262 |  |  |  | 0 | 0% | 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 23 | 223 | 262 | 358-25 | 39
SNF | 2026-06-29 | 002-26 | 436 |  |  |  | 0 | 0% | 2026-05-18: 50; 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 21 | 371 | 436 | 002-26 | 65
SNF | 2026-06-29 | 003-26 | 436 |  |  |  | 0 | 0% | 2026-05-18: 50; 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 21 | 371 | 436 | 003-26 | 65
SNF | 2026-06-29 | 004-26 | 436 |  |  |  | 0 | 0% | 2026-05-18: 50; 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 21 | 371 | 436 | 004-26 | 65
US Sugar | 2026-06-08 | 005-26 | 203 |  |  |  | 0 | 0% | 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 23 | 173 | 203 | 005-26 | 30
SNF R1 | 2026-06-01 | 014-26 | 429 |  |  |  | 0 | 0% | 2026-04-13: 50; 2026-04-20: 75; 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 75; 2026-05-18: 15 | 365 | 429 | 014-26 | 64
SNF R2 | 2026-06-01 | 015-26 | 393 |  |  |  | 0 | 0% | 2026-05-25: 50; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 70; 2026-06-22: 64 | 334 | 393 | 015-26 | 59
SNF R3 | 2026-06-01 | 016-26 | 574 |  |  |  | 0 | 0% | 2026-05-11: 50; 2026-05-18: 75; 2026-05-25: 60; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 78 | 488 | 574 | 016-26 | 86
SNF CS1 EPI | 2026-07-01 | 017-26 | 553 |  |  |  | 0 | 0% | 2026-05-18: 70; 2026-05-25: 50; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 75; 2026-06-29: 50 | 470 | 553 | 017-26 | 83
SNF CS2 EPI | 2026-07-01 | 018-26 | 553 |  |  |  | 0 | 0% | 2026-05-18: 70; 2026-05-25: 50; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 75; 2026-06-29: 50 | 470 | 553 | 018-26 | 83
US Sugar | 2026-07-20 | 020-26 | 247 |  |  |  | 0 | 0% | 2026-06-15: 50; 2026-06-22: 50; 2026-06-29: 50; 2026-07-06: 50; 2026-07-13: 10 | 210 | 247 | 020-26 | 37
US Sugar | 2026-07-20 | 021-26 | 268 |  |  |  | 0 | 0% | 2026-06-15: 50; 2026-06-22: 50; 2026-06-29: 50; 2026-07-06: 50; 2026-07-13: 28 | 228 | 268 | 021-26 | 40
Andritz | 2026-06-08 | 022-26 | 260 |  |  |  | 0 | 0% | 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 50; 2026-06-01: 21 | 221 | 260 | 022-26 | 39
Polynt | 2026-07-28 | 024-26 | 89 |  |  |  | 0 | 0% | 2026-07-13: 40; 2026-07-20: 36 | 76 | 89 | 024-26 | 13
IMI |  |  | 603 | [5 empty] | 2026-04-06: PO; 2026-04-13: d1; 2026-04-20: d2; 2026-04-27: d3; 2026-05-04: d4; 2026-05-11: r1; 2026-05-18: r2; 2026-06-08: 50; 2026-06-15: 50; 2026-06-22: 50; 2026-06-29: 50; 2026-07-06: 50; 2026-07-13: 50; 2026-07-20: 50; 2026-07-27: 50; 2026-08-03: 50; 2026-08-10: 50; 2026-08-17: 13 | 513 | 603 | 0 | 90
|  |  |  | TOT | 2514.5388 | 3243.8388 |  | PROJ | 690 | 638 | 770 | 961 | 1080 | 1043 | 1082 | 936 | 1120 | 1166 | 1021 | 1190 | 878 | 860 | 832 | 900 | 735 | 400 | 200 | 178 | 136 | 100 | 100 | 100 | 63 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17188
| 48 HRS | 40 HRS |  | PCT |  |  |  | PCT | 57.02% | 52.73% | 63.64% | 79.42% | 89.26% | 86.2% | 89.42% | 77.36% | 92.56% | 96.36% | 84.38% | 98.35% | 99.77% | 71.07% | 68.76% | 74.38% | 60.74% | 33.06% | 22.73% | 14.71% | 11.24% | 8.264% | 8.264% | 8.264% | 5.207% | 0.7438% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
BACKLOG | 14.0425 | 16.851 |  | BAL |  |  |  | BAL | 520 | 572 | 440 | 249 | 130 | 167 | 128 | 274 | 90 | 44 | 189 | 20 | 2 | 350 | 378 | 310 | 475 | 810 | 680 | 1032 | 1074 | 1110 | 1110 | 1110 | 1147 | 1201 | 1210 | 880 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 1210 | 880 | 1210 | 1210 | 1210 | 880
Pre Fab
Scott Shuman |  | 0.5
Arthur Morrison |  | 0.5
Kevin Free |  | 1
Chris Lapp "CNC Operator #2" |  | 1
Maurice Sellars |  | 1
Cody Moose |  | 1
Cory Shuman |  | 1
Brittany Mock "Cobot Operator" |  | 1
Ashley Boyles |  | 1
Joseph Fahey |  | 1
Danzel Daniels |  | 1
Fabrication
Sammy Chavis |  | 0
Shelbi Foltyn |  | 1
Kevin McMoore |  | 1
Randall Shuman |  | 1
Chris Allen |  | 1
Jason Batchelor |  | 1
Steven Lewis |  | 1
Wes Benoit |  | 1
Carl Wolfe |  | 1
Justin McAmis |  | 1
Launie Lacero |  | 1
Clean/ Test
Julian Adkins - Supervisor |  | 0.5
Jacquelle Leeks |  | 1
Robert Moore |  | 1
Keith Wheeler |  | 1
Jerry Hodge |  | 1
John |  | 1
.
Supervision / Overhead
Scott |  | 0.5
Supervisor Finishing Department |  | 0.5
Sammy |  | 1
Keith Shuman |  | 1
2nd Maintenance Tech |  | 0
Blake - Receiving & Inventory Clerk |  | 1
Arthur |  | 0.5
Albert |  | 1
2nd QC Inspector |  | 0
Total Direct |  | 25.5
Total Indirect |  | 5.5
Total |  | 31
Office
Nick |  | 1
Rutang |  | 1
Sherri |  | 1
Chris |  | 1
April Lewis |  | 1
John |  | 1
Dustin |  | 1
David |  | 1
Office |  | 8
Total Headcount |  | 39
Formulas:
ACT = [PLAN]