## Sheet1
Kick Off Meeting (PO RECEIVED)
Review T&L's, Scope & Schedule
Review with Ops to confirm schedule
Confirm Purchse Order Receipt to Customer
Intake Preparation
Job History
Job Entry Form
Job Design Form
UDR1 Form (ASME Only)
Preliminary Schedule in Excel
Job Folder Cretaion (paper/electronic)
Jobboss Entry
Design
Specifications
Schedule
Testing
Procurement Restrictions
Operations
Add to Production Schhedule
Procurement
Order long Lead Items
Engineering
Final Calculations
Drawings
Projct Management
Send Preliminary Schedule to Customer
Drawing Approval Process
Drawing Review Meeting
Review for Change Orders
Send Drawings and Change Orders (if needed) to Customer
Receive Customer Comments
Edit Drawings
Review for Change Orders
Repeat Process as needed until Drawing Certification
Drawing Certified
Invoice Released
BOM Finalized
ITP Created
Build Plan
Burn Files
Purchase remaining items
Release to Shop
Communicate Customer Updates
Communicate Schedule
Provide Photo Updates
Coordinate and attend internal & external meetings
Preparation for Shipping
Verify Documenation and Checklists
Ship Loose Items List
List for spares
List for Documentation to Go
Verify Date / Day of week with customer for delivery
Obtain shipping Quotes
Communicate Shipping information with Ops and Sales
Shipping Day
Preship
check loose items and spares
take photographs