## ITP - STD
INSPECTION AND TEST PLAN (ITP)
|  | Project name: | Mist Eliminator Housing |  | Equipment: |  | 098-25
|  | ITP Author: | John Corwin |  | ITP No.: |  | ITP-098-25
|  | P.O.: | 91687 |  | TAG / ID / KKS No: |  | N/A
|  | Rev. | 2
S No. | ACTIVITY | SPECIFICATION REFERENCE | VERIFYING REPORT / ACCEPTANCE CRITERIA |  | Actions (inspections, tests) needs signature by inspector |  |  | Responsible | REMARKS
|  |  |  | DATE | SUPPLIER | Coastal | Client/Third party
1 SPECIFICATIONS REVIEW
1.1 | Review of Client Specifications | List specifications here | Doc. Review Check List |  | R
1.2 | Review of any other specifications | List specifications here | Doc. Review Check List |  | R
1.3 | Review Quality Plan | Manufacturing & Quality Plan | Doc. Review Check List |  | R
1.4 | Purchase Order / Contract to Supplier | PO / Contract # XXXX | Doc. Review Check List |  | R
2 DESIGN & DRAWINGS REVIEW
2.1 | Client Drawings | Drawing #'s.. | Dwgs Check Sheet |  | R
2.2 | Supplier Drawings | Drawing #'s.. | Dwgs Check Sheet |  | R
2.3 | Design Review (For Quality) |  |  |  | R
3 SUPPLIER QUALITY ASSURANCE
3.1 | Supplier QC MANUAL & Certificate | QC Manual | Review Checklist |  | R
3.2 | WPS / PQR Review | ASME Sec IX | ASME Sec IX |  | R
3.3 | Sodium Hydroxide Etch Testing | ASTM A923-25 Method A | ASTM A923-25 Method A |  | R
3.4 | Ferric Chloride Corrosion Testing | ASTM A923-25 Method C | ASTM A923-25 Method C |  | R
3.5 | NDE Procedures Review | ASME Sec V | ASME Sec V |  | N/A
3.6 | NDE Personal Qualifications Review | ASME, Quality Plan |  |  | N/A
3.7 | Review Welder Qualification Records | ASME, Quality Plan |  |  | R
3.8 | Acceptance of Shop QA | Quality Plan |  |  | R
4 KICK OFF MEETINGS (If any)
4.1 | Internal Meeting |  |  |  | R
4.2 | Client / Coastal / Supplier Meetings |  |  |  | R
4.3 | Release for Fabrication |  |  |  | H
5 MATERIALS
5.1 | Material Verifications | ASME Sec. II |  |  | R
5.2 | Welding Consumables | ASME Sec. II |  |  | R
5.3 | Material Storage | Quality Plan |  |  | R
6 PRODUCT FABRICATION
6.1 | Cutting | Fabrication Plan |  |  | SP
6.2 | Forming / Rolling | Fabrication Plan |  |  | SP
6.3 | Fit up | Fabrication Plan |  |  | R
6.4 | Welding | Fabrication Plan |  |  | R
6.5 | Visual inspection | ASME Sec VIII | ASME Sec VIII |  | H
6.6 | NDE | ASME Sec VIII | ASME Sec VIII |  | N/A
6.7 | Dimensional inspection | Drawings #'s | Drawings #'s |  | H
6.8 | Water Quality Test | Customer Specs. | Customer Specs. |  | H |  |  |  | Approve before hydro testing
6.9 | Pressure Testing | Quality Plan | Quality Plan |  | H
6.10 | Blasting & Painting | Supplier Standards |  |  | R
6.11 | Ext. Cleaned Inspection | Supplier Standards |  |  | H
6.12 | Int. Cleaned Inspection | Supplier Standards |  |  | H
7 REVIEW OF NDE
7.1 | Evaluation of Dye penetrant test | ASME, Quality Plan | Reports |  | N/A
7.2 | Evaluation of Radiography | ASME, Quality Plan | Reports |  | N/A
8 FINAL PACKAGING
8.1 | Preparation for transportation | Project instruction |  |  | H
8.2 | Pictures | Project instruction | Purchase order, project specific instructions if applicable |  | H
8.3 | Final Shipping Inspection | Supplier Standards |  |  | H
9 FINAL DOCUMENTATION
9.1 | ALL NCR's are closed | XXXXX | XXXXXX |  | H
INSPECTION POINTS
H = HOLD POINT |  | CUSTOMER shall be notified in writing when the holding point has been reached. The Owner or his representative shall be informed by CUSTOMER. Execution of the respective manufacturing, testing and/or inspection step is only permissible in the presence of the nominated party or if the party has agreed in writing not to participate.
W = WITNESS POINT |  | A written invitation to CUSTOMER is required: the respective manufacturing, testing and/or inspection step may be conducted on the scheduled date even in the absence of or non-participation of the respective party, provided that the time limit of three days for the invitation has been observed.
R = REVIEW |  | The supplier/manufacturer shall furnish the relevant certification to the specified party on the next agreed date.
SP = SPOT-CHECK / SURVEILLANCE |  | Random attendance and spot checks
N/A |  | Not Applicable

## List_values (hidden)
Equipment type | Equipment | Revision | Activity | Specification Reference | Acceptance Criteria | Verifying Document | Test inspected by | explination(Test inspected by) | Responsible Party
PED | LimeGreen Filter | 1 | Main dimension drawing | Customer drawing | ISO 9001 | Drawing | H | Hold point | Project and Engineering
MD | Moduscreen | 2 | Manufacturing drawings, calculations | EN 13445 _ PED 97/23/EC | EN 13445 | Design approval | W | Witness point | Engineering
ATM Tank | Support Roller | 3 | Design Approval | EN13445 and PMA | EN 10024 -3.1 or 3.2 | EN 10204 2.2 or 3.1 | R | Document for Client review | Third Party
MD/PED |  | 4 | Material Purchasing and Traceability | EN13445-4 | Material Traceabilty, 13445-4 | BOM, manufacturer´s system | N.A | Not Applicaple | Manufacturer
ATM Tank/PED |  | 5 | Welding consumable | Drawing, EN 13445-4 , Manufacturer instruction | EN13445-4 | Welders qualification certificates | W/R |  | Engineering, Manufacturer
ATM Tank/MD |  | 6 | Material identification marks transfer | EN287 or EN ISO 9606 , EN1418 or EN ISO 14732 EN13445-4 | EN287, EN1418, EN13445 | PED approved WPS / WPQR, Welding List |  |  | Project
|  | 7 | Bending and Forming | EN15614-1 / EN13445, EN 15609 | EN15614-1 / EN13445-4 and 6, EN 15609 | Manufacturer NDT MAP , reports
|  | 8 | Welder Qualification | EN13445-5, Manufacturer system | EN13445-5 | NDT procedure in accordance to ISO/EN 17635
|  | 9 | WPQR/WPS | ISO/EN17635 | Minimum required level 2 of ISO 9712 or above | NDT Qualification cert in accordance to ISO/EN 9712
|  | 10 | Welding and NDT MAP | ISO/EN 9712 | ISO EN 5817 Class C | Report
|  | 11 | NDT Procedure | ISO EN 17637 | ISO EN 11666 | Hydrostatic test procedure
|  | 12 | NDT Operator Qualification | ISO EN 17640 | ISO EN 10675-1 | Hydrostatic test record
|  | 13 | Visual | ISO EN17636-1 | ISO EN 23278 | Verified QC-Drawing
|  |  | Ultrasonic | IS0 EN 17638 | ISO EN 23277 | Report, pictures
|  |  | Radigraphy | ISO EN 3432-1 | EN 13445-5 | Drawing, pictures
|  |  | Magnetiflux | EN 13445-5, Manufacturer procedure | QC- Drawing based on EN13445, EN22768, ISO EN13920 | QC - Drawing
|  |  | Penetration | EN 13445-5, Strenght calculations | EN ISO 8502 | QC - Drawing, FAT report
|  |  | Hydrostatic test procedure | QC - Drawing | Report based on ISO 19840, EN ISO 12944, EN ISO 1461 | Dispatch note
|  |  | Hydrostatic test | Surface treatment specification | Insulation drawing | Manufacturing Data Records (MDR)
|  |  | Dimensional Inspection | Surface treatment specificication; QA-1508, QA-1534 | Preservation instruction | Packing report
|  |  | Surface pre treatment | Insulation specification, Insulation drawing | QC-Drawing | Manufacturing Data Records (MDR)
|  |  | Surface treatment | Preservation instruction | Packing instruction | EC -Conformity
|  |  | Insulation (if applicable) | FAT procedure | PED 97/23/EC | EC -Conformity, Declaration of conformity
|  |  | Preservation for storing and transportation | Packing instruction
|  |  | Final Acceptance Test (FAT) | PED 97/23/EC
Release dispatch note
Review of Manufacture Data Records
Preparation for transportation
EC -Conformity
Declaration of conformity
Manufacturer Data Records Book

## Footer (hidden)
W | = | Witness Point; The point of which the Andritz and/or Inspection Authorities must be notified. The Manufacturer may proceed if the Andritz and/or Inspection Authorities will not be present. | <-JATKETAAN, JOS EI ASIANOMAINEN OLE PAIKALLA
H | = | Hold Point; The point of which the Andritz and/or Inspection Authorities must be notified.The Manufacturer shall not proceed unless specifically so instructed by the party indicating the hold point. | <-JATKETAAN VASTA, KUN ASIANOMAINEN ON HYVÄKSYNYT
R | = | Document Review; Verification by the party concerned if data given in inspection document(s) meets the requirements. | <-TARKASTUS, JOS ASIANOMAISTA EPÄILYTTÄÄ, TÄYTTYYKÖ VAATIMUKSET
F | = | Final documentation; Document delivered as part of Final Documentation. | <-DOKUMENTTI TOIMITETAAN LOPPUDOKUMENTAATIOSSA
N/A | = | Not Applicaple | <-EI SOVELLETA
W = Witness Point; The point of which the Andritz and/or Inspection Authorities must be notified. The Manufacturer may proceed if the Andritz and/or Inspection Authorities will not be present. H = Hold Point; The point of which the Andritz and/or Inspection Authorities must be notified.The Manufacturer shall not proceed unless specifically so instructed by the party indicating the hold point. R = Document Review; Verification by the party concerned if data given in inspection document(s) meets the requirements. F = Final documentation; Document delivered as part of Final Documentation. N/A = Not Applicable.