## Build Plan w Hours
Job #: | 004-24
| Description: | SOLUTIZER |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 7 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 15 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes M2 | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel M1, M2, M3 | 5 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck M1, M2, M3 | 5 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam M2 & M3 | 5 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 1 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door BUILD AND WELD CLEAN OUT (M1) | 10 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 12 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 24 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 5 |  |  |  | 0 | 0
PRE FAB |  | .215 | Burn and clean baffles (CHECK BEFORE BURNING) | 4 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports | 3 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .245 | Cut parts for mixer bridge | 4 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes DRILL AGITATOR BEAMS | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (2) DOUBLE SHELLS | 15 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS | 10 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .360 | Bevel top head CLEAN UP HOLES AND PREP FOR WELDING | 3 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 10 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 14 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners | 4 |  |  |  | 0 | 0
PRE FAB |  | .380 | Build mixer bridge INSTALL AGITATOR SUPPORT BEAMS ***PAINT FIRST*** | 6 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .470 | Install and weld out repads - bottom head FIT & WELD REINFORCING PLATE ***WATCH TEMP*** | 10 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE | 13 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 5 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 5 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only AND WELD | 25 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 6 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 13 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 10 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 4 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 15 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 20 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 28 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 6 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 35 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area BLAST & PAINT AGITATOR SUPPORT BEAMS | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment SEE DRAWINGS FOR INSTRUCTIONS | 40 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 15 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 004-24
| Description: | SOLUTIZER |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 7 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 15 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes M2 | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel M1, M2, M3 | 5 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck M1, M2, M3 | 5 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam M2 & M3 | 5 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 1 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door BUILD AND WELD CLEAN OUT (M1) | 10 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 12 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 24 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 5 |  |  |  | 0 | 0
PRE FAB |  | .215 | Burn and clean baffles (CHECK BEFORE BURNING) | 4 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports | 3 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .245 | Cut parts for mixer bridge | 4 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes DRILL AGITATOR BEAMS | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (2) DOUBLE SHELLS | 15 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS | 10 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .360 | Bevel top head CLEAN UP HOLES AND PREP FOR WELDING | 3 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 10 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 14 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners | 4 |  |  |  | 0 | 0
PRE FAB |  | .380 | Build mixer bridge INSTALL AGITATOR SUPPORT BEAMS ***PAINT FIRST*** | 6 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .470 | Install and weld out repads - bottom head FIT & WELD REINFORCING PLATE ***WATCH TEMP*** | 10 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE | 13 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 5 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 5 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only AND WELD | 25 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 6 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 13 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 10 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 4 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 15 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 20 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 28 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 6 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 35 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area BLAST & PAINT AGITATOR SUPPORT BEAMS | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment SEE DRAWINGS FOR INSTRUCTIONS | 40 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 15 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | SOLUTIZER | Customer PO: | 4503100351 | Quote: | 8670.2 | SOLUTIZER | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2024-02-16 | Make Qty: | 1 | / | ea | Est Hours: | 503
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 48693 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 48694 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 48695 | 0 | Cut Nozzle Pipe and Clean | 0 | 7 | FixedHrs | 7 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 48696 | 0 | Build Nozzles-Weld | 0 | 15 | FixedHrs | 15 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 48697 | 0 | Build Repads for Nozzles | 0 | 2 | FixedHrs | 2 | .107 | 0 | Build Repads for Nozzles, drill and tap holes M2 | _________________ | _________________ | _________________
PRE FAB | 48698 | 0 | Make Manway Parts | 0 | 1 | FixedHrs | 1 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 48699 | 0 | Brn MW Neck, Clean, Bevel | 0 | 5 | FixedHrs | 5 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel M1, M2, M3 | _________________ | _________________ | _________________
PRE FAB | 48700 | 0 | Roll Manway Neck | 0 | 5 | FixedHrs | 5 | .125 | 0 | Roll manway neck M1, M2, M3 | _________________ | _________________ | _________________
PRE FAB | 48701 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 5 | FixedHrs | 5 | .130 | 0 | Set up and weld manway flange and neck seam M2 & M3 | _________________ | _________________ | _________________
PRE FAB | 48702 | 0 | Bld Davit Arm Aby Cover | 0 | 1 | FixedHrs | 1 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 48703 | 0 | Build Hatch/Door | 0 | 10 | FixedHrs | 10 | .140 | 0 | Build hatch/door BUILD AND WELD CLEAN OUT (M1) | _________________ | _________________ | _________________
PRE FAB | 48704 | 0 | Cut Parts on Burn Table | 0 | 12 | FixedHrs | 12 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 48705 | 0 | Clean & Prep Parts | 0 | 24 | FixedHrs | 24 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 48706 | 0 | Build Supports | 0 | 4 | FixedHrs | 4 | .165 | 0 | Build supports: legs, lugs, saddles TACK ONLY | _________________ | _________________ | _________________
PRE FAB | 48707 | 0 | Roll Repads-Drill & Tap | 0 | 4 | FixedHrs | 4 | .170 | 0 | Roll repads: drill and tap | _________________ | _________________ | _________________
PRE FAB | 48708 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 5 | FixedHrs | 5 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 48709 | 0 | B&C Baffles | 0 | 4 | FixedHrs | 4 | .215 | 0 | Burn and clean baffles (CHECK BEFORE BURNING) | _________________ | _________________ | _________________
PRE FAB | 48710 | 0 | Cut, Make Baffle Supports | 0 | 3 | FixedHrs | 3 | .225 | 0 | Cut and make baffle supports | _________________ | _________________ | _________________
PRE FAB | 48711 | 0 | Build Baffles-Weld | 0 | 8 | FixedHrs | 8 | .230 | 0 | Build baffles and weld | _________________ | _________________ | _________________
PRE FAB | 48712 | 0 | Cut Parts-Mixer Bridge | 0 | 4 | FixedHrs | 4 | .245 | 0 | Cut parts for mixer bridge | _________________ | _________________ | _________________
PRE FAB | 48713 | 0 | Drill/Punch holes | 0 | 3 | FixedHrs | 3 | .255 | 0 | Drill/punch holes DRILL AGITATOR BEAMS | _________________ | _________________ | _________________
INSPECTION | 48714 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 48715 | 0 | BI, SQ, T&C Shells | 0 | 15 | FixedHrs | 15 | .305 | 0 | Shells: bring in plate, square, trim and clean PREP (2) DOUBLE SHELLS | _________________ | _________________ | _________________
PRE FAB | 48716 | 0 | Roll Shell, Tack-Weld I/S | 0 | 10 | FixedHrs | 10 | .315 | 0 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS | _________________ | _________________ | _________________
PRE FAB | 48717 | 0 | Build Top Head/Cone | 0 | 10 | FixedHrs | 10 | .350 | 0 | Build top head/cone | _________________ | _________________ | _________________
INSPECTION | 48718 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 48719 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 48720 | 0 | Bevel Top Head | 0 | 3 | FixedHrs | 3 | .360 | 0 | Bevel top head CLEAN UP HOLES AND PREP FOR WELDING | _________________ | _________________ | _________________
PRE FAB | 48721 | 0 | Set Nozzles & Lugs - Top | 0 | 10 | FixedHrs | 10 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 48722 | 0 | Weld Nozzles - Top Head | 0 | 14 | FixedHrs | 14 | .366 | 0 | Weld out top head nozzles, etc. | _________________ | _________________ | _________________
PRE FAB | 48723 | 0 | Install Top Stiffeners | 0 | 4 | FixedHrs | 4 | .375 | 0 | Install top stiffeners | _________________ | _________________ | _________________
PRE FAB | 48724 | 0 | Build Mixer Bridge | 0 | 6 | FixedHrs | 6 | .380 | 0 | Build mixer bridge INSTALL AGITATOR SUPPORT BEAMS ***PAINT FIRST*** | _________________ | _________________ | _________________
PRE FAB | 48725 | 0 | Build Bottom Head/Cone | 0 | 10 | FixedHrs | 10 | .450 | 0 | Build bottom head/cone | _________________ | _________________ | _________________
INSPECTION | 48726 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 48727 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 48728 | 0 | I&W Bottom Repads | 0 | 10 | FixedHrs | 10 | .470 | 0 | Install and weld out repads - bottom head FIT & WELD REINFORCING PLATE ***WATCH TEMP*** | _________________ | _________________ | _________________
FIT | 48729 | 0 | Fit Bottom Head to Shell | 0 | 13 | FixedHrs | 13 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE | _________________ | _________________ | _________________
FIT | 48730 | 0 | Tack Shell Courses | 0 | 5 | FixedHrs | 5 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 48731 | 0 | Weld Inside Round Seams | 0 | 5 | FixedHrs | 5 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 48732 | 0 | Install Rim Angle | 0 | 25 | FixedHrs | 25 | .615 | 0 | Install rim angle - tack only AND WELD | _________________ | _________________ | _________________
FIT | 48733 | 0 | L/O Shell, B&C Holes | 0 | 6 | FixedHrs | 6 | .620 | 0 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | _________________ | _________________ | _________________
FIT | 48734 | 0 | Install Baffles-Weld | 0 | 13 | FixedHrs | 13 | .625 | 0 | Install baffles and weld | _________________ | _________________ | _________________
INSPECTION | 48735 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 48736 | 0 | Fit Top to Shell | 0 | 10 | FixedHrs | 10 | .640 | 0 | Fit top head to shell - tack AND WELD TO RIM ANGLE | _________________ | _________________ | _________________
FIT | 48737 | 0 | Weld all Outside Seams | 0 | 20 | FixedHrs | 20 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 48738 | 0 | Move Tank to Detail Rolls | 0 | 2 | FixedHrs | 2 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 48739 | 0 | Install Lift Lugs on Shl | 0 | 4 | FixedHrs | 4 | .717 | 0 | Install lift lugs on shell INCL REPADS | _________________ | _________________ | _________________
FIT | 48740 | 0 | Install Support Parts | 0 | 15 | FixedHrs | 15 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt | _________________ | _________________ | _________________
FIT | 48741 | 0 | Set Nozzles in Shell | 0 | 20 | FixedHrs | 20 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 48742 | 0 | Weld Shell Nozz & M/Ws | 0 | 28 | FixedHrs | 28 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
FIT | 48743 | 0 | Add Repads-Weld | 0 | 6 | FixedHrs | 6 | .730 | 0 | Add repads and weld | _________________ | _________________ | _________________
FINISHING | 48744 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 48745 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 48746 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 48747 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 48748 | 0 | Test Tank | 0 | 16 | FixedHrs | 16 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 48749 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 48750 | 0 | Clean Tank Complete | 0 | 35 | FixedHrs | 35 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 48751 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
MOVE TANK | 48752 | 0 | Move to Paint Area | 0 | 2 | FixedHrs | 2 | .802 | 0 | Move to paint area BLAST & PAINT AGITATOR SUPPORT BEAMS | _________________ | _________________ | _________________
INSPECTION | 48753 | 0 | QC Inspection - Sandblast | 0 | 0 | FixedHrs | 0 | .QC9 | 0 | QC Inspection - Sandblast | _________________ | _________________ | _________________
INSPECTION | 48754 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 48755 | 0 | Prepare Tank for Shipment | 0 | 40 | FixedHrs | 40 | .940 | 0 | Prepare tank for shipment SEE DRAWINGS FOR INSTRUCTIONS | _________________ | _________________ | _________________
FINISHING | 48756 | 0 | Check BOM, Pack Parts | 0 | 3 | FixedHrs | 3 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 48757 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 48758 | 0 | Load on Truck | 0 | 15 | FixedHrs | 15 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | SOLUTIZER |  |  |  | Rev:

## Tasks with Hours
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 7
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 15
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes M2
Hours | 2
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 1
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel M1, M2, M3
Hours | 5
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck M1, M2, M3
Hours | 5
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam M2 & M3
Hours | 5
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 1
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door BUILD AND WELD CLEAN OUT (M1)
Hours | 10
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 12
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 24
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
Hours | 4
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap
Hours | 4
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 5
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .215 | Burn and clean baffles (CHECK BEFORE BURNING)
Hours | 4
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports
Hours | 3
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld
Hours | 8
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .245 | Cut parts for mixer bridge
Hours | 4
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes DRILL AGITATOR BEAMS
Hours | 3
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (2) DOUBLE SHELLS
Hours | 15
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS
Hours | 10
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
Hours | 10
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .360 | Bevel top head CLEAN UP HOLES AND PREP FOR WELDING
Hours | 3
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 10
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
Hours | 14
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners
Hours | 4
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .380 | Build mixer bridge INSTALL AGITATOR SUPPORT BEAMS ***PAINT FIRST***
Hours | 6
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
Hours | 10
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
Hours | 1
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .470 | Install and weld out repads - bottom head FIT & WELD REINFORCING PLATE ***WATCH TEMP***
Hours | 10
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE
Hours | 13
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 5
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 5
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only AND WELD
Hours | 25
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
Hours | 6
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
Hours | 13
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
Hours | 10
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 20
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 2
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
Hours | 4
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
Hours | 15
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 20
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 28
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
Hours | 6
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 16
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 35
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area BLAST & PAINT AGITATOR SUPPORT BEAMS
Hours | 2
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment SEE DRAWINGS FOR INSTRUCTIONS
Hours | 40
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 3
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 15
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes M2
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel M1, M2, M3
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck M1, M2, M3
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam M2 & M3
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door BUILD AND WELD CLEAN OUT (M1)
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .215 | Burn and clean baffles (CHECK BEFORE BURNING)
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .245 | Cut parts for mixer bridge
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes DRILL AGITATOR BEAMS
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (2) DOUBLE SHELLS
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .360 | Bevel top head CLEAN UP HOLES AND PREP FOR WELDING
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .380 | Build mixer bridge INSTALL AGITATOR SUPPORT BEAMS ***PAINT FIRST***
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .470 | Install and weld out repads - bottom head FIT & WELD REINFORCING PLATE ***WATCH TEMP***
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only AND WELD
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area BLAST & PAINT AGITATOR SUPPORT BEAMS
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment SEE DRAWINGS FOR INSTRUCTIONS
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_