## Build Plan w Hours
Job #: | 018-24
| Description: | RBD OIL TANK #2 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 16 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 20 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 40 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts (8) LEG BRACES & (3) TUBING SUPPORTS | 6 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 6 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 2 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 18 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail INCL CROSS-OVER HANDRAILS | 9 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe | 3 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 1 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 21 |  |  |  | 0 | 0
PRE FAB |  | .285 | Cut/Build parts for platform | 3 |  |  |  | 0 | 0
PRE FAB |  | .290 | Burn grating for platforms, clean and band | 5 |  |  |  | 0 | 0
PRE FAB |  | .292 | Build platform - weld out | 9 |  |  |  | 0 | 0
PRE FAB |  | .295 | Mount handrail on platform | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (1) SINGLE SHELL & (5) DOUBLE SHELLS | 33 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (1) SINGLE SHELL & (5) DOUBLE SHELLS | 18 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 9 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 5 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 8 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 20 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 20 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 6 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE; LAYOUT LADDER POSITION | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 8 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 42 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 4 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 4 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT (8) LEGS & WELD COMPLETE (INCL BRACING) | 88 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 5 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 12 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld INSTALL (3) TUBING SUPPORTS | 3 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 10 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 10 |  |  |  | 0 | 0
FIT |  | .760 | Fit platform - install and weld clips, bracing, etc. | 10 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 3 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 60 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 7 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC21 | QC Inspection - Returned Components from Subcontractor | 0 |  |  |  | 1 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 018-24
| Description: | RBD OIL TANK #2 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 16 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 20 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 40 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts (8) LEG BRACES & (3) TUBING SUPPORTS | 6 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 6 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 2 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 18 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail INCL CROSS-OVER HANDRAILS | 9 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe | 3 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 1 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 21 |  |  |  | 0 | 0
PRE FAB |  | .285 | Cut/Build parts for platform | 3 |  |  |  | 0 | 0
PRE FAB |  | .290 | Burn grating for platforms, clean and band | 5 |  |  |  | 0 | 0
PRE FAB |  | .292 | Build platform - weld out | 9 |  |  |  | 0 | 0
PRE FAB |  | .295 | Mount handrail on platform | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (1) SINGLE SHELL & (5) DOUBLE SHELLS | 33 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (1) SINGLE SHELL & (5) DOUBLE SHELLS | 18 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 9 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 5 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 8 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 20 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 20 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 6 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE; LAYOUT LADDER POSITION | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 8 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 42 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 4 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 4 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT (8) LEGS & WELD COMPLETE (INCL BRACING) | 88 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 5 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 12 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld INSTALL (3) TUBING SUPPORTS | 3 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 10 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 10 |  |  |  | 0 | 0
FIT |  | .760 | Fit platform - install and weld clips, bracing, etc. | 10 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 3 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 60 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 7 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC21 | QC Inspection - Returned Components from Subcontractor | 0 |  |  |  | 1 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | RBD OIL TANK #2 | Customer PO: | 3002519BOR | Quote: | 8701.4 | RBD OIL TANK #2 | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2024-03-15 | Make Qty: | 1 | / | ea | Est Hours: | 628
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 48957 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 48958 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 48959 | 0 | Cut Nozzle Pipe and Clean | 0 | 4 | FixedHrs | 4 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 48960 | 0 | Build Nozzles-Weld | 0 | 8 | FixedHrs | 8 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 48961 | 0 | Make Manway Parts | 0 | 2 | FixedHrs | 2 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 48962 | 0 | Brn MW Neck, Clean, Bevel | 0 | 2 | FixedHrs | 2 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 48963 | 0 | Roll Manway Neck | 0 | 2 | FixedHrs | 2 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 48964 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 4 | FixedHrs | 4 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 48965 | 0 | Bld Davit Arm Aby Cover | 0 | 4 | FixedHrs | 4 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 48966 | 0 | Cut Parts on Burn Table | 0 | 16 | FixedHrs | 16 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 48967 | 0 | Clean & Prep Parts | 0 | 20 | FixedHrs | 20 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 48968 | 0 | Build Supports | 0 | 40 | FixedHrs | 40 | .165 | 0 | Build supports: legs, lugs, saddles | _________________ | _________________ | _________________
PRE FAB | 48969 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 48970 | 0 | Roll Rim Angle | 0 | 3 | FixedHrs | 3 | .205 | 0 | Roll rim angle | _________________ | _________________ | _________________
PRE FAB | 48971 | 0 | Fab Miscellaneous Parts | 0 | 6 | FixedHrs | 6 | .252 | 0 | Fabricate miscellaneous parts (8) LEG BRACES & (3) TUBING SUPPORTS | _________________ | _________________ | _________________
PRE FAB | 48972 | 0 | Cut, Build Ladder Parts | 0 | 6 | FixedHrs | 6 | .262 | 0 | Cut/make parts for ladder: rungs, rails, etc. | _________________ | _________________ | _________________
PRE FAB | 48973 | 0 | Form and Roll Ladder Hoop | 0 | 2 | FixedHrs | 2 | .265 | 0 | Form and roll ladder hoops | _________________ | _________________ | _________________
PRE FAB | 48974 | 0 | Build Ladder-Weld | 0 | 18 | FixedHrs | 18 | .270 | 0 | Build ladder - weld out | _________________ | _________________ | _________________
PRE FAB | 48975 | 0 | Cut, Build Handrail Parts | 0 | 9 | FixedHrs | 9 | .272 | 0 | Cut/Build parts for handrail INCL CROSS-OVER HANDRAILS | _________________ | _________________ | _________________
PRE FAB | 48976 | 0 | Roll Handrail Pipe | 0 | 3 | FixedHrs | 3 | .275 | 0 | Roll handrail pipe | _________________ | _________________ | _________________
PRE FAB | 48977 | 0 | Roll Handrail Toe Plate | 0 | 1 | FixedHrs | 1 | .280 | 0 | Roll handrail toe plate | _________________ | _________________ | _________________
PRE FAB | 48978 | 0 | Build Handrail-Weld | 0 | 21 | FixedHrs | 21 | .282 | 0 | Build handrail - weld out | _________________ | _________________ | _________________
PRE FAB | 48979 | 0 | Cut, Build Platform Parts | 0 | 3 | FixedHrs | 3 | .285 | 0 | Cut/Build parts for platform | _________________ | _________________ | _________________
PRE FAB | 48980 | 0 | Burn Platform Grating | 0 | 5 | FixedHrs | 5 | .290 | 0 | Burn grating for platforms, clean and band | _________________ | _________________ | _________________
PRE FAB | 48981 | 0 | Build Platform-Weld | 0 | 9 | FixedHrs | 9 | .292 | 0 | Build platform - weld out | _________________ | _________________ | _________________
PRE FAB | 48982 | 0 | Mount Platform Handrail | 0 | 2 | FixedHrs | 2 | .295 | 0 | Mount handrail on platform | _________________ | _________________ | _________________
INSPECTION | 48983 | 0 | QC Inspection - Pre Sub C | 0 | 0 | FixedHrs | 0 | .QC2 | 0 | QC Inspection - Components prior to shipping to Subcontractor | _________________ | _________________ | _________________
PRE FAB | 48984 | 0 | Wrap Top & Bottom Heads | 0 | 1 | FixedHrs | 1 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________
INSPECTION | 48985 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 48986 | 0 | BI, SQ, T&C Shells | 0 | 33 | FixedHrs | 33 | .305 | 0 | Shells: bring in plate, square, trim and clean PREP (1) SINGLE SHELL & (5) DOUBLE SHELLS | _________________ | _________________ | _________________
PRE FAB | 48987 | 0 | Roll Shell, Tack-Weld I/S | 0 | 18 | FixedHrs | 18 | .315 | 0 | Roll shells, tack and weld inside seams ROLL (1) SINGLE SHELL & (5) DOUBLE SHELLS | _________________ | _________________ | _________________
PRE FAB | 48988 | 0 | Build Top Head/Cone | 0 | 9 | FixedHrs | 9 | .350 | 0 | Build top head/cone | _________________ | _________________ | _________________
INSPECTION | 48989 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 48990 | 0 | L/O Top, B&C Holes | 0 | 2 | FixedHrs | 2 | .355 | 0 | Lay out top head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 48991 | 0 | Set Nozzles & Lugs - Top | 0 | 4 | FixedHrs | 4 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 48992 | 0 | Weld Nozzles - Top Head | 0 | 5 | FixedHrs | 5 | .366 | 0 | Weld out top head nozzles, etc. | _________________ | _________________ | _________________
INSPECTION | 48993 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 48994 | 0 | L/O Bottom, B&C Holes | 0 | 2 | FixedHrs | 2 | .455 | 0 | Lay out bottom head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 48995 | 0 | Set Nozzles - Bottom Head | 0 | 4 | FixedHrs | 4 | .465 | 0 | Set nozzles in bottom head - tack | _________________ | _________________ | _________________
PRE FAB | 48996 | 0 | Weld Nozzles - Bot. Head | 0 | 5 | FixedHrs | 5 | .466 | 0 | Weld nozzles in bottom head; weld complete | _________________ | _________________ | _________________
FIT | 48997 | 0 | Fit Bottom Head to Shell | 0 | 8 | FixedHrs | 8 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________
FIT | 48998 | 0 | Tack Shell Courses | 0 | 20 | FixedHrs | 20 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 48999 | 0 | Weld Inside Round Seams | 0 | 20 | FixedHrs | 20 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 49000 | 0 | Install Rim Angle | 0 | 4 | FixedHrs | 4 | .615 | 0 | Install rim angle - tack only | _________________ | _________________ | _________________
FIT | 49001 | 0 | Weld Rim Angle | 0 | 6 | FixedHrs | 6 | .616 | 0 | Weld rim angle complete | _________________ | _________________ | _________________
FIT | 49002 | 0 | L/O Shell, B&C Holes | 0 | 2 | FixedHrs | 2 | .620 | 0 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE; LAYOUT LADDER POSITION | _________________ | _________________ | _________________
INSPECTION | 49003 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 49004 | 0 | Fit Top to Shell | 0 | 8 | FixedHrs | 8 | .640 | 0 | Fit top head to shell - tack AND WELD TO RIM ANGLE | _________________ | _________________ | _________________
FIT | 49005 | 0 | Weld all Outside Seams | 0 | 42 | FixedHrs | 42 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 49006 | 0 | Move Tank to Detail Rolls | 0 | 4 | FixedHrs | 4 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 49007 | 0 | Install Lift Lugs on Shl | 0 | 4 | FixedHrs | 4 | .717 | 0 | Install lift lugs on shell INCL REPADS | _________________ | _________________ | _________________
FIT | 49008 | 0 | Install Support Parts | 0 | 88 | FixedHrs | 88 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt FIT (8) LEGS & WELD COMPLETE (INCL BRACING) | _________________ | _________________ | _________________
FIT | 49009 | 0 | Set Nozzles in Shell | 0 | 5 | FixedHrs | 5 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 49010 | 0 | Weld Shell Nozz & M/Ws | 0 | 12 | FixedHrs | 12 | .726 | 0 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | _________________ | _________________ | _________________
FIT | 49011 | 0 | Add Repads-Weld | 0 | 3 | FixedHrs | 3 | .730 | 0 | Add repads and weld INSTALL (3) TUBING SUPPORTS | _________________ | _________________ | _________________
FIT | 49012 | 0 | Fit Handrail, I&W Clips | 0 | 10 | FixedHrs | 10 | .750 | 0 | Fit handrail - install and weld clips | _________________ | _________________ | _________________
FIT | 49013 | 0 | Fit Ladder, I&W Clips | 0 | 10 | FixedHrs | 10 | .755 | 0 | Fit ladder - install and weld clips | _________________ | _________________ | _________________
FIT | 49014 | 0 | Fit Platform, I&W Clips | 0 | 10 | FixedHrs | 10 | .760 | 0 | Fit platform - install and weld clips, bracing, etc. | _________________ | _________________ | _________________
FINISHING | 49015 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 49016 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 49017 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 49018 | 0 | Move to Shop Test Area | 0 | 3 | FixedHrs | 3 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 49019 | 0 | Test Tank | 0 | 12 | FixedHrs | 12 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 49020 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 49021 | 0 | Clean Tank Complete | 0 | 60 | FixedHrs | 60 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 49022 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 49023 | 0 | Prepare Tank for Shipment | 0 | 3 | FixedHrs | 3 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 49024 | 0 | Check BOM, Pack Parts | 0 | 4 | FixedHrs | 4 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 49025 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 49026 | 0 | Load on Truck | 0 | 7 | FixedHrs | 7 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
SHIPPING | 49027 | 0 | Take Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .970 | 0 | Take parts to galvanizers | _________________ | _________________ | _________________
SHIPPING | 49028 | 0 | P/U Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .972 | 0 | Pick up parts from galvanizers | _________________ | _________________ | _________________
INSPECTION | 49029 | 0 | QC Inspection - Ret Com | 0 | 0 | FixedHrs | 0 | .QC21 | 0 | QC Inspection - Returned Components from Subcontractor | _________________ | _________________ | _________________
| Part: | RBD OIL TANK #2 |  |  |  | Rev:

## Tasks with Hours
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 8
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 16
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 20
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
Hours | 40
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts (8) LEG BRACES & (3) TUBING SUPPORTS
Hours | 6
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
Hours | 6
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
Hours | 18
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail INCL CROSS-OVER HANDRAILS
Hours | 9
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
Hours | 1
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
Hours | 21
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .285 | Cut/Build parts for platform
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .290 | Burn grating for platforms, clean and band
Hours | 5
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .292 | Build platform - weld out
Hours | 9
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .295 | Mount handrail on platform
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 1
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (1) SINGLE SHELL & (5) DOUBLE SHELLS
Hours | 33
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (1) SINGLE SHELL & (5) DOUBLE SHELLS
Hours | 18
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
Hours | 9
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
Hours | 5
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
Hours | 5
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 8
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 20
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 20
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
Hours | 6
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE; LAYOUT LADDER POSITION
Hours | 2
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
Hours | 8
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 42
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT (8) LEGS & WELD COMPLETE (INCL BRACING)
Hours | 88
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 5
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
Hours | 12
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld INSTALL (3) TUBING SUPPORTS
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
Hours | 10
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
Hours | 10
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .760 | Fit platform - install and weld clips, bracing, etc.
Hours | 10
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 12
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 60
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 4
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 7
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
Hours | 3
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC21 | QC Inspection - Returned Components from Subcontractor
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts (8) LEG BRACES & (3) TUBING SUPPORTS
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail INCL CROSS-OVER HANDRAILS
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .285 | Cut/Build parts for platform
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .290 | Burn grating for platforms, clean and band
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .292 | Build platform - weld out
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .295 | Mount handrail on platform
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (1) SINGLE SHELL & (5) DOUBLE SHELLS
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (1) SINGLE SHELL & (5) DOUBLE SHELLS
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE; LAYOUT LADDER POSITION
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT (8) LEGS & WELD COMPLETE (INCL BRACING)
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld INSTALL (3) TUBING SUPPORTS
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .760 | Fit platform - install and weld clips, bracing, etc.
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC21 | QC Inspection - Returned Components from Subcontractor
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 018-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_