## Build Plan w Hours
Job #: | 054-24
| Description: | 40K GALLON TANK #4 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 13 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 18 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 3 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 35 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 25 |  |  |  | 0 | 0
PRE FAB |  | .175 | Build and weld base ring - skirt | 8 |  |  |  | 0 | 0
PRE FAB |  | .180 | Skirt: bring in plate, square, trim and clean | 6 |  |  |  | 0 | 0
PRE FAB |  | .185 | Roll skirt shells | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports | 4 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld | 36 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts ROLL (3) SKIRT OPENINGS | 3 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 8 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe ***NOTE EXTRA MID RAIL*** | 4 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 1 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out ***NOTE EXTRA MID RAIL*** | 32 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 20 |  |  |  | 0 | 0
PRE FAB |  | .310 | Bevel shell plates | 24 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes INCL PREP HOLES FOR FULL PEN WELDS | 20 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 8 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (4) LIFT LUGS AND (2) 12"X12" PADS | 32 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 4 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners (4) GUSSETS & (4) STIFFENERS. WELD COMPLETE. | 14 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes INCL PREP FOR FULL PEN WELD | 6 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 2 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 7 |  |  |  | 0 | 0
PRE FAB |  | .470 | Install and weld out repads - bottom head | 4 |  |  |  | 0 | 0
PRE FAB |  | .510 | Build skirt; fit base ring to shell and weld AND WELD INSIDE & OUTSIDE | 8 |  |  |  | 0 | 0
FIT |  | .520 | Lay out skirt, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .530 | Build skirt - fit anchors / gussets AND WELD COMPLETE | 18 |  |  |  | 0 | 0
FIT |  | .540 | Set nozzles / manway in skirt - tack INSTALL (7) SKIRT OPENINGS | 14 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 10 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 20 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 20 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes PREP FOR FULL PEN WELDS | 16 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 4 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside INCL HOLE WATCH | 14 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 40 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt INSTALL SKIRT & WELD TO BOTTOM HEAD | 24 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 10 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 20 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld (4) WELDMENT PADS | 12 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 8 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 24 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 8 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 8 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 054-24
| Description: | 40K GALLON TANK #4 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 13 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 18 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 3 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 35 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 25 |  |  |  | 0 | 0
PRE FAB |  | .175 | Build and weld base ring - skirt | 8 |  |  |  | 0 | 0
PRE FAB |  | .180 | Skirt: bring in plate, square, trim and clean | 6 |  |  |  | 0 | 0
PRE FAB |  | .185 | Roll skirt shells | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports | 4 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld | 36 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts ROLL (3) SKIRT OPENINGS | 3 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 8 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe ***NOTE EXTRA MID RAIL*** | 4 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 1 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out ***NOTE EXTRA MID RAIL*** | 32 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 20 |  |  |  | 0 | 0
PRE FAB |  | .310 | Bevel shell plates | 24 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes INCL PREP HOLES FOR FULL PEN WELDS | 20 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 8 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (4) LIFT LUGS AND (2) 12"X12" PADS | 32 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 4 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners (4) GUSSETS & (4) STIFFENERS. WELD COMPLETE. | 14 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes INCL PREP FOR FULL PEN WELD | 6 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 2 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 7 |  |  |  | 0 | 0
PRE FAB |  | .470 | Install and weld out repads - bottom head | 4 |  |  |  | 0 | 0
PRE FAB |  | .510 | Build skirt; fit base ring to shell and weld AND WELD INSIDE & OUTSIDE | 8 |  |  |  | 0 | 0
FIT |  | .520 | Lay out skirt, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .530 | Build skirt - fit anchors / gussets AND WELD COMPLETE | 18 |  |  |  | 0 | 0
FIT |  | .540 | Set nozzles / manway in skirt - tack INSTALL (7) SKIRT OPENINGS | 14 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 10 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 20 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 20 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes PREP FOR FULL PEN WELDS | 16 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 4 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside INCL HOLE WATCH | 14 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 40 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt INSTALL SKIRT & WELD TO BOTTOM HEAD | 24 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 10 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 20 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld (4) WELDMENT PADS | 12 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 8 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 24 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 8 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 8 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | 40K GALLON TANK #4 | Customer PO: | 4501905971 | Quote: | 8981 | 40K GALLON TANK #4 | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2024-08-29 | Make Qty: | 1 | / | ea | Est Hours: | 684
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 50131 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 50132 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 50133 | 0 | Cut Nozzle Pipe and Clean | 0 | 13 | FixedHrs | 13 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 50134 | 0 | Build Nozzles-Weld | 0 | 18 | FixedHrs | 18 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 50135 | 0 | Build Repads for Nozzles | 0 | 3 | FixedHrs | 3 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 50136 | 0 | Make Manway Parts | 0 | 2 | FixedHrs | 2 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 50137 | 0 | Brn MW Neck, Clean, Bevel | 0 | 2 | FixedHrs | 2 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 50138 | 0 | Roll Manway Neck | 0 | 2 | FixedHrs | 2 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 50139 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 4 | FixedHrs | 4 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 50140 | 0 | Bld Davit Arm Aby Cover | 0 | 4 | FixedHrs | 4 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 50141 | 0 | Cut Parts on Burn Table | 0 | 35 | FixedHrs | 35 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 50142 | 0 | Clean & Prep Parts | 0 | 25 | FixedHrs | 25 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 50143 | 0 | B&W Base Ring, Skirt | 0 | 8 | FixedHrs | 8 | .175 | 0 | Build and weld base ring - skirt | _________________ | _________________ | _________________
PRE FAB | 50144 | 0 | Skirt-BI, SQ, T&C | 0 | 6 | FixedHrs | 6 | .180 | 0 | Skirt: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 50145 | 0 | Roll Skirt Shells | 0 | 4 | FixedHrs | 4 | .185 | 0 | Roll skirt shells | _________________ | _________________ | _________________
PRE FAB | 50146 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 50147 | 0 | Cut, Make Baffle Supports | 0 | 4 | FixedHrs | 4 | .225 | 0 | Cut and make baffle supports | _________________ | _________________ | _________________
PRE FAB | 50148 | 0 | Build Baffles-Weld | 0 | 36 | FixedHrs | 36 | .230 | 0 | Build baffles and weld | _________________ | _________________ | _________________
PRE FAB | 50149 | 0 | Fab Miscellaneous Parts | 0 | 3 | FixedHrs | 3 | .252 | 0 | Fabricate miscellaneous parts ROLL (3) SKIRT OPENINGS | _________________ | _________________ | _________________
PRE FAB | 50150 | 0 | Cut, Build Handrail Parts | 0 | 8 | FixedHrs | 8 | .272 | 0 | Cut/Build parts for handrail | _________________ | _________________ | _________________
PRE FAB | 50151 | 0 | Roll Handrail Pipe | 0 | 4 | FixedHrs | 4 | .275 | 0 | Roll handrail pipe ***NOTE EXTRA MID RAIL*** | _________________ | _________________ | _________________
PRE FAB | 50152 | 0 | Roll Handrail Toe Plate | 0 | 1 | FixedHrs | 1 | .280 | 0 | Roll handrail toe plate | _________________ | _________________ | _________________
PRE FAB | 50153 | 0 | Build Handrail-Weld | 0 | 32 | FixedHrs | 32 | .282 | 0 | Build handrail - weld out ***NOTE EXTRA MID RAIL*** | _________________ | _________________ | _________________
PRE FAB | 50154 | 0 | Wrap Top & Bottom Heads | 0 | 2 | FixedHrs | 2 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________
INSPECTION | 50155 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 50156 | 0 | BI, SQ, T&C Shells | 0 | 20 | FixedHrs | 20 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 50157 | 0 | Bevel Shell Plates | 0 | 24 | FixedHrs | 24 | .310 | 0 | Bevel shell plates | _________________ | _________________ | _________________
PRE FAB | 50158 | 0 | Roll Shell, Tack-Weld I/S | 0 | 16 | FixedHrs | 16 | .315 | 0 | Roll shells, tack and weld inside seams | _________________ | _________________ | _________________
INSPECTION | 50159 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 50160 | 0 | L/O Top, B&C Holes | 0 | 20 | FixedHrs | 20 | .355 | 0 | Lay out top head, burn and clean holes INCL PREP HOLES FOR FULL PEN WELDS | _________________ | _________________ | _________________
PRE FAB | 50161 | 0 | Set Nozzles & Lugs - Top | 0 | 8 | FixedHrs | 8 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 50162 | 0 | Weld Nozzles - Top Head | 0 | 32 | FixedHrs | 32 | .366 | 0 | Weld out top head nozzles, etc. INCL (4) LIFT LUGS AND (2) 12"X12" PADS | _________________ | _________________ | _________________
PRE FAB | 50163 | 0 | I&W Repads -Top | 0 | 4 | FixedHrs | 4 | .370 | 0 | Install and weld out repads - top head | _________________ | _________________ | _________________
PRE FAB | 50164 | 0 | Install Top Stiffeners | 0 | 14 | FixedHrs | 14 | .375 | 0 | Install top stiffeners (4) GUSSETS & (4) STIFFENERS. WELD COMPLETE. | _________________ | _________________ | _________________
INSPECTION | 50165 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 50166 | 0 | L/O Bottom, B&C Holes | 0 | 6 | FixedHrs | 6 | .455 | 0 | Lay out bottom head, burn and clean holes INCL PREP FOR FULL PEN WELD | _________________ | _________________ | _________________
PRE FAB | 50167 | 0 | Set Nozzles - Bottom Head | 0 | 2 | FixedHrs | 2 | .465 | 0 | Set nozzles in bottom head - tack | _________________ | _________________ | _________________
PRE FAB | 50168 | 0 | Weld Nozzles - Bot. Head | 0 | 7 | FixedHrs | 7 | .466 | 0 | Weld nozzles in bottom head; weld complete | _________________ | _________________ | _________________
PRE FAB | 50169 | 0 | I&W Bottom Repads | 0 | 4 | FixedHrs | 4 | .470 | 0 | Install and weld out repads - bottom head | _________________ | _________________ | _________________
PRE FAB | 50170 | 0 | Bld Skirt, F&T to Base | 0 | 8 | FixedHrs | 8 | .510 | 0 | Build skirt; fit base ring to shell and weld AND WELD INSIDE & OUTSIDE | _________________ | _________________ | _________________
FIT | 50171 | 0 | L/O Skirt, B&C Holes | 0 | 1 | FixedHrs | 1 | .520 | 0 | Lay out skirt, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________
FIT | 50172 | 0 | Bld Skirt, Fit Anchor/Gst | 0 | 18 | FixedHrs | 18 | .530 | 0 | Build skirt - fit anchors / gussets AND WELD COMPLETE | _________________ | _________________ | _________________
FIT | 50173 | 0 | Set Nzl/MW in Skirt-Tack | 0 | 14 | FixedHrs | 14 | .540 | 0 | Set nozzles / manway in skirt - tack INSTALL (7) SKIRT OPENINGS | _________________ | _________________ | _________________
FIT | 50174 | 0 | Fit Bottom Head to Shell | 0 | 10 | FixedHrs | 10 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________
FIT | 50175 | 0 | Tack Shell Courses | 0 | 20 | FixedHrs | 20 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 50176 | 0 | Weld Inside Round Seams | 0 | 20 | FixedHrs | 20 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 50177 | 0 | L/O Shell, B&C Holes | 0 | 16 | FixedHrs | 16 | .620 | 0 | Lay out shell, burn and clean holes PREP FOR FULL PEN WELDS | _________________ | _________________ | _________________
FIT | 50178 | 0 | Install Baffles-Weld | 0 | 20 | FixedHrs | 20 | .625 | 0 | Install baffles and weld | _________________ | _________________ | _________________
INSPECTION | 50179 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 50180 | 0 | Fit Top to Shell | 0 | 4 | FixedHrs | 4 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________
FIT | 50181 | 0 | Weld top to shell | 0 | 14 | FixedHrs | 14 | .641 | 0 | Weld top head to shell - inside INCL HOLE WATCH | _________________ | _________________ | _________________
FIT | 50182 | 0 | Weld all Outside Seams | 0 | 40 | FixedHrs | 40 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 50183 | 0 | Move Tank to Detail Rolls | 0 | 2 | FixedHrs | 2 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 50184 | 0 | Install Support Parts | 0 | 24 | FixedHrs | 24 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt INSTALL SKIRT & WELD TO BOTTOM HEAD | _________________ | _________________ | _________________
FIT | 50185 | 0 | Set Nozzles in Shell | 0 | 10 | FixedHrs | 10 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 50186 | 0 | Weld Shell Nozz & M/Ws | 0 | 20 | FixedHrs | 20 | .726 | 0 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | _________________ | _________________ | _________________
FIT | 50187 | 0 | Add Repads-Weld | 0 | 12 | FixedHrs | 12 | .730 | 0 | Add repads and weld (4) WELDMENT PADS | _________________ | _________________ | _________________
FIT | 50188 | 0 | Fit Handrail, I&W Clips | 0 | 8 | FixedHrs | 8 | .750 | 0 | Fit handrail - install and weld clips | _________________ | _________________ | _________________
FINISHING | 50189 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 50190 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 50191 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 50192 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 50193 | 0 | Test Tank | 0 | 24 | FixedHrs | 24 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 50194 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
MOVE TANK | 50195 | 0 | Move to Paint Area | 0 | 2 | FixedHrs | 2 | .802 | 0 | Move to paint area | _________________ | _________________ | _________________
INSPECTION | 50196 | 0 | QC Inspection - Sandblast | 0 | 0 | FixedHrs | 0 | .QC9 | 0 | QC Inspection - Sandblast | _________________ | _________________ | _________________
INSPECTION | 50197 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 50198 | 0 | Prepare Tank for Shipment | 0 | 8 | FixedHrs | 8 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 50199 | 0 | Check BOM, Pack Parts | 0 | 2 | FixedHrs | 2 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 50200 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 50201 | 0 | Load on Truck | 0 | 8 | FixedHrs | 8 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | 40K GALLON TANK #4 |  |  |  | Rev:

## Tasks with Hours
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 13
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 18
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 3
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 35
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 25
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .175 | Build and weld base ring - skirt
Hours | 8
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .180 | Skirt: bring in plate, square, trim and clean
Hours | 6
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .185 | Roll skirt shells
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld
Hours | 36
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts ROLL (3) SKIRT OPENINGS
Hours | 3
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
Hours | 8
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe ***NOTE EXTRA MID RAIL***
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
Hours | 1
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out ***NOTE EXTRA MID RAIL***
Hours | 32
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 20
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .310 | Bevel shell plates
Hours | 24
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
Hours | 16
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes INCL PREP HOLES FOR FULL PEN WELDS
Hours | 20
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 8
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (4) LIFT LUGS AND (2) 12"X12" PADS
Hours | 32
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners (4) GUSSETS & (4) STIFFENERS. WELD COMPLETE.
Hours | 14
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes INCL PREP FOR FULL PEN WELD
Hours | 6
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
Hours | 7
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .470 | Install and weld out repads - bottom head
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .510 | Build skirt; fit base ring to shell and weld AND WELD INSIDE & OUTSIDE
Hours | 8
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .520 | Lay out skirt, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 1
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .530 | Build skirt - fit anchors / gussets AND WELD COMPLETE
Hours | 18
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .540 | Set nozzles / manway in skirt - tack INSTALL (7) SKIRT OPENINGS
Hours | 14
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 10
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 20
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 20
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes PREP FOR FULL PEN WELDS
Hours | 16
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
Hours | 20
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 4
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside INCL HOLE WATCH
Hours | 14
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 40
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt INSTALL SKIRT & WELD TO BOTTOM HEAD
Hours | 24
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 10
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
Hours | 20
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld (4) WELDMENT PADS
Hours | 12
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
Hours | 8
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 24
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 8
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 2
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 8
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .175 | Build and weld base ring - skirt
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .180 | Skirt: bring in plate, square, trim and clean
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .185 | Roll skirt shells
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts ROLL (3) SKIRT OPENINGS
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe ***NOTE EXTRA MID RAIL***
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out ***NOTE EXTRA MID RAIL***
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .310 | Bevel shell plates
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes INCL PREP HOLES FOR FULL PEN WELDS
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (4) LIFT LUGS AND (2) 12"X12" PADS
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners (4) GUSSETS & (4) STIFFENERS. WELD COMPLETE.
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes INCL PREP FOR FULL PEN WELD
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .470 | Install and weld out repads - bottom head
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .510 | Build skirt; fit base ring to shell and weld AND WELD INSIDE & OUTSIDE
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .520 | Lay out skirt, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .530 | Build skirt - fit anchors / gussets AND WELD COMPLETE
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .540 | Set nozzles / manway in skirt - tack INSTALL (7) SKIRT OPENINGS
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes PREP FOR FULL PEN WELDS
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside INCL HOLE WATCH
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt INSTALL SKIRT & WELD TO BOTTOM HEAD
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld (4) WELDMENT PADS
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 054-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_