## Build Plan w Hours
Job #: | 007-25
| Description: | 160-TK-16001 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 8 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld PLUS EXTRA LENGTH FOR B2 | 16 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 6 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. FOR HATCH X3 | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck FOR B1 | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam FOR B1 | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover FOR HATCH X1 | 1 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door FOR HATCH X1 | 1 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 25 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 15 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 6 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe | 3 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 2 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 22 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL & (1) SINGLE SHELL | 12 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL & (1) SINGLE SHELL; WELD L/S W/COBOT | 6 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 8 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 10 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone FOR FLAT BOTTOM & SLOPED BOTTOM | 18 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .475 | Install bottom stiffeners | 20 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell FOR FLAT & SLOPED BOTTOM; WELD COMPLETE | 25 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 3 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 3 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 8 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 4 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell | 2 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 14 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. **SEE SAMMY BEFORE WELDING MANWAY** | 18 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld FOR MANWAY AND MIXER STIFFENERS | 16 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports | 2 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 5 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 28 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 5 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 007-25
| Description: | 160-TK-16001 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 8 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld PLUS EXTRA LENGTH FOR B2 | 16 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 6 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. FOR HATCH X3 | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck FOR B1 | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam FOR B1 | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover FOR HATCH X1 | 1 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door FOR HATCH X1 | 1 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 25 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 15 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 6 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe | 3 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 2 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 22 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL & (1) SINGLE SHELL | 12 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL & (1) SINGLE SHELL; WELD L/S W/COBOT | 6 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 8 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 10 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone FOR FLAT BOTTOM & SLOPED BOTTOM | 18 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .475 | Install bottom stiffeners | 20 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell FOR FLAT & SLOPED BOTTOM; WELD COMPLETE | 25 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 3 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 3 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 8 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 4 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell | 2 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 14 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. **SEE SAMMY BEFORE WELDING MANWAY** | 18 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld FOR MANWAY AND MIXER STIFFENERS | 16 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports | 2 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 5 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 28 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 5 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | 160-TK-16001 | Customer PO: | C000139275 | Quote: | 9063.3 | 160-TK-16001 | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-01-28 | Make Qty: | 1 | / | ea | Est Hours: | 389
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 52437 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 52438 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 52439 | 0 | Cut Nozzle Pipe and Clean | 0 | 8 | FixedHrs | 8 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 52440 | 0 | Build Nozzles-Weld | 0 | 16 | FixedHrs | 16 | .105 | 0 | Build nozzles and weld PLUS EXTRA LENGTH FOR B2 | _________________ | _________________ | _________________
PRE FAB | 52441 | 0 | Build Repads for Nozzles | 0 | 6 | FixedHrs | 6 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 52442 | 0 | Make Manway Parts | 0 | 1 | FixedHrs | 1 | .115 | 0 | Make manway parts: cut clips, form handles, etc. FOR HATCH X3 | _________________ | _________________ | _________________
PRE FAB | 52443 | 0 | Brn MW Neck, Clean, Bevel | 0 | 1 | FixedHrs | 1 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 52444 | 0 | Roll Manway Neck | 0 | 2 | FixedHrs | 2 | .125 | 0 | Roll manway neck FOR B1 | _________________ | _________________ | _________________
PRE FAB | 52445 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 2 | FixedHrs | 2 | .130 | 0 | Set up and weld manway flange and neck seam FOR B1 | _________________ | _________________ | _________________
PRE FAB | 52446 | 0 | Bld Davit Arm Aby Cover | 0 | 1 | FixedHrs | 1 | .135 | 0 | Build davit arm assembly and cover FOR HATCH X1 | _________________ | _________________ | _________________
PRE FAB | 52447 | 0 | Build Hatch/Door | 0 | 1 | FixedHrs | 1 | .140 | 0 | Build hatch/door FOR HATCH X1 | _________________ | _________________ | _________________
PRE FAB | 52448 | 0 | Cut Parts on Burn Table | 0 | 25 | FixedHrs | 25 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 52449 | 0 | Clean & Prep Parts | 0 | 15 | FixedHrs | 15 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 52450 | 0 | Build Supports | 0 | 4 | FixedHrs | 4 | .165 | 0 | Build supports: legs, lugs, saddles TACK ONLY | _________________ | _________________ | _________________
PRE FAB | 52451 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 52452 | 0 | Roll Rim Angle | 0 | 3 | FixedHrs | 3 | .205 | 0 | Roll rim angle | _________________ | _________________ | _________________
PRE FAB | 52453 | 0 | Cut, Build Handrail Parts | 0 | 6 | FixedHrs | 6 | .272 | 0 | Cut/Build parts for handrail | _________________ | _________________ | _________________
PRE FAB | 52454 | 0 | Roll Handrail Pipe | 0 | 3 | FixedHrs | 3 | .275 | 0 | Roll handrail pipe | _________________ | _________________ | _________________
PRE FAB | 52455 | 0 | Roll Handrail Toe Plate | 0 | 2 | FixedHrs | 2 | .280 | 0 | Roll handrail toe plate | _________________ | _________________ | _________________
PRE FAB | 52456 | 0 | Build Handrail-Weld | 0 | 22 | FixedHrs | 22 | .282 | 0 | Build handrail - weld out | _________________ | _________________ | _________________
INSPECTION | 52457 | 0 | QC Inspection - Pre Sub C | 0 | 0 | FixedHrs | 0 | .QC2 | 0 | QC Inspection - Components prior to shipping to Subcontractor | _________________ | _________________ | _________________
INSPECTION | 52458 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 52459 | 0 | BI, SQ, T&C Shells | 0 | 12 | FixedHrs | 12 | .305 | 0 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL & (1) SINGLE SHELL | _________________ | _________________ | _________________
PRE FAB | 52460 | 0 | Roll Shell, Tack-Weld I/S | 0 | 6 | FixedHrs | 6 | .315 | 0 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL & (1) SINGLE SHELL; WELD L/S W/COBOT | _________________ | _________________ | _________________
PRE FAB | 52461 | 0 | Build Top Head/Cone | 0 | 10 | FixedHrs | 10 | .350 | 0 | Build top head/cone | _________________ | _________________ | _________________
INSPECTION | 52462 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 52463 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 52464 | 0 | Set Nozzles & Lugs - Top | 0 | 4 | FixedHrs | 4 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 52465 | 0 | Weld Nozzles - Top Head | 0 | 8 | FixedHrs | 8 | .366 | 0 | Weld out top head nozzles, etc. | _________________ | _________________ | _________________
PRE FAB | 52466 | 0 | I&W Repads -Top | 0 | 10 | FixedHrs | 10 | .370 | 0 | Install and weld out repads - top head | _________________ | _________________ | _________________
PRE FAB | 52467 | 0 | Build Bottom Head/Cone | 0 | 18 | FixedHrs | 18 | .450 | 0 | Build bottom head/cone FOR FLAT BOTTOM & SLOPED BOTTOM | _________________ | _________________ | _________________
INSPECTION | 52468 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 52469 | 0 | Install Bottom Stiffeners | 0 | 20 | FixedHrs | 20 | .475 | 0 | Install bottom stiffeners | _________________ | _________________ | _________________
FIT | 52470 | 0 | Fit Bottom Head to Shell | 0 | 25 | FixedHrs | 25 | .600 | 0 | Fit bottom head to shell FOR FLAT & SLOPED BOTTOM; WELD COMPLETE | _________________ | _________________ | _________________
FIT | 52471 | 0 | Tack Shell Courses | 0 | 3 | FixedHrs | 3 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 52472 | 0 | Weld Inside Round Seams | 0 | 3 | FixedHrs | 3 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 52473 | 0 | Install Rim Angle | 0 | 4 | FixedHrs | 4 | .615 | 0 | Install rim angle - tack only | _________________ | _________________ | _________________
FIT | 52474 | 0 | Weld Rim Angle | 0 | 4 | FixedHrs | 4 | .616 | 0 | Weld rim angle complete | _________________ | _________________ | _________________
FIT | 52475 | 0 | L/O Shell, B&C Holes | 0 | 1 | FixedHrs | 1 | .620 | 0 | Lay out shell, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
INSPECTION | 52476 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 52477 | 0 | Fit Top to Shell | 0 | 8 | FixedHrs | 8 | .640 | 0 | Fit top head to shell - tack AND WELD TO RIM ANGLE | _________________ | _________________ | _________________
FIT | 52478 | 0 | Weld all Outside Seams | 0 | 4 | FixedHrs | 4 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 52479 | 0 | Move Tank to Detail Rolls | 0 | 2 | FixedHrs | 2 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 52480 | 0 | Install Lift Lugs on Shl | 0 | 2 | FixedHrs | 2 | .717 | 0 | Install lift lugs on shell | _________________ | _________________ | _________________
FIT | 52481 | 0 | Install Support Parts | 0 | 12 | FixedHrs | 12 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | _________________ | _________________ | _________________
FIT | 52482 | 0 | Set Nozzles in Shell | 0 | 14 | FixedHrs | 14 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 52483 | 0 | Weld Shell Nozz & M/Ws | 0 | 18 | FixedHrs | 18 | .726 | 0 | Weld shell nozzles, manways, etc. **SEE SAMMY BEFORE WELDING MANWAY** | _________________ | _________________ | _________________
FIT | 52484 | 0 | Add Repads-Weld | 0 | 16 | FixedHrs | 16 | .730 | 0 | Add repads and weld FOR MANWAY AND MIXER STIFFENERS | _________________ | _________________ | _________________
FIT | 52485 | 0 | Install Dip Pipe Supports | 0 | 2 | FixedHrs | 2 | .735 | 0 | Install dip pipe supports | _________________ | _________________ | _________________
FIT | 52486 | 0 | Fit Handrail, I&W Clips | 0 | 5 | FixedHrs | 5 | .750 | 0 | Fit handrail - install and weld clips | _________________ | _________________ | _________________
FINISHING | 52487 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 52488 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 52489 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 52490 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 52491 | 0 | Test Tank | 0 | 10 | FixedHrs | 10 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 52492 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 52493 | 0 | Clean Tank Complete | 0 | 28 | FixedHrs | 28 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 52494 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 52495 | 0 | Prepare Tank for Shipment | 0 | 2 | FixedHrs | 2 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 52496 | 0 | Check BOM, Pack Parts | 0 | 2 | FixedHrs | 2 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 52497 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 52498 | 0 | Load on Truck | 0 | 5 | FixedHrs | 5 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
SHIPPING | 52499 | 0 | Take Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .970 | 0 | Take parts to galvanizers | _________________ | _________________ | _________________
SHIPPING | 52500 | 0 | P/U Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .972 | 0 | Pick up parts from galvanizers | _________________ | _________________ | _________________
| Part: | 160-TK-16001 |  |  |  | Rev:

## Tasks with Hours
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 8
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld PLUS EXTRA LENGTH FOR B2
Hours | 16
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 6
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc. FOR HATCH X3
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck FOR B1
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam FOR B1
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover FOR HATCH X1
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door FOR HATCH X1
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 25
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 15
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
Hours | 4
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
Hours | 3
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
Hours | 6
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe
Hours | 3
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
Hours | 22
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL & (1) SINGLE SHELL
Hours | 12
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL & (1) SINGLE SHELL; WELD L/S W/COBOT
Hours | 6
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
Hours | 10
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 4
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
Hours | 8
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
Hours | 10
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone FOR FLAT BOTTOM & SLOPED BOTTOM
Hours | 18
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .475 | Install bottom stiffeners
Hours | 20
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FOR FLAT & SLOPED BOTTOM; WELD COMPLETE
Hours | 25
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 3
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 3
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
Hours | 4
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
Hours | 4
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
Hours | 8
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 4
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
Hours | 12
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 14
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. **SEE SAMMY BEFORE WELDING MANWAY**
Hours | 18
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld FOR MANWAY AND MIXER STIFFENERS
Hours | 16
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
Hours | 5
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 10
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 28
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 5
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
Hours | 3
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
Hours | 3
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld PLUS EXTRA LENGTH FOR B2
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc. FOR HATCH X3
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck FOR B1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam FOR B1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover FOR HATCH X1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door FOR HATCH X1
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL & (1) SINGLE SHELL
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL & (1) SINGLE SHELL; WELD L/S W/COBOT
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone FOR FLAT BOTTOM & SLOPED BOTTOM
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .475 | Install bottom stiffeners
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FOR FLAT & SLOPED BOTTOM; WELD COMPLETE
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. **SEE SAMMY BEFORE WELDING MANWAY**
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld FOR MANWAY AND MIXER STIFFENERS
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 007-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_