## Build Plan w Hours
Job #: | 023-25
| Description: | PRODUCT LIQUOR FLASH TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 3 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld INCL INSTALL (2) COUPLINGS IN N8 | 6 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld INLET PIPE ASSEMBLY | 3 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 4 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap REPADS FOR LEGS | 2 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CUT PIPE & CONE SUPPTS ON SHEAR; MAKE & WELD CONE | 4 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE VORTEX BREAKER | 1 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack INCL INLET PIPE & VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete INCL INLET PIPE & VORTEX BREAKER | 4 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell | 2 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. PIPE SUPPORTS & CONE ASSEMBLY | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 2 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams INCL FULL PEN WELDS-FROM OUTSIDE FOR TOP & BOT HEADS | 8 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (4) REPADS AND (4) LEGS | 8 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 3 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 4 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 023-25
| Description: | PRODUCT LIQUOR FLASH TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 3 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld INCL INSTALL (2) COUPLINGS IN N8 | 6 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld INLET PIPE ASSEMBLY | 3 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 4 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap REPADS FOR LEGS | 2 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CUT PIPE & CONE SUPPTS ON SHEAR; MAKE & WELD CONE | 4 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE VORTEX BREAKER | 1 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack INCL INLET PIPE & VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete INCL INLET PIPE & VORTEX BREAKER | 4 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell | 2 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. PIPE SUPPORTS & CONE ASSEMBLY | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 2 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams INCL FULL PEN WELDS-FROM OUTSIDE FOR TOP & BOT HEADS | 8 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (4) REPADS AND (4) LEGS | 8 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 3 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 4 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | PRODUCT LIQUOR FLASH TANK | Customer PO: | 4504524626 | Quote: | 9070.2 | PRODUCT LIQUOR FLASH TANK | Line: | 10 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-01-30 | Make Qty: | 1 | / | ea | Est Hours: | 121
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 50523 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 50524 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 50525 | 0 | Cut Nozzle Pipe and Clean | 0 | 3 | FixedHrs | 3 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 50526 | 0 | Build Nozzles-Weld | 0 | 6 | FixedHrs | 6 | .105 | 0 | Build nozzles and weld INCL INSTALL (2) COUPLINGS IN N8 | _________________ | _________________ | _________________
PRE FAB | 50527 | 0 | Build Repads for Nozzles | 0 | 2 | FixedHrs | 2 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 50528 | 0 | Build Dip Tubes-Weld | 0 | 3 | FixedHrs | 3 | .110 | 0 | Build dip tubes and weld INLET PIPE ASSEMBLY | _________________ | _________________ | _________________
PRE FAB | 50529 | 0 | Make Manway Parts | 0 | 1 | FixedHrs | 1 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 50530 | 0 | Brn MW Neck, Clean, Bevel | 0 | 1 | FixedHrs | 1 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 50531 | 0 | Roll Manway Neck | 0 | 1 | FixedHrs | 1 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 50532 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 2 | FixedHrs | 2 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 50533 | 0 | Bld Davit Arm Aby Cover | 0 | 2 | FixedHrs | 2 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 50534 | 0 | Cut Parts on Burn Table | 0 | 6 | FixedHrs | 6 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 50535 | 0 | Clean & Prep Parts | 0 | 4 | FixedHrs | 4 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 50536 | 0 | Build Supports | 0 | 4 | FixedHrs | 4 | .165 | 0 | Build supports: legs, lugs, saddles BUILD (4) LEGS | _________________ | _________________ | _________________
PRE FAB | 50537 | 0 | Roll Repads-Drill & Tap | 0 | 2 | FixedHrs | 2 | .170 | 0 | Roll repads: drill and tap REPADS FOR LEGS | _________________ | _________________ | _________________
PRE FAB | 50538 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 50539 | 0 | Fab Miscellaneous Parts | 0 | 4 | FixedHrs | 4 | .252 | 0 | Fabricate miscellaneous parts CUT PIPE & CONE SUPPTS ON SHEAR; MAKE & WELD CONE | _________________ | _________________ | _________________
PRE FAB | 50540 | 0 | Misc Fabrication | 0 | 1 | FixedHrs | 1 | .261 | 0 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE VORTEX BREAKER | _________________ | _________________ | _________________
PRE FAB | 50541 | 0 | Wrap Top & Bottom Heads | 0 | 1 | FixedHrs | 1 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________
INSPECTION | 50542 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 50543 | 0 | BI, SQ, T&C Shells | 0 | 1 | FixedHrs | 1 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 50544 | 0 | Roll Shell, Tack-Weld I/S | 0 | 3 | FixedHrs | 3 | .315 | 0 | Roll shells, tack and weld inside seams | _________________ | _________________ | _________________
INSPECTION | 50545 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 50546 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 50547 | 0 | Set Nozzles & Lugs - Top | 0 | 1 | FixedHrs | 1 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 50548 | 0 | Weld Nozzles - Top Head | 0 | 2 | FixedHrs | 2 | .366 | 0 | Weld out top head nozzles, etc. | _________________ | _________________ | _________________
PRE FAB | 50549 | 0 | I&W Repads -Top | 0 | 2 | FixedHrs | 2 | .370 | 0 | Install and weld out repads - top head | _________________ | _________________ | _________________
INSPECTION | 50550 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 50551 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 50552 | 0 | Set Nozzles - Bottom Head | 0 | 3 | FixedHrs | 3 | .465 | 0 | Set nozzles in bottom head - tack INCL INLET PIPE & VORTEX BREAKER | _________________ | _________________ | _________________
PRE FAB | 50553 | 0 | Weld Nozzles - Bot. Head | 0 | 4 | FixedHrs | 4 | .466 | 0 | Weld nozzles in bottom head; weld complete INCL INLET PIPE & VORTEX BREAKER | _________________ | _________________ | _________________
INSPECTION | 50554 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 50555 | 0 | Fit Bottom Head to Shell | 0 | 2 | FixedHrs | 2 | .600 | 0 | Fit bottom head to shell | _________________ | _________________ | _________________
FIT | 50556 | 0 | L/O Shell, B&C Holes | 0 | 2 | FixedHrs | 2 | .620 | 0 | Lay out shell, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
FIT | 50557 | 0 | Install Internal Parts | 0 | 4 | FixedHrs | 4 | .630 | 0 | Install internals - wear plates, rings, clips, etc. PIPE SUPPORTS & CONE ASSEMBLY | _________________ | _________________ | _________________
INSPECTION | 50558 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 50559 | 0 | Fit Top to Shell | 0 | 2 | FixedHrs | 2 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________
FIT | 50560 | 0 | Weld all Outside Seams | 0 | 8 | FixedHrs | 8 | .645 | 0 | Weld all outside seams INCL FULL PEN WELDS-FROM OUTSIDE FOR TOP & BOT HEADS | _________________ | _________________ | _________________
MOVE TANK | 50561 | 0 | Move Tank to Detail Rolls | 0 | 1 | FixedHrs | 1 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 50562 | 0 | Install Support Parts | 0 | 8 | FixedHrs | 8 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (4) REPADS AND (4) LEGS | _________________ | _________________ | _________________
FIT | 50563 | 0 | Set Nozzles in Shell | 0 | 3 | FixedHrs | 3 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 50564 | 0 | Weld Shell Nozz & M/Ws | 0 | 4 | FixedHrs | 4 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
FIT | 50565 | 0 | Add Repads-Weld | 0 | 3 | FixedHrs | 3 | .730 | 0 | Add repads and weld | _________________ | _________________ | _________________
FINISHING | 50566 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 50567 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 50568 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 50569 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________
MOVE TANK | 50570 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 50571 | 0 | Test Tank | 0 | 8 | FixedHrs | 8 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 50572 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 50573 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
FINISHING | 50574 | 0 | Clean Tank Complete | 0 | 6 | FixedHrs | 6 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 50575 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
MOVE TANK | 50576 | 0 | Move to Paint Area | 0 | 1 | FixedHrs | 1 | .802 | 0 | Move to paint area | _________________ | _________________ | _________________
INSPECTION | 50577 | 0 | QC Inspection - Sandblast | 0 | 0 | FixedHrs | 0 | .QC9 | 0 | QC Inspection - Sandblast | _________________ | _________________ | _________________
INSPECTION | 50578 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 50579 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
INSPECTION | 50580 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 50581 | 0 | Load on Truck | 0 | 2 | FixedHrs | 2 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | PRODUCT LIQUOR FLASH TANK |  |  |  | Rev:

## Tasks with Hours
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 3
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld INCL INSTALL (2) COUPLINGS IN N8
Hours | 6
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld INLET PIPE ASSEMBLY
Hours | 3
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 6
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 4
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS
Hours | 4
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap REPADS FOR LEGS
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CUT PIPE & CONE SUPPTS ON SHEAR; MAKE & WELD CONE
Hours | 4
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE VORTEX BREAKER
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
Hours | 3
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack INCL INLET PIPE & VORTEX BREAKER
Hours | 3
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete INCL INLET PIPE & VORTEX BREAKER
Hours | 4
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. PIPE SUPPORTS & CONE ASSEMBLY
Hours | 4
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams INCL FULL PEN WELDS-FROM OUTSIDE FOR TOP & BOT HEADS
Hours | 8
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (4) REPADS AND (4) LEGS
Hours | 8
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 3
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 4
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
Hours | 3
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 8
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 6
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 2
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld INCL INSTALL (2) COUPLINGS IN N8
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld INLET PIPE ASSEMBLY
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap REPADS FOR LEGS
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CUT PIPE & CONE SUPPTS ON SHEAR; MAKE & WELD CONE
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE VORTEX BREAKER
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack INCL INLET PIPE & VORTEX BREAKER
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete INCL INLET PIPE & VORTEX BREAKER
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. PIPE SUPPORTS & CONE ASSEMBLY
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams INCL FULL PEN WELDS-FROM OUTSIDE FOR TOP & BOT HEADS
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (4) REPADS AND (4) LEGS
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_