## Build Plan w Hours
Job #: | 027-25
| Description: | YANKEE MACHINE CHEST |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 13 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. ASSEMBLE MANWAY | 5 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door BUILD N10 INCL. RAILS & CROSS BRACING | 16 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 25 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 12 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap FOR CABLE SUPPORT | 1 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .235 | Build top and bottom stiffeners FORM TOP STIFFENERS | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CABLE SUPPORT | 2 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes PARTS FOR HATCH N10 | 1 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 3 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 2 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 9 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 4 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 6 |  |  |  | 0 | 0
PRE FAB |  | .285 | Cut/Build parts for platform | 3 |  |  |  | 0 | 0
PRE FAB |  | .290 | Burn grating for platforms, clean and band | 2 |  |  |  | 0 | 0
PRE FAB |  | .292 | Build platform - weld out | 5 |  |  |  | 0 | 0
PRE FAB |  | .295 | Mount handrail on platform | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean (1) DOUBLE SHELL & (1) SINGLE SHELL **NOTE BOTTOM HEAD SLOPE** | 10 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ***WELD LONG SEAMS W COBOT*** | 6 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT AND HATCH | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT AND HATCH | 8 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners | 3 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE | 9 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 3 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 3 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. HANDLE | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD | 6 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 5 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell AND TIE-OFF LUGS | 2 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 5 |  |  |  | 0 | 0
FIT |  | .721 | Weld insulation / vacuum rings, lugs, supports, etc. | 5 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL HANDLE AND HOOK | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. ***SEE SAMMY VEFORE WELDING CHASE MANWAY*** | 15 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 3 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 5 |  |  |  | 0 | 0
FIT |  | .760 | Fit platform - install and weld clips, bracing, etc. | 5 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 25 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 4 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 027-25
| Description: | YANKEE MACHINE CHEST |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 13 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. ASSEMBLE MANWAY | 5 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door BUILD N10 INCL. RAILS & CROSS BRACING | 16 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 25 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 12 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap FOR CABLE SUPPORT | 1 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .235 | Build top and bottom stiffeners FORM TOP STIFFENERS | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CABLE SUPPORT | 2 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes PARTS FOR HATCH N10 | 1 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 3 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 2 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 9 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 4 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 6 |  |  |  | 0 | 0
PRE FAB |  | .285 | Cut/Build parts for platform | 3 |  |  |  | 0 | 0
PRE FAB |  | .290 | Burn grating for platforms, clean and band | 2 |  |  |  | 0 | 0
PRE FAB |  | .292 | Build platform - weld out | 5 |  |  |  | 0 | 0
PRE FAB |  | .295 | Mount handrail on platform | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean (1) DOUBLE SHELL & (1) SINGLE SHELL **NOTE BOTTOM HEAD SLOPE** | 10 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ***WELD LONG SEAMS W COBOT*** | 6 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT AND HATCH | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT AND HATCH | 8 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners | 3 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE | 9 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 3 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 3 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. HANDLE | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD | 6 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 5 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell AND TIE-OFF LUGS | 2 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 5 |  |  |  | 0 | 0
FIT |  | .721 | Weld insulation / vacuum rings, lugs, supports, etc. | 5 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL HANDLE AND HOOK | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. ***SEE SAMMY VEFORE WELDING CHASE MANWAY*** | 15 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 3 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 5 |  |  |  | 0 | 0
FIT |  | .760 | Fit platform - install and weld clips, bracing, etc. | 5 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 25 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 4 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | YANKEE MACHINE CHEST | Customer PO: | 20615990 OP | Quote: | 9032.4 | YANKEE MACHINE CHEST | Line: | 3.000 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-02-04 | Make Qty: | 1 | / | ea | Est Hours: | 313
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 51707 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 51708 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 51709 | 0 | Cut Nozzle Pipe and Clean | 0 | 5 | FixedHrs | 5 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 51710 | 0 | Build Nozzles-Weld | 0 | 13 | FixedHrs | 13 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 51782 | 0 | Build Repads for Nozzles | 0 | 2 | FixedHrs | 2 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 51711 | 0 | Make Manway Parts | 0 | 5 | FixedHrs | 5 | .115 | 0 | Make manway parts: cut clips, form handles, etc. ASSEMBLE MANWAY | _________________ | _________________ | _________________
PRE FAB | 51716 | 0 | Build Hatch/Door | 0 | 16 | FixedHrs | 16 | .140 | 0 | Build hatch/door BUILD N10 INCL. RAILS & CROSS BRACING | _________________ | _________________ | _________________
PRE FAB | 51717 | 0 | Cut Parts on Burn Table | 0 | 25 | FixedHrs | 25 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 51718 | 0 | Clean & Prep Parts | 0 | 12 | FixedHrs | 12 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 51719 | 0 | Build Supports | 0 | 4 | FixedHrs | 4 | .165 | 0 | Build supports: legs, lugs, saddles | _________________ | _________________ | _________________
PRE FAB | 51720 | 0 | Roll Repads-Drill & Tap | 0 | 1 | FixedHrs | 1 | .170 | 0 | Roll repads: drill and tap FOR CABLE SUPPORT | _________________ | _________________ | _________________
PRE FAB | 51721 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS | _________________ | _________________ | _________________
PRE FAB | 51722 | 0 | Roll Rim Angle | 0 | 3 | FixedHrs | 3 | .205 | 0 | Roll rim angle | _________________ | _________________ | _________________
PRE FAB | 51783 | 0 | Bld T-B Stiffeners | 0 | 2 | FixedHrs | 2 | .235 | 0 | Build top and bottom stiffeners FORM TOP STIFFENERS | _________________ | _________________ | _________________
PRE FAB | 51723 | 0 | Fab Miscellaneous Parts | 0 | 2 | FixedHrs | 2 | .252 | 0 | Fabricate miscellaneous parts CABLE SUPPORT | _________________ | _________________ | _________________
PRE FAB | 51724 | 0 | Drill/Punch holes | 0 | 1 | FixedHrs | 1 | .255 | 0 | Drill/punch holes PARTS FOR HATCH N10 | _________________ | _________________ | _________________
PRE FAB | 51726 | 0 | Cut, Build Ladder Parts | 0 | 3 | FixedHrs | 3 | .262 | 0 | Cut/make parts for ladder: rungs, rails, etc. | _________________ | _________________ | _________________
PRE FAB | 51727 | 0 | Form and Roll Ladder Hoop | 0 | 2 | FixedHrs | 2 | .265 | 0 | Form and roll ladder hoops | _________________ | _________________ | _________________
PRE FAB | 51728 | 0 | Build Ladder-Weld | 0 | 9 | FixedHrs | 9 | .270 | 0 | Build ladder - weld out | _________________ | _________________ | _________________
PRE FAB | 51729 | 0 | Cut, Build Handrail Parts | 0 | 4 | FixedHrs | 4 | .272 | 0 | Cut/Build parts for handrail | _________________ | _________________ | _________________
PRE FAB | 51730 | 0 | Build Handrail-Weld | 0 | 6 | FixedHrs | 6 | .282 | 0 | Build handrail - weld out | _________________ | _________________ | _________________
PRE FAB | 51731 | 0 | Cut, Build Platform Parts | 0 | 3 | FixedHrs | 3 | .285 | 0 | Cut/Build parts for platform | _________________ | _________________ | _________________
PRE FAB | 51732 | 0 | Burn Platform Grating | 0 | 2 | FixedHrs | 2 | .290 | 0 | Burn grating for platforms, clean and band | _________________ | _________________ | _________________
PRE FAB | 51733 | 0 | Build Platform-Weld | 0 | 5 | FixedHrs | 5 | .292 | 0 | Build platform - weld out | _________________ | _________________ | _________________
PRE FAB | 51734 | 0 | Mount Platform Handrail | 0 | 2 | FixedHrs | 2 | .295 | 0 | Mount handrail on platform | _________________ | _________________ | _________________
INSPECTION | 51735 | 0 | QC Inspection - Pre Sub C | 0 | 0 | FixedHrs | 0 | .QC2 | 0 | QC Inspection - Components prior to shipping to Subcontractor | _________________ | _________________ | _________________
INSPECTION | 51736 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 51737 | 0 | BI, SQ, T&C Shells | 0 | 10 | FixedHrs | 10 | .305 | 0 | Shells: bring in plate, square, trim and clean (1) DOUBLE SHELL & (1) SINGLE SHELL **NOTE BOTTOM HEAD SLOPE** | _________________ | _________________ | _________________
PRE FAB | 51738 | 0 | Roll Shell, Tack-Weld I/S | 0 | 6 | FixedHrs | 6 | .315 | 0 | Roll shells, tack and weld inside seams ***WELD LONG SEAMS W COBOT*** | _________________ | _________________ | _________________
PRE FAB | 51739 | 0 | Build Top Head/Cone | 0 | 5 | FixedHrs | 5 | .350 | 0 | Build top head/cone | _________________ | _________________ | _________________
INSPECTION | 51740 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 51741 | 0 | L/O Top, B&C Holes | 0 | 2 | FixedHrs | 2 | .355 | 0 | Lay out top head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 51742 | 0 | Set Nozzles & Lugs - Top | 0 | 6 | FixedHrs | 6 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT AND HATCH | _________________ | _________________ | _________________
PRE FAB | 51743 | 0 | Weld Nozzles - Top Head | 0 | 8 | FixedHrs | 8 | .366 | 0 | Weld out top head nozzles, etc. INCL CABLE SUPPORT AND HATCH | _________________ | _________________ | _________________
PRE FAB | 51784 | 0 | Install Top Stiffeners | 0 | 3 | FixedHrs | 3 | .375 | 0 | Install top stiffeners | _________________ | _________________ | _________________
PRE FAB | 51745 | 0 | Build Bottom Head/Cone | 0 | 5 | FixedHrs | 5 | .450 | 0 | Build bottom head/cone | _________________ | _________________ | _________________
INSPECTION | 51746 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 51747 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes | _________________ | _________________ | _________________
FIT | 51748 | 0 | Fit Bottom Head to Shell | 0 | 9 | FixedHrs | 9 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE | _________________ | _________________ | _________________
FIT | 51749 | 0 | Tack Shell Courses | 0 | 3 | FixedHrs | 3 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 51750 | 0 | Weld Inside Round Seams | 0 | 3 | FixedHrs | 3 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 51751 | 0 | Install Rim Angle | 0 | 4 | FixedHrs | 4 | .615 | 0 | Install rim angle - tack only | _________________ | _________________ | _________________
FIT | 51752 | 0 | Weld Rim Angle | 0 | 4 | FixedHrs | 4 | .616 | 0 | Weld rim angle complete | _________________ | _________________ | _________________
FIT | 51753 | 0 | L/O Shell, B&C Holes | 0 | 2 | FixedHrs | 2 | .620 | 0 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | _________________ | _________________ | _________________
FIT | 51754 | 0 | Install Internal Parts | 0 | 1 | FixedHrs | 1 | .630 | 0 | Install internals - wear plates, rings, clips, etc. HANDLE | _________________ | _________________ | _________________
INSPECTION | 51755 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 51756 | 0 | Fit Top to Shell | 0 | 6 | FixedHrs | 6 | .640 | 0 | Fit top head to shell - tack AND WELD | _________________ | _________________ | _________________
FIT | 51757 | 0 | Weld all Outside Seams | 0 | 5 | FixedHrs | 5 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 51758 | 0 | Move Tank to Detail Rolls | 0 | 2 | FixedHrs | 2 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 51759 | 0 | Install Lift Lugs on Shl | 0 | 2 | FixedHrs | 2 | .717 | 0 | Install lift lugs on shell AND TIE-OFF LUGS | _________________ | _________________ | _________________
FIT | 51760 | 0 | Install Support Parts | 0 | 5 | FixedHrs | 5 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt | _________________ | _________________ | _________________
FIT | 51761 | 0 | Weld rings, lugs, suppts | 0 | 5 | FixedHrs | 5 | .721 | 0 | Weld insulation / vacuum rings, lugs, supports, etc. | _________________ | _________________ | _________________
FIT | 51762 | 0 | Set Nozzles in Shell | 0 | 8 | FixedHrs | 8 | .725 | 0 | Set nozzles in shell - tack INCL HANDLE AND HOOK | _________________ | _________________ | _________________
FIT | 51763 | 0 | Weld Shell Nozz & M/Ws | 0 | 15 | FixedHrs | 15 | .726 | 0 | Weld shell nozzles, manways, etc. ***SEE SAMMY VEFORE WELDING CHASE MANWAY*** | _________________ | _________________ | _________________
FIT | 51764 | 0 | Add Repads-Weld | 0 | 3 | FixedHrs | 3 | .730 | 0 | Add repads and weld | _________________ | _________________ | _________________
FIT | 51767 | 0 | Fit Ladder, I&W Clips | 0 | 5 | FixedHrs | 5 | .755 | 0 | Fit ladder - install and weld clips | _________________ | _________________ | _________________
FIT | 51768 | 0 | Fit Platform, I&W Clips | 0 | 5 | FixedHrs | 5 | .760 | 0 | Fit platform - install and weld clips, bracing, etc. | _________________ | _________________ | _________________
FINISHING | 51769 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 51771 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 51772 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 51773 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 51774 | 0 | Test Tank | 0 | 8 | FixedHrs | 8 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 51775 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 51776 | 0 | Clean Tank Complete | 0 | 25 | FixedHrs | 25 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 51777 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 51786 | 0 | Prepare Tank for Shipment | 0 | 2 | FixedHrs | 2 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 51785 | 0 | Check BOM, Pack Parts | 0 | 2 | FixedHrs | 2 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 51778 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 51779 | 0 | Load on Truck | 0 | 4 | FixedHrs | 4 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
SHIPPING | 51780 | 0 | Take Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .970 | 0 | Take parts to galvanizers | _________________ | _________________ | _________________
SHIPPING | 51781 | 0 | P/U Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .972 | 0 | Pick up parts from galvanizers | _________________ | _________________ | _________________
| Part: | YANKEE MACHINE CHEST |  |  |  | Rev:

## Tasks with Hours
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 13
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc. ASSEMBLE MANWAY
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door BUILD N10 INCL. RAILS & CROSS BRACING
Hours | 16
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 25
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 12
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
Hours | 4
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap FOR CABLE SUPPORT
Hours | 1
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .235 | Build top and bottom stiffeners FORM TOP STIFFENERS
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CABLE SUPPORT
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes PARTS FOR HATCH N10
Hours | 1
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
Hours | 9
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
Hours | 4
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
Hours | 6
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .285 | Cut/Build parts for platform
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .290 | Burn grating for platforms, clean and band
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .292 | Build platform - weld out
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .295 | Mount handrail on platform
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean (1) DOUBLE SHELL & (1) SINGLE SHELL **NOTE BOTTOM HEAD SLOPE**
Hours | 10
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ***WELD LONG SEAMS W COBOT***
Hours | 6
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT AND HATCH
Hours | 6
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT AND HATCH
Hours | 8
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
Hours | 1
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE
Hours | 9
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
Hours | 4
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
Hours | 4
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. HANDLE
Hours | 1
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD
Hours | 6
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell AND TIE-OFF LUGS
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .721 | Weld insulation / vacuum rings, lugs, supports, etc.
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL HANDLE AND HOOK
Hours | 8
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. ***SEE SAMMY VEFORE WELDING CHASE MANWAY***
Hours | 15
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .760 | Fit platform - install and weld clips, bracing, etc.
Hours | 5
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 8
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 25
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 2
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 4
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
Hours | 3
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc. ASSEMBLE MANWAY
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door BUILD N10 INCL. RAILS & CROSS BRACING
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap FOR CABLE SUPPORT
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .235 | Build top and bottom stiffeners FORM TOP STIFFENERS
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CABLE SUPPORT
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes PARTS FOR HATCH N10
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .285 | Cut/Build parts for platform
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .290 | Burn grating for platforms, clean and band
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .292 | Build platform - weld out
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .295 | Mount handrail on platform
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean (1) DOUBLE SHELL & (1) SINGLE SHELL **NOTE BOTTOM HEAD SLOPE**
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ***WELD LONG SEAMS W COBOT***
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT AND HATCH
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT AND HATCH
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. HANDLE
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell AND TIE-OFF LUGS
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .721 | Weld insulation / vacuum rings, lugs, supports, etc.
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL HANDLE AND HOOK
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. ***SEE SAMMY VEFORE WELDING CHASE MANWAY***
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .760 | Fit platform - install and weld clips, bracing, etc.
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 027-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_