## Build Plan w Hours
Job #: | 25-074 | Description: | T306 FERRIC SULFATE STORAGE TANK |  | Total Est Hours: | 483
Similar jobs used: | 25-054, 23-027, 23-031, 23-004, 23-005
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | none | nan
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4 | 7.9 | high | group_total:36h
PRE FAB |  | .105 | Build Nozzles-Weld | 10 | 16.5 | high | group_total:36h
PRE FAB |  | .115 | Make Manway Parts | 2 | 1.5 | high | group_total:36h
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2 | 1.2 | high | group_total:36h
PRE FAB |  | .125 | Roll Manway Neck | 2 | 1.7 | high | group_total:36h
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 8 | 3.9 | high | group_total:36h
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 2 | 3.2 | high | group_total:36h
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 24 | 33.9 | high | group_total:42h
PRE FAB |  | .156 | Clean & Prep Parts | 16 | 7.8 | high | group_total:42h
Supports
PRE FAB |  | .165 | Build Supports | 20 | 36.6 | high | group_total:42h
PRE FAB |  | .170 | Roll Repads-Drill & Tap | 6 | 5.8 | high | group_total:42h
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 5.6 | high | group_total:25h
PRE FAB |  | .215 | B&C Baffles | 4 | 0.2 | high | group_total:25h
PRE FAB |  | .220 | Form Baffles | 5 | 0.2 | high | group_total:25h
PRE FAB |  | .225 | Cut, Make Baffle Supports | 4 | 1.9 | high | group_total:25h
PRE FAB |  | .230 | Build Baffles-Weld | 16 | 6.1 | high | group_total:25h
PRE FAB |  | .261 | Misc Fabrication | 8 | 10.5 | high | group_total:25h
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2 | 0.5 | high | group_total:27h
INSPECTION |  | .QC3 | UT Shells |  |  | none | nan
PRE FAB |  | .305 | BI, SQ, T&C Shells | 20 | 13.9 | high | group_total:27h
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 24 | 12.9 | high | group_total:27h
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | none | nan
PRE FAB |  | .355 | L/O Top, B&C Holes | 1 | 5.5 | high | group_total:22h
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 3 | 5.5 | high | group_total:22h
PRE FAB |  | .366 | Weld Nozzles - Top Head | 8 | 10.8 | high | group_total:22h
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1 | 2.3 | high | group_total:6h
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 1.2 | high | group_total:6h
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2 | 2.3 | high | group_total:6h
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 8 | 17.2 | high | group_total:86h
FIT |  | .605 | Tack Shell Courses | 12 | 10 | high | group_total:86h
FIT |  | .610 | Weld Inside Round Seams | 18 | 11.8 | high | group_total:86h
FIT |  | .620 | L/O Shell, B&C Holes | 7 | 3.8 | high | group_total:86h
FIT |  | .625 | Install Baffles-Weld | 20 | 3.7 | high | group_total:86h
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | none | nan
FIT |  | .640 | Fit Top to Shell | 8 | 10.3 | high | group_total:86h
FIT |  | .641 | Weld top to shell | 16 | 5.2 | high | group_total:86h
FIT |  | .645 | Weld all Outside Seams | 24 | 23.9 | high | group_total:86h
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3 | 3 | none | nan
Install Nozzles and Externals
FIT |  | .720 | Install Support Parts | 32 | 24.4 | high | group_total:71h
FIT |  | .725 | Set Nozzles in Shell | 16 | 12.2 | high | group_total:71h
FIT |  | .726 | Weld Shell Nozz & M/Ws | 24 | 24.3 | high | group_total:71h
FIT |  | .760 | Fit Platform, I&W Clips | 12 | 5.8 | high | group_total:71h
INSPECTION |  | .QC51 | UT Components |  |  | none | nan
FINISHING |  | .765 | Install Name Tag | 1 | 1.5 | high | group_total:71h
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 2 | 2.7 | high | group_total:71h
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | none | nan
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 3 | 6.4 | high | group_total:112h
FINISHING |  | .910 | Test Tank | 20 | 30.5 | high | group_total:112h
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | none | nan
FINISHING |  | .920 | Clean Tank Complete | 50 | 52.7 | high | group_total:112h
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | none | nan
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 4 | 10.1 | high | group_total:112h
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | none | nan
SHIPPING |  | .960 | Load on Truck | 6 | 12.7 | high | group_total:112h
|  |  | Total Predicted Hours |  | 471.6

## Build Plan - No Hours
Job #: | 25-074 | Description: | T306 FERRIC SULFATE STORAGE TANK |  | Total Est Hours: | 483
Similar jobs used: | 25-054, 23-027, 23-031, 23-004, 23-005
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4
PRE FAB |  | .105 | Build Nozzles-Weld | 10
PRE FAB |  | .115 | Make Manway Parts | 2
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2
PRE FAB |  | .125 | Roll Manway Neck | 2
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 8
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 2
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 24
PRE FAB |  | .156 | Clean & Prep Parts | 16
Supports
PRE FAB |  | .165 | Build Supports | 20
PRE FAB |  | .170 | Roll Repads-Drill & Tap | 6
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .215 | B&C Baffles | 4
PRE FAB |  | .220 | Form Baffles | 5
PRE FAB |  | .225 | Cut, Make Baffle Supports | 4
PRE FAB |  | .230 | Build Baffles-Weld | 16
PRE FAB |  | .261 | Misc Fabrication | 8
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 20
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 24
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 1
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 3
PRE FAB |  | .366 | Weld Nozzles - Top Head | 8
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 8
FIT |  | .605 | Tack Shell Courses | 12
FIT |  | .610 | Weld Inside Round Seams | 18
FIT |  | .620 | L/O Shell, B&C Holes | 7
FIT |  | .625 | Install Baffles-Weld | 20
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 8
FIT |  | .641 | Weld top to shell | 16
FIT |  | .645 | Weld all Outside Seams | 24
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3
Install Nozzles and Externals
FIT |  | .720 | Install Support Parts | 32
FIT |  | .725 | Set Nozzles in Shell | 16
FIT |  | .726 | Weld Shell Nozz & M/Ws | 24
FIT |  | .760 | Fit Platform, I&W Clips | 12
INSPECTION |  | .QC51 | UT Components
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 2
INSPECTION |  | .QC6 | QC Inspection - Fab
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 3
FINISHING |  | .910 | Test Tank | 20
INSPECTION |  | .QC7 | QC Inspection - Test
FINISHING |  | .920 | Clean Tank Complete | 50
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 4
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 6
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-054
23-027
23-031
23-004
23-005
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | none | nan | nan
.100 | Cut Nozzle Pipe and Clean | 7.9 | high | group_total:36h | model(NOZZLES)
.105 | Build Nozzles-Weld | 16.5 | high | group_total:36h | model(NOZZLES)
.115 | Make Manway Parts | 1.5 | high | group_total:36h | model(NOZZLES)
.120 | Brn MW Neck, Clean, Bevel | 1.2 | high | group_total:36h | model(NOZZLES)
.125 | Roll Manway Neck | 1.7 | high | group_total:36h | model(NOZZLES)
.130 | S/U Weld MW Flg, Neck Sem | 3.9 | high | group_total:36h | model(NOZZLES)
.135 | Bld Davit Arm Aby Cover | 3.2 | high | group_total:36h | model(NOZZLES)
.155 | Cut Parts on Burn Table | 33.9 | high | group_total:42h | model(CUT_PREP)
.156 | Clean & Prep Parts | 7.8 | high | group_total:42h | model(CUT_PREP)
.165 | Build Supports | 36.6 | high | group_total:42h | model(SUPPORTS)
.170 | Roll Repads-Drill & Tap | 5.8 | high | group_total:42h | model(SUPPORTS)
.200 | Bld Lift Lugs, Grd Lugs | 5.6 | high | group_total:25h | model(MISC_PARTS)
.215 | B&C Baffles | 0.2 | high | group_total:25h | model(MISC_PARTS)
.220 | Form Baffles | 0.2 | high | group_total:25h | model(MISC_PARTS)
.225 | Cut, Make Baffle Supports | 1.9 | high | group_total:25h | model(MISC_PARTS)
.230 | Build Baffles-Weld | 6.1 | high | group_total:25h | model(MISC_PARTS)
.261 | Misc Fabrication | 10.5 | high | group_total:25h | model(MISC_PARTS)
.300 | Wrap Top & Bottom Heads | 0.5 | high | group_total:27h | model(SHELLS)
.QC3 | UT Shells | 0 | none | nan | nan
.305 | BI, SQ, T&C Shells | 13.9 | high | group_total:27h | model(SHELLS)
.315 | Roll Shell, Tack-Weld I/S | 12.9 | high | group_total:27h | model(SHELLS)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.355 | L/O Top, B&C Holes | 5.5 | high | group_total:22h | model(TOP_HEAD)
.365 | Set Nozzles & Lugs - Top | 5.5 | high | group_total:22h | model(TOP_HEAD)
.366 | Weld Nozzles - Top Head | 10.8 | high | group_total:22h | model(TOP_HEAD)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.455 | L/O Bottom, B&C Holes | 2.3 | high | group_total:6h | model(BTM_HEAD)
.465 | Set Nozzles - Bottom Head | 1.2 | high | group_total:6h | model(BTM_HEAD)
.466 | Weld Nozzles - Bot. Head | 2.3 | high | group_total:6h | model(BTM_HEAD)
.600 | Fit Bottom Head to Shell | 17.2 | high | group_total:86h | model(FIT_ASSEMBLY)
.605 | Tack Shell Courses | 10 | high | group_total:86h | model(FIT_ASSEMBLY)
.610 | Weld Inside Round Seams | 11.8 | high | group_total:86h | model(FIT_ASSEMBLY)
.620 | L/O Shell, B&C Holes | 3.8 | high | group_total:86h | model(FIT_ASSEMBLY)
.QC5 | QC Inspection - Internal | 0 | none | nan | nan
.640 | Fit Top to Shell | 10.3 | high | group_total:86h | model(FIT_ASSEMBLY)
.641 | Weld top to shell | 5.2 | high | group_total:86h | model(FIT_ASSEMBLY)
.645 | Weld all Outside Seams | 23.9 | high | group_total:86h | model(FIT_ASSEMBLY)
.800 | Move Tank to Detail Rolls | 3 | none | nan | nan
.720 | Install Support Parts | 24.4 | high | group_total:71h | model(DETAIL_EXT)
.725 | Set Nozzles in Shell | 12.2 | high | group_total:71h | model(DETAIL_EXT)
.726 | Weld Shell Nozz & M/Ws | 24.3 | high | group_total:71h | model(DETAIL_EXT)
.760 | Fit Platform, I&W Clips | 5.8 | high | group_total:71h | model(DETAIL_EXT)
.QC51 | UT Components | 0 | none | nan | nan
.765 | Install Name Tag | 1.5 | high | group_total:71h | model(DETAIL_EXT)
.770 | Inspect Tank, Make Repair | 2.7 | high | group_total:71h | model(DETAIL_EXT)
.QC6 | QC Inspection - Fab | 0 | none | nan | nan
.801 | Move to Shop Test Area | 6.4 | high | group_total:112h | model(TEST_CLEAN)
.910 | Test Tank | 30.5 | high | group_total:112h | model(TEST_CLEAN)
.QC7 | QC Inspection - Test | 0 | none | nan | nan
.920 | Clean Tank Complete | 52.7 | high | group_total:112h | model(TEST_CLEAN)
.QC8 | QC Inspection - Clean | 0 | none | nan | nan
.940 | Prepare Tank for Shipment | 10.1 | high | group_total:112h | model(TEST_CLEAN)
.QC95 | QC Inspection - Final & L | 0 | none | nan | nan
.960 | Load on Truck | 12.7 | high | group_total:112h | model(TEST_CLEAN)
.625 | Install Baffles-Weld | 3.7 | high | group_total:86h | model(FIT_ASSEMBLY)