## Build Plan w Hours
Job #: | 25-080 | Description: | DAF FILTRATE TANK |  | Total Est Hours: | 236
Similar jobs used: | 25-084, 23-094, 23-099, 23-095, 23-098
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | none | nan
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | none | nan
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 6 | 6.2 | high | group_total:30h
PRE FAB |  | .105 | Build Nozzles-Weld | 9 | 13.1 | high | group_total:30h
PRE FAB |  | .107 | Build Repads for Nozzles | 5 | 2 | high | group_total:30h
PRE FAB |  | .115 | Make Manway Parts | 2 | 1.2 | high | group_total:30h
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2 | 1 | high | group_total:30h
PRE FAB |  | .125 | Roll Manway Neck | 3 | 1.4 | high | group_total:30h
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 6 | 3.1 | high | group_total:30h
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 3 | 2.5 | high | group_total:30h
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 15 | 19.1 | high | group_total:24h
PRE FAB |  | .156 | Clean & Prep Parts | 15 | 4.4 | high | group_total:24h
Supports
PRE FAB |  | .165 | Build Supports | 3 | 5 | high | group_total:5h
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1 | 5.2 | high | group_total:10h
PRE FAB |  | .205 | Roll Rim Angle | 3 | 4.7 | high | group_total:10h
Shells
INSPECTION |  | .QC3 | UT Shells |  |  | none | nan
PRE FAB |  | .305 | BI, SQ, T&C Shells | 5 | 4.1 | high | group_total:8h
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 10 | 3.7 | high | group_total:8h
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 12 | 6.5 | high | group_total:31h
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | none | nan
PRE FAB |  | .355 | L/O Top, B&C Holes | 4 | 5.7 | high | group_total:31h
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 4 | 5.7 | high | group_total:31h
PRE FAB |  | .366 | Weld Nozzles - Top Head | 8 | 11.2 | high | group_total:31h
PRE FAB |  | .370 | I&W Repads -Top | 7 | 2.1 | high | group_total:31h
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 8 | 10 | high | group_total:10h
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 12 | 11.5 | high | group_total:58h
FIT |  | .605 | Tack Shell Courses | 3 | 6.7 | high | group_total:58h
FIT |  | .610 | Weld Inside Round Seams | 3 | 7.9 | high | group_total:58h
FIT |  | .615 | Install Rim Angle | 4 | 2.8 | high | group_total:58h
FIT |  | .616 | Weld Rim Angle | 6 | 3.1 | high | group_total:58h
FIT |  | .620 | L/O Shell, B&C Holes | 4 | 2.6 | high | group_total:58h
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | none | nan
FIT |  | .640 | Fit Top to Shell | 9 | 6.9 | high | group_total:58h
FIT |  | .645 | Weld all Outside Seams | 4 | 16 | high | group_total:58h
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2 | 2 | none | nan
Install Nozzles and Externals
FIT |  | .717 | Install Lift Lugs on Shl | 3 | 1.9 | high | group_total:29h
FIT |  | .725 | Set Nozzles in Shell | 6 | 8.1 | high | group_total:29h
FIT |  | .726 | Weld Shell Nozz & M/Ws | 25 | 16.1 | high | group_total:29h
FINISHING |  | .765 | Install Name Tag | 1 | 1 | high | group_total:29h
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1.8 | high | group_total:29h
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | none | nan
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2 | 4.2 | high | group_total:41h
FINISHING |  | .910 | Test Tank | 12 | 20.3 | high | group_total:41h
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | none | nan
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | none | nan
MOVE TANK |  | .802 | Move to Paint Area | 2 | 1.1 | high | group_total:41h
INSPECTION |  | .QC9 | QC Inspection - Sandblast |  |  | none | nan
INSPECTION |  | .QC90 | QC Inspection - Paint |  |  | none | nan
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 2 | 6.7 | high | group_total:41h
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | none | nan
SHIPPING |  | .960 | Load on Truck | 4 | 8.5 | high | group_total:41h
|  |  | Total Predicted Hours |  | 247.1

## Build Plan - No Hours
Job #: | 25-080 | Description: | DAF FILTRATE TANK |  | Total Est Hours: | 236
Similar jobs used: | 25-084, 23-094, 23-099, 23-095, 23-098
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 6
PRE FAB |  | .105 | Build Nozzles-Weld | 9
PRE FAB |  | .107 | Build Repads for Nozzles | 5
PRE FAB |  | .115 | Make Manway Parts | 2
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2
PRE FAB |  | .125 | Roll Manway Neck | 3
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 6
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 3
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 15
PRE FAB |  | .156 | Clean & Prep Parts | 15
Supports
PRE FAB |  | .165 | Build Supports | 3
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1
PRE FAB |  | .205 | Roll Rim Angle | 3
Shells
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 5
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 10
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 12
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 4
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 4
PRE FAB |  | .366 | Weld Nozzles - Top Head | 8
PRE FAB |  | .370 | I&W Repads -Top | 7
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 8
Build Main Tank and Install Internals
FIT |  | .600 | Fit Bottom Head to Shell | 12
FIT |  | .605 | Tack Shell Courses | 3
FIT |  | .610 | Weld Inside Round Seams | 3
FIT |  | .615 | Install Rim Angle | 4
FIT |  | .616 | Weld Rim Angle | 6
FIT |  | .620 | L/O Shell, B&C Holes | 4
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 9
FIT |  | .645 | Weld all Outside Seams | 4
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2
Install Nozzles and Externals
FIT |  | .717 | Install Lift Lugs on Shl | 3
FIT |  | .725 | Set Nozzles in Shell | 6
FIT |  | .726 | Weld Shell Nozz & M/Ws | 25
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2
FINISHING |  | .910 | Test Tank | 12
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
MOVE TANK |  | .802 | Move to Paint Area | 2
INSPECTION |  | .QC9 | QC Inspection - Sandblast
INSPECTION |  | .QC90 | QC Inspection - Paint
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 2
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 4
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-084
23-094
23-099
23-095
23-098
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | none | nan | nan
.QC1 | UT Top & Bottom Heads | 0 | none | nan | nan
.100 | Cut Nozzle Pipe and Clean | 6.2 | high | group_total:30h | model(NOZZLES)
.105 | Build Nozzles-Weld | 13.1 | high | group_total:30h | model(NOZZLES)
.107 | Build Repads for Nozzles | 2 | high | group_total:30h | model(NOZZLES)
.115 | Make Manway Parts | 1.2 | high | group_total:30h | model(NOZZLES)
.120 | Brn MW Neck, Clean, Bevel | 1 | high | group_total:30h | model(NOZZLES)
.125 | Roll Manway Neck | 1.4 | high | group_total:30h | model(NOZZLES)
.130 | S/U Weld MW Flg, Neck Sem | 3.1 | high | group_total:30h | model(NOZZLES)
.135 | Bld Davit Arm Aby Cover | 2.5 | high | group_total:30h | model(NOZZLES)
.155 | Cut Parts on Burn Table | 19.1 | high | group_total:24h | model(CUT_PREP)
.156 | Clean & Prep Parts | 4.4 | high | group_total:24h | model(CUT_PREP)
.165 | Build Supports | 5 | high | group_total:5h | model(SUPPORTS)
.200 | Bld Lift Lugs, Grd Lugs | 5.2 | high | group_total:10h | model(MISC_PARTS)
.205 | Roll Rim Angle | 4.7 | high | group_total:10h | model(MISC_PARTS)
.QC3 | UT Shells | 0 | none | nan | nan
.305 | BI, SQ, T&C Shells | 4.1 | high | group_total:8h | model(SHELLS)
.315 | Roll Shell, Tack-Weld I/S | 3.7 | high | group_total:8h | model(SHELLS)
.350 | Build Top Head/Cone | 6.5 | high | group_total:31h | model(TOP_HEAD)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.355 | L/O Top, B&C Holes | 5.7 | high | group_total:31h | model(TOP_HEAD)
.365 | Set Nozzles & Lugs - Top | 5.7 | high | group_total:31h | model(TOP_HEAD)
.366 | Weld Nozzles - Top Head | 11.2 | high | group_total:31h | model(TOP_HEAD)
.370 | I&W Repads -Top | 2.1 | high | group_total:31h | model(TOP_HEAD)
.450 | Build Bottom Head/Cone | 10 | high | group_total:10h | model(BTM_HEAD)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.600 | Fit Bottom Head to Shell | 11.5 | high | group_total:58h | model(FIT_ASSEMBLY)
.605 | Tack Shell Courses | 6.7 | high | group_total:58h | model(FIT_ASSEMBLY)
.610 | Weld Inside Round Seams | 7.9 | high | group_total:58h | model(FIT_ASSEMBLY)
.615 | Install Rim Angle | 2.8 | high | group_total:58h | model(FIT_ASSEMBLY)
.616 | Weld Rim Angle | 3.1 | high | group_total:58h | model(FIT_ASSEMBLY)
.620 | L/O Shell, B&C Holes | 2.6 | high | group_total:58h | model(FIT_ASSEMBLY)
.QC5 | QC Inspection - Internal | 0 | none | nan | nan
.640 | Fit Top to Shell | 6.9 | high | group_total:58h | model(FIT_ASSEMBLY)
.645 | Weld all Outside Seams | 16 | high | group_total:58h | model(FIT_ASSEMBLY)
.800 | Move Tank to Detail Rolls | 2 | none | nan | nan
.717 | Install Lift Lugs on Shl | 1.9 | high | group_total:29h | model(DETAIL_EXT)
.725 | Set Nozzles in Shell | 8.1 | high | group_total:29h | model(DETAIL_EXT)
.726 | Weld Shell Nozz & M/Ws | 16.1 | high | group_total:29h | model(DETAIL_EXT)
.765 | Install Name Tag | 1 | high | group_total:29h | model(DETAIL_EXT)
.770 | Inspect Tank, Make Repair | 1.8 | high | group_total:29h | model(DETAIL_EXT)
.QC6 | QC Inspection - Fab | 0 | none | nan | nan
.801 | Move to Shop Test Area | 4.2 | high | group_total:41h | model(TEST_CLEAN)
.910 | Test Tank | 20.3 | high | group_total:41h | model(TEST_CLEAN)
.QC7 | QC Inspection - Test | 0 | none | nan | nan
.OI3 | ASME Inspection Test | 0 | none | nan | nan
.802 | Move to Paint Area | 1.1 | high | group_total:41h | model(TEST_CLEAN)
.QC9 | QC Inspection - Sandblast | 0 | none | nan | nan
.QC90 | QC Inspection - Paint | 0 | none | nan | nan
.940 | Prepare Tank for Shipment | 6.7 | high | group_total:41h | model(TEST_CLEAN)
.QC95 | QC Inspection - Final & L | 0 | none | nan | nan
.960 | Load on Truck | 8.5 | high | group_total:41h | model(TEST_CLEAN)