## Build Plan w Hours
Job #: | 25-085 | Description: | HIGH FBCR TANK (316 OPTION) |  | Total Est Hours: | 403
Similar jobs used: | 25-039, 25-025, 25-037, 23-098, 25-026
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4 | 4.4 | high | ratio=1.10 (1.08-1.20)
PRE FAB |  | .105 | Build Nozzles-Weld | 6 | 8.2 | high | ratio=1.36 (0.29-1.82)
PRE FAB |  | .107 | Build Repads for Nozzles | 9 | 9 | medium | ratio=1.00 (n=1)
PRE FAB |  | .115 | Make Manway Parts | 2 | 2 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2 | 2 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .125 | Roll Manway Neck | 2 | 2 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 4 | 6 | high | ratio=1.50 (1.00-2.00)
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 4 | 8 | high | ratio=2.00 (1.00-2.00)
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 40 | 42.5 | high | ratio=1.06 (0.86-1.50)
PRE FAB |  | .156 | Clean & Prep Parts | 20 | 18.3 | high | ratio=0.92 (0.79-1.10)
Supports
PRE FAB |  | .165 | Build Supports | 8 | 6 | high | ratio=0.75 (0.75-1.10)
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 2 | high | ratio=1.00 (0.50-1.00)
PRE FAB |  | .205 | Roll Rim Angle | 3 | 3 | high | ratio=1.00 (1.00-1.00)
Shells
INSPECTION |  | .QC3 | UT Shells |  |  | skip | 0h estimate
PRE FAB |  | .305 | BI, SQ, T&C Shells | 28 | 21 | high | ratio=0.75 (0.67-1.09)
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 20 | 21.4 | high | ratio=1.07 (0.62-1.36)
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 12 | 8.3 | high | ratio=0.69 (0.56-1.20)
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | skip | 0h estimate
PRE FAB |  | .355 | L/O Top, B&C Holes | 2 | 5 | high | ratio=2.50 (1.00-5.00)
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 4 | 3.3 | high | ratio=0.83 (0.50-1.17)
PRE FAB |  | .366 | Weld Nozzles - Top Head | 8 | 7.5 | high | ratio=0.94 (0.58-1.19)
PRE FAB |  | .370 | I&W Repads -Top | 6 | 3 | high | ratio=0.50 (0.50-0.67)
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 8 | 6.7 | high | ratio=0.83 (0.83-0.88)
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | skip | 0h estimate
FIT |  | .600 | Fit Bottom Head to Shell | 15 | 13.2 | high | ratio=0.88 (0.38-1.15)
FIT |  | .605 | Tack Shell Courses | 12 | 16 | high | ratio=1.33 (0.67-1.67)
FIT |  | .610 | Weld Inside Round Seams | 10 | 11.7 | high | ratio=1.17 (0.33-2.00)
FIT |  | .615 | Install Rim Angle | 5 | 6.9 | high | ratio=1.38 (0.75-2.40)
FIT |  | .616 | Weld Rim Angle | 6 | 8.2 | high | ratio=1.38 (1.12-1.60)
FIT |  | .620 | L/O Shell, B&C Holes | 1 | 1 | high | ratio=1.00 (0.83-1.00)
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
FIT |  | .640 | Fit Top to Shell | 9 | 9 | high | ratio=1.00 (0.62-1.33)
FIT |  | .645 | Weld all Outside Seams | 14 | 14 | high | ratio=1.00 (0.64-1.43)
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2 | 3 | high | ratio=1.50 (0.50-3.25)
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 39 | 27.3 | medium | ratio=0.70 (n=1)
FIT |  | .717 | Install Lift Lugs on Shl | 5 | 3.5 | medium | ratio=0.71 (n=2)
FIT |  | .725 | Set Nozzles in Shell | 5 | 2.2 | high | ratio=0.43 (0.36-0.73)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 16 | 8.7 | high | ratio=0.55 (0.33-0.72)
FIT |  | .730 | Add Repads-Weld | 6 | 4.2 | high | ratio=0.71 (0.50-0.75)
INSPECTION |  | .QC51 | UT Components |  |  | skip | 0h estimate
FINISHING |  | .765 | Install Name Tag | 1 | 1 | high | ratio=1.00 (0.50-1.00)
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 0.9 | high | ratio=0.88 (0.50-1.00)
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
INSPECTION |  | .OI4 | Customer Inspection |  |  | skip | 0h estimate
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2 | 6 | high | ratio=3.00 (0.50-4.12)
FINISHING |  | .910 | Test Tank | 12 | 15 | high | ratio=1.25 (0.90-1.90)
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | skip | 0h estimate
FINISHING |  | .920 | Clean Tank Complete | 40 | 45 | high | ratio=1.12 (0.50-1.60)
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | skip | 0h estimate
INSPECTION |  | .QC9 | QC Inspection - Sandblast |  |  | skip | 0h estimate
INSPECTION |  | .QC90 | QC Inspection - Paint |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 2 | 2.5 | medium | ratio=1.25 (n=2)
FINISHING |  | .950 | Check BOM, Pack Parts | 2 | 2 | low | wc_ratio=1.00
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 4 | 7 | high | ratio=1.75 (0.33-2.25)
|  |  | Total Predicted Hours |  | 397.9

## Build Plan - No Hours
Job #: | 25-085 | Description: | HIGH FBCR TANK (316 OPTION) |  | Total Est Hours: | 403
Similar jobs used: | 25-039, 25-025, 25-037, 23-098, 25-026
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4
PRE FAB |  | .105 | Build Nozzles-Weld | 6
PRE FAB |  | .107 | Build Repads for Nozzles | 9
PRE FAB |  | .115 | Make Manway Parts | 2
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 2
PRE FAB |  | .125 | Roll Manway Neck | 2
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 4
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 4
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 40
PRE FAB |  | .156 | Clean & Prep Parts | 20
Supports
PRE FAB |  | .165 | Build Supports | 8
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .205 | Roll Rim Angle | 3
Shells
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 28
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 20
Top Head
PRE FAB |  | .350 | Build Top Head/Cone | 12
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 2
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 4
PRE FAB |  | .366 | Weld Nozzles - Top Head | 8
PRE FAB |  | .370 | I&W Repads -Top | 6
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 8
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 15
FIT |  | .605 | Tack Shell Courses | 12
FIT |  | .610 | Weld Inside Round Seams | 10
FIT |  | .615 | Install Rim Angle | 5
FIT |  | .616 | Weld Rim Angle | 6
FIT |  | .620 | L/O Shell, B&C Holes | 1
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 9
FIT |  | .645 | Weld all Outside Seams | 14
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 39
FIT |  | .717 | Install Lift Lugs on Shl | 5
FIT |  | .725 | Set Nozzles in Shell | 5
FIT |  | .726 | Weld Shell Nozz & M/Ws | 16
FIT |  | .730 | Add Repads-Weld | 6
INSPECTION |  | .QC51 | UT Components
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI4 | Customer Inspection
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2
FINISHING |  | .910 | Test Tank | 12
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 40
INSPECTION |  | .QC8 | QC Inspection - Clean
INSPECTION |  | .QC9 | QC Inspection - Sandblast
INSPECTION |  | .QC90 | QC Inspection - Paint
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 2
FINISHING |  | .950 | Check BOM, Pack Parts | 2
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 4
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-039
25-025
25-037
23-098
25-026
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 4.4 | high | ratio=1.10 (1.08-1.20) | 25-039, 25-037, 25-026, 25-025
.105 | Build Nozzles-Weld | 8.2 | high | ratio=1.36 (0.29-1.82) | 25-039, 25-037, 25-026, 25-025, 23-098
.107 | Build Repads for Nozzles | 9 | medium | ratio=1.00 (n=1) | 25-039
.115 | Make Manway Parts | 2 | high | ratio=1.00 (1.00-1.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.120 | Brn MW Neck, Clean, Bevel | 2 | high | ratio=1.00 (1.00-1.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.125 | Roll Manway Neck | 2 | high | ratio=1.00 (1.00-1.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.130 | S/U Weld MW Flg, Neck Sem | 6 | high | ratio=1.50 (1.00-2.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.135 | Bld Davit Arm Aby Cover | 8 | high | ratio=2.00 (1.00-2.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.155 | Cut Parts on Burn Table | 42.5 | high | ratio=1.06 (0.86-1.50) | 25-039, 25-037, 25-026, 25-025, 23-098
.156 | Clean & Prep Parts | 18.3 | high | ratio=0.92 (0.79-1.10) | 25-039, 25-037, 25-026, 25-025
.165 | Build Supports | 6 | high | ratio=0.75 (0.75-1.10) | 25-039, 25-037, 25-026, 25-025, 23-098
.200 | Bld Lift Lugs, Grd Lugs | 2 | high | ratio=1.00 (0.50-1.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.205 | Roll Rim Angle | 3 | high | ratio=1.00 (1.00-1.00) | 25-037, 25-026, 25-025, 23-098
.QC3 | UT Shells | 0 | skip | 0h estimate
.305 | BI, SQ, T&C Shells | 21 | high | ratio=0.75 (0.67-1.09) | 25-039, 25-037, 25-026, 25-025, 23-098
.315 | Roll Shell, Tack-Weld I/S | 21.4 | high | ratio=1.07 (0.62-1.36) | 25-039, 25-037, 25-026, 25-025, 23-098
.350 | Build Top Head/Cone | 8.3 | high | ratio=0.69 (0.56-1.20) | 25-037, 25-026, 25-025, 23-098
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.355 | L/O Top, B&C Holes | 5 | high | ratio=2.50 (1.00-5.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.365 | Set Nozzles & Lugs - Top | 3.3 | high | ratio=0.83 (0.50-1.17) | 25-039, 25-037, 25-026, 25-025, 23-098
.366 | Weld Nozzles - Top Head | 7.5 | high | ratio=0.94 (0.58-1.19) | 25-039, 25-037, 25-026, 25-025, 23-098
.370 | I&W Repads -Top | 3 | high | ratio=0.50 (0.50-0.67) | 25-039, 25-037, 25-026, 25-025
.450 | Build Bottom Head/Cone | 6.7 | high | ratio=0.83 (0.83-0.88) | 25-037, 25-026, 25-025, 23-098
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.OI1 | ASME Hold Point | 0 | skip | 0h estimate
.600 | Fit Bottom Head to Shell | 13.2 | high | ratio=0.88 (0.38-1.15) | 25-039, 25-037, 25-026, 25-025, 23-098
.605 | Tack Shell Courses | 16 | high | ratio=1.33 (0.67-1.67) | 25-039, 25-037, 25-025
.610 | Weld Inside Round Seams | 11.7 | high | ratio=1.17 (0.33-2.00) | 25-039, 25-037, 25-026, 25-025
.615 | Install Rim Angle | 6.9 | high | ratio=1.38 (0.75-2.40) | 25-037, 25-026, 25-025, 23-098
.616 | Weld Rim Angle | 8.2 | high | ratio=1.38 (1.12-1.60) | 25-037, 25-026, 25-025, 23-098
.620 | L/O Shell, B&C Holes | 1 | high | ratio=1.00 (0.83-1.00) | 25-039, 25-037, 25-026
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.640 | Fit Top to Shell | 9 | high | ratio=1.00 (0.62-1.33) | 25-039, 25-037, 25-026, 25-025, 23-098
.645 | Weld all Outside Seams | 14 | high | ratio=1.00 (0.64-1.43) | 25-039, 25-037, 25-026, 25-025, 23-098
.800 | Move Tank to Detail Rolls | 3 | high | ratio=1.50 (0.50-3.25) | 25-039, 25-037, 25-026, 25-025, 23-098
.715 | Install Insul/Vac Rings | 27.3 | medium | ratio=0.70 (n=1) | 23-098
.717 | Install Lift Lugs on Shl | 3.5 | medium | ratio=0.71 (n=2) | 25-037, 23-098
.725 | Set Nozzles in Shell | 2.2 | high | ratio=0.43 (0.36-0.73) | 25-039, 25-037, 25-026, 25-025, 23-098
.726 | Weld Shell Nozz & M/Ws | 8.7 | high | ratio=0.55 (0.33-0.72) | 25-039, 25-037, 25-026, 25-025, 23-098
.730 | Add Repads-Weld | 4.2 | high | ratio=0.71 (0.50-0.75) | 25-039, 25-026, 25-025, 23-098
.QC51 | UT Components | 0 | skip | 0h estimate
.765 | Install Name Tag | 1 | high | ratio=1.00 (0.50-1.00) | 25-039, 25-037, 25-026, 25-025, 23-098
.770 | Inspect Tank, Make Repair | 0.9 | high | ratio=0.88 (0.50-1.00) | 25-037, 25-026, 25-025, 23-098
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.OI4 | Customer Inspection | 0 | skip | 0h estimate
.OI2 | ASME Inspection Internal | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 6 | high | ratio=3.00 (0.50-4.12) | 25-039, 25-037, 25-026, 25-025, 23-098
.910 | Test Tank | 15 | high | ratio=1.25 (0.90-1.90) | 25-039, 25-037, 25-026, 25-025, 23-098
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.OI3 | ASME Inspection Test | 0 | skip | 0h estimate
.920 | Clean Tank Complete | 45 | high | ratio=1.12 (0.50-1.60) | 25-039, 25-037, 25-026, 25-025, 23-098
.QC8 | QC Inspection - Clean | 0 | skip | 0h estimate
.QC9 | QC Inspection - Sandblast | 0 | skip | 0h estimate
.QC90 | QC Inspection - Paint | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 2.5 | medium | ratio=1.25 (n=2) | 25-039, 23-098
.950 | Check BOM, Pack Parts | 2 | low | wc_ratio=1.00 | wc_avg
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 7 | high | ratio=1.75 (0.33-2.25) | 25-039, 25-026, 25-025, 23-098