## Build Plan w Hours
Job #: | 25-087 | Description: | WASTE WATER TANK |  | Total Est Hours: | 128
Similar jobs used: | 25-039, 24-006, 25-042, 25-088, 25-085
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 3 | 3.2 | high | ratio=1.08 (0.88-1.50)
PRE FAB |  | .105 | Build Nozzles-Weld | 7 | 8.2 | high | ratio=1.17 (0.29-2.00)
PRE FAB |  | .107 | Build Repads for Nozzles | 1 | 0.8 | medium | ratio=0.78 (n=2)
PRE FAB |  | .115 | Make Manway Parts | 1 | 1 | medium | ratio=1.00 (n=2)
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1 | 1 | medium | ratio=1.00 (n=2)
PRE FAB |  | .125 | Roll Manway Neck | 1 | 1.5 | medium | ratio=1.50 (n=2)
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 2 | 2 | medium | ratio=1.00 (n=2)
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 2 | 2.4 | medium | ratio=1.19 (n=2)
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 7 | 7 | high | ratio=1.00 (0.60-1.10)
PRE FAB |  | .156 | Clean & Prep Parts | 3 | 2.2 | high | ratio=0.75 (0.47-1.10)
Supports
PRE FAB |  | .165 | Build Supports | 5 | 4.2 | high | ratio=0.83 (0.58-1.10)
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1 | 1 | high | ratio=1.00 (1.00-1.00)
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 1 | 1.2 | medium | ratio=1.25 (n=2)
INSPECTION |  | .QC3 | UT Shells |  |  | skip | 0h estimate
PRE FAB |  | .305 | BI, SQ, T&C Shells | 2 | 2 | high | ratio=1.00 (0.75-1.50)
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 5 | 3.7 | high | ratio=0.73 (0.62-1.00)
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | skip | 0h estimate
PRE FAB |  | .355 | L/O Top, B&C Holes | 2 | 3 | high | ratio=1.50 (1.00-3.00)
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2 | 2 | high | ratio=1.00 (0.50-1.33)
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6 | 4.9 | high | ratio=0.81 (0.42-1.00)
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 2 | 2.5 | high | ratio=1.25 (1.00-3.00)
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 1 | high | ratio=1.00 (1.00-1.00)
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 3 | 3 | high | ratio=1.00 (0.67-1.00)
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | skip | 0h estimate
FIT |  | .600 | Fit Bottom Head to Shell | 4 | 3.6 | high | ratio=0.90 (0.38-1.00)
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
FIT |  | .640 | Fit Top to Shell | 3 | 3 | high | ratio=1.00 (0.75-2.25)
FIT |  | .641 | Weld top to shell | 5 | 2.9 | medium | ratio=0.57 (n=1)
FIT |  | .645 | Weld all Outside Seams | 5 | 6.3 | high | ratio=1.27 (1.23-1.60)
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1 | 1.2 | high | ratio=1.25 (1.00-3.00)
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 7 | 3.8 | medium | ratio=0.54 (n=2)
FIT |  | .720 | Install Support Parts | 6 | 5 | high | ratio=0.83 (0.40-0.88)
FIT |  | .725 | Set Nozzles in Shell | 3 | 3 | high | ratio=1.00 (0.36-1.33)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 10 | 5.8 | high | ratio=0.58 (0.40-1.00)
FIT |  | .730 | Add Repads-Weld | 3 | 2.3 | medium | ratio=0.77 (n=2)
FINISHING |  | .765 | Install Name Tag | 1 | 1 | high | ratio=1.00 (0.25-2.00)
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 0.9 | low | wc_ratio=0.88
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1 | 1 | medium | ratio=1.00 (n=2)
FINISHING |  | .910 | Test Tank | 8 | 12 | high | ratio=1.50 (0.50-1.73)
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | skip | 0h estimate
FINISHING |  | .920 | Clean Tank Complete | 10 | 10 | high | ratio=1.00 (0.50-1.71)
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1 | 2 | high | ratio=2.00 (1.00-2.50)
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 1 | 3.1 | medium | ratio=3.12 (n=2)
|  |  | Total Predicted Hours |  | 124.7

## Build Plan - No Hours
Job #: | 25-087 | Description: | WASTE WATER TANK |  | Total Est Hours: | 128
Similar jobs used: | 25-039, 24-006, 25-042, 25-088, 25-085
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 3
PRE FAB |  | .105 | Build Nozzles-Weld | 7
PRE FAB |  | .107 | Build Repads for Nozzles | 1
PRE FAB |  | .115 | Make Manway Parts | 1
PRE FAB |  | .120 | Brn MW Neck, Clean, Bevel | 1
PRE FAB |  | .125 | Roll Manway Neck | 1
PRE FAB |  | .130 | S/U Weld MW Flg, Neck Sem | 2
PRE FAB |  | .135 | Bld Davit Arm Aby Cover | 2
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 7
PRE FAB |  | .156 | Clean & Prep Parts | 3
Supports
PRE FAB |  | .165 | Build Supports | 5
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 1
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 2
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 5
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 2
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 2
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 2
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 3
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 4
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 3
FIT |  | .641 | Weld top to shell | 5
FIT |  | .645 | Weld all Outside Seams | 5
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 7
FIT |  | .720 | Install Support Parts | 6
FIT |  | .725 | Set Nozzles in Shell | 3
FIT |  | .726 | Weld Shell Nozz & M/Ws | 10
FIT |  | .730 | Add Repads-Weld | 3
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1
FINISHING |  | .910 | Test Tank | 8
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 10
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 1
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-039
24-006
25-042
25-088
25-085
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 3.2 | high | ratio=1.08 (0.88-1.50) | 25-088, 25-085, 25-042, 25-039, 24-006
.105 | Build Nozzles-Weld | 8.2 | high | ratio=1.17 (0.29-2.00) | 25-088, 25-085, 25-042, 25-039, 24-006
.107 | Build Repads for Nozzles | 0.8 | medium | ratio=0.78 (n=2) | 25-085, 25-039
.115 | Make Manway Parts | 1 | medium | ratio=1.00 (n=2) | 25-085, 25-039
.120 | Brn MW Neck, Clean, Bevel | 1 | medium | ratio=1.00 (n=2) | 25-085, 25-039
.125 | Roll Manway Neck | 1.5 | medium | ratio=1.50 (n=2) | 25-085, 25-039
.130 | S/U Weld MW Flg, Neck Sem | 2 | medium | ratio=1.00 (n=2) | 25-085, 25-039
.135 | Bld Davit Arm Aby Cover | 2.4 | medium | ratio=1.19 (n=2) | 25-085, 25-039
.155 | Cut Parts on Burn Table | 7 | high | ratio=1.00 (0.60-1.10) | 25-088, 25-085, 25-042, 25-039, 24-006
.156 | Clean & Prep Parts | 2.2 | high | ratio=0.75 (0.47-1.10) | 25-088, 25-085, 25-042, 25-039
.165 | Build Supports | 4.2 | high | ratio=0.83 (0.58-1.10) | 25-088, 25-085, 25-042, 25-039, 24-006
.200 | Bld Lift Lugs, Grd Lugs | 1 | high | ratio=1.00 (1.00-1.00) | 25-088, 25-085, 25-042, 25-039
.300 | Wrap Top & Bottom Heads | 1.2 | medium | ratio=1.25 (n=2) | 25-042, 25-039
.QC3 | UT Shells | 0 | skip | 0h estimate
.305 | BI, SQ, T&C Shells | 2 | high | ratio=1.00 (0.75-1.50) | 25-085, 25-042, 25-039, 24-006
.315 | Roll Shell, Tack-Weld I/S | 3.7 | high | ratio=0.73 (0.62-1.00) | 25-085, 25-042, 25-039, 24-006
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.355 | L/O Top, B&C Holes | 3 | high | ratio=1.50 (1.00-3.00) | 25-088, 25-085, 25-042, 25-039, 24-006
.365 | Set Nozzles & Lugs - Top | 2 | high | ratio=1.00 (0.50-1.33) | 25-088, 25-085, 25-042, 25-039, 24-006
.366 | Weld Nozzles - Top Head | 4.9 | high | ratio=0.81 (0.42-1.00) | 25-088, 25-085, 25-042, 25-039, 24-006
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.455 | L/O Bottom, B&C Holes | 2.5 | high | ratio=1.25 (1.00-3.00) | 25-088, 25-042, 25-039, 24-006
.465 | Set Nozzles - Bottom Head | 1 | high | ratio=1.00 (1.00-1.00) | 25-088, 25-042, 25-039, 24-006
.466 | Weld Nozzles - Bot. Head | 3 | high | ratio=1.00 (0.67-1.00) | 25-088, 25-042, 25-039, 24-006
.OI1 | ASME Hold Point | 0 | skip | 0h estimate
.600 | Fit Bottom Head to Shell | 3.6 | high | ratio=0.90 (0.38-1.00) | 25-088, 25-085, 25-042, 25-039, 24-006
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.640 | Fit Top to Shell | 3 | high | ratio=1.00 (0.75-2.25) | 25-088, 25-085, 25-042, 25-039, 24-006
.641 | Weld top to shell | 2.9 | medium | ratio=0.57 (n=1) | 25-039
.645 | Weld all Outside Seams | 6.3 | high | ratio=1.27 (1.23-1.60) | 25-085, 25-042, 25-039, 24-006
.800 | Move Tank to Detail Rolls | 1.2 | high | ratio=1.25 (1.00-3.00) | 25-085, 25-042, 25-039, 24-006
.715 | Install Insul/Vac Rings | 3.8 | medium | ratio=0.54 (n=2) | 25-085, 24-006
.720 | Install Support Parts | 5 | high | ratio=0.83 (0.40-0.88) | 25-088, 25-042, 25-039, 24-006
.725 | Set Nozzles in Shell | 3 | high | ratio=1.00 (0.36-1.33) | 25-088, 25-085, 25-042, 25-039
.726 | Weld Shell Nozz & M/Ws | 5.8 | high | ratio=0.58 (0.40-1.00) | 25-088, 25-085, 25-042, 25-039
.730 | Add Repads-Weld | 2.3 | medium | ratio=0.77 (n=2) | 25-085, 25-039
.765 | Install Name Tag | 1 | high | ratio=1.00 (0.25-2.00) | 25-088, 25-085, 25-042, 25-039, 24-006
.770 | Inspect Tank, Make Repair | 0.9 | low | wc_ratio=0.88 | wc_avg
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.OI2 | ASME Inspection Internal | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 1 | medium | ratio=1.00 (n=2) | 25-042, 25-039
.910 | Test Tank | 12 | high | ratio=1.50 (0.50-1.73) | 25-088, 25-085, 25-042, 25-039, 24-006
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.OI3 | ASME Inspection Test | 0 | skip | 0h estimate
.920 | Clean Tank Complete | 10 | high | ratio=1.00 (0.50-1.71) | 25-088, 25-085, 25-042, 25-039, 24-006
.QC8 | QC Inspection - Clean | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 2 | high | ratio=2.00 (1.00-2.50) | 25-088, 25-085, 25-042, 25-039, 24-006
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 3.1 | medium | ratio=3.12 (n=2) | 25-085, 25-039