## Build Plan w Hours
Job #: | 25-099 | Description: | CONE BOTTOM W/COIL |  | Total Est Hours: | 137
Similar jobs used: | 25-036, 25-034, 25-035, 25-017, 25-016
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | skip | 0h estimate
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | skip | 0h estimate
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 1 | 1.2 | high | ratio=1.17 (0.50-1.20)
PRE FAB |  | .105 | Build Nozzles-Weld | 2 | 3.1 | high | ratio=1.54 (0.20-2.33)
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 3 | 3.9 | high | ratio=1.30 (0.65-2.38)
PRE FAB |  | .156 | Clean & Prep Parts | 2 | 1.5 | high | ratio=0.75 (0.45-1.62)
Misc. Parts
PRE FAB |  | .250 | Roll Pipe-Internal Coil | 12 | 12 | low | wc_ratio=1.00
PRE FAB |  | .261 | Misc Fabrication | 8 | 9.6 | medium | ratio=1.20 (n=1)
Shells
INSPECTION |  | .QC3 | UT Shells |  |  | skip | 0h estimate
PRE FAB |  | .305 | BI, SQ, T&C Shells | 2 | 1.5 | high | ratio=0.75 (0.42-1.12)
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 6 | 5.2 | high | ratio=0.88 (0.67-1.75)
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | skip | 0h estimate
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 40 | 26.7 | high | ratio=0.67 (0.20-1.00)
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 1 | low | wc_ratio=1.00
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2 | 2 | low | wc_ratio=1.00
Internal Coils
PRE FAB |  | .580 | Fab Internal Coil Support | 5 | 5 | low | wc_ratio=1.00
PRE FAB |  | .590 | Fab Internal Coil | 10 | 10 | low | wc_ratio=1.00
Build Main Tank and Install Internals
FIT |  | .635 | Install Internal Coil/Spt | 15 | 17.5 | low | wc_ratio=1.17
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | skip | 0h estimate
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2 | 3.5 | high | ratio=1.75 (1.50-5.00)
Install Nozzles and Externals
FIT |  | .725 | Set Nozzles in Shell | 3 | 3.5 | high | ratio=1.17 (0.81-2.29)
FIT |  | .726 | Weld Shell Nozz & M/Ws | 4 | 4.5 | high | ratio=1.12 (0.71-1.96)
Inspect and Repair
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | skip | 0h estimate
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2 | 4 | high | ratio=2.00 (0.50-2.50)
FINISHING |  | .900 | Dye Pen Test | 5 | 6.4 | low | wc_ratio=1.28
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | skip | 0h estimate
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | skip | 0h estimate
FINISHING |  | .920 | Clean Tank Complete | 8 | 10.1 | high | ratio=1.27 (0.75-1.40)
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | skip | 0h estimate
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1 | 3 | high | ratio=3.00 (2.00-5.00)
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | skip | 0h estimate
SHIPPING |  | .960 | Load on Truck | 3 | 4.5 | high | ratio=1.50 (0.83-5.00)
|  |  | Total Predicted Hours |  | 139.7

## Build Plan - No Hours
Job #: | 25-099 | Description: | CONE BOTTOM W/COIL |  | Total Est Hours: | 137
Similar jobs used: | 25-036, 25-034, 25-035, 25-017, 25-016
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 1
PRE FAB |  | .105 | Build Nozzles-Weld | 2
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 3
PRE FAB |  | .156 | Clean & Prep Parts | 2
Misc. Parts
PRE FAB |  | .250 | Roll Pipe-Internal Coil | 12
PRE FAB |  | .261 | Misc Fabrication | 8
Shells
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 2
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 6
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
Bottom Head
PRE FAB |  | .450 | Build Bottom Head/Cone | 40
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2
Internal Coils
PRE FAB |  | .580 | Fab Internal Coil Support | 5
PRE FAB |  | .590 | Fab Internal Coil | 10
Build Main Tank and Install Internals
FIT |  | .635 | Install Internal Coil/Spt | 15
INSPECTION |  | .QC5 | QC Inspection - Internal
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 2
Install Nozzles and Externals
FIT |  | .725 | Set Nozzles in Shell | 3
FIT |  | .726 | Weld Shell Nozz & M/Ws | 4
Inspect and Repair
INSPECTION |  | .QC6 | QC Inspection - Fab
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2
FINISHING |  | .900 | Dye Pen Test | 5
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 8
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 3
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-036
25-034
25-035
25-017
25-016
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | skip | 0h estimate
.QC1 | UT Top & Bottom Heads | 0 | skip | 0h estimate
.100 | Cut Nozzle Pipe and Clean | 1.2 | high | ratio=1.17 (0.50-1.20) | 25-036, 25-035, 25-034
.105 | Build Nozzles-Weld | 3.1 | high | ratio=1.54 (0.20-2.33) | 25-036, 25-035, 25-034, 25-017, 25-016
.155 | Cut Parts on Burn Table | 3.9 | high | ratio=1.30 (0.65-2.38) | 25-036, 25-035, 25-034, 25-017, 25-016
.156 | Clean & Prep Parts | 1.5 | high | ratio=0.75 (0.45-1.62) | 25-036, 25-034, 25-017, 25-016
.250 | Roll Pipe-Internal Coil | 12 | low | wc_ratio=1.00 | wc_avg
.261 | Misc Fabrication | 9.6 | medium | ratio=1.20 (n=1) | 25-034
.QC3 | UT Shells | 0 | skip | 0h estimate
.305 | BI, SQ, T&C Shells | 1.5 | high | ratio=0.75 (0.42-1.12) | 25-036, 25-035, 25-017, 25-016
.315 | Roll Shell, Tack-Weld I/S | 5.2 | high | ratio=0.88 (0.67-1.75) | 25-036, 25-035, 25-034, 25-017, 25-016
.450 | Build Bottom Head/Cone | 26.7 | high | ratio=0.67 (0.20-1.00) | 25-036, 25-035, 25-034, 25-017, 25-016
.QC4 | QC Inspection -Top/Bot/Co | 0 | skip | 0h estimate
.465 | Set Nozzles - Bottom Head | 1 | low | wc_ratio=1.00 | wc_avg
.466 | Weld Nozzles - Bot. Head | 2 | low | wc_ratio=1.00 | wc_avg
.580 | Fab Internal Coil Support | 5 | low | wc_ratio=1.00 | wc_avg
.590 | Fab Internal Coil | 10 | low | wc_ratio=1.00 | wc_avg
.635 | Install Internal Coil/Spt | 17.5 | low | wc_ratio=1.17 | wc_avg
.QC5 | QC Inspection - Internal | 0 | skip | 0h estimate
.800 | Move Tank to Detail Rolls | 3.5 | high | ratio=1.75 (1.50-5.00) | 25-036, 25-034, 25-017, 25-016
.725 | Set Nozzles in Shell | 3.5 | high | ratio=1.17 (0.81-2.29) | 25-036, 25-035, 25-034, 25-017, 25-016
.726 | Weld Shell Nozz & M/Ws | 4.5 | high | ratio=1.12 (0.71-1.96) | 25-036, 25-035, 25-034, 25-017, 25-016
.900 | Dye Pen Test | 6.4 | low | wc_ratio=1.28 | wc_avg
.QC6 | QC Inspection - Fab | 0 | skip | 0h estimate
.801 | Move to Shop Test Area | 4 | high | ratio=2.00 (0.50-2.50) | 25-036, 25-035, 25-034, 25-017, 25-016
.QC7 | QC Inspection - Test | 0 | skip | 0h estimate
.OI3 | ASME Inspection Test | 0 | skip | 0h estimate
.920 | Clean Tank Complete | 10.1 | high | ratio=1.27 (0.75-1.40) | 25-036, 25-035, 25-034, 25-017, 25-016
.QC8 | QC Inspection - Clean | 0 | skip | 0h estimate
.940 | Prepare Tank for Shipment | 3 | high | ratio=3.00 (2.00-5.00) | 25-036, 25-035, 25-034, 25-016
.QC95 | QC Inspection - Final & L | 0 | skip | 0h estimate
.960 | Load on Truck | 4.5 | high | ratio=1.50 (0.83-5.00) | 25-035, 25-034, 25-017, 25-016