## Schedule
Savannah Tank and Equipment |  |  |  |  | PLAN | ACT |  |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[5 empty] | 2026-03-23 | 2026-03-23 |  |  | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
[5 empty] | 22 | 24 |  |  | 22 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
OVERHEAD | 565 | REL |  |  | 55 | 55 |  |  | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 40 | 55 | 55 | 55 | 40
| DUE | JOB # | QTE | PRE |  |  | WK | WK% | [39 empty] | REQ | BAL | JOB #
SYMS (Lansing) |  | 046-24 | 705 | 296 | 130 | 66 | 362 | 51.35% | 2026-03-30: 100; 2026-04-06: 64 | 164 | 343 | 046-24 | 179
Kimberly Clark 330-TK-33001 | 2026-01-05 | 012-25 | 314 | 311 |  |  | 311 | 99.04% | [39 empty] | 0 | 3 | 012-25 | 3
Kimberly Clark 340-TK-34001 | 2026-01-05 | 013-25 | 513 | 239 |  | 84 | 323 | 62.96% | [39 empty] | 0 | 190 | 013-25 | 190
Nak Kiln | 2025-09-03 | 040-25 | 190 | 276 | 40 | 29 | 305 | 160.5% | [39 empty] | 0 | -115 | 040-25 | -115 | bar: 2026-03-30
Andritz | 2025-08-15 | 053-25 | 244 | 171 |  |  | 171 | 70.08% | 2026-05-18: 50; 2026-05-25: 23 | 73 | 73 | 053-25 | 0
Air Gas | 2025-11-16 | 055-25 | 665 |  | 50 | 9 | 9 | 1.353% | 2026-03-30: 80; 2026-04-06: 80; 2026-04-13: 70; 2026-04-20: 70; 2026-04-27: 60; 2026-05-04: 60; 2026-05-11: 50; 2026-05-18: 45 | 515 | 656 | 055-25 | 141
Nudyne Tank 13 | 2026-04-06 | 068-25 | 520 | 394 | 10 | 8 | 402 | 77.31% | [39 empty] | 0 | 118 | 068-25 | 118 | bar: 2026-04-06
Nudyne Tank 14 | 2026-04-06 | 069-25 | 520 | 283 | 15 | 58 | 341 | 65.58% | [39 empty] | 0 | 179 | 069-25 | 179 | bar: 2026-04-06
Nudyne Tank 15 | 2026-04-20 | 070-25 | 520 | 171 | 50 | 39 | 210 | 40.38% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 42 | 142 | 310 | 070-25 | 168
Nudyne Tank 16 | 2026-04-20 | 071-25 | 520 | 191 | 50 | 52 | 243 | 46.73% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 51 | 151 | 277 | 071-25 | 126
Synthomer | 2026-02-18 | 083-25 | 597 | 205 | 80 | 20 | 225 | 37.69% | 2026-03-30: 80 | 80 | 372 | 083-25 | 292
Atlas | 2025-11-27 | 084-25 | 392 | 514 |  |  | 514 | 131.1% | [39 empty] | 0 | -122 | 084-25 | -122 | bar: 2026-04-13
Symrise | 2026-02-16 | 092-25 | 373 | 110 | 80 | 67 | 177 | 47.45% | 2026-03-30: 90; 2026-04-06: 75; 2026-04-13: 30 | 195 | 196 | 092-25 | 1
Symrise | 2026-02-16 | 093-25 | 373 | 103 | 80 | 64 | 167 | 44.77% | 2026-03-30: 90; 2026-04-06: 75; 2026-04-13: 30 | 195 | 206 | 093-25 | 11
Coastal Tech. | 2026-01-16 | 098-25 | 198 |  |  |  | 0 | 0% | 2026-04-06: 75; 2026-04-13: 68; 2026-04-20: 55 | 198 | 198 | 098-25 | 0
Burke | 2026-02-16 | 099-25 | 162 | 119 |  | 14 | 133 | 82.1% | [39 empty] | 0 | 29 | 099-25 | 29
Harper Love | 2026-04-09 | 101-25 | 781 | 105 | 40 | 46 | 151 | 19.33% | 2026-03-30: 100; 2026-04-06: 120; 2026-04-13: 120; 2026-04-20: 120; 2026-04-27: 100; 2026-05-04: 76 | 636 | 630 | 101-25 | -6
Epic | 2026-04-20 | 109-25 | 99 |  |  |  | 0 | 0% | 2026-03-30: 20; 2026-04-06: 40; 2026-04-13: 24 | 84 | 99 | 109-25 | 15
Epic | 2026-04-20 | 110-25 | 184 |  |  |  | 0 | 0% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 6 | 156 | 184 | 110-25 | 28
Epic | 2026-04-20 | 111-25 | 180 |  |  |  | 0 | 0% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 3 | 153 | 180 | 111-25 | 27
Epic | 2026-04-20 | 113-25 | 189 |  |  |  | 0 | 0% | 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 11 | 161 | 189 | 113-25 | 28
Merrick | 2026-05-07 | 117-25 | 526 | 295 | 100 | 114 | 409 | 77.76% | 2026-03-30: 100; 2026-04-06: 17 | 117 | 117 | 117-25 | 0
Merrick | 2026-05-07 | 118-25 | 526 | 117 | 30 | 119 | 236 | 44.87% | 2026-03-30: 40; 2026-04-06: 50; 2026-04-13: 50; 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 50 | 290 | 290 | 118-25 | 0
Vertiv Tanks |  |  | 2240 | 2009 | 50 | 16 | 2025 | 90.4% | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 150 |  | 11250 | 215 | 0 | -11035
Work Order | [6 empty] | 0 | [40 empty] | 0 | 0 | 0 | 0
|  |  |  | TOT | 805 | 739 | 6352 | PRO | 1250 | 1146 | 935 | 615 | 510 | 486 | 350 | 395 | 323 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 150 | 0 | 14396
|  |  |  | PCT | 66.53% | 55.98% |  | PCT | 103.3% | 77.17% | 62.96% | 41.41% | 34.34% | 32.73% | 23.57% | 26.6% | 29.91% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 27.78% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 27.78% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 20.2% | 27.78% | 20.2% | 20.2% | 10.1% | 0%
|  |  |  | BAL | 405 | 581 |  | BAL | -40 | 339 | 550 | 870 | 975 | 999 | 1135 | 1090 | 757 | 1185 | 1185 | 1185 | 1185 | 1185 | 780 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 780 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 1185 | 780 | 1185 | 1185 | 1335 | 1080
| DUE | JOB # | QTE | PRE | PLAN | ACT | SUB | SUB% | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | REQ | BAL | JOB #
Epic | 2026-04-20 | 102-25 | 290 |  |  |  | 0 | 0% | 2026-04-13: 50; 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 46 | 246 | 290 | 102-25 | 44
Epic | 2026-04-20 | 103-25 | 322 |  |  |  | 0 | 0% | 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 74 | 274 | 322 | 103-25 | 48
Epic | 2026-04-20 | 104-25 | 316 |  |  |  | 0 | 0% | 2026-04-13: 50; 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 69 | 269 | 316 | 104-25 | 47
Epic | 2026-04-20 | 105-25 | 303 |  |  |  | 0 | 0% | 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 50; 2026-06-01: 50; 2026-06-08: 58 | 258 | 303 | 105-25 | 45
Epic | 2026-04-20 | 106-25 | 215 |  |  |  | 0 | 0% | 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 33 | 183 | 215 | 106-25 | 32
Epic | 2026-04-20 | 107-25 | 114 |  |  |  | 0 | 0% | 2026-05-11: 40; 2026-05-18: 40; 2026-05-25: 17 | 97 | 114 | 107-25 | 17
Epic | 2026-04-20 | 108-25 | 86 |  |  |  | 0 | 0% | 2026-05-18: 40; 2026-05-25: 33 | 73 | 86 | 108-25 | 13
Epic | 2026-04-20 | 112-25 | 180 |  |  |  | 0 | 0% | 2026-04-13: 50; 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 3 | 153 | 180 | 112-25 | 27
Epic | 2026-04-20 | 115-25 | 86 |  |  |  | 0 | 0% | 2026-04-27: 50; 2026-05-04: 23 | 73 | 86 | 115-25 | 13
Polynt | 2026-04-30 | 116-25 | 522 |  |  |  | 0 | 0% | 2026-04-20: 25; 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 75; 2026-05-18: 75; 2026-05-25: 75; 2026-06-01: 44 | 444 | 522 | 116-25 | 78
Andritz - Dis Tank | 2026-06-01 | 120-25 | 1842 |  |  |  | 0 | 0% | 2026-04-27: 150; 2026-05-04: 180; 2026-05-11: 180; 2026-05-18: 100; 2026-05-25: 56; 2026-06-01: 180; 2026-06-08: 180; 2026-06-15: 180; 2026-06-22: 180; 2026-06-29: 180 | 1566 | 1842 | 120-25 | 276
Kimberly Clark | 2026-05-19 | 121-25 | 528 |  |  |  | 0 | 0% | 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 49 | 449 | 528 | 121-25 | 79
Kimberly Clark | 2026-05-19 | 122-25 | 466 |  |  |  | 0 | 0% | 2026-05-11: 75; 2026-05-18: 30; 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 40; 2026-06-22: 26 | 396 | 466 | 122-25 | 70
Kimberly Clark | 2026-05-19 | 123-25 | 413 |  |  |  | 0 | 0% | 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 50; 2026-06-22: 76 | 351 | 413 | 123-25 | 62
Synthomer | 2026-06-15 | 356-25 | 461 |  |  |  | 0 | 0% | 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 75; 2026-05-18: 40; 2026-05-25: 25; 2026-06-01: 75; 2026-06-08: 27 | 392 | 461 | 356-25 | 69
Sylvamo | 2026-06-02 | 357-25 | 214 |  |  |  | 0 | 0% | 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 32 | 182 | 214 | 357-25 | 32
Sylvamo | 2026-06-02 | 358-25 | 262 |  |  |  | 0 | 0% | 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 23 | 223 | 262 | 358-25 | 39
SNF | 2026-06-29 | 002-26 | 436 |  |  |  | 0 | 0% | 2026-05-18: 50; 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 21 | 371 | 436 | 002-26 | 65
SNF | 2026-06-29 | 003-26 | 436 |  |  |  | 0 | 0% | 2026-05-18: 75; 2026-05-25: 50; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 21 | 371 | 436 | 003-26 | 65
SNF | 2026-06-29 | 004-26 | 436 |  |  |  | 0 | 0% | 2026-05-18: 75; 2026-05-25: 50; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 21 | 371 | 436 | 004-26 | 65
US Sugar | 2026-06-08 | 005-26 | 203 |  |  |  | 0 | 0% | 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 23 | 173 | 203 | 005-26 | 30
SNF R1 | 2026-06-01 | 014-26 | 429 |  |  |  | 0 | 0% | 2026-04-13: 50; 2026-04-20: 75; 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 75; 2026-05-18: 15 | 365 | 429 | 014-26 | 64
SNF R2 | 2026-06-01 | 015-26 | 393 |  |  |  | 0 | 0% | 2026-06-08: 50; 2026-06-15: 75; 2026-06-22: 75; 2026-06-29: 70; 2026-07-06: 64 | 334 | 393 | 015-26 | 59
SNF R3 | 2026-06-01 | 016-26 | 574 |  |  |  | 0 | 0% | 2026-05-25: 25; 2026-06-01: 100; 2026-06-08: 60; 2026-06-15: 75; 2026-06-22: 75; 2026-06-29: 75; 2026-07-06: 78 | 488 | 574 | 016-26 | 86
SNF CS1 EPI | 2026-07-01 | 017-26 | 553 |  |  |  | 0 | 0% | 2026-05-18: 70; 2026-05-25: 25; 2026-06-01: 100; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 75; 2026-06-29: 50 | 470 | 553 | 017-26 | 83
SNF CS2 EPI | 2026-07-01 | 018-26 | 553 |  |  |  | 0 | 0% | 2026-05-18: 70; 2026-05-25: 25; 2026-06-01: 100; 2026-06-08: 75; 2026-06-15: 75; 2026-06-22: 75; 2026-06-29: 50 | 470 | 553 | 018-26 | 83
US Sugar | 2026-07-20 | 020-26 | 247 |  |  |  | 0 | 0% | 2026-06-15: 50; 2026-06-22: 50; 2026-06-29: 50; 2026-07-06: 50; 2026-07-13: 10 | 210 | 247 | 020-26 | 37
US Sugar | 2026-07-20 | 021-26 | 268 |  |  |  | 0 | 0% | 2026-06-15: 50; 2026-06-22: 50; 2026-06-29: 50; 2026-07-06: 50; 2026-07-13: 28 | 228 | 268 | 021-26 | 40
Andritz | 2026-06-08 | 022-26 | 260 |  |  |  | 0 | 0% | 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: 50; 2026-05-25: 50; 2026-06-01: 21 | 221 | 260 | 022-26 | 39
Polynt | 2026-07-28 | 024-26 | 89 |  |  |  | 0 | 0% | 2026-07-13: 40; 2026-07-20: 36 | 76 | 89 | 024-26 | 13
Blake & Pendleton | 2026-07-21 | 025-26 | 173 |  |  |  | 0 | 0% | 2026-06-08: 50; 2026-06-15: 50; 2026-06-22: 47 | 147 | 173 | 025-26 | 26
Symrise | 2026-08-20 | 030-26 | 373 |  |  |  | 0 | 0% | 2026-07-06: 50; 2026-07-13: 50; 2026-07-20: 50; 2026-07-27: 50; 2026-08-03: 50; 2026-08-10: 50; 2026-08-17: 13 | 313 | 373 | 030-26 | 60
Syensqo | 2026-08-27 | 031-26 | 922 |  |  |  | 0 | 0% | 2026-07-20: 55; 2026-07-27: 75; 2026-08-03: 75; 2026-08-10: 75; 2026-08-17: 75; 2026-08-24: 75; 2026-08-31: 75; 2026-09-07: 75; 2026-09-14: 75; 2026-09-21: 75; 2026-09-28: 54 | 784 | 922 | 031-26 | 138
Kimberly Clark | 2026-08-26 | 032-26 | 310 |  |  |  | 0 | 0% | 2026-07-20: 50; 2026-07-27: 50; 2026-08-03: 50; 2026-08-10: 50; 2026-08-17: 40; 2026-08-24: 23 | 263 | 310 | 032-26 | 47
Kimberly Clark | 2026-08-26 | 033-26 | 81 |  |  |  | 0 | 0% | 2026-08-17: 39; 2026-08-24: 30 | 69 | 81 | 033-26 | 12
IMI |  |  | 603 | [5 empty] | 2026-04-06: PO; 2026-04-13: d1; 2026-04-20: d2; 2026-04-27: d3; 2026-05-04: d4; 2026-05-11: r1; 2026-05-18: r2; 2026-06-08: 50; 2026-06-15: 50; 2026-06-22: 50; 2026-06-29: 50; 2026-07-06: 50; 2026-07-13: 50; 2026-07-20: 50; 2026-07-27: 50; 2026-08-03: 50; 2026-08-10: 50; 2026-08-17: 13 | 513 | 603 | 0 | 90
Weyerhaeuser - Resin Storage 1 |  |  | 586 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [10 empty] | 25 | 75 | 75 | 75 | 75 | 75 | 50 | 48 | [12 empty] | 498 | 586 | 0 | 88
Weyerhaeuser - Resin Storage 2 |  |  | 586 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [10 empty] | 25 | 75 | 75 | 75 | 75 | 75 | 50 | 48 | [12 empty] | 498 | 586 | 0 | 88
Weyerhaeuser - Resin Storage 3 |  |  | 586 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [10 empty] | 25 | 75 | 75 | 75 | 75 | 75 | 50 | 48 | [12 empty] | 498 | 586 | 0 | 88
Weyerhaeuser - Release Agent 1 |  |  | 495 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [14 empty] | 50 | 50 | 75 | 75 | 75 | 75 | 21 | [9 empty] | 421 | 495 | 0 | 74
Weyerhaeuser - Wax Storage 1 |  |  | 568 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [15 empty] | 50 | 50 | 75 | 75 | 75 | 75 | 50 | 33 | [7 empty] | 483 | 568 | 0 | 85
Weyerhaeuser - Wax Storage 2 |  |  | 568 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [15 empty] | 50 | 50 | 75 | 75 | 75 | 75 | 50 | 33 | [7 empty] | 483 | 568 | 0 | 85
Weyerhaeuser - Water Tank 1 |  |  | 582 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [17 empty] | 50 | 50 | 75 | 75 | 75 | 75 | 50 | 45 | [5 empty] | 495 | 582 | 0 | 87
Weyerhaeuser - Water Tank 2 |  |  | 582 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [17 empty] | 50 | 50 | 75 | 75 | 75 | 75 | 50 | 45 | [5 empty] | 495 | 582 | 0 | 87
Weyerhaeuser - Effluent Tank |  |  | 571 | [5 empty] | PO | d1 | d2 | d3 | d4 | d5 | d6 | r1 | r2 | [17 empty] | 50 | 50 | 75 | 75 | 75 | 75 | 50 | 35 | [5 empty] | 485 | 571 | 0 | 86
Eagle Materials |  |  | 424 | [5 empty] | PO | d1 | d2 | d3 | d4 | r1 | r2 | [9 empty] | 21 | 40 | 70 | 70 | 60 | 60 | 40 | [16 empty] | 361 | 424 | 0 | 63
Sterling Speciality Chem |  |  | 371 | [5 empty] | PO | d1 | d2 | d3 | d4 | r1 | r2 | [10 empty] | 30 | 60 | 60 | 60 | 60 | 46 | [16 empty] | 316 | 371 | 0 | 55
Reco - Tank 1 |  |  | 425 | [17 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [20 empty] | 361 | 425 | 0 | 64
Reco - Tank 2 |  |  | 425 | [17 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [20 empty] | 361 | 425 | 0 | 64
Reco - Tank 3 |  |  | 425 | [22 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [15 empty] | 361 | 425 | 0 | 64
Reco - Tank 4 |  |  | 425 | [22 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [15 empty] | 361 | 425 | 0 | 64
Reco - Tank 5 |  |  | 425 | [27 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [10 empty] | 361 | 425 | 0 | 64
Reco - Tank 6 |  |  | 425 | [27 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [10 empty] | 361 | 425 | 0 | 64
Reco - Tank 7 |  |  | 425 | [32 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [5 empty] | 361 | 425 | 0 | 64
Reco - Tank 8 |  |  | 425 | [32 empty] | 21 | 60 | 70 | 70 | 60 | 60 | 20 | [5 empty] | 361 | 425 | 0 | 64
Vertiv - CST Tank 1 |  |  | 204 | [18 empty] | 25 | 50 | 50 | 50 | [22 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 2 |  |  | 204 | [18 empty] | 25 | 50 | 50 | 50 | [22 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 3 |  |  | 204 | [21 empty] | 25 | 50 | 50 | 50 | [19 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 4 |  |  | 204 | [21 empty] | 25 | 50 | 50 | 50 | [19 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 5 |  |  | 204 | [24 empty] | 25 | 50 | 50 | 50 | [16 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 6 |  |  | 204 | [24 empty] | 25 | 50 | 50 | 50 | [16 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 7 |  |  | 204 | [27 empty] | 25 | 50 | 50 | 50 | [13 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 8 |  |  | 204 | [27 empty] | 25 | 50 | 50 | 50 | [13 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 9 |  |  | 204 | [30 empty] | 25 | 50 | 50 | 50 | [10 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 10 |  |  | 204 | [30 empty] | 25 | 50 | 50 | 50 | [10 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 11 |  |  | 204 | [33 empty] | 25 | 50 | 50 | 50 | [7 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 12 |  |  | 204 | [33 empty] | 25 | 50 | 50 | 50 | [7 empty] | 175 | 204 | 0 | 29
Vertiv - CST Tank 13 |  |  | 204 | [36 empty] | 25 | 50 | 50 | 50 |  |  |  |  | 175 | 204 | 0 | 29
Vertiv - CST Tank 14 |  |  | 204 | [36 empty] | 25 | 50 | 50 | 50 |  |  |  |  | 175 | 204 | 0 | 29
Vertiv - CST Tank 15 |  |  | 204 | [39 empty] | 25 | 50 | 50 | 50 |  | 175 | 204 | 0 | 29
[48 empty] | 0 | 0 | 0 | 0
|  |  |  | TOT | 2820.6653 | 2864.5598 |  | PROJ | 1250 | 1146 | 1135 | 965 | 1235 | 1317 | 1385 | 1454 | 1160 | 1420 | 1375 | 1370 | 1233 | 1045 | 882 | 718 | 832 | 857 | 915 | 1020 | 1065 | 993 | 998 | 910 | 990 | 990 | 1093 | 937 | 1060 | 936 | 865 | 861 | 670 | 565 | 425 | 350 | 350 | 200 | 0 | 36972
| 48 HRS | 40 HRS |  | PCT |  |  |  | PCT | 103.3% | 77.17% | 76.43% | 64.98% | 83.16% | 88.69% | 93.27% | 97.91% | 107.4% | 95.62% | 92.59% | 92.26% | 83.03% | 70.37% | 81.67% | 48.35% | 56.03% | 57.71% | 61.62% | 68.69% | 71.72% | 66.87% | 67.21% | 84.26% | 66.67% | 66.67% | 73.6% | 63.1% | 71.38% | 63.03% | 58.25% | 57.98% | 45.12% | 38.05% | 39.35% | 23.57% | 23.57% | 13.47% | 0%
BACKLOG | 32.7766 | 39.3319 |  | BAL |  |  |  | BAL | -40 | 339 | 350 | 520 | 250 | 168 | 100 | 31 | -80 | 65 | 110 | 115 | 252 | 440 | 198 | 767 | 653 | 628 | 570 | 465 | 420 | 492 | 487 | 170 | 495 | 495 | 392 | 548 | 425 | 549 | 620 | 624 | 815 | 920 | 655 | 1135 | 1135 | 1285 | 1080
Pre Fab
Scott Shuman |  | 0.5
Arthur Morrison |  | 0.5
Kevin Free |  | 1
Chris Lapp "CNC Operator #2" |  | 1
Maurice Sellars |  | 1
Cody Moose |  | 1
Cory Shuman |  | 1
Brittany Mock "Cobot Operator" |  | 1
Lucas Davis |  | 1
Joseph Fahey |  | 1
Danzel Daniels |  | 1
Fabrication
Sammy Chavis |  | 0
Shelbi Foltyn |  | 1
Kevin McMoore |  | 1
Randall Shuman |  | 1
Chris Allen |  | 1
Jason Batchelor |  | 1
Steven Lewis |  | 1
Wes Benoit |  | 1
Carl Wolfe |  | 1
Justin McAmis |  | 1
0
Clean/ Test
Julian Adkins - Supervisor |  | 0.5
Jacquelle Leeks |  | 1
Robert Moore |  | 1
Keith Wheeler |  | 1
Eric |  | 1
.
Supervision / Overhead
Scott |  | 0.5
Supervisor Finishing Department |  | 0.5
Sammy |  | 1
Keith Shuman |  | 1
Hayla Roberts |  | 1
Blake - Receiving & Inventory Clerk |  | 0
Arthur |  | 0.5
Albert |  | 1
2nd QC Inspector |  | 0
Total Direct |  | 23.5
Total Indirect |  | 5.5
Total |  | 29
Office
Nick |  | 1
Rutang |  | 1
Sherri |  | 1
Chris |  | 1
April Lewis |  | 1
John |  | 1
Dustin |  | 1
David |  | 1
Office |  | 8
Total Headcount |  | 37
Formulas:
ACT = [PLAN]