## Released By Tank
| Job # | Customer | Shop Location | Category | Ship Date | Progress | Complete | Recv Plate | Head(s) Rcvd | Pipe & Flange Rcvd | Receive Special Item(s) | Materials Inspected | Cut Parts on Plasma | Form Internal Coil | Shell(s) Rolled | Skirt Rolled | Roll Repads | Build Supports | Nozzle(s) Made | Build Top and/or Bottom | Build Manway | Make Ladders/ Handrail/ Platform | Weld Cone(s) | Fit Ladders/ Handrail/ Platform | QA Inspect Ladders/ Handrail/ Platform | Weld Shell Seams | Weld Top To Shell | Weld Bottom To Shell | Weld Tank Support(s) | Install Nozzles | Install Special External Part(s) | Install Special Internal Part(s) | Test | Clean & Prep | Sandblast / Paint | Ship to Galv Ladders/ Handrail/ Platform | Recv from Galv Ladders/ Handrail/ Platform | Take parts to Machine Shop | Recv Parts from Machine Shop | Arrange Truck
| 24-046 | Syms |  | On Track | 2026-04-13 | 72.38% | 76 | 1 |  | 20 |  | 1 |  |  | 6 |  | 4 | 4 | 20 | 1 | 2 | 2 |  | 2 | 1 | 17 | 1 | 1 |  | 18 |  |  | 1 | 1 | 1 |  |  |  |  | 1
| 25-040 | Nak Kiln |  | On Track | 2026-04-03 | 68.97% | 40 | 1 |  |  | 1 | 1 |  |  | 3 | [10 empty] | 21 | [5 empty] | 28 | 1 | 1 | [5 empty] | 1
| 25-053 | Andritz |  | On Track | 2026-06-01 | 18.18% | 6 | 1 |  | 5 |  | 1 | 5 |  | 2 |  | 2 |  | 4 | [6 empty] | 4 | 1 |  |  | 4 | 1 |  | 1 | 1 | [5 empty] | 1
| 25-055 | Air Gas |  | On Track | 2026-05-25 | 36.05% | 31 | 1 | 1 | 28 |  | 1 | 1 | 1 | 1 |  | 3 | 4 | 16 |  | 1 |  | 1 |  |  | 1 | 1 | 1 | 4 | 16 |  | 1 | 1 | 1 | [5 empty] | 1
| 25-069 | Reco/Nudyne |  | On Track | 2026-04-06 | 93.88% | 46 | 1 | 1 | 7 |  | 1 | 1 |  | 3 | 1 | 1 |  | 6 |  | 1 |  |  |  |  | 5 | 1 | 1 | 2 | 6 |  | 7 | 2 | 1 | 1
| 25-070 | Reco/Nudyne |  | On Track | 2026-04-20 | 73.47% | 36 | 1 | 1 | 7 |  | 1 | 1 |  | 3 | 1 | 1 |  | 6 |  | 1 |  |  |  |  | 5 | 1 | 1 | 2 | 6 |  | 7 | 2 | 1 | 1
Jobs Released | 25-071 | Reco/Nudyne |  | On Track | 2026-04-20 | 67.44% | 29 | 1 | 1 | 7 |  | 1 | 1 |  | 3 | 1 | 1 |  | 6 |  | 1 |  |  |  |  | 5 | 1 | 1 | 2 | 6 |  | 1 | 2 | 1 | 1
| 25-083 | Synthomer |  | On Track | 2026-04-09 | 95.74% | 90 | 1 | 2 | 22 | 1 | 1 | 1 |  | 2 |  | 1 | 4 | 22 |  | 1 |  |  |  |  | 3 | 1 | 1 | 4 | 22 | 1 | 1 | 1 | 1 | [5 empty] | 1
| 25-092 | Symrise |  | On Track | 2026-04-02 | 88.57% | 62 | 1 | 1 | 13 |  | 1 | 2 |  | 4 | 1 | 1 |  | 17 |  | 1 |  |  |  |  | 7 | 1 | 1 | 1 | 12 |  | 2 | 1 | 1 | 1 |  |  |  |  | 1
| 25-093 | Symrise |  | On Track | 2026-04-02 | 88.57% | 62 | 1 | 1 | 13 |  | 1 | 2 |  | 4 | 1 | 1 |  | 17 |  | 1 |  |  |  |  | 7 | 1 | 1 | 1 | 12 |  | 2 | 1 | 1 | 1 |  |  |  |  | 1
| 25-098 | Coastal Tech |  | Starting | 2026-05-10 | 19.23% | 10 | 1 |  | 8 |  | 1 | 3 |  | 1 |  |  | 2 | 7 | 1 |  |  | 2 |  |  |  | 8 | 4 | 2 | 7 |  | 2 | 1 | 1 | [5 empty] | 1
| 25-101 | Harper Love |  | Late | 2026-05-11 | 25.93% | 14 | 1 | 2 | 8 |  | 1 | 1 |  | 1 |  | 1 | 1 | 8 |  | 1 |  |  |  |  | 7 | 1 | 1 | 4 | 7 | 2 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
| 25-109 | Epic |  | On Track | 2026-04-30 | 27.59% | 8 |  | 2 | 5 |  | 1 | 1 |  |  |  |  | 2 | 5 | [7 empty] | 1 | 1 | 2 | 5 | 1 |  | 1 | 1 | [5 empty] | 1
| 25-110 | Epic |  | On Track | 2026-04-30 | 29.23% | 19 | 2 | 2 | 12 | 2 | 1 | 2 |  | 1 |  | 1 | 4 | 13 | [6 empty] | 1 | 1 | 1 | 4 | 13 |  | 2 | 1 | 1 | [5 empty] | 1
| 25-111 | Epic |  | Starting | 2026-05-15 | 3.704% | 2 | 1 | 2 | 9 | 1 | 1 | 1 |  | 1 |  | 2 | 4 | 9 |  | 1 |  |  |  |  | 1 | 1 | 1 | 4 | 9 | 2 | 1 | 1 | 1 | [5 empty] | 1
| 25-113 | Epic |  | Starting | 2026-05-15 | 3.279% | 2 | 1 | 2 | 11 | 2 | 1 | 1 |  | 2 |  | 1 | 4 | 11 |  | 1 |  |  |  |  | 2 | 1 | 1 | 4 | 11 |  | 2 | 1 | 1 | [5 empty] | 1
| 25-117 | Merrick |  | On Track | 2026-04-13 | 49.45% | 45 | 1 |  | 9 |  | 1 | 1 |  |  |  | 1 |  | 9 | 2 | 6 |  |  |  |  | 16 | 16 | 16 |  | 9 |  |  | 1 | 1 | 1 |  |  |  |  | 1
| 25-118 | Merrick |  | On Track | 2026-05-11 | 38.46% | 35 | 1 |  | 9 |  | 1 | 1 |  |  |  | 1 |  | 9 | 2 | 6 |  |  |  |  | 16 | 16 | 16 |  | 9 |  |  | 1 | 1 | 1 |  |  |  |  | 1
| 26-026 | Andritz (Repair) |  | On Track | 2026-04-09 | 57.14% | 4 | 2 |  |  |  | 1 | 1 | [16 empty] | 2 |  |  |  | 1
|  | Legend: | Complete
In Process
@ Risk
Late
N/A
To Start