## Sheet1
Priority List
AS OF: |  | 2026-02-17
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | 25-018 | SS-316 | 2026-01-29 | TBD | fab complete, repair complete (Add stiffeners around manway),add grating material to top opening (customer request) then test, clean and ship prep. | YES | Handrails | NO
2 | 25-021 | SS-304 | 2026-02-03 | 2026-02-19 | fab complete, testing and cleaning complete ready to ship | NO |  | NO
3 | 25-010 | SS-304 | 2026-02-11 | 2026-02-19 | fab complete, testing and cleaning complete ready to ship | NO |  | NO
4 | 25-016 | SS-304 | 2026-02-11 | 2026-02-19 | fab complete, testing and cleaning complete ready to ship | NO |  | NO
5 | 25-019 | SS-304 | 2026-02-17 | 2026-02-19 | x-ray for manway shell seam on 1/27/26 complete good, fitting and welding stiffeners on agitator nozzles, then a few attachments and nameplate | NO |  | NO
6 | 25-012 | SS-304 | 2026-02-18 | 2026-02-19 | installing manway, install nozzles in top head, fit and weld top head. | NO |  | NO
7 | 25-084 | SA36 | 2026-01-27 | 2026-02-23 | fab complete, coil test with AI on 2/6/26 complete and good, tank test complete and good, ready for blast and paint. | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
8 | 25-092 | SS-316 | 2026-02-25 | 2026-03-02 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
9 | 25-093 | SS-316 | 2026-02-25 | 2026-03-02 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
10 | 25-013 | SS-304 | 2026-02-28 | 2026-03-02 | flat bottom cut, slope bottom cut, stiffeners for slope bottom cut, top head pulled and holes cut | NO |  | NO
11 | 25-089 | 2205 | 2026-03-03 | 2026-03-05 | installing nozzles, installing side (A) roof, finishing welding side (B) roof, install agitator rings, install shell and roof stiffeners | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
12 | 25-040 | HR120 | 2026-03-03 | 2026-03-09 | need to have spider bracing installed, will need to weld (1) 3 shell section to the 4 shell section. Customer requesting UT of all weld seams | NO |  | NO
13 | 25-066 | 516-70 | 2026-02-26 | 2026-03-09 | all shell courses fit and welded, x-ray on bottom head and shell seams on 1/30/26 are good, install attachments, nozzles, and insulation rings. | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
14 | 25-067 | 516-70 | 2026-02-26 | 2026-03-09 | Start fitting shell courses | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
15 | 25-089 | 2205 | 2026-03-03 | 2026-03-05 | floor sections done and x-ray good other than (1) short seam that still needs repair and reshoot, (1) half of shell section fit and 90% welded, other shell section 50% fit and welded. Once shell is fit and welded, fit to bottom section and weld. | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
16 | 25-099 | SS-304 | 2026-03-04 | 2026-03-11 | processing in pre-fab | NO |  | NO
17 | 25-083 | SS-316 w/ #4 Polish | 2026-03-04 | 2026-03-12 | half pipe bottom head installed, shells welded and x-ray passed, all nozzles fit and welded in top head, fitting shell half pipe. | NO |  | NO
18 | 24-046 | SS-304 | 2026-03-11 | 2026-03-16 | shells rolled, start fitting bottom and bottom shell section | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
19 | 25-101 | SS-304 | 2026-03-25 | 2026-04-06 | processing in pre-fab | NO |  | NO
20 | 25-068 | 516-70 | 2026-03-19 | 2026-03-30 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
21 | 25-069 | 516-70 | 2026-03-19 | 2026-03-30 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
22 | 25-070 | 516-70 | 2026-04-06 | 2026-04-20 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
23 | 25-071 | 516-70 | 2026-04-06 | 2026-04-20 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
YES
NO
N/A