## Sheet1
Priority List
AS OF: |  | 2026-02-02
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | 25-062 | 516-70 | 2026-01-20 | 2026-02-02 | Fab complete other than last insulation ring at head, X-ray top head on good, AI testing good, blasting and painting complete, ready to ship | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
2 | 25-063 | 516-70 | 2026-01-20 | 2026-02-02 | Fab complete other than last insulation ring at head, X-ray top head on good, AI testing good, blasting and painting complete, ready to ship | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
3 | 25-011 | SS-304 | 2026-01-29 | 2026-02-04 | Finish welding top head, install dip pipe supports, test and clean | NO |  | NO
4 | 25-020 | SS-316 | 2026-01-13 | 2026-02-04 | Fab complete, testing complete, cleaning and ship prep complete, need to add bracing to bottom side of top head | NO |  | NO
6 | 25-021 | SS-304 | 2026-02-03 | 2026-02-10 | all shell courses fit need to be welded on outside, rim angle fit and welded, install shell nozzles & attachments, then top head | NO |  | NO
5 | 25-018 | SS-316 | 2026-01-29 | 2026-02-11 | fab complete, making repair (Add stiffeners around manway),then test, clean and ship prep. | YES | Handrails | NO
7 | 25-040 | HR120 | 2026-02-09 | TBD | need to have spider bracing installed, will need to weld (1) 3 shell section to the 4 shell section. Customer requesting UT of all weld seams | NO |  | NO
8 | 25-010 | SS-304 | 2026-02-11 | 2026-02-17 | slope bottom complete, flat bottom complete, welding in shell nozzles. | NO |  | NO
9 | 25-016 | SS-304 | 2026-02-11 | 2026-02-17 | slope bottom fit and welded, flat bottom fit and welded, x-ray for manway shell seam on 1/27/26 complete good, fit and weld rim angle. | NO |  | NO
10 | 25-019 | SS-304 | 2026-02-11 | 2026-02-17 | slope bottom fit and welded, flat bottom fit and welded, x-ray for manway shell seam on 1/27/26 complete good, fit and weld rim angle. | NO |  | NO
11 | 25-064 | 516-70 | 2026-02-03 | 2026-02-17 | finishing welding last insulation ring, x-ray on closure head and repair shot on shell seam on 1/30/26 all good, AI testing on 2/6/26 | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
12 | 25-065 | 516-70 | 2026-02-03 | 2026-02-17 | x-ray shell seams and bottom head completed and good on 1/16/26, internal header piping installed, fit and weld out closure head, x-ray on closure head on 2/5/26, AI testing on 2/6/26 | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
13 | 25-013 | SS-304 | 2026-02-05 | 2026-02-18 | flat bottom cut, slope bottom cut, stiffeners for slope bottom cut, top head pulled and holes cut | NO |  | NO
14 | 25-012 | SS-304 | 2026-02-13 | 2026-02-18 | processing in pre-fab | NO |  | NO
15 | 25-084 | SA36 | 2026-01-27 | 2026-02-18 | fab complete, coil has been shop air tested, vessel testing complete, coil tested with AI on 2/6/26. | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
16 | 25-089 | 2205 | 2026-02-09 | 2026-02-19 | floor sections done and x-ray good other than (1) short seam that still needs repair and reshoot, (1) half of shell section fit and 80% welded, other shell section partially fit and welded. | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
17 | 25-099 | SS-304 | 2026-02-17 | 2026-02-24 | processing in pre-fab | NO |  | NO
18 | 25-083 | SS-316 w/ #4 Polish | 2026-02-09 | 2026-02-25 | half pipe bottom head installed, shells welded and x-ray passed, all nozzles fit and welded in top head, fitting shell half pipe. | NO |  | NO
19 | 25-092 | SS-316 | 2026-02-17 | 2026-02-25 | processing in pre-fab | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
20 | 25-093 | SS-316 | 2026-02-17 | 2026-02-25 | processing in pre-fab | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
21 | 25-098 | 2507 | 2026-02-24 | 2026-03-03 | processing in pre-fab | NO |  | NO
22 | 24-046 | SS-304 | 2026-02-24 | 2026-03-03 | processing in pre-fab | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
23 | 25-066 | 516-70 | 2026-02-19 | 2026-03-09 | all shell courses fit and welded, x-ray on bottom head and shell seams on 1/30/26 are good, install attachments, nozzles, and insulation rings. | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
24 | 25-067 | 516-70 | 2026-02-19 | 2026-03-09 | Start fitting shell courses | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
25 | 25-101 | SS-304 | 2026-03-25 | 2026-04-06 | processing in pre-fab | NO |  | NO
YES
NO
N/A