## Sheet1
Priority List
AS OF: |  | 2026-02-09
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | 25-021 | SS-304 | 2026-02-03 | 2026-02-12 | welding in manway, tailing lug, nameplate bracket. Then QC inspect,test, and clean. | NO |  | NO
2 | 25-018 | SS-316 | 2026-01-29 | TBD | fab complete, repair complete (Add stiffeners around manway),add grating material to top opening (customer request) then test, clean and ship prep. | YES | Handrails | NO
3 | 25-040 | HR120 | 2026-02-09 | TBD | need to have spider bracing installed, will need to weld (1) 3 shell section to the 4 shell section. Customer requesting UT of all weld seams | NO |  | NO
4 | 25-064 | 516-70 | 2026-02-03 | 2026-02-16 | fab complete, x-ray 1/30/26 all good, AI testing on 2/6/26 all good, blasting and painting | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
5 | 25-065 | 516-70 | 2026-02-03 | 2026-02-16 | fab complete, x-ray 1/30/26 all good, AI testing on 2/6/26 all good, blasting and painting | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
6 | 25-010 | SS-304 | 2026-02-11 | 2026-02-17 | fab complete, test and clean | NO |  | NO
7 | 25-016 | SS-304 | 2026-02-11 | 2026-02-17 | installing remaining attachments, QC check then test and clean | NO |  | NO
8 | 25-019 | SS-304 | 2026-02-11 | 2026-02-17 | slope bottom fit and welded, flat bottom fit and welded, x-ray for manway shell seam on 1/27/26 complete good, fit and weld rim angle. | NO |  | NO
9 | 25-012 | SS-304 | 2026-02-13 | 2026-02-19 | slope bottom installed, flat bottom installed and welded, installing rim angle | NO |  | NO
10 | 25-084 | SA36 | 2026-01-27 | 2026-02-23 | fab complete, coil test with AI on 2/6/26 complete and good, tank test complete and good, ready for blast and paint. | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
11 | 25-099 | SS-304 | 2026-02-17 | 2026-02-24 | processing in pre-fab | NO |  | NO
12 | 25-083 | SS-316 w/ #4 Polish | 2026-02-09 | 2026-02-25 | half pipe bottom head installed, shells welded and x-ray passed, all nozzles fit and welded in top head, fitting shell half pipe. | NO |  | NO
13 | 25-092 | SS-316 | 2026-02-17 | 2026-02-25 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
14 | 25-093 | SS-316 | 2026-02-17 | 2026-02-25 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
15 | 25-089 | 2205 | 2026-02-09 | 2026-02-26 | floor sections done and x-ray good other than (1) short seam that still needs repair and reshoot, (1) half of shell section fit and 90% welded, other shell section 50% fit and welded. Once shell is fit and welded, fit to bottom section and weld. | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
16 | 25-013 | SS-304 | 2026-02-05 | 2026-02-26 | flat bottom cut, slope bottom cut, stiffeners for slope bottom cut, top head pulled and holes cut | NO |  | NO
17 | 25-098 | 2507 | 2026-02-24 | 2026-03-03 | processing in pre-fab | NO |  | NO
18 | 24-046 | SS-304 | 2026-02-24 | 2026-03-03 | shells rolled, start fitting bottom and bottom shell section | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
19 | 25-066 | 516-70 | 2026-02-19 | 2026-03-09 | all shell courses fit and welded, x-ray on bottom head and shell seams on 1/30/26 are good, install attachments, nozzles, and insulation rings. | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
20 | 25-067 | 516-70 | 2026-02-19 | 2026-03-09 | Start fitting shell courses | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
21 | 25-101 | SS-304 | 2026-03-25 | 2026-04-06 | processing in pre-fab | NO |  | NO
YES
NO
N/A