## Sheet1
Priority List
AS OF: |  | 2026-01-26
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | 25-011 | SS-304 | 2026-01-29 | 2026-02-02 | fitting shell stiffeners, fit and weld manway, fit and weld top head | NO |  | NO
2 | 25-018 | SS-316 | 2026-01-29 | 2026-02-02 | fab complete, making repair (Add larger repad),then test, clean and ship prep. | YES | Handrails | NO
3 | 25-062 | 516-70 | 2026-01-20 | 2026-02-03 | Fab complete other than last insulation ring at head, X-ray top head on good, AI testing good, blasting and painting complete, need to ship prep | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
4 | 25-063 | 516-70 | 2026-01-20 | 2026-02-03 | Fab complete other than last insulation ring at head, X-ray top head on good, AI testing good, blasting and painting complete, need to ship prep | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
5 | 25-020 | SS-316 | 2026-01-13 | 2026-02-04 | Fab complete, testing complete, cleaning and ship prep in progress. | NO |  | NO
6 | 25-013 | SS-304 | 2026-02-05 | 2026-02-10 | flat bottom cut, slope bottom cut, stiffeners for slope bottom cut, top head pulled and holes cut | NO |  | NO
7 | 25-021 | SS-304 | 2026-02-03 | 2026-02-10 | all shell courses fit need to be welded inside and outside, rim angle fit, install shell nozzles & attachments, then top head | NO |  | NO
8 | 25-040 | HR120 | 2026-02-09 | 2026-02-12 | need to have spider bracing installed, will need to weld (1) 3 shell section to the 4 shell section. | NO |  | NO
9 | 25-010 | SS-304 | 2026-02-11 | 2026-02-17 | processing in pre-fab | NO |  | NO
10 | 25-016 | SS-304 | 2026-02-11 | 2026-02-17 | slope bottom fit and welded, x-ray for manway shell seam on 1/27/26, then fit and weld to flat bottom. | NO |  | NO
11 | 25-019 | SS-304 | 2026-02-11 | 2026-02-17 | slope bottom fit and welded, x-ray for manway shell seam on 1/27/26, then fit and weld to flat bottom. | NO |  | NO
12 | 25-064 | 516-70 | 2026-02-03 | 2026-02-17 | welding outside closure head, x-ray on closure head and repair shot on shell seam on 1/30/26, AI testing on 2/4/26 | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
13 | 25-065 | 516-70 | 2026-02-03 | 2026-02-17 | x-ray shell seams and bottom head completed and good on 1/16/26, install internal header piping, fit and weld out closure head, x-ray on closure head on 1/30/26, AI testing on 2/4/26 | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
14 | 25-012 | SS-304 | 2026-02-13 | 2026-02-18 | processing in pre-fab | NO |  | NO
15 | 25-084 | SA36 | 2026-01-27 | 2026-02-18 | coil shop tested, coil installed, top head fit and welded, install platform and handrails | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
16 | 25-089 | 2205 | 2026-02-09 | 2026-02-19 | finish welding bottom seams, spot x-ray bottom seams on 1/16/26, shell sections beveled and rolled, fit and weld shell seams for 1 half, fit shell to bottom with with customer to visit on 1/22/26 to witness shell to floor fitup and welding. | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
17 | 25-099 | SS-304 | 2026-02-17 | 2026-02-24 | processing in pre-fab | NO |  | NO
18 | 25-083 | SS-316 w/ #4 Polish | 2026-02-09 | 2026-02-25 | half pipe bottom head installed, shells welded and x-ray passed, all nozzles fit and welded in top head, fitting shell half pipe. | NO |  | NO
19 | 25-092 | SS-316 | 2026-02-17 | 2026-02-25 | processing in pre-fab | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
20 | 25-093 | SS-316 | 2026-02-17 | 2026-02-25 | processing in pre-fab | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
21 | 25-098 | 2507 | 2026-02-24 | 2026-03-03 | releasing drawing week of 1/26/26 | NO |  | NO
22 | 24-046 | SS-304 | 2026-02-24 | 2026-03-03 | processing in pre-fab | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
23 | 25-066 | 516-70 | 2026-02-19 | 2026-03-09 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
24 | 25-067 | 516-70 | 2026-02-19 | 2026-03-09 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
25 | 25-101 | SS-304 | 2026-03-25 | 2026-04-06 | processing in pre-fab | NO |  | NO
YES
NO
N/A