## Sheet1
Priority List
AS OF: |  | 2026-01-05
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | 25-040 | HR120 | 2025-11-20 | TBD | on hold for further customer instructions, will need to have spider bracing installed | NO |  | NO
2 | 25-052 | 516-70 | 2025-12-09 | 2025-12-29 | Vessel and ship loose was all shipped on 12/29/25 other than 1 ladder that still needs to be picked up at galv. | YES | Handrail, ladder, platform, & grating | YES | Interior: blast and (2) coats Chemline 784. Exterior: blast and (1) coat prime interbond 2340
3 | 25-078 | SS-304 | 2025-11-20 | 2026-01-06 | fab complete, AI testing complete, cleaning complete, ready to ship | NO |  | NO
4 | 25-079 | SS-304 | 2025-11-20 | 2026-01-06 | fab complete, AI testing complete, cleaning complete, ready to ship | NO |  | NO
5 | 25-077 | SS-304 | 2025-12-02 | 2026-01-06 | fab complete, AI testing complete, cleaning complete, ready to ship
6 | 25-080 | SA36 | 2025-12-18 | 2026-01-07 | fab complete, testing complete, painting in progress, then ship prep | NO |  | YES | Blast & (2) coats of Duraplate 235 & (1) coat Acrolon 218 HS
8 | 25-096 | SS-316 | 2026-01-02 | 2026-01-07 | fab complete, AI testing complete, needs to be cleaned and ship prep | NO |  | NO
9 | 25-097 | SS-316 | 2026-01-02 | 2026-01-07 | fab complete, AI testing complete, needs to be cleaned and ship prep | NO |  | NO
11 | 25-060 | 516-70 | 2026-01-02 | 2026-01-13 | fab complete, AI testing complete 1/2/26, blasting and painting | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
12 | 25-061 | 516-70 | 2026-01-02 | 2026-01-13 | fab complete, AI testing complete 1/2/26, blasting and painting | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
7 | 25-094 | SS-316 | 2025-12-23 | 2026-01-20 | fab complete, needs to be tested, then needs to be cleaned and ship prep | NO |  | NO
10 | 25-018 | SS-316 | 2025-12-23 | 2026-01-20 | fab complete, needs testing & cleaning | YES | Handrails | NO
13 | 25-084 | SA36 | 2026-01-08 | 2026-01-21 | welding shell seams, coil built | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
14 | 25-012 | SS-304 | 2026-01-07 | 2026-01-21 | processing in pre-fab | NO |  | NO
15 | 25-016 | SS-304 | 2026-01-07 | 2026-01-21 | flat bottom cut | NO |  | NO
16 | 25-019 | SS-304 | 2026-01-07 | 2026-01-21 | flat bottom cut | NO |  | NO
17 | 25-010 | SS-304 | 2026-01-07 | 2026-01-21 | processing in pre-fab | NO |  | NO
18 | 25-017 | SS-304 | 2026-01-13 | 2026-01-22 | tank is built minus top head, top head pulled and nozzle holes cut, waiting on nozzles to arrive from India | NO |  | NO
19 | 25-020 | SS-316 | 2026-01-13 | 2026-01-22 | tank is built minus top head, top head pulled but still needs to be laid out and nozzle holes cut, waiting on nozzles to arrive from India | NO |  | NO
20 | 25-011 | SS-304 | 2026-01-19 | 2026-01-27 | tank built up to rim angle, top head pulled and nozzle holes cut, waiting on nozzles to arrive from India | NO |  | NO
21 | 25-083 | SS-316 w/ #4 Polish | 2026-01-19 | 2026-01-27 | fit half pipe to bottom head, shell courses fit. | NO |  | NO
22 | 25-021 | SS-304 | 2026-01-19 | 2026-01-27 | bottom and bottom 2 shell courses fit and welded, top head pulled and nozzle holes cut, waiting on nozzles to arrive from India | NO |  | NO
23 | 25-013 | SS-304 | 2026-01-19 | 2026-01-27 | flat bottom cut, slope bottom cut, stiffeners for slope bottom cut, top head pulled and holes cut | NO |  | NO
24 | 25-062 | 516-70 | 2026-01-20 | 2026-02-03 | install stiffeners and closure head | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
25 | 25-063 | 516-70 | 2026-01-20 | 2026-02-03 | install stiffeners and internal pipe header | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
26 | 25-064 | 516-70 | 2026-02-03 | 2026-02-17 | bottom head welded to skirt, rolling shells | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
27 | 25-065 | 516-70 | 2026-02-03 | 2026-02-17 | bottom head welded to skirt, rolling shells | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
28 | 24-046 | SS-304 | 2026-02-09 | 2026-02-17 | processing in pre-fab | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
29 | 25-089 | 2205 | 2026-02-09 | 2026-02-19 | top & bottom cut on CNC and tacked together, stiffeners cut, mandoor cladding in progress | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
YES
NO
N/A