## Sheet1
Priority List
AS OF: |  | 2026-02-23
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | 25-018 | SS-316 | 2026-01-29 | TBD | fab complete, repair complete (Add stiffeners around manway),add grating material to top opening (customer request) then test, clean and ship prep. | YES | Handrails | NO
2 | 25-084 | SA36 | 2026-01-27 | TBD | fab complete, coil test with AI on 2/6/26 complete and good, tank test complete and good, blast and paint complete, waiting on customer to accept delivery date. | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
3 | 25-012 | SS-304 | 2026-02-18 | 2026-03-04 | installing wall ring bracing, (1) nozzle, lift lugs, and name plate | NO |  | NO
4 | 25-013 | SS-304 | 2026-02-28 | 2026-03-04 | top head complete with nozzles, fitting slope botttom then flat bottom | NO |  | NO
5 | 25-089 | 2205 | 2026-03-03 | 2026-03-05 | fitting sparger nozzles, fit and weld last (2) shell supports on side (A), PT on floor, shell nozzles, wall rings, and door being done on 2/24/26. | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
6 | 25-066 | 516-70 | 2026-02-26 | 2026-03-09 | Ready to test | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
7 | 25-067 | 516-70 | 2026-02-26 | 2026-03-09 | weld out internal header pipe, install and weld out closure head | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
8 | 25-099 | SS-304 | 2026-03-11 | 2026-03-18 | processing in pre-fab | NO |  | NO
9 | 25-098 | 2507 | 2026-03-16 | 2026-03-19 | processing in pre-fab | NO |  | NO
10 | 25-040 | HR120 | 2026-03-24 | 2026-03-30 | need to have spider bracing installed, will need to weld (1) 3 shell section to the 4 shell section. Customer requesting UT of all weld seams | NO |  | NO
11 | 25-092 | SS-316 | 2026-03-23 | 2026-03-30 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
12 | 25-093 | SS-316 | 2026-03-23 | 2026-03-30 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
13 | 25-068 | 516-70 | 2026-03-19 | 2026-03-30 | ready to fit nozzles | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
14 | 25-069 | 516-70 | 2026-03-19 | 2026-03-30 | move to roller fit remaining shell courses | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
15 | 25-083 | SS-316 w/ #4 Polish | 2026-03-30 | 2026-04-06 | half pipe bottom head installed, shells welded and x-ray passed, all nozzles fit and welded in top head, fitting shell half pipe. | NO |  | NO
16 | 25-117 | SA36 | 2026-04-06 | 2026-04-13 | processing in pre-fab | NO |  | YES | Blast & (1) coat Macropoxy 646 HAZE GRAY.
17 | 24-046 | SS-304 | 2026-04-06 | 2026-04-15 | shells rolled, bottom fit to bottom shell course | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
18 | 25-070 | 516-70 | 2026-04-06 | 2026-04-20 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
19 | 25-071 | 516-70 | 2026-04-06 | 2026-04-20 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
20 | 25-101 | SS-304 | 2026-04-30 | 2026-05-11 | processing in pre-fab | NO |  | NO
YES
NO
N/A