## Sheet1
Priority List
AS OF: |  | 2026-03-16
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | Vertiv Tanks (First 24) | SS-304 | 2026-03-10 | 2026-03-16 | Fab, testing, cleaning complete on first (11). Shipping out (8) with (7) expansion tanks on 3/16/26 | NO |  | NO
2 | 25-066 | 516-70 | 2026-02-26 | 2026-03-16 | Fab complete, AI testing complete, blasting & painting complete, ready to ship | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
3 | 25-067 | 516-70 | 2026-02-26 | 2026-03-16 | Fab complete, AI testing complete, blasting & painting complete, ready to ship | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
4 | 25-012 | SS-304 | 2026-02-18 | 2026-03-23 | Fab complete, testing complete, ready to ship | NO |  | NO
5 | 25-013 | SS-304 | 2026-02-28 | 2026-03-23 | fit and weld top head to rim angle, install nozzles, manway, and attachments | NO |  | NO
6 | 25-099 | SS-304 | 2026-03-18 | 2026-03-25 | both cone sections formed and welded. Coil rolled and welded in. AI testing of coil on 3/18/26, then join the sections together. Vacuum box testing on 3/23/26 | NO |  | NO
7 | 25-040 | HR120 | 2026-03-24 | 2026-03-30 | need to have spider bracing installed, will need to weld (1) 3 shell section to the 4 shell section. Customer requesting UT of all weld seams | NO |  | NO
8 | 25-092 | SS-316 | 2026-03-23 | 2026-03-30 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
9 | 25-093 | SS-316 | 2026-03-23 | 2026-03-30 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
10 | 25-068 | 516-70 | 2026-03-19 | 2026-03-30 | Closure head x-ray on 3/17/26, then finish last insulation ring and nameplate. AI testing on 3/25/26 | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
11 | 25-069 | 516-70 | 2026-03-19 | 2026-03-30 | shell seam x-ray on 3/17/26, then install header and closure head, closure head x-ray on 3/23/26. AI testing on 3/25/26 | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
12 | 25-083 | SS-316 w/ #4 Polish | 2026-03-30 | 2026-04-06 | half pipe bottom head installed, shells welded and x-ray passed, all nozzles fit and welded in top head, shoot x-ray on closure head, then start fitting shell half pipe. | NO |  | NO
13 | 25-098 | 2507 | 2026-03-16 | 2026-04-06 | remaking welding procedures per customer request | NO |  | NO
14 | 25-117 | SA36 | 2026-04-06 | 2026-04-13 | top has all stiffeners install and access hatches, fitting bottom/shell sections together | NO |  | YES | Blast & (1) coat Macropoxy 646 HAZE GRAY.
15 | 25-084 | SA36 | 2026-01-27 | 2026-04-15 | fab complete, coil test with AI on 2/6/26 complete and good, tank test complete and good, blast and paint complete, waiting on customer to accept delivery date. | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
16 | 24-046 | SS-304 | 2026-04-06 | 2026-04-15 | shells rolled, bottom fit to bottom shell course | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
17 | 25-070 | 516-70 | 2026-04-06 | 2026-04-20 | fitting shell courses | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
18 | 25-071 | 516-70 | 2026-04-06 | 2026-04-20 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
19 | 25-101 | SS-304 | 2026-04-30 | 2026-05-11 | shell courses rolled | NO |  | NO
20 | 25-118 | SA36 | 2026-05-04 | 2026-05-11 | processing in pre-fab | NO |  | YES | Blast & (1) coat Macropoxy 646 HAZE GRAY.
YES
NO
N/A