## Sheet1
Priority List
AS OF: |  | 2026-03-02
| Job # | MOC | FAB COMP / TEST DATE | SHIP DATE | SHOP STATUS | GALV. | GALV STATUS | PAINT | PAINT STATUS
1 | 25-084 | SA36 | 2026-01-27 | TBD | fab complete, coil test with AI on 2/6/26 complete and good, tank test complete and good, blast and paint complete, waiting on customer to accept delivery date. | YES | Handrail, ladder, platform, & grating | YES | Blast & (1) coat of Carbozinc
2 | 25-089 | 2205 | 2026-03-03 | 2026-03-05 | fitting and root pass sparger nozzles, 3rd party PT of root pass on spargers and floor drains on 3/2/26. Cut holes in beams and weld on lifting eye repads on (4) columns for each side, Fit and weld all remaining repads. Split half apart move side (A) to the back by the afternoon of 3/3/26. | NO |  | YES | painting supports, flange and manway cover. Macropoxy 646 Haze Gray
3 | 25-018 | SS-316 | 2026-01-29 | 2026-03-10 | fab complete, repair complete (Add stiffeners around manway),add grating material to top opening (customer request) then test, clean and ship prep. | YES | Handrails | NO
4 | 25-012 | SS-304 | 2026-02-18 | 2026-03-12 | fab complete, ready to test, then clean and ship prep. | NO |  | NO
5 | 25-013 | SS-304 | 2026-02-28 | 2026-03-12 | top head complete with nozzles, fitting slope botttom then flat bottom | NO |  | NO
6 | Vertiv Tanks (First 24) | SS-304 | 2026-03-10 | 2026-03-16 | Fabrication and welding well underway, need to build (2) testing beds this week, testing in batches of 5 - 10 at a time and will begin testing tanks on 3/10/26 thru 3/12/26. First batch of (24) ships out on 3/16/26 | NO |  | NO
7 | 25-066 | 516-70 | 2026-02-26 | 2026-03-16 | Ready to test | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
8 | 25-067 | 516-70 | 2026-02-26 | 2026-03-16 | X-ray of closure head on 3/2/26. | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
9 | 25-099 | SS-304 | 2026-03-11 | 2026-03-18 | processing in pre-fab | NO |  | NO
10 | 25-098 | 2507 | 2026-03-16 | 2026-03-19 | processing in pre-fab | NO |  | NO
11 | 25-040 | HR120 | 2026-03-24 | 2026-03-30 | need to have spider bracing installed, will need to weld (1) 3 shell section to the 4 shell section. Customer requesting UT of all weld seams | NO |  | NO
12 | 25-092 | SS-316 | 2026-03-23 | 2026-03-30 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
13 | 25-093 | SS-316 | 2026-03-23 | 2026-03-30 | bottom head nozzles installed used as AI hold point and good, fit bottom head to shell | NO |  | YES | Blast & (1) coat Macropoxy 646 on skirt, skirt opening, and base ring.
14 | 25-068 | 516-70 | 2026-03-19 | 2026-03-30 | ready to fit nozzles | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
15 | 25-069 | 516-70 | 2026-03-19 | 2026-03-30 | move to roller fit remaining shell courses | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
16 | 25-083 | SS-316 w/ #4 Polish | 2026-03-30 | 2026-04-06 | half pipe bottom head installed, shells welded and x-ray passed, all nozzles fit and welded in top head, fitting shell half pipe. | NO |  | NO
17 | 25-117 | SA36 | 2026-04-06 | 2026-04-13 | processing in pre-fab | NO |  | YES | Blast & (1) coat Macropoxy 646 HAZE GRAY.
18 | 24-046 | SS-304 | 2026-04-06 | 2026-04-15 | shells rolled, bottom fit to bottom shell course | NO |  | YES | Ladder, handrails, platform, & grating blasted and coating OSHA safety yellow
19 | 25-070 | 516-70 | 2026-04-06 | 2026-04-20 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
20 | 25-071 | 516-70 | 2026-04-06 | 2026-04-20 | processing in pre-fab | NO |  | YES | Interior: blast and (2) coats Tnemec epoxoline series 21. Exterior: blast and (1) coat red oxide primer
21 | 25-101 | SS-304 | 2026-04-30 | 2026-05-11 | processing in pre-fab | NO |  | NO
YES
NO
N/A