## Sheet1
Priority | Job # | Customer | Description | MOC | Fab Comp / Test Date | Ship Date | Shop Status | Galv | Galv Status | Paint | Paint Status
1 | 26-027 | KEMIRA WATER SOLUTIONS INC. | t-103R DRAWING | T-103R DRAWING |  |  | No operations | NO |  | NO
2 | 26-028 | KEMIRA WATER SOLUTIONS INC. | t-107R DRAWING | T-107R DRAWING |  |  | No operations | NO |  | NO
3 | 26-029 | AMERITERPENES LLC | ALLOWABLE NOZZLE LOAD ANALYSIS | ALLOWABLE NOZZLE LOAD ANALYSIS |  |  | No operations | NO |  | NO
4 | 26-030 | AMERITERPENES LLC | 0.374 SHELL_205-14 REPLACEMENT | 0.375 SHELL_205-14 REPLACEMENT |  |  | No operations | NO |  | NO
5 | 26-026 | ANDRITZ INC | STEAM PIPE REPAIR PIECES | STEAM PIPE REPAIR PIECES |  |  | No operations | NO |  | NO
6 | 26-025 | BLAKE & PENDLETON | AIR RECEIVER TANK | AIR RECEIVER TANK |  |  | No operations | NO |  | NO
7 | 26-023 | SAVANNAH TANK AND EQUIPMENT, INC. | DEMO TANK | DEMO TANK |  |  | In fabrication (0% ops complete) | NO |  | NO
8 | 26-024 | POLYNT COMPOSITES USA INC | WATER TANK | WATER TANK |  |  | No operations | NO |  | NO
9 | 26-022 | ANDRITZ INC | WASH LIQUOR FLASH TANK | WASH LIQUOR FLASH TANK |  |  | No operations | NO |  | NO
10 | 26-020 | US SUGAR CORPORATION | SECONDARY SCREENED JUICE TANK C | SECONDARY SCREENED JUICE TANK C |  |  | No operations | NO |  | NO
11 | 26-021 | US SUGAR CORPORATION | PRIMARY SCREENED JUICE TANK C | PRIMARY SCREENED JUICE TANK C |  |  | No operations | NO |  | NO
12 | 26-019 | VONORE FIBER PRODUCTS LLC | NOZZLES W/REPADS | NOZZLES W/REPADS |  |  | No operations | NO |  | NO
13 | 26-001 | SYNTHOMER INC. | 25-356 CHANGE ORDER | 25-356 CHANGE ORDER |  |  | No operations | NO |  | NO
14 | 26-007 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 2 | TEMP SENSOR SHIPMENT 2 |  |  | No operations | NO |  | NO
15 | 26-008 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 3 | TEMP SENSOR SHIPMENT 3 |  |  | No operations | NO |  | NO
16 | 26-009 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 4 | TEMP SENSOR SHIPMENT 4 |  |  | No operations | NO |  | NO
17 | 26-010 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 5 | TEMP SENSOR SHIPMENT 5 |  |  | No operations | NO |  | NO
18 | 26-011 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 6 | TEMP SENSOR SHIPMENT 6 |  |  | No operations | NO |  | NO
19 | 26-012 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 7 | TEMP SENSOR SHIPMENT 7 |  |  | No operations | NO |  | NO
20 | 26-013 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 8 | TEMP SENSOR SHIPMENT 8 |  |  | No operations | NO |  | NO
21 | 26-002 | FLOQUIP ENGINEERIING CO | RAIL BUFFER TANK #1 | RAIL BUFFER TANK #1 |  |  | No operations | NO |  | NO
22 | 26-003 | FLOQUIP ENGINEERIING CO | RAIL BUFFER TANK #2 | RAIL BUFFER TANK #2 |  |  | No operations | NO |  | NO
23 | 26-004 | FLOQUIP ENGINEERIING CO | RAIL BUFFER TANK #3 | RAIL BUFFER TANK #3 |  |  | No operations | NO |  | NO
24 | 26-006 | VERTIV CORPORATION | TEMP SENSOR SHIPMENT 1 | TEMP SENSOR SHIPMENT 1 |  |  | No operations | NO |  | NO
25 | 26-005 | US SUGAR CORPORATION | POLISHING/TRAP FILTER BLOWDN TANK | POLISHING/TRAP FILTER BLOWDN TANK |  |  | No operations | NO |  | NO
26 | 26-015 | FLOQUIP ENGINEERIING CO | R2 REACTOR | R2 REACTOR |  |  | No operations | NO |  | NO
27 | 26-017 | FLOQUIP ENGINEERIING CO | EPI TANK #1 | EPI TANK #1 |  |  | No operations | NO |  | NO
28 | 26-018 | FLOQUIP ENGINEERIING CO | EPI TANK #2 | EPI TANK #2 |  |  | No operations | NO |  | NO
29 | 26-014 | FLOQUIP ENGINEERIING CO | R1 REACTOR | R1 REACTOR |  |  | No operations | NO |  | NO
30 | 26-016 | FLOQUIP ENGINEERIING CO | R3 REACTOR | R3 REACTOR |  |  | No operations | NO |  | NO
31 | 25-134 | VERTIV CORPORATION | BUFFER TANK 11 OF 224 | BUFFER TANK 11 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
32 | 25-127 | VERTIV CORPORATION | BUFFER TANK 4 OF 224 | BUFFER TANK 4 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
33 | 25-308 | VERTIV CORPORATION | BUFFER TANK 185 OF 224 | BUFFER TANK 185 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
34 | 25-170 | VERTIV CORPORATION | BUFFER TANK 47 OF 224 | BUFFER TANK 47 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
35 | 25-171 | VERTIV CORPORATION | BUFFER TANK 48 OF 224 | BUFFER TANK 48 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
36 | OH-26 | SAVANNAH TANK AND EQUIPMENT, INC. |  |  |  |  | In progress: | NO |  | NO
37 | 25-357 | SYLVAMO | SEAL TANK STAND PIPE | SEAL TANK STAND PIPE |  |  | No operations | NO |  | NO
38 | 25-358 | SYLVAMO | RECTANGULAR SEAL TANK | RECTANGULAR SEAL TANK |  |  | No operations | NO |  | NO
39 | 25-356 | SYNTHOMER INC. | EMULSION TANK | EMULSION TANK |  |  | No operations | NO |  | NO
40 | 25-202 | VERTIV CORPORATION | BUFFER TANK 79 OF 224 | BUFFER TANK 79 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
41 | 25-203 | VERTIV CORPORATION | BUFFER TANK 80 OF 224 | BUFFER TANK 80 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
42 | 25-160 | VERTIV CORPORATION | BUFFER TANK 37 OF 224 | BUFFER TANK 37 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
43 | 25-161 | VERTIV CORPORATION | BUFFER TANK 38 OF 224 | BUFFER TANK 38 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
44 | 25-162 | VERTIV CORPORATION | BUFFER TANK 39 OF 224 | BUFFER TANK 39 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
45 | 25-163 | VERTIV CORPORATION | BUFFER TANK 40 OF 224 | BUFFER TANK 40 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
46 | 25-204 | VERTIV CORPORATION | BUFFER TANK 81 OF 224 | BUFFER TANK 81 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
47 | 25-205 | VERTIV CORPORATION | BUFFER TANK 82 OF 224 | BUFFER TANK 82 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
48 | 25-206 | VERTIV CORPORATION | BUFFER TANK 83 OF 224 | BUFFER TANK 83 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
49 | 25-207 | VERTIV CORPORATION | BUFFER TANK 84 OF 224 | BUFFER TANK 84 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
50 | 25-208 | VERTIV CORPORATION | BUFFER TANK 85 OF 224 | BUFFER TANK 85 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
51 | 25-209 | VERTIV CORPORATION | BUFFER TANK 86 OF 224 | BUFFER TANK 86 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
52 | 25-210 | VERTIV CORPORATION | BUFFER TANK 87 OF 224 | BUFFER TANK 87 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
53 | 25-211 | VERTIV CORPORATION | BUFFER TANK 88 OF 224 | BUFFER TANK 88 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
54 | 25-212 | VERTIV CORPORATION | BUFFER TANK 89 OF 224 | BUFFER TANK 89 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
55 | 25-213 | VERTIV CORPORATION | BUFFER TANK 90 OF 224 | BUFFER TANK 90 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
56 | 25-137 | VERTIV CORPORATION | BUFFER TANK 14 OF 224 | BUFFER TANK 14 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
57 | 25-146 | VERTIV CORPORATION | BUFFER TANK 23 OF 224 | BUFFER TANK 23 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
58 | 25-140 | VERTIV CORPORATION | BUFFER TANK 17 OF 224 | BUFFER TANK 17 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
59 | 25-192 | VERTIV CORPORATION | BUFFER TANK 69 OF 224 | BUFFER TANK 69 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
60 | 25-193 | VERTIV CORPORATION | BUFFER TANK 70 OF 224 | BUFFER TANK 70 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
61 | 25-194 | VERTIV CORPORATION | BUFFER TANK 71 OF 224 | BUFFER TANK 71 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
62 | 25-195 | VERTIV CORPORATION | BUFFER TANK 72 OF 224 | BUFFER TANK 72 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
63 | 25-196 | VERTIV CORPORATION | BUFFER TANK 73 OF 224 | BUFFER TANK 73 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
64 | 25-197 | VERTIV CORPORATION | BUFFER TANK 74 OF 224 | BUFFER TANK 74 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
65 | 25-198 | VERTIV CORPORATION | BUFFER TANK 75 OF 224 | BUFFER TANK 75 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
66 | 25-199 | VERTIV CORPORATION | BUFFER TANK 76 OF 224 | BUFFER TANK 76 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
67 | 25-200 | VERTIV CORPORATION | BUFFER TANK 77 OF 224 | BUFFER TANK 77 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
68 | 25-201 | VERTIV CORPORATION | BUFFER TANK 78 OF 224 | BUFFER TANK 78 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
69 | 25-157 | VERTIV CORPORATION | BUFFER TANK 34 OF 224 | BUFFER TANK 34 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
70 | 25-158 | VERTIV CORPORATION | BUFFER TANK 35 OF 224 | BUFFER TANK 35 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
71 | 25-184 | VERTIV CORPORATION | BUFFER TANK 61 OF 224 | BUFFER TANK 61 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
72 | 25-185 | VERTIV CORPORATION | BUFFER TANK 62 OF 224 | BUFFER TANK 62 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
73 | 25-186 | VERTIV CORPORATION | BUFFER TANK 63 OF 224 | BUFFER TANK 63 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
74 | 25-187 | VERTIV CORPORATION | BUFFER TANK 64 OF 224 | BUFFER TANK 64 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
75 | 25-188 | VERTIV CORPORATION | BUFFER TANK 65 OF 224 | BUFFER TANK 65 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
76 | 25-189 | VERTIV CORPORATION | BUFFER TANK 66 OF 224 | BUFFER TANK 66 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
77 | 25-190 | VERTIV CORPORATION | BUFFER TANK 67 OF 224 | BUFFER TANK 67 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
78 | 25-191 | VERTIV CORPORATION | BUFFER TANK 68 OF 224 | BUFFER TANK 68 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
79 | 25-132 | VERTIV CORPORATION | BUFFER TANK 9 OF 224 | BUFFER TANK 9 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
80 | 25-133 | VERTIV CORPORATION | BUFFER TANK 10 OF 224 | BUFFER TANK 10 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
81 | 25-182 | VERTIV CORPORATION | BUFFER TANK 59 OF 224 | BUFFER TANK 59 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
82 | 25-183 | VERTIV CORPORATION | BUFFER TANK 60 OF 224 | BUFFER TANK 60 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
83 | 25-123 | KIMBERLY CLARK CORP | BACKWATER TANK | BACKWATER TANK |  |  | No operations | NO |  | NO
84 | 25-344 | VERTIV CORPORATION | BUFFER TANK 221 OF 224 | BUFFER TANK 221 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
85 | 25-345 | VERTIV CORPORATION | BUFFER TANK 222 OF 224 | BUFFER TANK 222 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
86 | 25-346 | VERTIV CORPORATION | BUFFER TANK 223 OF 224 | BUFFER TANK 223 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
87 | 25-143 | VERTIV CORPORATION | BUFFER TANK 20 OF 224 | BUFFER TANK 20 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
88 | 25-175 | VERTIV CORPORATION | BUFFER TANK 52 OF 224 | BUFFER TANK 52 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
89 | 25-176 | VERTIV CORPORATION | BUFFER TANK 53 OF 224 | BUFFER TANK 53 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
90 | 25-152 | VERTIV CORPORATION | BUFFER TANK 29 OF 224 | BUFFER TANK 29 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
91 | 25-153 | VERTIV CORPORATION | BUFFER TANK 30 OF 224 | BUFFER TANK 30 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
92 | 25-148 | VERTIV CORPORATION | BUFFER TANK 25 OF 224 | BUFFER TANK 25 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
93 | 25-177 | VERTIV CORPORATION | BUFFER TANK 54 OF 224 | BUFFER TANK 54 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
94 | 25-178 | VERTIV CORPORATION | BUFFER TANK 55 OF 224 | BUFFER TANK 55 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
95 | 25-179 | VERTIV CORPORATION | BUFFER TANK 56 OF 224 | BUFFER TANK 56 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
96 | 25-180 | VERTIV CORPORATION | BUFFER TANK 57 OF 224 | BUFFER TANK 57 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
97 | 25-181 | VERTIV CORPORATION | BUFFER TANK 58 OF 224 | BUFFER TANK 58 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
98 | 25-138 | VERTIV CORPORATION | BUFFER TANK 15 OF 224 | BUFFER TANK 15 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
99 | 25-126 | VERTIV CORPORATION | BUFFER TANK 3 OF 224 | BUFFER TANK 3 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
100 | 25-129 | VERTIV CORPORATION | BUFFER TANK 6 OF 224 | BUFFER TANK 6 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
101 | 25-139 | VERTIV CORPORATION | BUFFER TANK 16 OF 224 | BUFFER TANK 16 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
102 | 25-309 | VERTIV CORPORATION | BUFFER TANK 186 OF 224 | BUFFER TANK 186 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
103 | 25-310 | VERTIV CORPORATION | BUFFER TANK 187 OF 224 | BUFFER TANK 187 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
104 | 25-311 | VERTIV CORPORATION | BUFFER TANK 188 OF 224 | BUFFER TANK 188 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
105 | 25-312 | VERTIV CORPORATION | BUFFER TANK 189 OF 224 | BUFFER TANK 189 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
106 | 25-313 | VERTIV CORPORATION | BUFFER TANK 190 OF 224 | BUFFER TANK 190 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
107 | 25-314 | VERTIV CORPORATION | BUFFER TANK 191 OF 224 | BUFFER TANK 191 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
108 | 25-315 | VERTIV CORPORATION | BUFFER TANK 192 OF 224 | BUFFER TANK 192 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
109 | 25-284 | VERTIV CORPORATION | BUFFER TANK 161 OF 224 | BUFFER TANK 161 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
110 | 25-285 | VERTIV CORPORATION | BUFFER TANK 162 OF 224 | BUFFER TANK 162 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
111 | 25-286 | VERTIV CORPORATION | BUFFER TANK 163 OF 224 | BUFFER TANK 163 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
112 | 25-287 | VERTIV CORPORATION | BUFFER TANK 164 OF 224 | BUFFER TANK 164 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
113 | 25-288 | VERTIV CORPORATION | BUFFER TANK 165 OF 224 | BUFFER TANK 165 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
114 | 25-289 | VERTIV CORPORATION | BUFFER TANK 166 OF 224 | BUFFER TANK 166 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
115 | 25-290 | VERTIV CORPORATION | BUFFER TANK 167 OF 224 | BUFFER TANK 167 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
116 | 25-291 | VERTIV CORPORATION | BUFFER TANK 168 OF 224 | BUFFER TANK 168 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
117 | 25-292 | VERTIV CORPORATION | BUFFER TANK 169 OF 224 | BUFFER TANK 169 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
118 | 25-293 | VERTIV CORPORATION | BUFFER TANK 170 OF 224 | BUFFER TANK 170 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
119 | 25-294 | VERTIV CORPORATION | BUFFER TANK 171 OF 224 | BUFFER TANK 171 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
120 | 25-295 | VERTIV CORPORATION | BUFFER TANK 172 OF 224 | BUFFER TANK 172 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
121 | 25-274 | VERTIV CORPORATION | BUFFER TANK 151 OF 224 | BUFFER TANK 151 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
122 | 25-275 | VERTIV CORPORATION | BUFFER TANK 152 OF 224 | BUFFER TANK 152 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
123 | 25-276 | VERTIV CORPORATION | BUFFER TANK 153 OF 224 | BUFFER TANK 153 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
124 | 25-277 | VERTIV CORPORATION | BUFFER TANK 154 OF 224 | BUFFER TANK 154 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
125 | 25-278 | VERTIV CORPORATION | BUFFER TANK 155 OF 224 | BUFFER TANK 155 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
126 | 25-279 | VERTIV CORPORATION | BUFFER TANK 156 OF 224 | BUFFER TANK 156 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
127 | 25-280 | VERTIV CORPORATION | BUFFER TANK 157 OF 224 | BUFFER TANK 157 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
128 | 25-281 | VERTIV CORPORATION | BUFFER TANK 158 OF 224 | BUFFER TANK 158 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
129 | 25-282 | VERTIV CORPORATION | BUFFER TANK 159 OF 224 | BUFFER TANK 159 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
130 | 25-283 | VERTIV CORPORATION | BUFFER TANK 160 OF 224 | BUFFER TANK 160 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
131 | 25-316 | VERTIV CORPORATION | BUFFER TANK 193 OF 224 | BUFFER TANK 193 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
132 | 25-317 | VERTIV CORPORATION | BUFFER TANK 194 OF 224 | BUFFER TANK 194 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
133 | 25-318 | VERTIV CORPORATION | BUFFER TANK 195 OF 224 | BUFFER TANK 195 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
134 | 25-319 | VERTIV CORPORATION | BUFFER TANK 196 OF 224 | BUFFER TANK 196 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
135 | 25-320 | VERTIV CORPORATION | BUFFER TANK 197 OF 224 | BUFFER TANK 197 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
136 | 25-321 | VERTIV CORPORATION | BUFFER TANK 198 OF 224 | BUFFER TANK 198 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
137 | 25-322 | VERTIV CORPORATION | BUFFER TANK 199 OF 224 | BUFFER TANK 199 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
138 | 25-323 | VERTIV CORPORATION | BUFFER TANK 200 OF 224 | BUFFER TANK 200 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
139 | 25-324 | VERTIV CORPORATION | BUFFER TANK 201 OF 224 | BUFFER TANK 201 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
140 | 25-325 | VERTIV CORPORATION | BUFFER TANK 202 OF 224 | BUFFER TANK 202 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
141 | 25-326 | VERTIV CORPORATION | BUFFER TANK 203 OF 224 | BUFFER TANK 203 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
142 | 25-327 | VERTIV CORPORATION | BUFFER TANK 204 OF 224 | BUFFER TANK 204 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
143 | 25-328 | VERTIV CORPORATION | BUFFER TANK 205 OF 224 | BUFFER TANK 205 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
144 | 25-329 | VERTIV CORPORATION | BUFFER TANK 206 OF 224 | BUFFER TANK 206 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
145 | 25-243 | VERTIV CORPORATION | BUFFER TANK 120 OF 224 | BUFFER TANK 120 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
146 | 25-244 | VERTIV CORPORATION | BUFFER TANK 121 OF 224 | BUFFER TANK 121 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
147 | 25-245 | VERTIV CORPORATION | BUFFER TANK 122 OF 224 | BUFFER TANK 122 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
148 | 25-246 | VERTIV CORPORATION | BUFFER TANK 123 OF 224 | BUFFER TANK 123 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
149 | 25-247 | VERTIV CORPORATION | BUFFER TANK 124 OF 224 | BUFFER TANK 124 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
150 | 25-248 | VERTIV CORPORATION | BUFFER TANK 125 OF 224 | BUFFER TANK 125 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
151 | 25-249 | VERTIV CORPORATION | BUFFER TANK 126 OF 224 | BUFFER TANK 126 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
152 | 25-250 | VERTIV CORPORATION | BUFFER TANK 127 OF 224 | BUFFER TANK 127 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
153 | 25-251 | VERTIV CORPORATION | BUFFER TANK 128 OF 224 | BUFFER TANK 128 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
154 | 25-252 | VERTIV CORPORATION | BUFFER TANK 129 OF 224 | BUFFER TANK 129 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
155 | 25-254 | VERTIV CORPORATION | BUFFER TANK 131 OF 224 | BUFFER TANK 131 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
156 | 25-255 | VERTIV CORPORATION | BUFFER TANK 132 OF 224 | BUFFER TANK 132 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
157 | 25-257 | VERTIV CORPORATION | BUFFER TANK 134 OF 224 | BUFFER TANK 134 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
158 | 25-258 | VERTIV CORPORATION | BUFFER TANK 135 OF 224 | BUFFER TANK 135 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
159 | 25-259 | VERTIV CORPORATION | BUFFER TANK 136 OF 224 | BUFFER TANK 136 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
160 | 25-260 | VERTIV CORPORATION | BUFFER TANK 137 OF 224 | BUFFER TANK 137 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
161 | 25-261 | VERTIV CORPORATION | BUFFER TANK 138 OF 224 | BUFFER TANK 138 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
162 | 25-262 | VERTIV CORPORATION | BUFFER TANK 139 OF 224 | BUFFER TANK 139 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
163 | 25-263 | VERTIV CORPORATION | BUFFER TANK 140 OF 224 | BUFFER TANK 140 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
164 | 25-264 | VERTIV CORPORATION | BUFFER TANK 141 OF 224 | BUFFER TANK 141 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
165 | 25-253 | VERTIV CORPORATION | BUFFER TANK 130 OF 224 | BUFFER TANK 130 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
166 | 25-256 | VERTIV CORPORATION | BUFFER TANK 133 OF 224 | BUFFER TANK 133 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
167 | 25-265 | VERTIV CORPORATION | BUFFER TANK 142 OF 224 | BUFFER TANK 142 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
168 | 25-266 | VERTIV CORPORATION | BUFFER TANK 143 OF 224 | BUFFER TANK 143 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
169 | 25-267 | VERTIV CORPORATION | BUFFER TANK 144 OF 224 | BUFFER TANK 144 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
170 | 25-268 | VERTIV CORPORATION | BUFFER TANK 145 OF 224 | BUFFER TANK 145 OF 224 |  |  | In fabrication (0% ops complete) | NO |  | NO
171 | 25-269 | VERTIV CORPORATION | BUFFER TANK 146 OF 224 | BUFFER TANK 146 OF 224 |  |  | In fabrication (0% ops complete) | NO |  | NO
172 | 25-270 | VERTIV CORPORATION | BUFFER TANK 147 OF 224 | BUFFER TANK 147 OF 224 |  |  | In fabrication (0% ops complete) | NO |  | NO
173 | 25-271 | VERTIV CORPORATION | BUFFER TANK 148 OF 224 | BUFFER TANK 148 OF 224 |  |  | In fabrication (0% ops complete) | NO |  | NO
174 | 25-272 | VERTIV CORPORATION | BUFFER TANK 149 OF 224 | BUFFER TANK 149 OF 224 |  |  | In fabrication (0% ops complete) | NO |  | NO
175 | 25-330 | VERTIV CORPORATION | BUFFER TANK 207 OF 224 | BUFFER TANK 207 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
176 | 25-331 | VERTIV CORPORATION | BUFFER TANK 208 OF 224 | BUFFER TANK 208 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
177 | 25-332 | VERTIV CORPORATION | BUFFER TANK 209 OF 224 | BUFFER TANK 209 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
178 | 25-333 | VERTIV CORPORATION | BUFFER TANK 210 OF 224 | BUFFER TANK 210 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
179 | 25-334 | VERTIV CORPORATION | BUFFER TANK 211 OF 224 | BUFFER TANK 211 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
180 | 25-335 | VERTIV CORPORATION | BUFFER TANK 212 OF 224 | BUFFER TANK 212 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
181 | 25-336 | VERTIV CORPORATION | BUFFER TANK 213 OF 224 | BUFFER TANK 213 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
182 | 25-337 | VERTIV CORPORATION | BUFFER TANK 214 OF 224 | BUFFER TANK 214 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
183 | 25-338 | VERTIV CORPORATION | BUFFER TANK 215 OF 224 | BUFFER TANK 215 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
184 | 25-339 | VERTIV CORPORATION | BUFFER TANK 216 OF 224 | BUFFER TANK 216 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
185 | 25-340 | VERTIV CORPORATION | BUFFER TANK 217 OF 224 | BUFFER TANK 217 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
186 | 25-341 | VERTIV CORPORATION | BUFFER TANK 218 OF 224 | BUFFER TANK 218 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
187 | 25-342 | VERTIV CORPORATION | BUFFER TANK 219 OF 224 | BUFFER TANK 219 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
188 | 25-343 | VERTIV CORPORATION | BUFFER TANK 220 OF 224 | BUFFER TANK 220 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
189 | 25-348 | VERTIV CORPORATION | EXP TANK SHIPMENT 1 (24) | EXP TANK SHIPMENT 1 (24) |  |  | No operations | NO |  | NO
190 | 25-214 | VERTIV CORPORATION | BUFFER TANK 91 OF 224 | BUFFER TANK 91 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
191 | 25-216 | VERTIV CORPORATION | BUFFER TANK 93 OF 224 | BUFFER TANK 93 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
192 | 25-217 | VERTIV CORPORATION | BUFFER TANK 94 OF 224 | BUFFER TANK 94 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
193 | 25-218 | VERTIV CORPORATION | BUFFER TANK 95 OF 224 | BUFFER TANK 95 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
194 | 25-219 | VERTIV CORPORATION | BUFFER TANK 96 OF 224 | BUFFER TANK 96 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
195 | 25-220 | VERTIV CORPORATION | BUFFER TANK 97 OF 224 | BUFFER TANK 97 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
196 | 25-221 | VERTIV CORPORATION | BUFFER TANK 98 OF 224 | BUFFER TANK 98 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
197 | 25-222 | VERTIV CORPORATION | BUFFER TANK 99 OF 224 | BUFFER TANK 99 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
198 | 25-223 | VERTIV CORPORATION | BUFFER TANK 100 OF 224 | BUFFER TANK 100 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
199 | 25-225 | VERTIV CORPORATION | BUFFER TANK 102 OF 224 | BUFFER TANK 102 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
200 | 25-226 | VERTIV CORPORATION | BUFFER TANK 103 OF 224 | BUFFER TANK 103 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
201 | 25-227 | VERTIV CORPORATION | BUFFER TANK 104 OF 224 | BUFFER TANK 104 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
202 | 25-228 | VERTIV CORPORATION | BUFFER TANK 105 OF 224 | BUFFER TANK 105 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
203 | 25-229 | VERTIV CORPORATION | BUFFER TANK 106 OF 224 | BUFFER TANK 106 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
204 | 25-230 | VERTIV CORPORATION | BUFFER TANK 107 OF 224 | BUFFER TANK 107 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
205 | 25-231 | VERTIV CORPORATION | BUFFER TANK 108 OF 224 | BUFFER TANK 108 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
206 | 25-232 | VERTIV CORPORATION | BUFFER TANK 109 OF 224 | BUFFER TANK 109 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
207 | 25-233 | VERTIV CORPORATION | BUFFER TANK 110 OF 224 | BUFFER TANK 110 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
208 | 25-234 | VERTIV CORPORATION | BUFFER TANK 111 OF 224 | BUFFER TANK 111 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
209 | 25-236 | VERTIV CORPORATION | BUFFER TANK 113 OF 224 | BUFFER TANK 113 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
210 | 25-237 | VERTIV CORPORATION | BUFFER TANK 114 OF 224 | BUFFER TANK 114 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
211 | 25-238 | VERTIV CORPORATION | BUFFER TANK 115 OF 224 | BUFFER TANK 115 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
212 | 25-239 | VERTIV CORPORATION | BUFFER TANK 116 OF 224 | BUFFER TANK 116 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
213 | 25-240 | VERTIV CORPORATION | BUFFER TANK 117 OF 224 | BUFFER TANK 117 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
214 | 25-241 | VERTIV CORPORATION | BUFFER TANK 118 OF 224 | BUFFER TANK 118 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
215 | 25-242 | VERTIV CORPORATION | BUFFER TANK 119 OF 224 | BUFFER TANK 119 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
216 | 25-224 | VERTIV CORPORATION | BUFFER TANK 101 OF 224 | BUFFER TANK 101 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
217 | 25-235 | VERTIV CORPORATION | BUFFER TANK 112 OF 224 | BUFFER TANK 112 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
218 | 25-215 | VERTIV CORPORATION | BUFFER TANK 92 OF 224 | BUFFER TANK 92 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
219 | 25-296 | VERTIV CORPORATION | BUFFER TANK 173 OF 224 | BUFFER TANK 173 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
220 | 25-297 | VERTIV CORPORATION | BUFFER TANK 174 OF 224 | BUFFER TANK 174 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
221 | 25-298 | VERTIV CORPORATION | BUFFER TANK 175 OF 224 | BUFFER TANK 175 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
222 | 25-299 | VERTIV CORPORATION | BUFFER TANK 176 OF 224 | BUFFER TANK 176 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
223 | 25-300 | VERTIV CORPORATION | BUFFER TANK 177 OF 224 | BUFFER TANK 177 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
224 | 25-301 | VERTIV CORPORATION | BUFFER TANK 178 OF 224 | BUFFER TANK 178 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
225 | 25-302 | VERTIV CORPORATION | BUFFER TANK 179 OF 224 | BUFFER TANK 179 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
226 | 25-303 | VERTIV CORPORATION | BUFFER TANK 180 OF 224 | BUFFER TANK 180 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
227 | 25-304 | VERTIV CORPORATION | BUFFER TANK 181 OF 224 | BUFFER TANK 181 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
228 | 25-305 | VERTIV CORPORATION | BUFFER TANK 182 OF 224 | BUFFER TANK 182 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
229 | 25-306 | VERTIV CORPORATION | BUFFER TANK 183 OF 224 | BUFFER TANK 183 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
230 | 25-307 | VERTIV CORPORATION | BUFFER TANK 184 OF 224 | BUFFER TANK 184 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
231 | 25-121 | KIMBERLY CLARK CORP | DUMP CHEST TANK | DUMP CHEST TANK |  |  | No operations | NO |  | NO
232 | 25-273 | VERTIV CORPORATION | BUFFER TANK 150 OF 224 | BUFFER TANK 150 OF 224 |  |  | In fabrication (0% ops complete) | NO |  | NO
233 | 25-347 | VERTIV CORPORATION | BUFFER TANK 224 OF 224 | BUFFER TANK 224 OF 224 |  |  | In fabrication (0% ops complete) | NO |  | NO
234 | 25-349 | VERTIV CORPORATION | EXP TANK SHIPMENT 2 (32) | EXP TANK SHIPMENT 2 (32) |  |  | No operations | NO |  | NO
235 | 25-350 | VERTIV CORPORATION | EXP TANK SHIPMENT 3 (44) | EXP TANK SHIPMENT 3 (44) |  |  | No operations | NO |  | NO
236 | 25-351 | VERTIV CORPORATION | EXP TANK SHIPMENT 4 (28) | EXP TANK SHIPMENT 4 (28) |  |  | No operations | NO |  | NO
237 | 25-352 | VERTIV CORPORATION | EXP TANK SHIPMENT 5 (32) | EXP TANK SHIPMENT 5 (32) |  |  | No operations | NO |  | NO
238 | 25-353 | VERTIV CORPORATION | EXP TANK SHIPMENT 6 (28) | EXP TANK SHIPMENT 6 (28) |  |  | No operations | NO |  | NO
239 | 25-354 | VERTIV CORPORATION | EXP TANK SHIPMENT 7 (24) | EXP TANK SHIPMENT 7 (24) |  |  | No operations | NO |  | NO
240 | 25-355 | VERTIV CORPORATION | EXP TANK SHIPMENT 8 (12) | EXP TANK SHIPMENT 8 (12) |  |  | No operations | NO |  | NO
241 | 25-144 | VERTIV CORPORATION | BUFFER TANK 21 OF 224 | BUFFER TANK 21 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
242 | 25-136 | VERTIV CORPORATION | BUFFER TANK 13 OF 224 | BUFFER TANK 13 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
243 | 25-149 | VERTIV CORPORATION | BUFFER TANK 26 OF 224 | BUFFER TANK 26 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
244 | 25-164 | VERTIV CORPORATION | BUFFER TANK 41 OF 224 | BUFFER TANK 41 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
245 | 25-135 | VERTIV CORPORATION | BUFFER TANK 12 OF 224 | BUFFER TANK 12 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
246 | 25-172 | VERTIV CORPORATION | BUFFER TANK 49 OF 224 | BUFFER TANK 49 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
247 | 25-173 | VERTIV CORPORATION | BUFFER TANK 50 OF 224 | BUFFER TANK 50 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
248 | 25-145 | VERTIV CORPORATION | BUFFER TANK 22 OF 224 | BUFFER TANK 22 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
249 | 25-130 | VERTIV CORPORATION | BUFFER TANK 7 OF 224 | BUFFER TANK 7 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
250 | 25-142 | VERTIV CORPORATION | BUFFER TANK 19 OF 224 | BUFFER TANK 19 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
251 | 25-141 | VERTIV CORPORATION | BUFFER TANK 18 OF 224 | BUFFER TANK 18 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
252 | 25-131 | VERTIV CORPORATION | BUFFER TANK 8 OF 224 | BUFFER TANK 8 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
253 | 25-147 | VERTIV CORPORATION | BUFFER TANK 24 OF 224 | BUFFER TANK 24 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
254 | 25-151 | VERTIV CORPORATION | BUFFER TANK 28 OF 224 | BUFFER TANK 28 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
255 | 25-159 | VERTIV CORPORATION | BUFFER TANK 36 OF 224 | BUFFER TANK 36 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
256 | 25-124 | VERTIV CORPORATION | BUFFER TANK 1 OF 224 | BUFFER TANK 1 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
257 | 25-125 | VERTIV CORPORATION | BUFFER TANK 2 OF 224 | BUFFER TANK 2 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
258 | 25-150 | VERTIV CORPORATION | BUFFER TANK 27 OF 224 | BUFFER TANK 27 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
259 | 25-155 | VERTIV CORPORATION | BUFFER TANK 32 OF 224 | BUFFER TANK 32 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
260 | 25-156 | VERTIV CORPORATION | BUFFER TANK 33 OF 224 | BUFFER TANK 33 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
261 | 25-174 | VERTIV CORPORATION | BUFFER TANK 51 OF 224 | BUFFER TANK 51 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
262 | 25-154 | VERTIV CORPORATION | BUFFER TANK 31 OF 224 | BUFFER TANK 31 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
263 | 25-165 | VERTIV CORPORATION | BUFFER TANK 42 OF 224 | BUFFER TANK 42 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
264 | 25-166 | VERTIV CORPORATION | BUFFER TANK 43 OF 224 | BUFFER TANK 43 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
265 | 25-167 | VERTIV CORPORATION | BUFFER TANK 44 OF 224 | BUFFER TANK 44 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
266 | 25-168 | VERTIV CORPORATION | BUFFER TANK 45 OF 224 | BUFFER TANK 45 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
267 | 25-169 | VERTIV CORPORATION | BUFFER TANK 46 OF 224 | BUFFER TANK 46 OF 224 |  |  | Cleaning and prep in progress | NO |  | NO
268 | 25-122 | KIMBERLY CLARK CORP | PROCESS TENSIDE TANK | PROCESS TENSIDE TANK |  |  | No operations | NO |  | NO
269 | 25-120 | ANDRITZ INC | DISSOLVING TANK (FABRICATION) | DISSOLVING TANK (FABRICATION) |  |  | No operations | NO |  | NO
270 | 25-119 | VERTIV CORPORATION | DWG ONLY-SMARTRUN BUFFER TANKS | DWG ONLY-SMARTRUN BUFFER TANKS |  |  | No operations | NO |  | NO
271 | 25-118 | MERRICK INDUSTRIES, INC. | MH-5301-HP-05000-CASING | MH-5301-HP-05000-CASING |  |  | Cleaning and prep in progress | NO |  | YES
272 | 25-117 | MERRICK INDUSTRIES, INC. | MH-5301-HP-02000-CASING | MH-5301-HP-02000-CASING |  |  | Cleaning and prep in progress | NO |  | YES
273 | 25-116 | POLYNT COMPOSITES USA INC | MALEIC ANHYDRIDE TANK | MALEIC ANHYDRIDE TANK |  |  | No operations | NO |  | NO
274 | 25-102 | EPIC SYSTEMS GROUP. LLC - P&M | T-101 | T-101 |  |  | No operations | NO |  | NO
275 | 25-103 | EPIC SYSTEMS GROUP. LLC - P&M | T-104 | T-104 |  |  | No operations | NO |  | NO
276 | 25-104 | EPIC SYSTEMS GROUP. LLC - P&M | T-103 | T-103 |  |  | No operations | NO |  | NO
277 | 25-106 | EPIC SYSTEMS GROUP. LLC - P&M | T-121 | T-121 |  |  | No operations | NO |  | NO
278 | 25-107 | EPIC SYSTEMS GROUP. LLC - P&M | T-113 | T-113 |  |  | No operations | NO |  | NO
279 | 25-108 | EPIC SYSTEMS GROUP. LLC - P&M | T-114 | T-114 |  |  | No operations | NO |  | NO
280 | 25-109 | EPIC SYSTEMS GROUP. LLC - P&M | V-117 | V-117 |  |  | No operations | NO |  | NO
281 | 25-110 | EPIC SYSTEMS GROUP. LLC - P&M | T-117 | T-117 |  |  | No operations | NO |  | NO
282 | 25-111 | EPIC SYSTEMS GROUP. LLC - P&M | T-118A | T-118A |  |  | No operations | NO |  | NO
283 | 25-112 | EPIC SYSTEMS GROUP. LLC - P&M | T-118B | T-118B |  |  | No operations | NO |  | NO
284 | 25-113 | EPIC SYSTEMS GROUP. LLC - P&M | T-120 | T-120 |  |  | No operations | NO |  | NO
285 | 25-115 | EPIC SYSTEMS GROUP. LLC - P&M | V-104 | V-104 |  |  | No operations | NO |  | NO
286 | 25-105 | EPIC SYSTEMS GROUP. LLC - P&M | T-105 | T-105 |  |  | No operations | NO |  | NO
287 | 25-114 | EPIC SYSTEMS GROUP. LLC - P&M | V-103 | V-103 |  |  | No operations | NO |  | NO
288 | 25-101 | HARPERLOVE | T-1615 RUPTURE DISK CATCH TANK | T-1615 RUPTURE DISK CATCH TANK |  |  | Cleaning and prep in progress | NO |  | NO
289 | 25-099 | BURKE INDUSTRIAL, INC. | CONE BOTTOM W/COIL | CONE BOTOOM W/COIL |  |  | Cleaning and prep in progress | NO |  | NO
290 | 25-098 | COASTAL TECHNOLOGIES, INC. | MIST ELIMINATOR W/FACE WASH | MIST ELIMINATOR W/FACE WASH |  |  | In fabrication (0% ops complete) | NO |  | NO
291 | 25-095 | ANDRITZ INC | DISSOLVING TANK (DWG ONLY) | DISSOLVING TANK (DWG ONLY) |  |  | No operations | NO |  | NO
292 | 25-092 | AMERITERPENES LLC | CARBON UNIT #1 | CARBON UNIT #1 |  |  | Cleaning and prep in progress | NO |  | YES
293 | 25-093 | AMERITERPENES LLC | CARBON UNIT #2 | CARBON UNIT #2 |  |  | Cleaning and prep in progress | NO |  | YES
294 | 25-091 | US SUGAR REFINERY, LLC | API MANWAY | API MANWAY |  |  | Cleaning and prep in progress | NO |  | NO
295 | 25-090 | GAF MATERIALS, LLC | (2) SSI SKI PLATE | (2) SS SKI PLATE |  |  | No operations | NO |  | NO
296 | 25-086 | TELLUS PRODUCTS | SS FLANGE RING | SS FLANGE RING |  |  | Cleaning and prep in progress | NO |  | NO
297 | 25-084 | ATLAS MINERALS & CHEMICALS | SULFUR HOLDING TANK | SULFUR HOLDING TANK |  |  | Cleaning and prep in progress | NO |  | YES
298 | 25-083 | SYNTHOMER INC. | REACTOR 12 | REACTOR 12 |  |  | Cleaning and prep in progress | NO |  | NO
299 | 25-082 | TOM HENLEY | ROLLED PLATE | ROLLED PLATE |  |  | In progress: Misc Fabrication | NO |  | NO
300 | 25-081 | PRO PIPE INC | 20" ROLLED PIPE | 20" ROLLED PIPE |  |  | Shell fabrication in progress | NO |  | NO
301 | 25-068 | RECO COMMERCIAL SYSTEMS | BUFFER TANK #13 |  |  |  | Cleaning and prep in progress | NO |  | YES
302 | 25-069 | RECO COMMERCIAL SYSTEMS | BUFFER TANK #14 | BUFFER TANK #14 |  |  | Cleaning and prep in progress | NO |  | YES
303 | 25-070 | RECO COMMERCIAL SYSTEMS | BUFFER TANK #15 | BUFFER TANK #15 |  |  | Cleaning and prep in progress | NO |  | YES
304 | 25-071 | RECO COMMERCIAL SYSTEMS | BUFFER TANK #16 | BUFFER TANK #16 |  |  | Cleaning and prep in progress | NO |  | YES
305 | 25-055 | AIRGAS NITROUS OXIDE | SST N20 REACTOR | SST N20 REACTOR |  |  | In fabrication (0% ops complete) | NO |  | NO
306 | 25-053 | ANDRITZ INC | VAPOR DUCTING 300122163 | VAPOR DUCTING 300122163 |  |  | Cleaning and prep in progress | NO |  | YES
307 | 24-073 | R2T CONSTRUCTORS | TAXES | TAXES |  |  | No operations | NO |  | NO
308 | 25-051 | US SUGAR CORPORATION | EXPLOSION VENT PANEL | EXPLOSION VENT PANEL |  |  | No operations | NO |  | NO
309 | 25-050 | TIC-THE INDUSTRIAL COMPANY | (8) GASKETS | (8) GASKETS |  |  | No operations | NO |  | NO
310 | 25-049 | YOWN'S BOILER & FURNACE SERVICE LLC | TANK PATCH REPAIR | TANK PATCH REPAIR |  |  | No operations | NO |  | NO
311 | 25-048 | US SUGAR CORPORATION | EXPLOSION VENT PANEL | EXPLOSION VENT PANEL |  |  | No operations | NO |  | NO
312 | 25-047 | APPLIED INDUSTRIAL TECHNOLOGIES | (2) VIBE PADS | (2) VIBE PADS |  |  | In progress: Fab Miscellaneous Parts | NO |  | NO
313 | 25-046 | INDUSTRIAL SUPPLIES COMPANY | CHASE GASKET | CHASE GASKET |  |  | No operations | NO |  | NO
314 | 25-045 | PRO PIPE INC | NOZZLES AND AGITATOR SUPPORTS | NOZZLES AND AGITATOR SUPPORTS |  |  | Cleaning and prep in progress | NO |  | NO
315 | 25-043 | Ecopol America, Inc. | FEA & CYCLIC ANALYSIS |  |  |  | No operations | NO |  | NO
316 | 25-042 | ANDRITZ INC | FOUL CONDENSATE TANK | FOUL CONDENSATE TANK |  |  | Cleaning and prep in progress | NO |  | NO
317 | 25-041 | INDUSTRIAL SUPPLIES COMPANY | CHASE GASKET | CHASE GASKET |  |  | No operations | NO |  | NO
318 | 25-040 | NAK KILN SERVICES, LLC | HR 120 SHELL | HR 120 SHELL |  |  | Cleaning and prep in progress | NO |  | NO
319 | 25-038 | AJAY NORTH AMERICA, LLC | PE STAMP FOR JN 122-22 | PE STAMP FOR JN 122-22 |  |  | No operations | NO |  | NO
320 | 25-022 | KIMBERLY CLARK CORP | EST SHIPPING 25-007/021;25-094 | EST SHIPPING 25-007/021;25-094 |  |  | No operations | NO |  | NO
321 | 25-012 | KIMBERLY CLARK CORP | 330-TK-3301 | 330-TK-33001 |  |  | Cleaning and prep in progress | NO |  | NO
322 | 25-013 | KIMBERLY CLARK CORP | 340-TK-34001 | 340-TK-34001 |  |  | Cleaning and prep in progress | NO |  | NO
323 | 25-006 | CONSOLIDATED DESIGN & MACHINE | USE OF SHOP INSULATION | USE OF SHOP INSULATION |  |  | No operations | NO |  | NO
324 | 25-001 | US SUGAR REFINERY, LLC | 144" FLAT BOTTOM | 144" FLAT BOTTOM |  |  | Cleaning and prep in progress | NO |  | NO
325 | 24-072 | R2T CONSTRUCTORS | EXTENDED WARRANTY | EXTENDED WARRANTY |  |  | No operations | NO |  | NO
326 | 24-071 | R2T CONSTRUCTORS | TANGENTIAL NOZZLE CHARGES | TANGENTIAL NOZZLE CHARGES |  |  | In fabrication (0% ops complete) | NO |  | NO
327 | 24-061 | INDUSTRIAL SUPPLIES COMPANY | (2) CHASE GASKETS | (2) CHASE GASKETS |  |  | No operations | NO |  | NO
328 | 24-059 | LF MULTICRAFT INC. | ROLL HANDRAIL & ANGLE | ROLL HANDRAIL & ANGLE |  |  | Shell fabrication in progress | NO |  | NO
329 | 24-058 | FLOQUIP ENGINEERIING CO | (5) MANWAY GASKETS | (5) MANWAY GASKETS |  |  | No operations | NO |  | NO
330 | 24-057 | HOLBROOK METAL FABRICATION | FORM (2) CONES | FORM (2) CONES |  |  | Cutting/pre-fab in progress | NO |  | NO
331 | 24 | [5 empty] | No operations | NO |  | NO
332 | 24-045 | PISTOL'S INDUSTRIAL SERVICE | OIL/WATER SEPARATION TANK | OIL/WATER SEPARATION TANK |  |  | Cleaning and prep in progress | NO |  | NO
333 | 24-046 | SYMS ENGINEERING, INC. | NMP STORAGE TANK (TK-F502R) | NMP STORAGE TANK (TK-F502R) |  |  | Cleaning and prep in progress | NO |  | YES
334 | 24-043 | FLOQUIP ENGINEERIING CO | MANWAY HARDWARE TO CONVERT TO TOOL LESS | MANWAY HARDWARE TO CONVERT TO TOOL LESS |  |  | No operations | NO |  | NO
335 | 24-040 | FIRST PLACE FABRICATION LLC | CUT AND BEND PLATES | CUT AND BEND PLATES |  |  | Cutting/pre-fab in progress | NO |  | NO
336 | 24-039 | ROSENBLAD DESIGN GROUP, INC. | FORM ELBOWS | FORM ELBOWS |  |  | In progress: Fab Miscellaneous Parts | NO |  | NO
337 | 24-038 | ROSENBLAD DESIGN GROUP, INC. | Form (2) Cones per Customer Drawing |  |  |  | In progress: Build Bottom Head/Cone | NO |  | NO
338 | 24-026 | NANT RENEWABLES, LLC | Blast & Paint Interior of JNs 068 & 069-22 |  |  |  | No operations | NO |  | NO
339 | 24-025 | US SUGAR CORPORATION | EXPLOSION VENT PANEL | EXPLOSION VENT PANEL |  |  | No operations | NO |  | NO
340 | 24-024 | GARRETT MACHINE | 310 SS CYLINDER | 310 SS CYLINDER |  |  | Shell fabrication in progress | NO |  | NO
341 | 23-105 | TIC-THE INDUSTRIAL COMPANY | SPARE GASKETS | SPARE GASKETS |  |  | No operations | NO |  | NO
342 | 23-104 | TURNER CONSTRUCTION COMPANY | FINANCE/STORAGE FEE | FINANCE/STORAGE FEE |  |  | No operations | NO |  | NO
343 | 24-020 | KANGWON N.T.S. CO., LTD | ADDITIONAL REPAIRS TO 007-24 | ADDITIONAL REPAIRS TO 007-24 |  |  | No operations | NO |  | NO
344 | 24-021 | KANGWON N.T.S. CO., LTD | ADDITIONAL REPAIRS TO 008-24 | ADDITIONAL REPAIRS TO 008-24 |  |  | No operations | NO |  | NO
345 | 24-001 | LIOCHEM | CHANGE ORDER TO 23-053 & 23-054 | CHANGE ORDER TO 23-053 & 23-054 |  |  | No operations | NO |  | NO
346 | 23-102 | TIC-THE INDUSTRIAL COMPANY | EXTENDED WARRANTY | EXTENDED WARRANTY |  |  | No operations | NO |  | NO
347 | 23-075 | TURNER CONSTRUCTION COMPANY | V-3091 ANU WORKING TANK W/AGITATOR | V-3091 ANU WORKING TANK W/AGITATOR |  |  | No operations | NO |  | NO
348 | 23-076 | TURNER CONSTRUCTION COMPANY | V-3101 ANU WORKING TANK W/AGITATOR | V-3101 ANU WORKING TANK W/AGITATOR |  |  | No operations | NO |  | NO
349 | 23-077 | TURNER CONSTRUCTION COMPANY | V-3111 ANU WORKING TANK W/AGITATOR | V-3111 ANU WORKING TANK W/AGITATOR |  |  | No operations | NO |  | NO
350 | 23-078 | TURNER CONSTRUCTION COMPANY | V-3121 ANU WORKING TANK W/AGITATOR | V-3121 ANU WORKING TANK W/AGITATOR |  |  | No operations | NO |  | NO
351 | 23-079 | TURNER CONSTRUCTION COMPANY | V-3141 ANU WORKING TANK W/AGITATOR | V-3141 ANU WORKING TANK W/AGITATOR |  |  | No operations | NO |  | NO
352 | 23-080 | TURNER CONSTRUCTION COMPANY | r-3401 OPACIFIER MIXING TANK | R-3401 OPACIFIER MIXING TANK |  |  | No operations | NO |  | NO
353 | 23-081 | TURNER CONSTRUCTION COMPANY | 4-3441 OPACIFIER DISTRIBUTION TANK | R-3441 OPACIFIER DISTRIBUTION TANK |  |  | No operations | NO |  | NO
354 | 23-082 | TURNER CONSTRUCTION COMPANY | R-3451 OPACIFIER DISTRIBUTION TANK | R-3451 OPACIFIER DISTRIBUTION TANK |  |  | No operations | NO |  | NO
355 | 23-084 | TURNER CONSTRUCTION COMPANY | V-5161 CIP COLLECTION TANK | V-5161 CIP COLLECTION TANK |  |  | No operations | NO |  | NO
356 | 23-085 | TURNER CONSTRUCTION COMPANY | V-4641 ETHANOL COLLECTION TANK | V-4641 ETHANOL COLLECTION TANK |  |  | No operations | NO |  | NO
357 | 23-086 | TURNER CONSTRUCTION COMPANY | R-3271 CATALYST TANK | R-3271 CATALYST TANK |  |  | No operations | NO |  | NO
358 | 23-087 | TURNER CONSTRUCTION COMPANY | R-3291 CATALYST TANK | R-3291 CATALYST TANK |  |  | No operations | NO |  | NO
359 | 23-088 | TURNER CONSTRUCTION COMPANY | R-3581 CATALYST NEUTRALIZATION TANK | R-3581 CATALYST NEUTRALIZATION TANK |  |  | No operations | NO |  | NO
360 | 23-089 | TURNER CONSTRUCTION COMPANY | V-5051 KNOCK OUT POT | V-5051 KNOCK OUT POT |  |  | No operations | NO |  | NO
361 | 23-090 | TURNER CONSTRUCTION COMPANY | V-5261 KNOCK OUT POT | V-5261 KNOCK OUT POT |  |  | No operations | NO |  | NO
362 | 23-091 | TURNER CONSTRUCTION COMPANY | V-5061 KNOCK OUT POT | V-5061 KNOCK OUT POT |  |  | No operations | NO |  | NO
363 | 23-092 | TURNER CONSTRUCTION COMPANY | V-6002 KNOCK OUT POT | V-6002 KNOCK OUT POT |  |  | No operations | NO |  | NO
364 | 23-093 | TURNER CONSTRUCTION COMPANY | SAMPLING VALVES | SAMPLING VALVES |  |  | No operations | NO |  | NO
365 | 23-083 | TURNER CONSTRUCTION COMPANY | V-5251 SEAL WATER COLLECTION TANK | V-5251 SEAL WATER COLLECTION TANK |  |  | No operations | NO |  | NO
366 | 23-072 | SYMS ENGINEERING, INC. | CHANGE ORDER TO 067-23 | CHANGE ORDER TO 067-23 |  |  | No operations | NO |  | NO
367 | 23-066 | ENCHEM AMERICA, LLC | ADDITIONS-YT-1410 & YT-1420 | ADDITIONS-YT-1410 & YT-1420 |  |  | No operations | NO |  | NO
368 | 23-056 | FLOQUIP ENGINEERIING CO | (4) 24" GASKETS | (4) 24" GASKETS |  |  | No operations | NO |  | NO
369 | 23-049 | ARCH WOOD PROTECTION, INC. | PLATFORM SYSTEM | PLATFORM SYSTEM |  |  | No operations | NO |  | NO
370 | 23-050 | ARCH WOOD PROTECTION, INC. | FREIGHT | FREIGHT |  |  | No operations | NO |  | NO
371 | 23-043 | ENCHEM AMERICA, LLC | INSTALL (6) 100 M3 STORAGE TANKS | INSTALL (6) 100 M3 STORAGE TANKS |  |  | No operations | NO |  | NO
372 | 23-042 | ENCHEM AMERICA, LLC | 300 M3 SS API TANK (FIELD KIT) | 300 M3 SS API TANK (FIELD KIT) |  |  | Cleaning and prep in progress | NO |  | YES
373 | 23-039 | CON-CRET, LLC | SPARE PARTS | SPARE PARTS |  |  | No operations | NO |  | NO
374 | 23-038 | CORROCOAT | REPLACEMENT PARTS | REPLACEMENT PARTS |  |  | In progress: Make Manway Parts | NO |  | NO
375 | 23-025 | LEAR WEST FABRICATION, LLC | (4) ROLLED RINGS | (4) ROLLED RINGS |  |  | Shell fabrication in progress | NO |  | NO
376 | 23-022 | SAVANNAH TANK AND EQUIPMENT, INC. | SAVANNAH TANK DEMO | SAVANNAH TANK DEMO |  |  | Cleaning and prep in progress | NO |  | YES
377 | 23-008 | TURNER CONSTRUCTION COMPANY | V-1121 (S-40 DAY TANK) | V-1121 (S-40 DAY TANK) |  |  | No operations | NO |  | NO
378 | 23-009 | TURNER CONSTRUCTION COMPANY | V-1141 (S-40 DAY TANK) | V-1141 (S-40 DAY TANK) |  |  | No operations | NO |  | NO
379 | 23-010 | TURNER CONSTRUCTION COMPANY | V-1131 (MTES DAY TANK) | V-1131 (MTES DAY TANK) |  |  | No operations | NO |  | NO
380 | 23-011 | TURNER CONSTRUCTION COMPANY | V-1151 (MTES DAY TANK) | V-1151 (MTES DAY TANK) |  |  | No operations | NO |  | NO
381 | 23-012 | TURNER CONSTRUCTION COMPANY | V-1161 (DMDES DAY TANK) | V-1161 (DMDES DAY TANK) |  |  | No operations | NO |  | NO
382 | 23-013 | TURNER CONSTRUCTION COMPANY | AGING ETHANOL TANK V-3491 | AGING ETHANOL TANK V-3491 |  |  | No operations | NO |  | NO
383 | 22-139 | SABINA GOLD & SILVER CORP. | PE STAMPS | PE STAMPS |  |  | No operations | NO |  | NO
384 | 22-140 | SABINA GOLD & SILVER CORP. | ESTIMATED SHIPPING | ESTIMATED SHIPPING |  |  | No operations | NO |  | NO
385 | 22-128 | CYTEC INDUSTRIES INC., NA | CHANGE ORDER-PO 4504462122 | CHANGE ORDER-PO 4504462122 |  |  | No operations | NO |  | NO
386 | 22-123 | SYMRISE | SS STORAGE TANK (#1406) | SS STORAGE TANK (#1406) |  |  | No operations | NO |  | NO
387 | 22-121 | FLOQUIP ENGINEERIING CO | (8) MANWAY HARDWARE | (8) MANWAY HARDWARE |  |  | No operations | NO |  | NO
388 | 22-117 | MILLIKEN & CO | 2,000 GAL FEED TK (TAK-70) CO | 2,000 GAL FEED TK (TAK-70) CO |  |  | No operations | NO |  | NO
389 | 22-087 | PINOVA INC | 24" API 650 ROOF MNWY CVR | 24" API 650 ROOF MNWY CVR |  |  | In progress: B&C parts-lugs, supp, etc | NO |  | NO
390 | 22-084 | NANT RENEWABLES, LLC | (4) LADDERS | (4) LADDERS |  |  | No operations | NO |  | NO
391 | 22-073 | NANT RENEWABLES, LLC | SHIPPING | SHIPPING |  |  | No operations | NO |  | NO
392 | 22-072 | NANT RENEWABLES, LLC | TANK ACCESSORIES | TANK ACCESSORIES |  |  | No operations | NO |  | NO
393 | 22-060 | SOUTH GEORGIA INDUSTRIAL SERVICES, INC. | USE OF R-STAMP | USE OF R-STAMP |  |  | No operations | NO |  | NO
394 | 22-017 | MILLIKEN & CO | SS PROCESS TANK (TAT-17) | SS PROCESS TANK (TAT-17) |  |  | Cleaning and prep in progress | NO |  | NO
395 | 22-013 | ENCHEM AMERICA, LLC | MECHANICAL INSTALLATION-TKS | MECHANICAL INSTALLATION-TKS |  |  | No operations | NO |  | NO
396 | 22-014 | ENCHEM AMERICA, LLC | FREIGHT TK-1005,1006,1007 | FREIGHT TK 1005,1006,1007 |  |  | No operations | NO |  | NO
397 | 21-158 | US SUGAR CORPORATION | 61100 GAL SYRUP TANK FIELD INS | 61100 GAL SYRUP TANK FIELD INS |  |  | No operations | NO |  | NO
398 | 21-156 | CON-CRET, LLC | 20,000 GAL SS ETHANOL STORAGE | 20,000 GAL SS ETHANOL STORAGE |  |  | Cleaning and prep in progress | NO |  | YES
399 | 21-127 | NOAH INDUSTRIAL | HEAT TRANSFER CALCULATION | HEAT TRANSFER CALCULATIONS |  |  | No operations | NO |  | NO
400 | 21-125 | PRYSMIAN CABLES AND SYSTEMS USA LLC | SS HORIZONTAL PRESSURE VESSEL | SS HORIZONTAL PRESSURE VESSEL |  |  | Cleaning and prep in progress | NO |  | NO
401 | 21-119 | LEAR WEST FABRICATION, LLC | 128 CST BURNED PLATES | 128 CST BURNED PLATES |  |  | In progress: B&C parts-lugs, supp, etc | NO |  | NO
402 | 21-084 | TELLUS PRODUCTS | 35,000 GAL SS STORAGE TANK | 35,000 GAL SS STORAGE TANK |  |  | Fab complete, ready to ship | NO |  | NO
403 | 21-085 | TELLUS PRODUCTS | 35,000 GAL SS STORAGE TANK | 35,000 GAL SS STORAGE TANK |  |  | Fab complete, ready to ship | NO |  | NO
404 | 21-086 | TELLUS PRODUCTS | 35,000 GAL SS STORAGE TANK | 35,000 GAL SS STORAGE TANK |  |  | Fab complete, ready to ship | NO |  | NO
405 | 21-083 | NOAH INDUSTRIAL | 6' X 8' SS FEED TANK | 6' X 8' SS FEED TANK |  |  | Fab complete, ready to ship | NO |  | NO