Weekly Project Management Meeting

Mondays – 1:30 p.m.

Attendees:

| April Lewis (Leader) | Dustin Bolgrihn | John Corwin |
| --- | --- | --- |
| Chris Fletcher | Nick Patel | David Onachilla |

Agenda:

- Engineering and Drawings

  - Certified Drawings

    - Identify any drawings that were certified since last meeting (Nick)

    - Assign committed completion dates to any newly-certified jobs based on quoted lead times (April)

    - Until further notice, or unless requested otherwise by the customer, these completion dates should be considered “commitments” and should be reflected as such on weekly production schedule and on any periodic customer updates (Dustin)

  - Change Orders

    - Review any change orders requested by customers since previous meeting, or any pending change orders awaiting final decision by customer (Nick)

    - Raise any known or anticipated schedule impacts and confirm with customer (Chris/April)

    - If change is authorized by customer, update committed completion dates accordingly (Dustin)

  - Job Release Schedule

    - Identify all jobs scheduled to be released to shop floor for current week and the following week (Dustin)

    - For each, confirm status of:

      - Drawings printed (Nick)

      - BOMs printed (Nick)

      - Burn files complete and transmitted (Nick)

      - Build Plan complete and in JobBoss (Dustin)

      - Required materials received and approved by QC (John)

- Jobs in Production

  - Red / Amber / Green (RAG) Review of all jobs on Production Schedule vs. committed completion date (Dustin)

    - For all jobs with Amber or Red status, discuss as a team:

      - What is the issue?

      - What are we doing to address the issue?

      - When will the issue be resolved, and what is the probable impact on schedule?

      - What help from the team is needed?

    - For jobs with Green status, no discussion is needed

  - Prepare for any customer inspections scheduled in next (2) weeks (John)

    - Vessel(s) must be inspected by Savannah Tank QC, and any issues must be addressed

    - Any required outside testing should be scheduled and completed prior to customer visit

    - ITP (if applicable) should be up-to-date and signed as appropriate

    - QC documentation including MTRs, test reports, inspection reports, etc. should be prepared and ready for customer review

  - Savannah Tank India shipping and delivery schedule (Nick)

    - Identify any jobs shipping from India in next (2) weeks

    - Confirm arrival date of any jobs currently on the water

- Shipping Schedule

  - For all jobs scheduled for completion in next (3) weeks:

    - Confirm project completion date, including all inspections, testing, finishing, painting, etc.  (Dustin)

    - Confirm customer has been notified of planned completion date and an agreeable delivery date has been arranged (Chris / April)

    - Confirm all ship loose items will be ready by target shipping date (Dustin)

    - Confirm all shipping arrangements have been made for pick-up and delivery by the agreed schedule (April)

  - For “super loads” (jobs 14’ diameter and over) trucking should be arranged 4-6 weeks prior to target ship date (April)

- Post-Shipment Close-Out Package

  - The following items should be sent within (2) weeks of shipment:

    - As-Built drawings (Nick)

    - Standard QC Package (John)

    - Any additional QC items requested by customer outside of our “standard” package (John)

- Post-Shipment Customer Feedback (Chris)

Red / Amber / Green Status Codes:

| Status | Meaning |
| --- | --- |
|  | Project is on schedule with no issues. |
|  | Risk. A problem has arisen, but the project schedule has not yet been compromised. We believe we can protect the schedule, but the problem must be managed successfully. |
|  | Project is off-track and completion schedule has been impacted. |