## Sheet1
JOB # | Priority | TAG # | STATUS | CHANGE ORDER | STATUS DATE | NEXT ACTION DATE | CURRENT SHIP DATE WEEK OF | DELIVERY DATE BASED ON ORIGINAL QUOTED LEAD TIME | Ship To
102-25 | C | T-101 | CERTIFIED | YES | 2026-02-19 |  | 2026-04-27 | 2026-06-30 | New Mexico
103-25 | C | T-104 | CERTIFIED | APPROVED | 2026-02-19 |  | 2026-04-27 | 2026-06-25 | New Mexico
104-25 | C | T-103 | CERTIFIED | APPROVED | 2026-02-19 |  | 2026-04-27 | 2026-06-25 | New Mexico
105-25 | C | T-105 | CERTIFIED | APPROVED | 2026-02-19 |  | 2026-06-01 | 2026-06-25 | New Mexico
106-25 | C | T-121 | CERTIFIED | APPROVED | 2026-02-19 |  | 2026-06-01 | 2026-06-30 | New Mexico
107-25 | C | T-113 | WITH EPIC FOR COMMENT | APPROVED | 2026-03-05 | 2026-03-12 | 2026-06-01 | 2026-07-22 | New Mexico
108-25 | C | T-114 | WITH EPIC FOR COMMENT | APPROVED | 2026-03-05 | 2026-03-12 | 2026-06-01 | 2026-07-22 | New Mexico
109-25 | B | V-117 | CERTIFIED |  | 2026-03-05 |  | 2026-04-27 | 2026-06-25 | St Louis
110-25 | A | T-117 | CERTIFIED |  | 2026-03-05 |  | 2026-04-27 | 2026-06-30 | St Louis | SPECIAL FLANGE
111-25 | A | T-118A | CERTIFIED |  | 2026-03-05 |  | 2026-04-27 | 2026-06-30 | St Louis | SPECIAL FLANGE
112-25 | A | T-118B | CERTIFIED |  | 2026-03-05 |  | 2026-04-27 | 2026-06-30 | St Louis | SPECIAL FLANGE
113-25 | C | T-120 | WITH EPIC FOR COMMENT |  | 2026-03-05 | 2026-03-12 | 2026-05-11 | 2026-07-22 | New Mexico
114-25 |  | V-103 | CANCELLED |  | CANCELLED | CANCELLED | CANCELLED | CANCELLED
115-25 | B | V-104 | CERTIFIED |  | 2026-02-19 |  | 2026-05-25 | 2026-06-25 | St Louis