## Schedule Not Certified
| MASTER SCHEDULE | Schedule Not Certified | time axis 2026-01-05 to 2026-12-28
| DESCRIPTION | JOB # | Tank Dimensions | PLANNED SHIPMENT WEEK OF | PO RECVD
ANDRITZ | Rayonier, Duct Spools and Piping | 053-25 | N/A | 2026-06-01 |  | 2026-05-18: 50; 2026-05-25: TESTING / CLEANING; 2026-06-01: SHIP
Testing Notes | bar: 2026-02-09; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Procurement Notes | bar: 2026-02-09; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
| Fabrication Notes |  |  |  |  | 2026-06-01: LOOSE ITEMS
Scheduling Notes | bar: 2026-02-09; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
AIR GAS | SST N2O Reactor | 055-25 | 7' OD x 3' straight side x 1/2” thick | 2026-05-26 | 2025-06-02 | 2026-02-02: DRAWING IN PROCESS; 2026-02-09: DRAWING IN PROCESS; 2026-02-16: DRAWING IN PROCESS; 2026-02-23: CUSTOMER DRAWING REVIEW; 2026-03-02: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
| Drawings Notes |  |  |  |  | 2026-05-18: HYDRO
| Procurement Notes |  |  |  |  | 2026-03-23: Dished head shipping from CA 2/20
Fabrication Notes
EPIC | T-113 | 107-25 | 5' ID x 8' Straight Side x 1/4” thick | 2026-06-01 | 2025-10-31 | 2026-02-02: DRAWING IN PROCESS; 2026-02-09: DRAWING IN PROCESS; 2026-02-16: DRAWING IN PROCESS; 2026-02-23: CUSTOMER DRAWING REVIEW; 2026-03-02: CUSTOMER DRAWING REVIEW; 2026-03-09: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes
EPIC | T-114 | 108-25 | 5' ID x 8' Straight Side x 1/4” thick | 2026-06-01 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: CUSTOMER DRAWING REVIEW; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-05-11: FABRICATION; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: TESTING; 2026-06-15: CLEANING; 2026-06-22: SHIP
Testing Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22 to 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Procurement Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22 to 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Fabrication Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22 to 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Scheduling Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22 to 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
EPIC | T-120 | 113-25 | 5' ID x 10' straight side x 1/4” thick | 2026-05-11 |  | 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: CUSTOMER DRAWING REVIEW; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
Testing Notes | bar: 2026-02-09; 2026-02-23; 2026-03-09; 2026-03-23; 2026-04-06; 2026-04-20; 2026-05-04; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Procurement Notes | bar: 2026-02-09; 2026-02-23; 2026-03-09; 2026-03-23; 2026-04-06; 2026-04-20; 2026-05-04; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes | bar: 2026-02-09; 2026-02-23; 2026-03-09; 2026-03-23; 2026-04-06; 2026-04-20; 2026-05-04; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Polynt | Maleic Anhydride Tank (38ft Shell) | 116-25 | 10' OD x 38' straight side x 3/16” thick | 2026-06-16 | 2025-11-04 | 2026-02-02: DRAWING IN PROCESS; 2026-03-16: DRAWING IN PROCESS; 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-05-11: 25; 2026-05-18: 75; 2026-05-25: 75; 2026-06-01: 75; 2026-06-08: 75; 2026-06-15: TESTING; 2026-06-22: CLEANING; 2026-06-29: SHIP
Testing Notes | bar: 2026-02-09; 2026-02-23; 2026-03-09; 2026-03-23; 2026-04-06; 2026-04-27; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Procurement Notes | bar: 2026-02-09; 2026-02-23; 2026-03-09; 2026-03-23; 2026-04-06; 2026-04-27; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
| Fabrication Notes |  |  |  |  | 2026-07-06: QUOTED
Scheduling Notes | bar: 2026-02-09; 2026-02-23; 2026-03-09; 2026-03-23; 2026-04-06; 2026-04-27; 2026-05-18; 2026-06-01; 2026-06-15; 2026-06-29; 2026-07-13; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
ANDRITZ | DISSOLVING TANK | 120-25 | 20' x 44' Oval x 17' x 1/2" thick | 2026-07-06 | 2025-11-20 | 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: DRAWING IN PROCESS; 2026-02-16: DRAWING IN PROCESS; 2026-02-23: DRAWING IN PROCESS; 2026-03-02: DRAWING IN PROCESS; 2026-03-09: CUSTOMER DRAWING REVIEW; 2026-03-16: CUSTOMER DRAWING REVIEW; 2026-03-23: DRAWING UPDATE(S); 2026-03-30: DRAWINGS CERTIFIED; 2026-04-06: PROCUREMENT; 2026-05-11: FABRICATION; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: FABRICATION; 2026-06-15: FABRICATION; 2026-06-22: TESTING; 2026-06-29: CLEANING & PAINTING (carbon steel only); 2026-07-06: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  | SPLIT IN 2
Kimberly Clark | Dump Chest | 121-25 | 16' ID x 18' straight side x 1/4” thick | 2026-05-18 | 2025-12-04 | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-02-23: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
Kimberly Clark | Process Tenside Recovery Tank | 122-25 | 14' ID x 18' straight side x 1/4” thick | 2026-05-18 | 2025-12-04 | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-02-23: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
Kimberly Clark | Backwater Tank | 123-25 | 10' ID X 10' straight side x 1/4” thick | 2026-05-18 | 2025-12-04 | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-02-23: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
Sylvamo | Former Vacuum Seal Tank, Stand Pipe | 357-25 | 5' ID x 8' Straight Side x 3/16” thick | 2026-05-18 | 2025-12-30 | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: DRAWING IN PROCESS; 2026-02-16: DRAWING IN PROCESS; 2026-02-23: CUSTOMER DRAWING REVIEW; 2026-03-02: CUSTOMER DRAWING REVIEW; 2026-03-09: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-04-06: FABRICATION; 2026-04-13: FABRICATION; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: TESTING; 2026-05-11: CLEANING; 2026-05-18: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
Sylvamo | Former Vacuum Seal Tank, Rectangular | 358-25 | 11' L x 6' W x 8' H | 2026-05-18 | 2025-12-30 | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: DRAWING IN PROCESS; 2026-02-16: DRAWING IN PROCESS; 2026-02-23: CUSTOMER DRAWING REVIEW; 2026-03-02: CUSTOMER DRAWING REVIEW; 2026-03-09: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-04-06: FABRICATION; 2026-04-13: FABRICATION; 2026-04-20: FABRICATION; 2026-04-27: FABRICATION; 2026-05-04: TESTING; 2026-05-11: CLEANING; 2026-05-18: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
SNF | RAIL BUFFER TANK 1 | 002-26 | 15' OD x 15' Straight Side | 2026-07-01 | 2026-01-06 | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: FABRICATION; 2026-06-15: TESTING; 2026-06-22: CLEANING; 2026-06-29: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
SNF | RAIL BUFFER TANK 2 | 003-26 | 15' OD x 15' Straight Side | 2026-07-01 | 2026-01-06 | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: FABRICATION; 2026-06-15: TESTING; 2026-06-22: CLEANING; 2026-06-29: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
SNF | RAIL BUFFER TANK 3 | 004-26 | 15' OD x 15' Straight Side | 2026-07-01 | 2026-01-06 | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: FABRICATION; 2026-06-15: TESTING; 2026-06-22: CLEANING; 2026-06-29: SHIP
Drawings Notes
Procurement Notes
Fabrication Notes | bar: 2026-06-29
SNF | LQ19-R1 Prepolymer Reactor Tank | 014-26 | 8' OD x 10' straight side | 2026-06-01 | 2026-01-13 | 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-05-11: FABRICATION; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: FABRICATION; 2026-06-15: TESTING; 2026-06-22: CLEANING; 2026-06-29: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-06-15: ASME REQ'D; 2026-06-22: LD
SNF | LQ19-R2 PAE Reactor Tank | 015-26 | 10' OD x 11' straight side | 2026-06-23 | 2026-01-13 | 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: ON HOLD CUSTOMER TO PROVIDE MATERIAL; 2026-02-23: DRAWING IN PROCESS; 2026-03-02: CUSTOMER DRAWING REVIEW; 2026-03-09: CUSTOMER DRAWING REVIEW; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: TESTING; 2026-06-15: CLEANING; 2026-06-22: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-06-08: ASME REQ'D; 2026-06-22: LD
SNF | LQ19-R3 PAE Dilution Reactor Tank | 016-26 | 13' OD x 14' straight side | 2026-06-23 | 2026-01-13 | 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: ON HOLD FOR CUSTOMER TO DETERMINE MATERIAL; 2026-02-16: DRAWING IN PROCESS; 2026-02-23: CUSTOMER DRAWING REVIEW; 2026-03-02: CUSTOMER DRAWING REVIEW; 2026-03-09: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: TESTING; 2026-06-15: CLEANING; 2026-06-22: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-06-08: ASME REQ'D; 2026-06-22: LD
SNF | B31-CS1EPI Epichlorohydrin storage tank 1 | 017-26 | 14' OD x 26' straight side | 2026-07-08 | 2026-01-13 | 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-02-23: CUSTOMER DRAWING REVIEW; 2026-03-02: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: FABRICATION; 2026-06-15: FABRICATION; 2026-06-22: TESTING; 2026-06-29: CLEANING; 2026-07-06: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-06-22: ASME REQ'D; 2026-07-06: LD
SNF | B31-CS1EPI Epichlorohydrin storage tank 2 | 018-26 | 14' OD x 26' straight side | 2026-07-08 | 2026-01-13 | 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: CUSTOMER DRAWING REVIEW; 2026-02-23: CUSTOMER DRAWING REVIEW; 2026-03-02: DRAWING UPDATE(S); 2026-03-16: DRAWINGS CERTIFIED; 2026-03-23: PROCUREMENT; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: FABRICATION; 2026-06-15: FABRICATION; 2026-06-22: TESTING; 2026-06-29: CLEANING; 2026-07-06: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-06-22: ASME REQ'D; 2026-07-06: LD
US SUGAR | SECONDARY SCREENED JUICE TANK C | 020-26 | 9' OD X 12' straight side x 1/4” thick | 2026-07-15 | 2026-03-06 | 2026-02-09: ON HOLD CUSTOMER TO PROVIDE FINAL DIMENSION; 2026-02-16: DRAWING IN PROCESS; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-06-22: FABRICATION; 2026-06-29: FABRICATION; 2026-07-06: FABRICATION; 2026-07-13: FABRICATION; 2026-07-20: FABRICATION; 2026-07-27: TEST / CLEAN; 2026-08-03: SHIP
Testing Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-20; 2026-08-03 to 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Procurement Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-20; 2026-08-03 to 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
| Fabrication Notes |  |  |  |  | 2026-07-27: QUOTED
Scheduling Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-20; 2026-08-03 to 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
US SUGAR | PRIMARY SCREENED JUICE TANK C | 021-26 | 9' OD X 12' straight side x 1/4” thick | 2026-07-15 | 2026-03-06 | 2026-02-09: ON HOLD CUSTOMER TO PROVIDE FINAL DIMENSION; 2026-02-16: DRAWING IN PROCESS; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-06-22: FABRICATION; 2026-06-29: FABRICATION; 2026-07-06: FABRICATION; 2026-07-13: FABRICATION; 2026-07-20: FABRICATION; 2026-07-27: TEST / CLEAN; 2026-08-03: SHIP
Testing Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-20; 2026-08-03 to 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Procurement Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-20; 2026-08-03 to 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
| Fabrication Notes |  |  |  |  | 2026-07-27: QUOTED
Scheduling Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-20; 2026-08-03 to 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
ANDRITZ | WASH LIQUOR FLASH TANK | 022-26 | 7' OD x 11' Straight Side x 1/4” thick | 2026-06-04 | 2026-03-06 | 2026-02-16: DRAWING IN PROCESS; 2026-03-16: DRAWING UPDATE(S); 2026-03-23: DRAWINGS CERTIFIED; 2026-03-30: PROCUREMENT; 2026-05-11: FABRICATION; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: TESTING; 2026-06-15: CLEANING; 2026-06-22: SHIP
Testing Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
Procurement Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
| Fabrication Notes |  |  |  |  | 2026-07-13: QUOTED
Scheduling Notes | bar: 2026-02-09; 2026-03-16; 2026-03-30; 2026-04-13; 2026-04-27; 2026-05-11; 2026-05-25; 2026-06-08; 2026-06-22; 2026-07-06; 2026-07-27; 2026-08-10; 2026-08-24; 2026-09-07; 2026-09-21; 2026-10-05; 2026-10-19; 2026-11-02; 2026-11-16; 2026-11-30; 2026-12-14; 2026-12-28
POLYNT | POTABLE WATER TANK | 024-26 | 36" OD X 120" straight side x 3/16” thick | 2026-07-20 | 2026-03-02 | 2026-03-02: DRAWING IN PROCESS; 2026-03-09: DRAWING IN PROCESS; 2026-03-16: DRAWING IN PROCESS; 2026-03-23: DRAWING IN PROCESS; 2026-03-30: CUSTOMER DRAWING REVIEW; 2026-04-06: CUSTOMER DRAWING REVIEW; 2026-04-13: DRAWINGS CERTIFIED; 2026-04-20: PROCUREMENT; 2026-06-08: FABRICATION; 2026-06-15: FABRICATION; 2026-06-22: FABRICATION; 2026-06-29: FABRICATION; 2026-07-06: TESTING; 2026-07-13: CLEANING; 2026-07-20: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-07-06: ASME REQ'D
Blake & Pendleton | Air Receiver Tank | 025-26 | 8' OD x 10' straight side 5/8" thick | 2026-08-10 | 2026-03-11 | 2026-03-16: DRAWING IN PROCESS; 2026-03-23: DRAWING IN PROCESS; 2026-03-30: DRAWING IN PROCESS; 2026-04-06: DRAWING IN PROCESS; 2026-04-13: CUSTOMER DRAWING REVIEW; 2026-04-20: CUSTOMER DRAWING REVIEW; 2026-04-27: DRAWINGS CERTIFIED; 2026-05-04: PROCUREMENT; 2026-06-29: FABRICATION; 2026-07-06: FABRICATION; 2026-07-13: FABRICATION; 2026-07-20: FABRICATION; 2026-07-27: TESTING; 2026-08-03: CLEANING; 2026-08-10: SHIP
Drawings Notes
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-07-27: ASME REQ'D
PROJECT ON HOLD
Yellow Areas = Drawing Process
Customer Drawing Review
Gray areas = Fabrication
Blue Areas = Testing/Dissassembly
Green Area Paint and/or 3RD Party
Orange areas = Shipping
2026-03-16

## CERTIFIED
| MASTER SCHEDULE | CERTIFIED | time axis 2026-01-05 to 2026-12-28
| DESCRIPTION | JOB # | TANK DIMENSIONS | PLANNED SHIPMENT WEEK OF | CERTIFIED | bar: 2026-02-09
Kimberly Clark | 330-TK-33001 | 012-25 | 10' X 6' straight side x 1/4” thick | 2026-03-12 |  | 2026-01-26: FABRICATION; 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-02-23: 20; 2026-03-02: TESTING; 2026-03-16: SHIP
| Testing Notes |  |  |  |  | 2026-03-02: Done
| Procurement Notes |  | PARTS HERE
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-16: 19TH
Kimberly Clark | 340-TK-34001 | 013-25 | 12' X 16' straight side x 1/4” thick | 2026-03-12 |  | 2026-01-26: FABRICATION; 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-03-09: 80; 2026-03-16: SHIP
| Testing Notes |  |  |  |  | 2026-03-02: Done
| Procurement Notes |  | PARTS HERE
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-16: 19TH
NUDYNE | TANK 11 | 066-25 | 12' OD x 26' straight side x 1/2” thick | 2026-03-17 |  | 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-02-16: FABRICATION; 2026-02-23: FABRICATION; 2026-03-02: TESTING; 2026-03-09: PAINTING; 2026-03-16: SHIP
| Testing Notes |  |  |  |  | 2026-03-02: 2026-03-06
| Procurement Notes |  | PARTS HERE
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-16: 17TH
NUDYNE | TANK 12 | 067-25 | 12' OD x 26' straight side x 1/2” thick | 2026-03-17 |  | 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-02-16: FABRICATION; 2026-02-23: 12; 2026-03-02: TESTING; 2026-03-09: PAINTING; 2026-03-16: SHIP
| Testing Notes |  |  |  |  | 2026-03-02: 2026-03-10
| Procurement Notes |  | PARTS HERE
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-16: 17TH
BURKE | SUMTER CONVERSION TANK | 099-25 | 12' OD x 26' Straight Side x 3/16” thick | 2026-03-19 |  | 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-02-16: FABRICATION; 2026-02-23: 50; 2026-03-02: TESTING; 2026-03-09: CLEANING; 2026-03-16: SHIP
| Testing Notes |  |  |  |  | 2026-03-02: HYDRO COIL
| Procurement Notes |  | PARTS HERE | bar: 2026-02-09 to 2026-02-16
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-16: 18TH
COASTAL TECH | MIST ELIMINATOR | 098-25 | 16” DIA X 25.5” SQ OPEN X 16” DIA X 62.625” AOL | 2026-03-30 |  | 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-02-16: FABRICATION; 2026-02-23: 60; 2026-03-02: 75; 2026-03-09: 63; 2026-03-16: TESTING; 2026-03-23: CLEANING; 2026-03-30: SHIP
| Testing Notes |  |  |  |  | 2026-03-16: CUSTOMER TO BE ON SITE
| Procurement Notes |  | PARTS HERE
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-16: ON HOLD
SYMRISE | CARBON UNIT #1 | 092-25 | 4' OD X 20' STRAIGHT SIDE X 3/8"THICK | 2026-04-02 |  | 2026-01-26: FABRICATION; 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-03-16: 80; 2026-03-23: TESTING; 2026-03-30: SHIP
| Testing Notes |  |  |  |  | 2026-03-23: ASME
Procurement Notes | bar: 2026-02-09
Fabrication Notes | bar: 2026-02-09
| Scheduling Notes |  |  |  |  | 2026-03-23: SEND UPDATE TO CUSTOMER
SYMRISE | CARBON UNIT #2 | 093-25 | 4' OD X 20' STRAIGHT SIDE X 3/8"THICK | 2026-04-02 |  | 2026-01-26: FABRICATION; 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-03-16: 80; 2026-03-23: TESTING; 2026-03-30: SHIP
| Testing Notes |  |  |  |  | 2026-03-23: ASME
Procurement Notes
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-23: SEND UPDATE TO CUSTOMER
NAK KILN | HR120 Shell | 040-25 | 7' ID X 58' STRAIGHT SIDE 1/2" THICK (3 SECTION) | 2026-04-03 |  | 2026-01-26: FABRICATION; 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-03-09: 50; 2026-03-16: TESTING; 2026-03-23: CLEANING; 2026-03-30: SHIP
| Testing Notes |  |  |  |  | 2026-03-16: UT TESTING REQUIRED
Procurement Notes
Fabrication Notes
| Scheduling Notes |  | Shipped in 3 |  |  | 2026-03-23: Customer to Arrange Shipping
SYNTHOMER | REACTOR 12 | 083-25 | 7' ID x 8' straight side x 1/4” thick | 2026-04-09 |  | 2026-01-19: FABRICATION; 2026-01-26: FABRICATION; 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-03-09: 80; 2026-03-16: 80; 2026-03-23: TESTING; 2026-03-30: CLEANING; 2026-04-06: SHIP
| Testing Notes |  |  |  |  | 2026-03-23: HYDROTEST; 2026-03-30: ASME; 2026-04-13: Hydro scheduled for the 24th
| Procurement Notes |  | PARTS HERE
Fabrication Notes
| Scheduling Notes |  |  |  |  | 2026-03-02: send email 3/9 with test date; 2026-05-25: MICHELLE TO BE ONSITE FOR TESTING
NUDYNE | TANK 13 | 068-25 | 12' OD x 26' straight side x 1/2” thick | 2026-04-06 |  | 2026-02-16: FABRICATION; 2026-02-23: 50; 2026-03-02: 50; 2026-03-09: 50; 2026-03-16: 50; 2026-03-23: TESTING; 2026-03-30: PAINTING; 2026-04-06: SHIP
Testing Notes
Procurement Notes
Fabrication Notes
Scheduling Notes
NUDYNE | TANK 14 | 069-25 | 12' OD x 26' straight side x 1/2” thick | 2026-04-06 |  | 2026-02-16: FABRICATION; 2026-02-23: 75; 2026-03-02: 75; 2026-03-09: 50; 2026-03-16: 40; 2026-03-23: TESTING; 2026-03-30: PAINTING; 2026-04-06: SHIP
Testing Notes
| Procurement Notes |  | PARTS HERE
Fabrication Notes
Scheduling Notes
ATLAS | SULFUR HOLDING TANK | 084-25 | 11' OD x 16' straight side x 1/4” thick | 2026-04-14 |  | 2026-02-16: PAINTING; 2026-04-13: SHIP
| Testing Notes |  |  |  |  | 2026-02-16: ASME; 2026-04-13: DONE
| Procurement Notes |  | PARTS HERE | bar: 2026-02-09
| Fabrication Notes |  | DONE |  |  | 2026-02-16: EXTERIOR PAINTED; 2026-04-13: ON HOLD
| Scheduling Notes |  |  |  |  | 2026-03-30: contact customer to verify delivery date
Merrick | Buffer Tank Live Bottom Screw | 117-25 | 26' X 8' X 6' 3/8” thick w/ stiffeners | 2026-04-13 |  | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: CUSTOMER DRAWING REVIEW; 2026-02-02: CUSTOMER DRAWING REVIEW; 2026-02-09: DRAWING UPDATE(S); 2026-02-16: DRAWINGS CERTIFIED; 2026-02-23: 30; 2026-03-02: 70; 2026-03-09: 70; 2026-03-16: 100; 2026-03-23: 70; 2026-03-30: TESTING; 2026-04-06: PAINTING; 2026-04-13: SHIP
| Testing Notes |  |  |  |  | 2026-03-30: QC VISIT
| Procurement Notes |  |  |  |  | 2026-04-13: LOOSE ITEMS
| Fabrication Notes |  |  |  |  | 2026-02-16: BUILD PLAN & BURN FILE DONE; 2026-06-29: QUOTED
Scheduling Notes | bar: 2026-06-29
SYMS (Lansing) | NMP STORAGE TANK | 046-24 | 13' OD x 30' straight side x 3/16” thick | 2026-04-13 |  | 2026-02-02: FABRICATION; 2026-02-09: FABRICATION; 2026-03-16: 150; 2026-03-23: 130; 2026-03-30: 100; 2026-04-06: 72; 2026-04-13: TESTING; 2026-04-20: SHIP
| Testing Notes |  |  |  |  | 2026-03-30: HYDRO TEST; 2026-06-01: Take Photos of Tank with Ladder attached
Procurement Notes
| Fabrication Notes |  |  |  |  | 2026-03-30: PAINT HANDRAIL, PLATFORM & LADDER ONLY
| Scheduling Notes |  |  |  |  | 2026-03-16: Arrange Crane (912)748-1318 - 4/1 & 4/3 Customer Visit
NUDYNE | TANK 15 | 070-25 | 12' OD x 26' straight side x 1/2” thick | 2026-04-27 |  | 2026-03-02: 50; 2026-03-09: 50; 2026-03-16: 50; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 42; 2026-04-13: TESTING; 2026-04-20: PAINTING; 2026-04-27: SHIP
Testing Notes
| Procurement Notes |  | PARTS HERE
Fabrication Notes
Scheduling Notes
NUDYNE | TANK 16 | 071-25 | 12' OD x 26' straight side x 1/2” thick | 2026-04-27 |  | 2026-03-02: 50; 2026-03-09: 50; 2026-03-16: 50; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 51; 2026-04-13: TESTING; 2026-04-20: PAINTING; 2026-04-27: SHIP
Testing Notes
| Procurement Notes |  | PARTS HERE
Fabrication Notes
Scheduling Notes
EPIC | V-117 | 109-25 | 18” ID x 48” Straight Side x 1/4” thick | 2026-04-27 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWINGS CERTIFIED; 2026-02-23: PROCUREMENT; 2026-03-23: 20; 2026-03-30: 40; 2026-04-06: 24; 2026-04-13: TESTING; 2026-04-20: CLEANING; 2026-04-27: SHIP
| Testing Notes |  |  |  |  | 2026-04-13: HYDRO
| Procurement Notes |  |  | PARTS HERE
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes
EPIC | T-101 | 102-25 | 10' OD x 18' straight side x 3/16” thick | 2026-04-27 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWING UPDATE(S); 2026-02-23: DRAWINGS CERTIFIED; 2026-03-02: PROCUREMENT; 2026-03-16: 50; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: TESTING; 2026-04-20: CLEANING; 2026-04-27: SHIP
Testing Notes
| Procurement Notes |  |  |  |  | 2026-03-09: 2026-03-12
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes
EPIC | T-104 | 103-25 | 10' OD x 18' straight side x 3/16” thick | 2026-04-27 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWINGS CERTIFIED; 2026-02-23: PROCUREMENT; 2026-03-16: 50; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: TESTING; 2026-04-20: CLEANING; 2026-04-27: SHIP
Testing Notes
| Procurement Notes |  |  |  |  | 2026-03-09: 2026-03-02
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes
EPIC | T-103 | 104-25 | 10' OD x 18' straight side x 3/16” thick | 2026-04-27 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWINGS CERTIFIED; 2026-02-23: PROCUREMENT; 2026-03-16: 50; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: TESTING; 2026-04-20: CLEANING; 2026-04-27: SHIP
Testing Notes
| Procurement Notes |  |  |  |  | 2026-03-09: 2026-03-02
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes
EPIC | T-117 | 110-25 | 3' ID x 5' straight side x 3/16” thick | 2026-04-27 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: ON HOLD; 2026-02-23: DRAWINGS CERTIFIED; 2026-03-02: PROCUREMENT; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: TESTING; 2026-04-20: CLEANING; 2026-04-27: SHIP
| Testing Notes |  |  |  |  | 2026-04-13: HYDRO
| Procurement Notes |  |  | PARTS HERE | bar: 2026-02-09
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes | bar: 2026-02-09
EPIC | T-118A | 111-25 | 4' x 6' straight side x 3/16” thick | 2026-04-27 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: ON HOLD; 2026-02-23: DRAWINGS CERTIFIED; 2026-03-02: PROCUREMENT; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: TESTING; 2026-04-20: CLEANING; 2026-04-27: SHIP
| Testing Notes |  |  |  |  | 2026-04-13: HYDRO
Procurement Notes | bar: 2026-02-09
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes | bar: 2026-02-09
EPIC | T-118B | 112-25 | 4' x 6' straight side x 3/16” thick | 2026-04-27 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: ON HOLD; 2026-02-23: DRAWINGS CERTIFIED; 2026-03-02: PROCUREMENT; 2026-03-23: 50; 2026-03-30: 50; 2026-04-06: 50; 2026-04-13: TESTING; 2026-04-20: CLEANING; 2026-04-27: SHIP
| Testing Notes |  |  |  |  | 2026-04-13: HYDRO
Procurement Notes | bar: 2026-02-09
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes | bar: 2026-02-09
Merrick | Buffer Tank Live Bottom Screw | 118-25 | 26' x 8' x 6' x 3/8” thick w/ stiffeners | 2026-05-11 |  | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: CUSTOMER DRAWING REVIEW; 2026-02-02: CUSTOMER DRAWING REVIEW; 2026-02-09: DRAWING UPDATE(S); 2026-02-16: DRAWINGS CERTIFIED; 2026-03-23: 30; 2026-03-30: 70; 2026-04-06: 70; 2026-04-13: 100; 2026-04-20: 70; 2026-04-27: TESTING; 2026-05-04: PAINTING; 2026-05-11: SHIP
| Testing Notes |  |  |  |  | 2026-04-27: QC VISIT
| Procurement Notes |  |  |  |  | 2026-05-11: LOOSE ITEMS
| Fabrication Notes |  |  |  |  | 2026-02-16: BUILD PLAN & BURN FILE DONE; 2026-06-29: QUOTED
Scheduling Notes | bar: 2026-06-29
HARPER LOVE | T1615 - Rupture Disk Catch Tank | 101-25 | 11' OD x 18' Straight Side x 1/2” thick | 2026-05-11 |  | 2026-03-23: 40; 2026-03-30: 100; 2026-04-06: 120; 2026-04-13: 120; 2026-04-20: 120; 2026-04-27: TESTING; 2026-05-04: SANDBLASTED; 2026-05-11: SHIP
| Testing Notes |  |  |  |  | 2026-04-27: ASME
| Procurement Notes |  |  |  |  | 2026-03-23: MATERIAL ON SITE
Fabrication Notes
Scheduling Notes
EPIC | V-104 | 115-25 | 18” SCH10 x 48” straight side | 2026-05-11 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWINGS CERTIFIED; 2026-02-23: PROCUREMENT; 2026-04-27: 50; 2026-05-04: TESTING / CLEANING; 2026-05-11: SHIP
Testing Notes
| Procurement Notes |  |  |  |  | 2026-03-23: 2026-03-23
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes
US SUGAR | Polishing & Trap Blowdown Tank | 005-26 | 9' ID x 11' straight shell x 3/16” thick | 2026-05-18 |  | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWING UPDATE(S); 2026-02-23: DRAWINGS CERTIFIED; 2026-03-02: PROCUREMENT; 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: FABRICATION; 2026-05-25: Test / Clean; 2026-06-01: SHIP
Testing Notes | bar: 2026-02-09
Procurement Notes | bar: 2026-02-09
Fabrication Notes | bar: 2026-02-09
Scheduling Notes | bar: 2026-02-09
EPIC | T-105 | 105-25 | 10' OD x 18' straight side x 3/16” thick | 2026-06-01 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWINGS CERTIFIED; 2026-02-23: PROCUREMENT; 2026-04-20: 50; 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
| Testing Notes |  |  |  |  | 2026-03-16: 2026-03-05
Procurement Notes | bar: 2026-02-09
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes | bar: 2026-02-09
EPIC | T-121 | 106-25 | 10' OD x 18' straight side x 3/16” thick | 2026-06-01 |  | 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWING UPDATE(S); 2026-02-23: DRAWINGS CERTIFIED; 2026-03-02: PROCUREMENT; 2026-04-27: 50; 2026-05-04: 50; 2026-05-11: 50; 2026-05-18: TESTING; 2026-05-25: CLEANING; 2026-06-01: SHIP
| Testing Notes |  |  |  |  | 2026-03-16: 2026-03-16
Procurement Notes | bar: 2026-02-09
| Fabrication Notes |  |  |  |  | 2026-06-22: QUOTED
Scheduling Notes | bar: 2026-02-09
Synthomer | Emulsion Tank | 356-25 | 8' ID x 10' Straight Side x 1/2” thick | 2026-06-08 |  | 2026-01-05: DRAWING IN PROCESS; 2026-01-12: DRAWING IN PROCESS; 2026-01-19: DRAWING IN PROCESS; 2026-01-26: DRAWING IN PROCESS; 2026-02-02: DRAWING IN PROCESS; 2026-02-09: CUSTOMER DRAWING REVIEW; 2026-02-16: DRAWING UPDATE(S); 2026-02-23: DRAWINGS CERTIFIED; 2026-03-02: PROCUREMENT; 2026-04-27: 75; 2026-05-04: 75; 2026-05-11: 75; 2026-05-18: 75; 2026-05-25: TESTING; 2026-06-01: CLEANING; 2026-06-08: SHIP
Testing Notes | bar: 2026-02-09
Procurement Notes | bar: 2026-02-09
| Fabrication Notes |  |  |  |  | 2026-06-29: QUOTED
Scheduling Notes | bar: 2026-02-09
Testing Notes | bar: 2026-02-09
Procurement Notes | bar: 2026-02-09
Fabrication Notes | bar: 2026-02-09
Scheduling Notes | bar: 2026-02-09
Testing Notes | bar: 2026-02-09
Procurement Notes | bar: 2026-02-09
Fabrication Notes | bar: 2026-02-09
Scheduling Notes | bar: 2026-02-09

## Sheet1
MASTER SCHEDULE | time axis 2026-03-09 to 2026-12-28
| DESCRIPTION | JOB # |  | Tentative ship week of | PO Recvd | bar: 2026-03-09; 2026-03-23; 2026-04-06; 2026-04-20; 2026-05-04; 2026-05-18; 2026-06-01; 2026-06-15
Polynt | Maleic Anhydride Tank (38ft Shell) | 116-25 | 10' OD x 38' straight side x 3/16” thick | 2026-06-16 | 2025-11-04 | 2026-04-27: FABRICATION; 2026-05-04: FABRICATION; 2026-05-11: FABRICATION; 2026-05-18: FABRICATION; 2026-05-25: FABRICATION; 2026-06-01: FABRICATION; 2026-06-08: TESTING & CLEANING; 2026-06-15: SHIP