## By Tank
| Job # | Customer | Shop Location | Category | Ship Date | Progress | Complete | Recv Plate | Head(s) Rcvd | Pipe & Flange Rcvd | Receive Special Item(s) | Materials Inspected | Cut Parts on Plasma | Form Internal Coil | Shell(s) Rolled | Skirt Rolled | Roll Repads | Build Supports | Nozzle(s) Made | Build Top and/or Bottom | Build Manway | Make Ladders/ Handrail/ Platform | Weld Cone(s) | Fit Ladders/ Handrail/ Platform | QA Inspect Ladders/ Handrail/ Platform | Weld Shell Seams | Weld Top To Shell | Weld Bottom To Shell | Weld Tank Support(s) | Install Nozzles | Install Special External Part(s) | Install Special Internal Part(s) | Test | Clean & Prep | Sandblast / Paint | Ship to Galv Ladders/ Handrail/ Platform | Recv from Galv Ladders/ Handrail/ Platform | Take parts to Machine Shop | Recv Parts from Machine Shop | Arrange Truck
| 25-099 | Burke |  | On Track | 2026-03-19 | 50% | 8 | 1 |  | 2 |  | 1 |  | 1 |  |  |  |  | 1 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  | 1 | 1 | 1 | [5 empty] | 1
| 25-013 | Kimberly-Clark |  | @ Risk | 2026-03-19 | 78.26% | 36 | 1 |  | 8 |  | 1 | 1 |  | 4 |  | 1 | 1 | 8 | 2 | 3 |  |  |  |  | 2 | 1 | 1 | 1 | 6 |  | 2 | 1 | 1 | [5 empty] | 1
| 25-098 | Coastal Tech |  | On Hold | 2026-03-30 | 19.23% | 10 | 1 |  | 8 |  | 1 | 3 |  | 1 |  |  | 2 | 7 | 1 |  |  | 2 |  |  |  | 8 | 4 | 2 | 7 |  | 2 | 1 | 1 | [5 empty] | 1
| 25-092 | Symrise |  | On Track | 2026-04-02 | 35.71% | 25 | 1 | 1 | 13 |  | 1 | 2 |  | 4 | 1 | 1 |  | 17 |  | 1 |  |  |  |  | 7 | 1 | 1 | 1 | 12 |  | 2 | 1 | 1 | 1 |  |  |  |  | 1
| 25-093 | Symrise |  | On Track | 2026-04-02 | 35.71% | 25 | 1 | 1 | 13 |  | 1 | 2 |  | 4 | 1 | 1 |  | 17 |  | 1 |  |  |  |  | 7 | 1 | 1 | 1 | 12 |  | 2 | 1 | 1 | 1 |  |  |  |  | 1
Jobs Released | 25-040 | Nak Kiln |  | On Track | 2026-04-03 | 3.125% | 2 | 1 |  |  | 1 | 1 |  |  | 3 | [10 empty] | 27 | [5 empty] | 28 | 1 | 1 | [5 empty] | 1
| 25-068 | Reco/Nudyne |  | On Track | 2026-04-06 | 95.08% | 58 | 1 | 1 | 7 |  | 1 | 1 |  | 3 | 1 | 1 |  | 6 |  | 1 |  |  |  |  | 15 | 2 | 2 | 2 | 6 |  | 7 | 1 | 1 | 1 |  |  |  |  | 1
| 25-069 | Reco/Nudyne |  | On Track | 2026-04-06 | 55.93% | 33 | 1 | 1 | 7 |  | 1 | 1 |  | 3 | 1 | 1 |  | 6 |  | 1 |  |  |  |  | 15 | 1 | 1 | 2 | 6 |  | 7 | 1 | 1 | 1 |  |  |  |  | 1
| 25-070 | Reco/Nudyne |  | On Track | 2026-04-27 | 28.81% | 17 | 1 | 1 | 7 |  | 1 | 1 |  | 3 | 1 | 1 |  | 6 |  | 1 |  |  |  |  | 15 | 1 | 1 | 2 | 6 |  | 7 | 1 | 1 | 1 |  |  |  |  | 1
| 25-071 | Reco/Nudyne |  | On Track | 2026-04-27 | 28.81% | 17 | 1 | 1 | 7 |  | 1 | 1 |  | 3 | 1 | 1 |  | 6 |  | 1 |  |  |  |  | 15 | 1 | 1 | 2 | 6 |  | 7 | 1 | 1 | 1 |  |  |  |  | 1
| 24-083 | Synthomer |  | On Track | 2026-04-09 | 63.83% | 60 | 1 | 2 | 22 | 1 | 1 | 1 |  | 2 |  | 1 | 4 | 22 |  | 1 |  |  |  |  | 3 | 1 | 1 | 4 | 22 | 1 | 1 | 1 | 1 | [5 empty] | 1
| 25-117 | Merrick |  | On Track | 2026-04-13 | 12.09% | 11 | 1 |  | 9 |  | 1 | 1 |  |  |  | 1 |  | 9 | 2 | 6 |  |  |  |  | 16 | 16 | 16 |  | 9 |  |  | 1 | 1 | 1 |  |  |  |  | 1
| 25-118 | Merrick |  | On Track | 2026-05-11 | 1.099% | 1 | 1 |  | 9 |  | 1 | 1 |  |  |  | 1 |  | 9 | 2 | 6 |  |  |  |  | 16 | 16 | 16 |  | 9 |  |  | 1 | 1 | 1 |  |  |  |  | 1
| 24-046 | Syms |  | On Track | 2026-04-13 | 21.9% | 23 | 1 |  | 20 |  | 1 |  |  | 6 |  | 4 | 4 | 20 | 1 | 2 | 2 |  | 2 | 1 | 17 | 1 | 1 |  | 18 |  |  | 1 | 1 | 1 |  |  |  |  | 1
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  |  |  | On Track | 2026-03-19 | 0%
|  | Legend: | Complete
In Process
@ Risk
Late
N/A
To Start
Note on AH8: April Lewis: Xray 3/17
Note on AH9: April Lewis: Xray 3/17