## About (hidden)
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## By Tank
Vertiv Count |  |  | Legend: | Complete |  |  |  |  | In Process | [5 empty] | @ Risk | [5 empty] | Late |  |  |  | To Start
Milestone description | Category | Ship Date | Progress | Shell Cut | Head Rcvd (2) | Shell Rolled | Flange Rcvd | Nozzle Made | Baffle Cut | Skirt Cut | Skirt Rolled | Backing Bar Cut | Weld Backing to Head | Weld Shell Seam | Weld Bottom Head to Shell | Weld Skirt | Install Nozzles | Install Baffle | Int Clean | Top Welded | Test | Final Clean & Prep | Arrange Truck | Temp Sensor | Exp Tank | SHIP
25-124 | In Process |  | 80%
25-125 | On Track | 2026-03-16 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-126 | On Track | 2026-03-16 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-127 | On Track | 2026-03-16 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-128 | On Track | 2026-03-16 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-129 | On Track | 2026-03-16 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-130 | On Track | 2026-03-16 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-131 | On Track | 2026-03-16 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-132 | On Track | 2026-03-16 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-133 | On Track | 2026-03-19 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-134 | On Track | 2026-03-19 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-135 | On Track | 2026-03-19 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-136 | On Track | 2026-03-19 | 91.3% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-137 | On Track | 2026-03-19 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-138 | On Track | 2026-03-19 | 82.61% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1
25-139 | On Track | 2026-03-19 | 82.61% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1
25-140 | On Track | 2026-03-19 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-141 | On Track | 2026-03-19 | 82.61% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1
25-142 | On Track | 2026-03-19 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-143 | On Track | 2026-03-19 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-144 | On Track | 2026-03-19 | 82.61% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1
25-145 | On Track | 2026-03-19 | 82.61% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1
25-146 | On Track | 2026-03-19 | 86.96% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  | 1
25-147 | On Track | 2026-03-19 | 82.61% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1
25-148 | Low Risk | 2026-05-04 | 56.52% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-149 | Low Risk | 2026-05-04 | 56.52% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-150 | Low Risk | 2026-05-04 | 56.52% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-151 | Low Risk | 2026-05-04 | 56.52% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-152 | Low Risk | 2026-05-04 | 56.52% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-153 | Low Risk | 2026-05-04 | 47.83% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1
25-154 | Low Risk | 2026-05-04 | 43.48% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
25-155 | Low Risk | 2026-05-04 | 39.13% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25-156 | Low Risk | 2026-05-04 | 34.78% | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1
25-157 | Low Risk | 2026-05-04 | 34.78% | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1
25-158 | Low Risk | 2026-05-04 | 30.43% |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1
25-159 | Low Risk | 2026-05-04 | 30.43% |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1
25-160 | Low Risk | 2026-05-04 | 26.09% |  |  | 1 | 1 | 1 |  | 1 | 1 | 1
25-161 | Low Risk | 2026-05-04 | 26.09% |  |  | 1 | 1 | 1 |  | 1 | 1 | 1
25-162 | Low Risk | 2026-05-04 | 26.09% |  |  | 1 | 1 | 1 |  | 1 | 1 | 1
25-163 | Low Risk | 2026-05-04 | 26.09% |  |  | 1 | 1 | 1 |  | 1 | 1 | 1
25-164 | Low Risk | 2026-05-04 | 21.74% |  |  | 1 | 1 | 1 |  | 1 |  | 1
25-165 | Low Risk | 2026-05-04 | 21.74% |  |  | 1 | 1 | 1 |  | 1 |  | 1
25-166 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-167 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-168 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-169 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-170 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-171 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-172 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-173 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-174 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-175 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-176 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-177 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-178 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-179 | Low Risk | 2026-05-04 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-180 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-181 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-182 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-183 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-184 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-185 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-186 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-187 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-188 | Low Risk | 2026-07-27 | 17.39% |  |  |  | 1 | 1 |  | 1 |  | 1
25-189 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-190 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-191 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-192 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-193 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-194 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-195 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-196 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-197 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-198 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-199 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-200 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-201 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-202 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-203 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-204 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-205 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-206 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-207 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-208 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-209 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-210 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-211 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-212 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-213 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-214 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-215 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-216 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-217 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-218 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-219 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-220 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-221 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-222 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-223 | Low Risk | 2026-07-27 | 13.04% |  |  |  | 1 | 1 |  | 1
25-224 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-225 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-226 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-227 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-228 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-229 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-230 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-231 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-232 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-233 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-234 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-235 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-236 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-237 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-238 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-239 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-240 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-241 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-242 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-243 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-244 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-245 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-246 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-247 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-248 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-249 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-250 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-251 | Low Risk | 2026-08-31 | 13.04% |  |  |  | 1 | 1 |  | 1
25-252 | Low Risk | 2026-11-02 | 0%
25-253 | Low Risk | 2026-11-02 | 0%
25-254 | Low Risk | 2026-11-02 | 0%
25-255 | Low Risk | 2026-11-02 | 0%
25-256 | Low Risk | 2026-11-02 | 0%
25-257 | Low Risk | 2026-11-02 | 0%
25-258 | Low Risk | 2026-11-02 | 0%
25-259 | Low Risk | 2026-11-02 | 0%
25-260 | Low Risk | 2026-11-02 | 0%
25-261 | Low Risk | 2026-11-02 | 0%
25-262 | Low Risk | 2026-11-02 | 0%
25-263 | Low Risk | 2026-11-02 | 0%
25-264 | Low Risk | 2026-11-02 | 0%
25-265 | Low Risk | 2026-11-02 | 0%
25-266 | Low Risk | 2026-11-02 | 0%
25-267 | Low Risk | 2026-11-02 | 0%
25-268 | Low Risk | 2026-11-02 | 0%
25-269 | Low Risk | 2026-11-02 | 0%
25-270 | Low Risk | 2026-11-02 | 0%
25-271 | Low Risk | 2026-11-02 | 0%
25-272 | Low Risk | 2026-11-02 | 0%
25-273 | Low Risk | 2026-11-02 | 0%
25-274 | Low Risk | 2026-11-02 | 0%
25-275 | Low Risk | 2026-11-02 | 0%
25-276 | Low Risk | 2026-11-02 | 0%
25-277 | Low Risk | 2026-11-02 | 0%
25-278 | Low Risk | 2026-11-02 | 0%
25-279 | Low Risk | 2026-11-02 | 0%
25-280 | Low Risk | 2026-11-02 | 0%
25-281 | Low Risk | 2026-11-02 | 0%
25-282 | Low Risk | 2026-11-02 | 0%
25-283 | Low Risk | 2026-11-02 | 0%
25-284 | Low Risk | 2026-12-21 | 0%
25-285 | Low Risk | 2026-12-21 | 0%
25-286 | Low Risk | 2026-12-21 | 0%
25-287 | Low Risk | 2026-12-21 | 0%
25-288 | Low Risk | 2026-12-21 | 0%
25-289 | Low Risk | 2026-12-21 | 0%
25-290 | Low Risk | 2026-12-21 | 0%
25-291 | Low Risk | 2026-12-21 | 0%
25-292 | Low Risk | 2026-12-21 | 0%
25-293 | Low Risk | 2026-12-21 | 0%
25-294 | Low Risk | 2026-12-21 | 0%
25-295 | Low Risk | 2026-12-21 | 0%
25-296 | Low Risk | 2026-12-21 | 0%
25-297 | Low Risk | 2026-12-21 | 0%
25-298 | Low Risk | 2026-12-21 | 0%
25-299 | Low Risk | 2026-12-21 | 0%
25-300 | Low Risk | 2026-12-21 | 0%
25-301 | Low Risk | 2026-12-21 | 0%
25-302 | Low Risk | 2026-12-21 | 0%
25-303 | Low Risk | 2026-12-21 | 0%
25-304 | Low Risk | 2026-12-21 | 0%
25-305 | Low Risk | 2026-12-21 | 0%
25-306 | Low Risk | 2026-12-21 | 0%
25-307 | Low Risk | 2026-12-21 | 0%
25-308 | Low Risk | 2026-12-21 | 0%
25-309 | Low Risk | 2026-12-21 | 0%
25-310 | Low Risk | 2026-12-21 | 0%
25-311 | Low Risk | 2026-12-21 | 0%
25-312 | Low Risk | 2027-01-25 | 0%
25-313 | Low Risk | 2027-01-25 | 0%
25-314 | Low Risk | 2027-01-25 | 0%
25-315 | Low Risk | 2027-01-25 | 0%
25-316 | Low Risk | 2027-01-25 | 0%
25-317 | Low Risk | 2027-01-25 | 0%
25-318 | Low Risk | 2027-01-25 | 0%
25-319 | Low Risk | 2027-01-25 | 0%
25-320 | Low Risk | 2027-01-25 | 0%
25-321 | Low Risk | 2027-01-25 | 0%
25-322 | Low Risk | 2027-01-25 | 0%
25-323 | Low Risk | 2027-01-25 | 0%
25-324 | Low Risk | 2027-01-25 | 0%
25-325 | Low Risk | 2027-01-25 | 0%
25-326 | Low Risk | 2027-01-25 | 0%
25-327 | Low Risk | 2027-01-25 | 0%
25-328 | Low Risk | 2027-01-25 | 0%
25-329 | Low Risk | 2027-01-25 | 0%
25-330 | Low Risk | 2027-01-25 | 0%
25-331 | Low Risk | 2027-01-25 | 0%
25-332 | Low Risk | 2027-01-25 | 0%
25-333 | Low Risk | 2027-01-25 | 0%
25-334 | Low Risk | 2027-01-25 | 0%
25-335 | Low Risk | 2027-01-25 | 0%
25-336 | Low Risk | 2027-02-08 | 0%
25-337 | Low Risk | 2027-02-08 | 0%
25-338 | Low Risk | 2027-02-08 | 0%
25-339 | Low Risk | 2027-02-08 | 0%
25-340 | Low Risk | 2027-02-08 | 0%
25-341 | Low Risk | 2027-02-08 | 0%
25-342 | Low Risk | 2027-02-08 | 0%
25-343 | Low Risk | 2027-02-08 | 0%
25-344 | Low Risk | 2027-02-08 | 0%
25-345 | Low Risk | 2027-02-08 | 0%
25-346 | Low Risk | 2027-02-08 | 0%
25-347 | Low Risk | 2027-02-08 | 0%
To add more data, Insert new rows ABOVE this one
Note on AA2: Author: 24 Due 3/16 32 Due 5/4 44 Due 7/27 28 Due 8/31 32 Due 11/2 28 Due 12/21 24 Due 1/25 12 Due 2/27

## Overall
Vertiv |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2026-02-09 |  |  |  |  | March | [27 empty] | April
Scrolling increment: | 28 | time axis 2026-03-09 to 2026-05-03
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-03-09 to 2026-05-03
Vertiv 124-25 through 147-25 | 24
Shell Cut | On Track | Pre-Fab | 100% | 2026-02-17 | 3
Shell Rolled | On Track | Pre-Fab | 100% | 2026-02-23 | 2
Baffle Cut | On Track | Pre-Fab | 100% | 2026-02-24 | 1
Skirt & Backing Bar Cut | On Track | Pre-Fab | 100% | 2026-02-24 | 1
Skirt Rolled | On Track | Pre-Fab | 100% | 2026-02-25 | 1
Shell Welded | On Track | Fabrication | 100% | 2026-02-25 | 1
Bottom Welded with backing | On Track | Pre-Fab | 100% | 2026-02-26 | 2
Bottom Welded to shell | On Track | Fabrication | 100% | 2026-02-26 | 2
Skirt Welded | On Track | Fabrication | 100% | 2026-02-26 | 2
Flange and Pipe Welded (Nozzle) | On Track | Fabrication | 100% | 2026-03-02 | 4
Nozzles Installed | On Track | Fabrication | 100% | 2026-03-05 | 2
Baffle Installed | On Track | Fabrication | 45.83% | 2026-03-09 | 3
Cleaning | On Track | Fabrication | 12.5% | 2026-03-09 | 3
Top Welded | On Track | Fabrication | 0.04167% | 2026-03-10 | 3
Receive Temp Sensors | High Risk | Purchasing | 0% | 2026-03-15 | 1 | bar: 2026-03-17
Receive Expansion Tanks | High Risk | Purchasing | 0% | 2026-03-23 | 1
Testing | Goal | Finishing | 0% | 2026-03-11 | 3 | 2026-03-11: 2; 2026-03-12: 2; 2026-03-13: 2
Cleaning & Shipping | Goal | Finishing | 0% | 2026-03-14 | 3 | 2026-03-14: 2; 2026-03-15: 2; 2026-03-16: 2
SHIPMENT TRUCKS ARRANGED | Milestone | Scheduling | 100% | 2026-03-16 | 4 | bar: 2026-03-16 to 2026-03-19
Vertiv 125-25 through 157-25 | 32
Shell Cut | On Track | Pre-Fab | 100% | 2026-03-17 | 3
Shell Rolled | On Track | Pre-Fab | 0% | 2026-03-19 | 2
Baffle Cut | On Track | Pre-Fab | 0% | 2026-03-23 | 1
Skirt & Backing Bar Cut | On Track | Pre-Fab | 0% | 2026-03-25 | 1
Skirt Rolled | On Track | Pre-Fab | 0% | 2026-03-26 | 2
Shell Welded | On Track | Fabrication | 0% | 2026-03-30 | 2
Bottom Welded with backing | On Track | Pre-Fab | 0% | 2026-03-31 | 2
Bottom Welded to shell | On Track | Fabrication | 0% | 2026-04-03 | 2
Skirt Welded | On Track | Fabrication | 0% | 2026-04-06 | 1
Flange and Pipe Welded (Nozzle) | On Track | Fabrication | 50% | 2026-04-07 | 1
Nozzles Installed | On Track | Fabrication | 0% | 2026-04-08 | 2
Baffle Installed | On Track | Fabrication | 0% | 2026-04-13 | 3
Cleaning | On Track | Fabrication | 0% | 2026-04-15 | 3
Top Welded | On Track | Fabrication | 0% | 2026-04-20 | 3
Receive Temp Sensors | Med Risk | Purchasing | 0% | 2026-04-07 | 1
Receive Expansion Tanks | Low Risk | Purchasing | 0% | 2026-03-23 | 1
Testing | Goal | Finishing | 0% | 2026-04-22 | 6 | 2026-04-22: 2; 2026-04-23: 2; 2026-04-24: 2; 2026-04-25: 2; 2026-04-26: 2; 2026-04-27: 2
Cleaning & Shipping | Goal | Finishing | 0% | 2026-04-29 | 3 | 2026-04-29: 2; 2026-04-30: 2; 2026-05-01: 2
SHIPMENT TRUCKS ARRANGED | Milestone | Scheduling | 0% | 2026-05-04 | 2

## Count Sheet
Shell Cut
Head Rcvd (2)
Shell Rolled
Flange Rcvd
Nozzle Made
Baffle Cut
Skirt Cut
Skirt Rolled
Backing Bar Cut
Weld Backing to Head | 8
Weld Shell Seam
Weld Bottom Head to Shell
Weld Skirt
Install Nozzles
Install Baffle
Int Clean
Top Welded
Test
Final Clean & Prep