## Inventory
QC Tracker 3/16/2026
JOB# | CUSTOMER | CODE | A.I. FIT UP HOLD POINT |  | MTR'S | NDE |  | QC Hold Points |  |  |  | Clean/ Paint |  | TESTING |  | NP Done
[8 empty] | I.S. | E.S. | F.I. | F.E. | Int. | Ext.
046-24 | Syms Engineering | API 650 | N/A | N/A |  | PT Shell to Floor Seam | [7 empty] | Vessel Pneumatic - 2 PSI
[6 empty] | PT All Shell Nozzles | [7 empty] | Full of Water Hydro
012-25 | Kimberly Clark | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X |  |  | Vessel Pneumatic 2 PSI | Done | X
[14 empty] | False Btm Pneumatic - 2 PSI | Done
013-25 | Kimberly Clark | API 650 | N/A | N/A | Done | RT @ M1 hole | Done | [6 empty] | Vessel Pneumatic 2 PSI
False Btm Pneumatic - 2 PSI
018-25 SHIPPED | Kimberly Clark | API 650 | N/A | N/A | Done | RT N5 Hole | Done | X | X | X | X |  |  | Vessel Pneumatic 2 PSI | Done | X
055-25 | Airgas | ASME | ??? |  |  | N/A | N/A | [6 empty] | Vessel Hydro 15 PSI
066-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done | Done | Shell Spot RT | Done | X | X | X | X |  |  | Vessel Pneumatic 111 PSI | Done | X
[6 empty] | Top Head to Shell Spot RT | Done
[6 empty] | Btm Head to Shell Spot RT | Done
067-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done | Done | Shell Spot RT | Done | X | X | X | X |  |  | Vessel Pneumatic 111 PSI | Done | X
[6 empty] | Top Head to Shell Spot RT | Done
[6 empty] | Btm Head to Shell Spot RT | Done
068-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done | Done | Shell Spot RT | Done | R | [5 empty] | Vessel Pneumatic 111 PSI | 3/25
[6 empty] | Top Head to Shell Spot RT | 3/17
[6 empty] | Btm Head to Shell Spot RT | Done
069-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done | Done | Shell Spot RT | 3/17 | [6 empty] | Vessel Pneumatic 111 PSI | 3/25
[6 empty] | Top Head to Shell Spot RT | 3/23
[6 empty] | Btm Head to Shell Spot RT | 3/17
070-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done | Done | Shell Spot RT | 3/23 | [6 empty] | Vessel Pneumatic 111 PSI
Top Head to Shell Spot RT
[6 empty] | Btm Head to Shell Spot RT | 3/23
071-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done | Done | Shell Spot RT | [7 empty] | Vessel Pneumatic 111 PSI
Top Head to Shell Spot RT
Btm Head to Shell Spot RT
083-25 | Synthomer | ASME | Either Head to Shell | Done | Done | 100% RT |  | X | [5 empty] | Vessel Hydro 102 PSI
JKT Hydro 195 PSI
Customer 2 week notice
084-25 | Atlas Minerals & Chemicals | ASME Coil Only | N/A | N/A | Done | N/A | N/A | X | X | X | X |  |  | Vessel Pneumatic 2 PSI | Done | X
[14 empty] | Coil Hydro 98 PSI | Done
089-25 SHIPPED | Valmet | API 650 | N/A | N/A | Done | RT 10% Shell Seams | Done | X | X | X | X | X | X | N/A | N/A | X
[6 empty] | PT Shell to Floor Seam | Done
[6 empty] | PT All Backgrinds | Done
[6 empty] | PT All Nozzle Roots | Done
[6 empty] | PT All Nozzle Finals | Done
[6 empty] | PMI All Heat Numbers | Done
[6 empty] | Vacuum Box Floor Seams | Done
092-25 | Symrise Inc. | ASME | Nozzle to Btm Head | Done |  | 100% RT | [7 empty] | Vessel Pneumatic 108 PSI
Does not cover 093
093-25 | Symrise Inc. | ASME | Nozzle to Btm Head | Done |  | 100% RT | [7 empty] | Vessel Pneumatic 108 PSI
Does not cover 092
098-25 | Aquatech | ASME | N1 or N2 flange to shell |  | Done
Customer to witness test
|  |  | MTRs for all (including bolting) | [10 empty] | Customer to witness cleaning
099-25 | Burke Industrial | ASME Coil Only | N/A | N/A | Done | Vacuum Box Cone Welds | 3/23 | [6 empty] | Coil Hydro 52 PSI
[6 empty] | PT Cone Welds | 3/23
101-25 | Harper Love | ASME | Btm Head to Shell |  |  | Shell Spot RT | [7 empty] | Vessel Pneumatic 123 PSI
103-25 | Epic | API 650 | N/A | N/A |  | N/A | N/A | [6 empty] | Vessel Pneumatic 2 PSI
104-25 | Epic | API 650 | N/A | N/A |  | N/A | N/A | [6 empty] | Vessel Pneumatic 2 PSI
105-25 | Epic | API 650 | N/A | N/A |  | N/A | N/A | [6 empty] | Vessel Pneumatic 2 PSI
109-25 | Epic | ASME | ??? |  | Done | N/A | N/A | [6 empty] | Vessel Hydro 20 PSI
110-25 | Epic | ASME | ??? |  | Done | N/A | N/A | [6 empty] | Vessel Hydro 65 PSI
111-25 | Epic | ASME | ??? |  |  | N/A | N/A | [6 empty] | Vessel Hydro 77 PSI
JKT Hydro 124 PSI
112-25 | Epic | ASME | ??? |  |  | N/A | N/A | [6 empty] | Vessel Hydro 77 PSI
JKT Hydro 124 PSI
116-25 | Polynt | ASME | ??? |  |  | N/A | N/A | [6 empty] | Vessel Pneumatic 19 PSI
117-25 | Merrick Industries Inc. | Cust. Spec | N/A | N/A |  | N/A | N/A | [6 empty] | Vessel Pneumatic 2 PSI
118-25 | Merrick Industries Inc. | Cust. Spec | N/A | N/A |  | N/A | N/A | [6 empty] | Vessel Pneumatic 2 PSI
124-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 124 - 128
125-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 124 - 128
126-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 124 - 128
127-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 124 - 128
128-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 124 - 128
129-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 129 - 133
130-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 129 - 133
131-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 129 - 133
132-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 129 - 133
133-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 129 - 133
134-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 134 - 138
135-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 134 - 138
136-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI |  | X
|  |  | Covers 134 - 138 | [11 empty] | 3/18
137-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 134 - 138
138-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 134 - 138
139-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI |  | X
|  |  | Covers 139 - 143 | [11 empty] | 3/18
140-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 139 - 143
141-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 139 - 143
142-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 139 - 143
143-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 139 - 143
144-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | [5 empty] | Vessel Hydro 163 PSI |  | X
|  |  | Covers 144 - 148 | [11 empty] | 3/18
145-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | [5 empty] | Vessel Hydro 163 PSI |  | X
|  |  | Covers 144 - 148 | [11 empty] | 3/18
146-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 144 - 148
147-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | X | X | X | X |  |  | Vessel Hydro 163 PSI | Done | X
Covers 144 - 148
148-25 | Vertiv Corp. | ASME | Head to Shell | Done |  | N/A | N/A | [6 empty] | Vessel Hydro 163 PSI |  | X
Covers 144 - 148

## Package
157-21 Ship Loose Checksheet
Package
Items |  | QC | Shipping
1/4" THK double shells (X6)
1/4" THK single shells (X3)
Top Cone (2 Pieces)
Flat Bottom (2 Pieces)
Rim Angle (X4)
N1 (Pipe & Flange)
N1 Vent
N1 Gasket & Hardware
N2 (Pipe & Flange)
N2 Repad (X2)
N3 (Pipe & Flange)
N3 Repad (X2)
N4 (Pipe, Flange, Blind, Gasket & Hardware)
N5 (Pipe & Flange)
N5 Repad (X2)
N6 (Pipe & Flange)
N7 (Pipe & Flange)
N8 (Pipe & Flange)
N9 (Pipe & Flange)
M1 (Pipe,Flange,Blind,Gasket,Davit Arm,Hardware)
M1 Repad (X2)
M2 (Pipe,Flange,Blind,Gasket,Davit Arm,Hardware)
M2 Repad (X2)
Handail W/ Toe Plate (X2)
Handrail post clips W/ hardware (X10)
Lift Lugs (X4)
Anchor Chair (X7)
Anchor Chair W/ Ground lug (X1)
Nameplate W/ Nameplate Bracket (X1)