## Inventory
QC Tracker 10/1/2025
JOB# | CUSTOMER | CODE | A.I. FIT UP HOLD POINT |  | MTR'S | NDE |  | QC Hold Points |  |  |  | TESTING
[8 empty] | I.S. | E.S. | F.I. | F.E.
063-24 | River To Tap | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X | Vessel Pneumatic - 2 PSI | Done
[12 empty] | False Btm Pneumatic - 2 PSI | Done
064-24 | River To Tap | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X | Vessel Pneumatic - 2 PSI | Done
[12 empty] | False Btm Pneumatic - 2 PSI | Done
065-24 | River To Tap | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X | Vessel Pneumatic - 2 PSI | Done
[12 empty] | False Btm Pneumatic - 2 PSI | Done
066-24 | River To Tap | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X | Vessel Pneumatic - 2 PSI | Done
[12 empty] | False Btm Pneumatic - 2 PSI | Done
007-25 | Kimberly Clark | API 650 | N/A | N/A | Done | RT @ M1 hole | Done | X | X | X | X | Vessel Pneumatic 2 PSI
[12 empty] | False Btm Pneumatic - 2 PSI | Done
008-25 | Kimberly Clark | API 650 | N/A | N/A | Done | RT @ M1 hole | Done | X | X | X | X | Vessel Pneumatic 2 PSI | Done
[12 empty] | False Btm Pneumatic - 2 PSI | Done
009-25 | Kimberly Clark | API 650 | N/A | N/A | Done | RT @ M1 hole | Done | X | X | R | R | Vessel Pneumatic 2 PSI
[12 empty] | False Btm Pneumatic - 2 PSI | Done
014-25 | Kimberly Clark | API 650 | N/A | N/A |  | RT @ M1 hole | Done |  |  |  |  | Vessel Pneumatic 2 PSI
False Btm Pneumatic - 2 PSI
015-25 | Kimberly Clark | API 650 | N/A | N/A |  | RT @ B2 Hole | Done |  |  |  |  | Vessel Pneumatic 2 PSI
[6 empty] | RT @ M1 hole | Done |  |  |  |  | False Btm Pneumatic - 2 PSI
020-25 | Kimberly Clark | API 650 | N/A | N/A |  | PT all nozzles | [5 empty] | Vessel Pneumatic 2 PSI
[6 empty] | RT M1 Hole | [5 empty] | False Btm Pneumatic 2 PSI
Vacuum Box All Seams
021-25 | Kimberly Clark | API 650 | N/A | N/A |  | N/A | N/A |  |  |  |  | Vessel Pneumatic 2 PSI
027-25 | Irving | API 650 | N/A | N/A | Done | PT shell nozzles | Done | X | X | X | X | Vessel Pneumatic 2 PSI | Done
[6 empty] | PT shell to floor seam | Done
[6 empty] | RT LS (1), CS (1), T-Joint (1) | Done
028-25 | Irving | API 650 | N/A | N/A | Done | PT shell nozzles | Done | X | X | X | X | Vessel Pneumatic 2 PSI | Done
[6 empty] | PT shell to floor seam | Done
[6 empty] | RT LS (1), CS (1), T-Joint (1) | Done
029-25 SHIPPED | Irving | API 650 | N/A | N/A | Done | PT shell nozzles | Done | X | X | X | X | Vessel Pneumatic 2 PSI | Done
[6 empty] | PT shell to floor seam | Done
[6 empty] | RT LS (1), CS (1), T-Joint (1) | Done
030-25 SHIPPED | Irving | API 650 | N/A | N/A | Done | PT shell nozzles | Done | X | X | X | X | Vessel Pneumatic 2 PSI | Done
[6 empty] | PT shell to floor seam | Done
[6 empty] | RT LS (1), CS (1), T-Joint (1) | Done
031-25 | Irving | API 650 | N/A | N/A | Done | PT shell nozzles |  | X | X | X | X | Vessel Pneumatic 2 PSI | Done
PT shell to floor seam
[6 empty] | RT LS (1), CS (1), T-Joint (1) | Done
032-25 | Irving | API 650 | N/A | N/A | Done | PT shell nozzles |  | X |  |  |  | Vessel Pneumatic 2 PSI
PT shell to floor seam
[6 empty] | RT LS (1), CS (1), T-Joint (1) | Done
033-25 | Irving | API 650 | N/A | N/A | Done | PT shell nozzles |  | X |  |  |  | Vessel Pneumatic 2 PSI
PT shell to floor seam
[6 empty] | RT LS (1), CS (1), T-Joint (1) | Repairs
052-25 | Kraton Chemical LLC | ASME | Any Long or Circ. Seam |  |  | Shell Spot RT | [5 empty] | Vessel Pneumatic 17 PSI
053-25 SHIPPED | Andritz | Customer Spec | N/A | N/A | Done | N/A | N/A | X | X | X | X | Vessel Pneumatic 2 PSI | Done
054-25 | Chromascape LLC | ASME | Any Long or Circ. Seam |  |  | Shell Spot RT | [5 empty] | Vessel Hydro 26 PSI
Shell Spot RT Due to Noz.
056-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done |  | Shell Spot RT | Done |  |  |  |  | Vessel Pneumatic 110 PSI
Top Head to Shell Spot RT
[6 empty] | Btm Head to Shell Spot RT | Done
057-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done |  | Shell Spot RT | Done |  |  |  |  | Vessel Pneumatic 110 PSI
Top Head to Shell Spot RT
[6 empty] | Btm Head to Shell Spot RT | Done
058-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done |  | Shell Spot RT | [5 empty] | Vessel Pneumatic 110 PSI
Top Head to Shell Spot RT
Btm Head to Shell Spot RT
059-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam | Done |  | Shell Spot RT | [5 empty] | Vessel Pneumatic 110 PSI
Top Head to Shell Spot RT
Btm Head to Shell Spot RT
060-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam |  |  | Shell Spot RT | [5 empty] | Vessel Pneumatic 110 PSI
Top Head to Shell Spot RT
Btm Head to Shell Spot RT
061-25 | Reco Commercial Systems | ASME | Long Seam & Circ. Seam |  |  | Shell Spot RT | [5 empty] | Vessel Pneumatic 110 PSI
Top Head to Shell Spot RT
Btm Head to Shell Spot RT
072-25 SHIPPED | Burke Industrial Inc. | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X | Vessel Pneumatic 2 PSI | Done
073-25 SHIPPED | Burke Industrial Inc. | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X | Vessel Pneumatic 2 PSI | Done
074-25 | Kemira | ASME No Stamp | N/A | N/A |  | RT @ Nozzle "F" Hole | [5 empty] | Vessel Pneumatic 2 PSI
076-25 SHIPPED | Irving | API 650 | N/A | N/A | Done | N/A | N/A | X | X | X | X | Full of Water Hydro | Done
087-25 | Solvay | ASME | Manway To Shell |  |  | N/A | N/A |  |  |  |  | Vessel Hydro 20 PSI
Customer Visit Before Testing

## Package
157-21 Ship Loose Checksheet
Package
Items |  | QC | Shipping
1/4" THK double shells (X6)
1/4" THK single shells (X3)
Top Cone (2 Pieces)
Flat Bottom (2 Pieces)
Rim Angle (X4)
N1 (Pipe & Flange)
N1 Vent
N1 Gasket & Hardware
N2 (Pipe & Flange)
N2 Repad (X2)
N3 (Pipe & Flange)
N3 Repad (X2)
N4 (Pipe, Flange, Blind, Gasket & Hardware)
N5 (Pipe & Flange)
N5 Repad (X2)
N6 (Pipe & Flange)
N7 (Pipe & Flange)
N8 (Pipe & Flange)
N9 (Pipe & Flange)
M1 (Pipe,Flange,Blind,Gasket,Davit Arm,Hardware)
M1 Repad (X2)
M2 (Pipe,Flange,Blind,Gasket,Davit Arm,Hardware)
M2 Repad (X2)
Handail W/ Toe Plate (X2)
Handrail post clips W/ hardware (X10)
Lift Lugs (X4)
Anchor Chair (X7)
Anchor Chair W/ Ground lug (X1)
Nameplate W/ Nameplate Bracket (X1)