## Sheet1
2025-01-12 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
| 116-25 |  | 055-25
|  |  | 092-25 | Done
|  |  | 093-25 | Done
098-25
|  |  | 066-25 | Done |  |  | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
|  |  | 067-25 | Done |  |  | AS BUIT WITH IN 2 WEEKS OF SHIP DATE
|  |  | 101-25 |  |  |  | 117 & 118-25 PE STAMP BY PADDY
099-25
2025-01-19 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
|  |  | 055-25 |  |  |  | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
|  |  | 098-25 | Done | Yes |  | AS BUIT WITH IN 2 WEEKS OF SHIP DATE
|  |  | 101-25 | Done | (4)12" tee -Feb-10 |  | 117 & 118-25 PE STAMP BY PADDY
(4)Drilled pipe Jan-29
Chiness pipe swap (1)3" sch40 x 3.25' & (2)12" pipe swap Jan-22
|  |  | 099-25 | Done | Yes
CATCH UP ON AS BUILT BY END OF JAN 2026
2025-01-26 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
| 109-25 |  | 055-25 |  |  |  | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
| 110-15 |  | 098-25 | Done | Yes |  | AS BUIT WITH IN 2 WEEKS OF SHIP DATE
|  |  | 101-25 | Done | (2)Dished heads-Feb-3
(4)12" tee -Feb-13
(4)Drilled pipe Jan-29
|  |  | 099-25 | Done | Yes |  | CATCH UP ON AS BUILT BY END OF JAN 2026
2026-02-09 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
| 102-25 |  | 055-25 |  | waiting on dish & beveling | 011-25 | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
| 103-25 |  | 068-25 | Done | yes | 020-25 | AS BUIT WITH IN 2 WEEKS OF SHIP DATE
| 104-25 |  | 069-25 | Done | yes
105-25
106-25
107-25 size change
108-25 size change
109-25
| 110-15 | [5 empty] | Save softcopy of 224 Vertive jobs in P: drive
| 111-25 | [5 empty] | CATCH UP ON AS BUILT BY END OF JAN 2026
112-25
115-25
116-25 un authorised
117-25 waiting for PE stamp
2026-02-23 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
| 103-25 |  | 055-25 |  | waiting on dish & beveling | 011-25 | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
| 104-25 |  |  |  |  | 020-25 | AS BUIT WITH IN 2 WEEKS OF SHIP DATE
| 105-25 |  |  |  |  | 064-25
| 109-25 |  |  |  |  | 065-25 | Save softcopy of (224) Vertive jobs in P:drive
| 113-25 |  |  |  |  | 021-25 | CATCH UP ON AS BUILT BY END OF JAN 2026
115-25
2026-03-02 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
| 102-25 |  | 055-25 |  | waiting on dish & beveling | 011-25 | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
| 106-25 |  |  |  |  | 020-25 | AS BUIT WITH IN 2 WEEKS OF SHIP DATE
| 110-25 |  |  |  |  | 064-25
| 111-25 |  |  |  |  | 065-25
| 112-25 |  |  |  |  | 021-25
| 356-25 |  |  |  |  | 010-25
016-25
019-25
SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
AS BUIT WITH IN 2 WEEKS OF SHIP DATE
Update botton conection for JB148/25 & onward for (200) Vertive jobs
2026-03-09 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
| 005-26 |  | 055-25 |  |  |  | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
AS BUIT WITH IN 2 WEEKS OF SHIP DATE
Update botton conection for JN#148/25 & onward for (200) Vertive jobs
2026-03-10 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
| 005-26 |  | 055-25 |  |  |  | SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
AS BUIT WITH IN 2 WEEKS OF SHIP DATE
Update botton conection for JN#148/25 & onward for (200) Vertive jobs
2026-03-23 | Cert. Dwg. | Change Order | Job release | Built plan | Materail recd. | As Built | Remarks
|  |  | 055-25 |  |  | 018-25
066-25
067-25
[6 empty] | 124 THRU 147-25 | 2026-03-19
[6 empty] | 013 & 012-25 | 2026-03-23
SHIPPING POSITION DRAWING FOR 8' AND BIG DIA
AS BUIT WITH IN 2 WEEKS OF SHIP DATE
Update botton conection for JN#148/25 & onward for (200) Vertive jobs