## New Build Plan
Job # | 056-25 | Job Estimated Hours |  | Fill in Green Cells Only as Needed
Work Center | # | Description | Estimated Hours | Notes to Add
prefab | 010 | Receive material
inspection | QC1 | UT top and bottom heads
Nozzles and Manways
prefab | 100 | Cut nozzle pipe and clean | 12 | INCL. FOR INLET MANIFOLD
prefab | 105 | Build nozzles and weld | 6
prefab | 107 | Build Repads for Nozzles, drill and tap holes | 3
prefab | 110 | Build dip tubes and weld | 30 | BUILD INLET MANIFOLD
prefab | 115 | Make manway parts: cut clips, form handles, etc.
prefab | 120 | Burn manway neck (CHECK BEFORE BURNING); Clean and bevel
prefab | 125 | Roll manway neck
prefab | 130 | Set up and weld manway flange and neck seam
prefab | 135 | Build davit arm assembly and cover
prefab | 140 | Build hatch/door
prefab | 145 | Install cladding on flange
prefab | 147 | Install cladding on blind / cover
Cut & Prep Parts
prefab | 155 | Cut parts on CNC plasma table | 40
prefab | 156 | Clean and prep parts | 20
Supports
prefab | 165 | Build supports (legs, lugs, saddles)
prefab | 170 | Roll repads; drill and tap
prefab | 175 | Build and weld base ring - skirt | 8
build | 180 | Skirt; bring in plate, square, trim and clean
build | 185 | Roll skirt shells
Misc. Parts
prefab | 200 | Make lift lugs, ground lugs, etc. | 2
prefab | 205 | Roll rim angle
prefab | 210 | Roll insulation rings
prefab | 215 | Burn and clean baffles (CHECK BEFORE BURNING)
prefab | 220 | Form baffles
prefab | 225 | Cut and make baffle supports
prefab | 230 | Build baffles and weld
prefab | 235 | Build top and bottom stiffeners
prefab | 240 | Roll/Burn vacuum rings (CHECK BEFORE BURNING)
prefab | 245 | Cut parts for mixer bridge
prefab | 250 | Roll pipe - internal coil
prefab | 252 | Fabricate miscellaneous parts
prefab | 255 | Drill / punch holes | 10 | BURN HOLES IN MANIFOLD PIPE & REDUCERS
prefab | 257 | Build Flange
prefab | 260 | Sandblast parts / plates
prefab | 261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks | 2 | MAKE INLET MANIFOLD PIPE SUPPORTS
Ladders, Handrails and Platforms
prefab | 262 | Cut / make parts for ladder (rungs, rails, etc.)
prefab | 265 | Form and roll ladder hoops
prefab | 270 | Build ladder; weld out
prefab | 272 | Cut / make parts for handrail
prefab | 275 | Roll handrail pipe
prefab | 280 | Roll handrail toe plate
prefab | 282 | Build handrail; weld out
prefab | 285 | Cut / make parts for platform
prefab | 290 | Burn grating for platforms; clean and band
prefab | 292 | Build platform; weld out
prefab | 295 | Mount handrail on platform
inspection | QC2 | QC Inspection - Components prior to shipment to subcontractor
Shells
build | 300 | Wrap top and bottom heads | 2
inspection | QC3 | UT Shells
build | 305 | Shells; bring in plate, square, trim and clean | 9
build | 310 | Bevel shell plates | 12
build | 315 | Roll shells, tack and weld inside seams | 18 | INCL. WELD LONG SEAM W/ COBOT
build | 320 | Set up and weld sides - rectangular tank
build | 325 | Install body flange on shell
weld | 326 | Weld body flange on shell
Top Head
build | 350 | Build top head / cone
inspection | QC4 | QC Inspection - Top
detail | 355 | Lay out top head, burn and clean holes | 1
build | 360 | Bevel top head | 1 | CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD
detail | 365 | Set nozzles in top head | 1
weld | 366 | Weld nozzles in top head | 6 | INCL. (2) LIFT LUGS W/ REPADS
weld | 370 | Install and weld out repads - top head
detail | 375 | Install top stiffeners
detail | 380 | Build mixer bridge
build | 382 | Install body flange on top head
weld | 383 | Weld body flange on top head
weld | 385 | Dye pen top head
weld | 390 | Grind inside welds smooth - top head
weld | 395 | Polish inside weld seams - top head
Bottom Head
build | 450 | Build bottom head / cone
inspection | QC4 | QC Inspection - Bottom
detail | 455 | Lay out bottom head, burn and clean holes | 1
build | 460 | Bevel bottom head | 1 | CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD
detail | 465 | Set nozzles in bottom head | 1
weld | 466 | Weld nozzles in bottom head | 2
weld | 470 | Install and weld out repads - bottom head
detail | 475 | Install bottom stiffeners
detail | 477 | Cut and fit jacket to bottom head
weld | 478 | Weld jacket to bottom head
detail | 479 | Install jacket nozzles - bottom head
build | 482 | Install body flange on bottom head
weld | 483 | Weld body flange on bottom head
weld | 485 | Dye pen bottom head
weld | 490 | Grind inside welds smooth - bottom head
weld | 495 | Polish inside weld seams - bottom head
Skirt
build | 500 | Build skirt; prep, roll and tack shells | 5 | ROLL (1) SHELL; INCL. WELD LONG SEAM W/ COBOT
build | 510 | Build skirt; fit base ring to shell | 5 | FIT & TACK BASE RING TO SHELL
weld | 515 | Weld skirt shell seams and base ring | 8 | WELD BASE RING TO SKIRT SHELL INSIDE & OUTSIDE
detail | 520 | Lay out skirt, burn and clean holes
detail | 530 | Build skirt; fit anchors / gussets | 3 | FIT (8) GUSSETS; TACK ONLY
detail | 540 | Set nozzles / manway in skirt
weld | 545 | Weld skirt anchors, gussets, nozzles, manways, etc. | 6 | WELD (8) GUSSETS
Internal Coils
prefab | 580 | Fabricate internal coil supports
prefab | 590 | Fabricate internal coil
Build Main Tank and Install Internals
inspection | OI1 | ASME Hold Point
build | 600 | Fit bottom head to shell | 4
build | 605 | Tack shell courses together | 8
weld | 610 | Weld inside round seams | 18
build | 615 | Install rim angle
weld | 616 | Weld rim angle inside and outside
detail | 620 | Lay out shell, burn and clean holes | 6 | PREP NOZZLE HOLES FOR FULL PEN WELDS
detail | 625 | Install baffles and weld
detail | 630 | Install internals (wear plates, rings, clips, etc.) | 36 | INSTALL INLET MANIFOLD & SUPPPORTS
detail | 635 | Install internal coil and supports
weld | 637 | Grind inside welds smooth - shell
weld | 638 | Polish inside weld seams - shell
inspection | QC5 | Q.C. Inspection - Internal
build | 640 | Fit top head to shell | 5
weld | 641 | Weld top head to shell inside | 12 | INCL. HOLE WATCH
weld | 645 | Weld all outside seams | 20
move | 800 | Move tank to detail rolls | 3
Install Nozzles and Externals
detail | 700 | Fit jacket to shell
weld | 705 | Weld jacket to shell
detail | 710 | Install jacket nozzles
weld | 711 | Weld jacket nozzles
detail | 715 | Install insulation / vacuum rings and weld | 48 | INCL. WELD COMPLETE
detail | 717 | Install lift lugs on shell
detail | 720 | Fit supports (legs, lugs, anchors, saddles, skirt) | 32 | FIT SKIRT TO BOTTOM HEAD AND WELD
weld | 721 | Weld insulation / vacuum rings, lugs, supports, etc.
detail | 725 | Set nozzles & manways in shell | 8
weld | 726 | Weld shell nozzles, manways, etc. | 30 | INCL. HOLE WATCH & NOZZLE A
weld | 730 | Add repads and weld | 5
detail | 735 | Install dip pipe supports
detail | 740 | Install dip pipes
detail | 745 | Install mixer bridge
detail | 750 | Fit handrail; install and weld clips
detail | 755 | Fit ladder; install and weld clips
detail | 760 | Fit platform; install and weld clips, bracing, etc.
inspection | QC51 | UT Components
finishing | 765 | Install name tag | 1
finishing | 900 | Dye pen test
weld | 770 | Inspect tank, make repairs, get QC inspector | 1
inspection | QC6 | Q.C. Inspection - Fabrication
inspection | OI4 | Customer Inspection
inspection | OI2 | ASME Inspection - Internal
Repairs
detail | 850 | Remove head
detail | 855 | Remove nozzles
detail | 860 | Remove jacket
Test and Clean
move | 801 | Move to shop test area | 2
finishing | 900 | Dye pen test
finishing | 910 | Test tank | 12
inspection | QC7 | QC Inspection - Test
inspection | OI3 | ASME Inspection - Test
finishing | 920 | Clean tank complete
inspection | QC8 | QC Inspection - Clean
move | 802 | Move to paint area | 2
inspection | QC9 | QC Inspection - Sandblast
inspection | QC90 | QC Inspection - Paint
finishing | 940 | Prepare tank for shipment | 3
finishing | 950 | Check bill of materials and pack loose parts
inspection | QC95 | Q.C. Inspection - Final & Loose Items
finishing | 960 | Load on truck | 5
shipping | 970 | Take parts to galvanizers
shipping | 971 | Take parts to machine shop
shipping | 972 | Pick up parts from galvanizers
shipping | 973 | Pick up parts from machine shop
inspection | QC21 | QC Inspection - Components return from subcontractor
shipping | 974 | Deliver tank
shipping | 975 | Deliver misc. parts
|  | Total Estimate Hours | 476