## Build Plan w Hours
Job #: | 031-24
| Description: | SMALL DRYER PLATE #5 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL COPE PIPES ***DO NOT CUT THREADED END*** | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) INCL STIFFENERS / STRONG BACKS | 8 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 8 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CUT ANGLES. FORM CLIPS AND SUPPORT HOLDERS | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL INNER & OUTER RINGS; WELD LONG SEAMS | 3 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell LOAD STAYS INTO BOTTOM PLATE & FIT TOP PLATE | 5 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together FIT & TACK INNER & OUTER RINGS | 5 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams WELD INNER & OUTER RINGS COMPLETE ***KEEP FLAT*** | 4 |  |  |  | 0 | 0
FIT |  | .705 | Weld jacket to shell WELD STAYS TO TOP & BOTTOM PLATES. ***KEEP FLAT*** | 16 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD SUPPORT ASSEMBLIES | 3 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 2 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld GRIND TOP WELDS SMOOTH & FLUSH | 18 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 031-24
| Description: | SMALL DRYER PLATE #5 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL COPE PIPES ***DO NOT CUT THREADED END*** | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) INCL STIFFENERS / STRONG BACKS | 8 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 8 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CUT ANGLES. FORM CLIPS AND SUPPORT HOLDERS | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL INNER & OUTER RINGS; WELD LONG SEAMS | 3 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell LOAD STAYS INTO BOTTOM PLATE & FIT TOP PLATE | 5 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together FIT & TACK INNER & OUTER RINGS | 5 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams WELD INNER & OUTER RINGS COMPLETE ***KEEP FLAT*** | 4 |  |  |  | 0 | 0
FIT |  | .705 | Weld jacket to shell WELD STAYS TO TOP & BOTTOM PLATES. ***KEEP FLAT*** | 16 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD SUPPORT ASSEMBLIES | 3 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 2 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld GRIND TOP WELDS SMOOTH & FLUSH | 18 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | SMALL DRYER PLATE #5 | Customer PO: | 5920 | Quote: | 8917 | SMALL DRYER PLATE #5 | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2024-05-30 | Make Qty: | 1 | / | ea | Est Hours: | 94
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 49223 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 49224 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 49225 | 0 | Cut Nozzle Pipe and Clean | 0 | 3 | FixedHrs | 3 | .100 | 0 | Cut nozzle pipe and clean INCL COPE PIPES ***DO NOT CUT THREADED END*** | _________________ | _________________ | _________________
PRE FAB | 49226 | 0 | Cut Parts on Burn Table | 0 | 8 | FixedHrs | 8 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) INCL STIFFENERS / STRONG BACKS | _________________ | _________________ | _________________
PRE FAB | 49227 | 0 | Clean & Prep Parts | 0 | 8 | FixedHrs | 8 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 49228 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 1 | FixedHrs | 1 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 49229 | 0 | Fab Miscellaneous Parts | 0 | 3 | FixedHrs | 3 | .252 | 0 | Fabricate miscellaneous parts CUT ANGLES. FORM CLIPS AND SUPPORT HOLDERS | _________________ | _________________ | _________________
INSPECTION | 49230 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 49231 | 0 | BI, SQ, T&C Shells | 0 | 1 | FixedHrs | 1 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 49232 | 0 | Roll Shell, Tack-Weld I/S | 0 | 3 | FixedHrs | 3 | .315 | 0 | Roll shells, tack and weld inside seams ROLL INNER & OUTER RINGS; WELD LONG SEAMS | _________________ | _________________ | _________________
FIT | 49233 | 0 | Fit Bottom Head to Shell | 0 | 5 | FixedHrs | 5 | .600 | 0 | Fit bottom head to shell LOAD STAYS INTO BOTTOM PLATE & FIT TOP PLATE | _________________ | _________________ | _________________
FIT | 49234 | 0 | Tack Shell Courses | 0 | 5 | FixedHrs | 5 | .605 | 0 | Tack shell courses together FIT & TACK INNER & OUTER RINGS | _________________ | _________________ | _________________
FIT | 49235 | 0 | Weld all Outside Seams | 0 | 4 | FixedHrs | 4 | .645 | 0 | Weld all outside seams WELD INNER & OUTER RINGS COMPLETE ***KEEP FLAT*** | _________________ | _________________ | _________________
FIT | 49236 | 0 | Weld Jacket to Shell | 0 | 16 | FixedHrs | 16 | .705 | 0 | Weld jacket to shell WELD STAYS TO TOP & BOTTOM PLATES. ***KEEP FLAT*** | _________________ | _________________ | _________________
FIT | 49237 | 0 | Install Support Parts | 0 | 3 | FixedHrs | 3 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD SUPPORT ASSEMBLIES | _________________ | _________________ | _________________
FIT | 49238 | 0 | Set Nozzles in Shell | 0 | 1 | FixedHrs | 1 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 49239 | 0 | Weld Shell Nozz & M/Ws | 0 | 2 | FixedHrs | 2 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
FIT | 49240 | 0 | Add Repads-Weld | 0 | 18 | FixedHrs | 18 | .730 | 0 | Add repads and weld GRIND TOP WELDS SMOOTH & FLUSH | _________________ | _________________ | _________________
FINISHING | 49241 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 49242 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 49243 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 49244 | 0 | Customer Inspection | 0 | 0 | FixedHrs | 0 | .OI4 | 0 | Customer Inspection | _________________ | _________________ | _________________
MOVE TANK | 49245 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 49246 | 0 | Test Tank | 0 | 6 | FixedHrs | 6 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 49247 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 49248 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
FINISHING | 49249 | 0 | Clean Tank Complete | 0 | 3 | FixedHrs | 3 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 49250 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
INSPECTION | 49251 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 49252 | 0 | Load on Truck | 0 | 1 | FixedHrs | 1 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | SMALL DRYER PLATE #5 |  |  |  | Rev:

## Tasks with Hours
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL COPE PIPES ***DO NOT CUT THREADED END***
Hours | 3
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) INCL STIFFENERS / STRONG BACKS
Hours | 8
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 8
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 1
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CUT ANGLES. FORM CLIPS AND SUPPORT HOLDERS
Hours | 3
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 1
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL INNER & OUTER RINGS; WELD LONG SEAMS
Hours | 3
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell LOAD STAYS INTO BOTTOM PLATE & FIT TOP PLATE
Hours | 5
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together FIT & TACK INNER & OUTER RINGS
Hours | 5
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams WELD INNER & OUTER RINGS COMPLETE ***KEEP FLAT***
Hours | 4
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .705 | Weld jacket to shell WELD STAYS TO TOP & BOTTOM PLATES. ***KEEP FLAT***
Hours | 16
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD SUPPORT ASSEMBLIES
Hours | 3
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 1
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 2
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld GRIND TOP WELDS SMOOTH & FLUSH
Hours | 18
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 6
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 3
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 1
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL COPE PIPES ***DO NOT CUT THREADED END***
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) INCL STIFFENERS / STRONG BACKS
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CUT ANGLES. FORM CLIPS AND SUPPORT HOLDERS
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL INNER & OUTER RINGS; WELD LONG SEAMS
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell LOAD STAYS INTO BOTTOM PLATE & FIT TOP PLATE
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together FIT & TACK INNER & OUTER RINGS
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams WELD INNER & OUTER RINGS COMPLETE ***KEEP FLAT***
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .705 | Weld jacket to shell WELD STAYS TO TOP & BOTTOM PLATES. ***KEEP FLAT***
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD SUPPORT ASSEMBLIES
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld GRIND TOP WELDS SMOOTH & FLUSH
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 031-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_