## Build Plan w Hours
Job #: | 063-24
| Description: | LIME DAY TANK #1 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 10 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 8 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 20 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 25 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 2 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports FORM (15) BAFFLE SUPPORTS | 3 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld | 12 |  |  |  | 0 | 0
PRE FAB |  | .245 | Cut parts for mixer bridge (2) CHANNELS & (4) MITERED BRACES | 3 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 3 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 8 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 20 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail INCL (4) TOE PLATE BREAK PIECES | 5 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe | 3 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 2 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 24 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 8 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone CLEAN UP & PREP HOLES CUT ON BURN TABLE | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 3 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 10 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 7 |  |  |  | 0 | 0
PRE FAB |  | .380 | Build mixer bridge | 12 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE | 10 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 4 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 4 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 5 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 7 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP & PREP HOLES CUT ON BURN TABLE | 3 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 7 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 12 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 3 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 6 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 18 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 3 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 6 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 8 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 063-24
| Description: | LIME DAY TANK #1 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 10 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 8 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 20 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 25 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 2 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports FORM (15) BAFFLE SUPPORTS | 3 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld | 12 |  |  |  | 0 | 0
PRE FAB |  | .245 | Cut parts for mixer bridge (2) CHANNELS & (4) MITERED BRACES | 3 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 3 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 8 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 20 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail INCL (4) TOE PLATE BREAK PIECES | 5 |  |  |  | 0 | 0
PRE FAB |  | .275 | Roll handrail pipe | 3 |  |  |  | 0 | 0
PRE FAB |  | .280 | Roll handrail toe plate | 2 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 24 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 8 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone CLEAN UP & PREP HOLES CUT ON BURN TABLE | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 3 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 10 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 7 |  |  |  | 0 | 0
PRE FAB |  | .380 | Build mixer bridge | 12 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE | 10 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 4 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 4 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 5 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 7 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP & PREP HOLES CUT ON BURN TABLE | 3 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE | 7 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 12 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 3 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 6 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 18 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 3 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 6 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 8 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | LIME DAY TANK #1 | Customer PO: | G0080008.46 | Quote: | 8961.4 | LIME DAY TANK #1 | Line: | 2 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2024-12-18 | Make Qty: | 1 | / | ea | Est Hours: | 389
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 50631 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 50632 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 50633 | 0 | Cut Nozzle Pipe and Clean | 0 | 5 | FixedHrs | 5 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 50634 | 0 | Build Nozzles-Weld | 0 | 10 | FixedHrs | 10 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 50635 | 0 | Build Repads for Nozzles | 0 | 8 | FixedHrs | 8 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 50636 | 0 | Make Manway Parts | 0 | 2 | FixedHrs | 2 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 50637 | 0 | Brn MW Neck, Clean, Bevel | 0 | 2 | FixedHrs | 2 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 50638 | 0 | Roll Manway Neck | 0 | 2 | FixedHrs | 2 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 50639 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 4 | FixedHrs | 4 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 50640 | 0 | Bld Davit Arm Aby Cover | 0 | 4 | FixedHrs | 4 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 50641 | 0 | Build Hatch/Door | 0 | 4 | FixedHrs | 4 | .140 | 0 | Build hatch/door | _________________ | _________________ | _________________
PRE FAB | 50642 | 0 | Cut Parts on Burn Table | 0 | 20 | FixedHrs | 20 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 50643 | 0 | Clean & Prep Parts | 0 | 25 | FixedHrs | 25 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 50644 | 0 | Build Supports | 0 | 2 | FixedHrs | 2 | .165 | 0 | Build supports: legs, lugs, saddles | _________________ | _________________ | _________________
PRE FAB | 50645 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 50646 | 0 | Roll Rim Angle | 0 | 3 | FixedHrs | 3 | .205 | 0 | Roll rim angle | _________________ | _________________ | _________________
PRE FAB | 50647 | 0 | Cut, Make Baffle Supports | 0 | 3 | FixedHrs | 3 | .225 | 0 | Cut and make baffle supports FORM (15) BAFFLE SUPPORTS | _________________ | _________________ | _________________
PRE FAB | 50648 | 0 | Build Baffles-Weld | 0 | 12 | FixedHrs | 12 | .230 | 0 | Build baffles and weld | _________________ | _________________ | _________________
PRE FAB | 50649 | 0 | Cut Parts-Mixer Bridge | 0 | 3 | FixedHrs | 3 | .245 | 0 | Cut parts for mixer bridge (2) CHANNELS & (4) MITERED BRACES | _________________ | _________________ | _________________
PRE FAB | 50650 | 0 | Cut, Build Ladder Parts | 0 | 3 | FixedHrs | 3 | .262 | 0 | Cut/make parts for ladder: rungs, rails, etc. | _________________ | _________________ | _________________
PRE FAB | 50651 | 0 | Form and Roll Ladder Hoop | 0 | 8 | FixedHrs | 8 | .265 | 0 | Form and roll ladder hoops | _________________ | _________________ | _________________
PRE FAB | 50652 | 0 | Build Ladder-Weld | 0 | 20 | FixedHrs | 20 | .270 | 0 | Build ladder - weld out | _________________ | _________________ | _________________
PRE FAB | 50653 | 0 | Cut, Build Handrail Parts | 0 | 5 | FixedHrs | 5 | .272 | 0 | Cut/Build parts for handrail INCL (4) TOE PLATE BREAK PIECES | _________________ | _________________ | _________________
PRE FAB | 50654 | 0 | Roll Handrail Pipe | 0 | 3 | FixedHrs | 3 | .275 | 0 | Roll handrail pipe | _________________ | _________________ | _________________
PRE FAB | 50655 | 0 | Roll Handrail Toe Plate | 0 | 2 | FixedHrs | 2 | .280 | 0 | Roll handrail toe plate | _________________ | _________________ | _________________
PRE FAB | 50656 | 0 | Build Handrail-Weld | 0 | 24 | FixedHrs | 24 | .282 | 0 | Build handrail - weld out | _________________ | _________________ | _________________
INSPECTION | 50657 | 0 | QC Inspection - Pre Sub C | 0 | 0 | FixedHrs | 0 | .QC2 | 0 | QC Inspection - Components prior to shipping to Subcontractor | _________________ | _________________ | _________________
INSPECTION | 50658 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 50659 | 0 | BI, SQ, T&C Shells | 0 | 4 | FixedHrs | 4 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 50660 | 0 | Roll Shell, Tack-Weld I/S | 0 | 8 | FixedHrs | 8 | .315 | 0 | Roll shells, tack and weld inside seams | _________________ | _________________ | _________________
PRE FAB | 50661 | 0 | Build Top Head/Cone | 0 | 8 | FixedHrs | 8 | .350 | 0 | Build top head/cone CLEAN UP & PREP HOLES CUT ON BURN TABLE | _________________ | _________________ | _________________
INSPECTION | 50662 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 50663 | 0 | L/O Top, B&C Holes | 0 | 3 | FixedHrs | 3 | .355 | 0 | Lay out top head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 50664 | 0 | Set Nozzles & Lugs - Top | 0 | 4 | FixedHrs | 4 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 50665 | 0 | Weld Nozzles - Top Head | 0 | 10 | FixedHrs | 10 | .366 | 0 | Weld out top head nozzles, etc. | _________________ | _________________ | _________________
PRE FAB | 50666 | 0 | I&W Repads -Top | 0 | 7 | FixedHrs | 7 | .370 | 0 | Install and weld out repads - top head | _________________ | _________________ | _________________
PRE FAB | 50667 | 0 | Build Mixer Bridge | 0 | 12 | FixedHrs | 12 | .380 | 0 | Build mixer bridge | _________________ | _________________ | _________________
PRE FAB | 50668 | 0 | Build Bottom Head/Cone | 0 | 8 | FixedHrs | 8 | .450 | 0 | Build bottom head/cone | _________________ | _________________ | _________________
INSPECTION | 50669 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 50670 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes | _________________ | _________________ | _________________
FIT | 50671 | 0 | Fit Bottom Head to Shell | 0 | 10 | FixedHrs | 10 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE | _________________ | _________________ | _________________
FIT | 50672 | 0 | Tack Shell Courses | 0 | 4 | FixedHrs | 4 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 50673 | 0 | Weld Inside Round Seams | 0 | 4 | FixedHrs | 4 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 50674 | 0 | Install Rim Angle | 0 | 5 | FixedHrs | 5 | .615 | 0 | Install rim angle - tack only | _________________ | _________________ | _________________
FIT | 50675 | 0 | Weld Rim Angle | 0 | 7 | FixedHrs | 7 | .616 | 0 | Weld rim angle complete | _________________ | _________________ | _________________
FIT | 50676 | 0 | L/O Shell, B&C Holes | 0 | 3 | FixedHrs | 3 | .620 | 0 | Lay out shell, burn and clean holes CLEAN UP & PREP HOLES CUT ON BURN TABLE | _________________ | _________________ | _________________
FIT | 50677 | 0 | Install Baffles-Weld | 0 | 8 | FixedHrs | 8 | .625 | 0 | Install baffles and weld | _________________ | _________________ | _________________
INSPECTION | 50678 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 50679 | 0 | Fit Top to Shell | 0 | 7 | FixedHrs | 7 | .640 | 0 | Fit top head to shell - tack AND WELD TO RIM ANGLE | _________________ | _________________ | _________________
FIT | 50680 | 0 | Weld all Outside Seams | 0 | 12 | FixedHrs | 12 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 50681 | 0 | Move Tank to Detail Rolls | 0 | 2 | FixedHrs | 2 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 50682 | 0 | Install Lift Lugs on Shl | 0 | 3 | FixedHrs | 3 | .717 | 0 | Install lift lugs on shell INCL REPADS | _________________ | _________________ | _________________
FIT | 50683 | 0 | Install Support Parts | 0 | 12 | FixedHrs | 12 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | _________________ | _________________ | _________________
FIT | 50684 | 0 | Set Nozzles in Shell | 0 | 6 | FixedHrs | 6 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 50685 | 0 | Weld Shell Nozz & M/Ws | 0 | 18 | FixedHrs | 18 | .726 | 0 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | _________________ | _________________ | _________________
FIT | 50686 | 0 | Add Repads-Weld | 0 | 3 | FixedHrs | 3 | .730 | 0 | Add repads and weld | _________________ | _________________ | _________________
FIT | 50687 | 0 | Fit Handrail, I&W Clips | 0 | 6 | FixedHrs | 6 | .750 | 0 | Fit handrail - install and weld clips | _________________ | _________________ | _________________
FIT | 50688 | 0 | Fit Ladder, I&W Clips | 0 | 8 | FixedHrs | 8 | .755 | 0 | Fit ladder - install and weld clips | _________________ | _________________ | _________________
FINISHING | 50689 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 50690 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 50691 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 50692 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 50693 | 0 | Test Tank | 0 | 12 | FixedHrs | 12 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 50694 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
MOVE TANK | 50695 | 0 | Move to Paint Area | 0 | 2 | FixedHrs | 2 | .802 | 0 | Move to paint area | _________________ | _________________ | _________________
INSPECTION | 50696 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 50697 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 50698 | 0 | Prepare Tank for Shipment | 0 | 3 | FixedHrs | 3 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 50699 | 0 | Check BOM, Pack Parts | 0 | 3 | FixedHrs | 3 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 50700 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 50701 | 0 | Take Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .970 | 0 | Take parts to galvanizers | _________________ | _________________ | _________________
SHIPPING | 50702 | 0 | P/U Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .972 | 0 | Pick up parts from galvanizers | _________________ | _________________ | _________________
| Part: | LIME DAY TANK #1 |  |  |  | Rev:

## Tasks with Hours
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 5
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 10
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 8
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 4
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 4
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door
Hours | 4
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 20
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 25
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports FORM (15) BAFFLE SUPPORTS
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld
Hours | 12
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .245 | Cut parts for mixer bridge (2) CHANNELS & (4) MITERED BRACES
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
Hours | 8
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
Hours | 20
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail INCL (4) TOE PLATE BREAK PIECES
Hours | 5
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
Hours | 24
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 4
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
Hours | 8
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone CLEAN UP & PREP HOLES CUT ON BURN TABLE
Hours | 8
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 4
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
Hours | 10
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
Hours | 7
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .380 | Build mixer bridge
Hours | 12
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
Hours | 8
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
Hours | 1
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE
Hours | 10
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 4
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 4
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
Hours | 5
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
Hours | 7
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP & PREP HOLES CUT ON BURN TABLE
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
Hours | 8
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
Hours | 7
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 12
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
Hours | 12
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 6
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
Hours | 18
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
Hours | 6
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
Hours | 8
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 12
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
Hours | 2
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
Hours | 3
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports FORM (15) BAFFLE SUPPORTS
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .245 | Cut parts for mixer bridge (2) CHANNELS & (4) MITERED BRACES
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail INCL (4) TOE PLATE BREAK PIECES
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .275 | Roll handrail pipe
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .280 | Roll handrail toe plate
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone CLEAN UP & PREP HOLES CUT ON BURN TABLE
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .380 | Build mixer bridge
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP & PREP HOLES CUT ON BURN TABLE
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD TO RIM ANGLE
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 063-24 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_