## Build Plan w Hours
Job #: | 004-25
| Description: | BLUNGER TANK #4 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 1 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 30 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 15 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles BUILD (6) ANCHOR CHAIRS. TACK ONLY | 6 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap FOR LIFT LUGS | 1 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .215 | Burn and clean baffles (CHECK BEFORE BURNING) BUILD DIVIDER PLATE ASSEMBLY | 15 |  |  |  | 0 | 0
PRE FAB |  | .220 | Form baffles FORM (4) BAFFLES | 2 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports MAKE (8) BAFFLE SUPPORTS | 4 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld BUILD (4) BAFFLES | 3 |  |  |  | 0 | 0
PRE FAB |  | .245 | Cut parts for mixer bridge CUT TUBES & ANGLES FOR AGITATION BRIDGE | 16 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts MAKE (5) SHELL SQUARE TUBE ASSEMBLIES | 5 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes DRILL THRU HOLES IN TUBES & BRACES | 3 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW BOX ASSEMBLY | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean SET UP (1) DOUBLE SHELL | 3 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL & WELD (1) DOUBLE SHELL | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .380 | Build mixer bridge | 65 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone MAKE FLAT BOTTOM | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE | 7 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only INSTALL TOP RING & WELD COMPLETE | 9 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete FIT & WELD (10) TOP RING GUSSETS | 8 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld INSTALL (4) BAFFLES | 6 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. INSTALL DIVIDER PLATE ASSEMBLY & WELD | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .645 | Weld all outside seams | 5 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 3 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (6) ANCHOR CHAIRS | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL OVERFLOW BOX | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL OVERFLOW BOX | 15 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld (6) SHELL REPADS FORSQ. TUBES ***WATCH HEAT*** | 6 |  |  |  | 0 | 0
FIT |  | .745 | Install mixer bridge TEST FIT AGITATOR BRIDGE AND TOP COVERS | 20 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 30 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 4 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 004-25
| Description: | BLUNGER TANK #4 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 1 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 2 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 4 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 30 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 15 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles BUILD (6) ANCHOR CHAIRS. TACK ONLY | 6 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap FOR LIFT LUGS | 1 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .215 | Burn and clean baffles (CHECK BEFORE BURNING) BUILD DIVIDER PLATE ASSEMBLY | 15 |  |  |  | 0 | 0
PRE FAB |  | .220 | Form baffles FORM (4) BAFFLES | 2 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports MAKE (8) BAFFLE SUPPORTS | 4 |  |  |  | 0 | 0
PRE FAB |  | .230 | Build baffles and weld BUILD (4) BAFFLES | 3 |  |  |  | 0 | 0
PRE FAB |  | .245 | Cut parts for mixer bridge CUT TUBES & ANGLES FOR AGITATION BRIDGE | 16 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts MAKE (5) SHELL SQUARE TUBE ASSEMBLIES | 5 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes DRILL THRU HOLES IN TUBES & BRACES | 3 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW BOX ASSEMBLY | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean SET UP (1) DOUBLE SHELL | 3 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL & WELD (1) DOUBLE SHELL | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .380 | Build mixer bridge | 65 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone MAKE FLAT BOTTOM | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE | 7 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only INSTALL TOP RING & WELD COMPLETE | 9 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete FIT & WELD (10) TOP RING GUSSETS | 8 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld INSTALL (4) BAFFLES | 6 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. INSTALL DIVIDER PLATE ASSEMBLY & WELD | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .645 | Weld all outside seams | 5 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL REPADS | 3 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (6) ANCHOR CHAIRS | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL OVERFLOW BOX | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL OVERFLOW BOX | 15 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld (6) SHELL REPADS FORSQ. TUBES ***WATCH HEAT*** | 6 |  |  |  | 0 | 0
FIT |  | .745 | Install mixer bridge TEST FIT AGITATOR BRIDGE AND TOP COVERS | 20 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 30 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 4 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | BLUNGER TANK #4 | Customer PO: | 247729 | Quote: | 9111 | BLUNGER TANK #4 | Line: | 3 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-01-17 | Make Qty: | 1 | / | ea | Est Hours: | 382
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 51382 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 51383 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 51384 | 0 | Cut Nozzle Pipe and Clean | 0 | 1 | FixedHrs | 1 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 51385 | 0 | Build Nozzles-Weld | 0 | 1 | FixedHrs | 1 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 51386 | 0 | Make Manway Parts | 0 | 2 | FixedHrs | 2 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 51387 | 0 | Brn MW Neck, Clean, Bevel | 0 | 2 | FixedHrs | 2 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 51388 | 0 | Roll Manway Neck | 0 | 2 | FixedHrs | 2 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 51389 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 4 | FixedHrs | 4 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 51390 | 0 | Bld Davit Arm Aby Cover | 0 | 4 | FixedHrs | 4 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 51391 | 0 | Cut Parts on Burn Table | 0 | 30 | FixedHrs | 30 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 51392 | 0 | Clean & Prep Parts | 0 | 15 | FixedHrs | 15 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 51393 | 0 | Build Supports | 0 | 6 | FixedHrs | 6 | .165 | 0 | Build supports: legs, lugs, saddles BUILD (6) ANCHOR CHAIRS. TACK ONLY | _________________ | _________________ | _________________
PRE FAB | 51394 | 0 | Roll Repads-Drill & Tap | 0 | 1 | FixedHrs | 1 | .170 | 0 | Roll repads: drill and tap FOR LIFT LUGS | _________________ | _________________ | _________________
PRE FAB | 51395 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 51396 | 0 | B&C Baffles | 0 | 15 | FixedHrs | 15 | .215 | 0 | Burn and clean baffles (CHECK BEFORE BURNING) BUILD DIVIDER PLATE ASSEMBLY | _________________ | _________________ | _________________
PRE FAB | 51397 | 0 | Form Baffles | 0 | 2 | FixedHrs | 2 | .220 | 0 | Form baffles FORM (4) BAFFLES | _________________ | _________________ | _________________
PRE FAB | 51398 | 0 | Cut, Make Baffle Supports | 0 | 4 | FixedHrs | 4 | .225 | 0 | Cut and make baffle supports MAKE (8) BAFFLE SUPPORTS | _________________ | _________________ | _________________
PRE FAB | 51399 | 0 | Build Baffles-Weld | 0 | 3 | FixedHrs | 3 | .230 | 0 | Build baffles and weld BUILD (4) BAFFLES | _________________ | _________________ | _________________
PRE FAB | 51400 | 0 | Cut Parts-Mixer Bridge | 0 | 16 | FixedHrs | 16 | .245 | 0 | Cut parts for mixer bridge CUT TUBES & ANGLES FOR AGITATION BRIDGE | _________________ | _________________ | _________________
PRE FAB | 51401 | 0 | Fab Miscellaneous Parts | 0 | 5 | FixedHrs | 5 | .252 | 0 | Fabricate miscellaneous parts MAKE (5) SHELL SQUARE TUBE ASSEMBLIES | _________________ | _________________ | _________________
PRE FAB | 51402 | 0 | Drill/Punch holes | 0 | 3 | FixedHrs | 3 | .255 | 0 | Drill/punch holes DRILL THRU HOLES IN TUBES & BRACES | _________________ | _________________ | _________________
PRE FAB | 51403 | 0 | Misc Fabrication | 0 | 10 | FixedHrs | 10 | .261 | 0 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW BOX ASSEMBLY | _________________ | _________________ | _________________
INSPECTION | 51404 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 51405 | 0 | BI, SQ, T&C Shells | 0 | 3 | FixedHrs | 3 | .305 | 0 | Shells: bring in plate, square, trim and clean SET UP (1) DOUBLE SHELL | _________________ | _________________ | _________________
PRE FAB | 51406 | 0 | Roll Shell, Tack-Weld I/S | 0 | 5 | FixedHrs | 5 | .315 | 0 | Roll shells, tack and weld inside seams ROLL & WELD (1) DOUBLE SHELL | _________________ | _________________ | _________________
INSPECTION | 51407 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 51408 | 0 | Build Mixer Bridge | 0 | 65 | FixedHrs | 65 | .380 | 0 | Build mixer bridge | _________________ | _________________ | _________________
PRE FAB | 51409 | 0 | Build Bottom Head/Cone | 0 | 5 | FixedHrs | 5 | .450 | 0 | Build bottom head/cone MAKE FLAT BOTTOM | _________________ | _________________ | _________________
INSPECTION | 51410 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
FIT | 51411 | 0 | Fit Bottom Head to Shell | 0 | 7 | FixedHrs | 7 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE | _________________ | _________________ | _________________
FIT | 51412 | 0 | Install Rim Angle | 0 | 9 | FixedHrs | 9 | .615 | 0 | Install rim angle - tack only INSTALL TOP RING & WELD COMPLETE | _________________ | _________________ | _________________
FIT | 51413 | 0 | Weld Rim Angle | 0 | 8 | FixedHrs | 8 | .616 | 0 | Weld rim angle complete FIT & WELD (10) TOP RING GUSSETS | _________________ | _________________ | _________________
FIT | 51414 | 0 | L/O Shell, B&C Holes | 0 | 1 | FixedHrs | 1 | .620 | 0 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | _________________ | _________________ | _________________
FIT | 51415 | 0 | Install Baffles-Weld | 0 | 6 | FixedHrs | 6 | .625 | 0 | Install baffles and weld INSTALL (4) BAFFLES | _________________ | _________________ | _________________
FIT | 51416 | 0 | Install Internal Parts | 0 | 20 | FixedHrs | 20 | .630 | 0 | Install internals - wear plates, rings, clips, etc. INSTALL DIVIDER PLATE ASSEMBLY & WELD | _________________ | _________________ | _________________
INSPECTION | 51417 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 51418 | 0 | Weld all Outside Seams | 0 | 5 | FixedHrs | 5 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 51419 | 0 | Move Tank to Detail Rolls | 0 | 1 | FixedHrs | 1 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 51420 | 0 | Install Lift Lugs on Shl | 0 | 3 | FixedHrs | 3 | .717 | 0 | Install lift lugs on shell INCL REPADS | _________________ | _________________ | _________________
FIT | 51421 | 0 | Install Support Parts | 0 | 12 | FixedHrs | 12 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (6) ANCHOR CHAIRS | _________________ | _________________ | _________________
FIT | 51422 | 0 | Set Nozzles in Shell | 0 | 8 | FixedHrs | 8 | .725 | 0 | Set nozzles in shell - tack INCL OVERFLOW BOX | _________________ | _________________ | _________________
FIT | 51423 | 0 | Weld Shell Nozz & M/Ws | 0 | 15 | FixedHrs | 15 | .726 | 0 | Weld shell nozzles, manways, etc. INCL OVERFLOW BOX | _________________ | _________________ | _________________
FIT | 51424 | 0 | Add Repads-Weld | 0 | 6 | FixedHrs | 6 | .730 | 0 | Add repads and weld (6) SHELL REPADS FORSQ. TUBES ***WATCH HEAT*** | _________________ | _________________ | _________________
FIT | 51425 | 0 | Install Mixer Bridge | 0 | 20 | FixedHrs | 20 | .745 | 0 | Install mixer bridge TEST FIT AGITATOR BRIDGE AND TOP COVERS | _________________ | _________________ | _________________
FINISHING | 51426 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 51427 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 51428 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 51429 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 51430 | 0 | Test Tank | 0 | 12 | FixedHrs | 12 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 51431 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 51432 | 0 | Clean Tank Complete | 0 | 30 | FixedHrs | 30 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 51433 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
MOVE TANK | 51434 | 0 | Move to Paint Area | 0 | 2 | FixedHrs | 2 | .802 | 0 | Move to paint area | _________________ | _________________ | _________________
INSPECTION | 51435 | 0 | QC Inspection - Sandblast | 0 | 0 | FixedHrs | 0 | .QC9 | 0 | QC Inspection - Sandblast | _________________ | _________________ | _________________
INSPECTION | 51436 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 51437 | 0 | Prepare Tank for Shipment | 0 | 2 | FixedHrs | 2 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 51438 | 0 | Check BOM, Pack Parts | 0 | 2 | FixedHrs | 2 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 51439 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 51440 | 0 | Load on Truck | 0 | 4 | FixedHrs | 4 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | BLUNGER TANK #4 |  |  |  | Rev:

## Tasks with Hours
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 4
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 4
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 30
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 15
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles BUILD (6) ANCHOR CHAIRS. TACK ONLY
Hours | 6
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap FOR LIFT LUGS
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .215 | Burn and clean baffles (CHECK BEFORE BURNING) BUILD DIVIDER PLATE ASSEMBLY
Hours | 15
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .220 | Form baffles FORM (4) BAFFLES
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports MAKE (8) BAFFLE SUPPORTS
Hours | 4
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld BUILD (4) BAFFLES
Hours | 3
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .245 | Cut parts for mixer bridge CUT TUBES & ANGLES FOR AGITATION BRIDGE
Hours | 16
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts MAKE (5) SHELL SQUARE TUBE ASSEMBLIES
Hours | 5
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes DRILL THRU HOLES IN TUBES & BRACES
Hours | 3
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW BOX ASSEMBLY
Hours | 10
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean SET UP (1) DOUBLE SHELL
Hours | 3
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL & WELD (1) DOUBLE SHELL
Hours | 5
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .380 | Build mixer bridge
Hours | 65
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone MAKE FLAT BOTTOM
Hours | 5
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE
Hours | 7
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only INSTALL TOP RING & WELD COMPLETE
Hours | 9
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete FIT & WELD (10) TOP RING GUSSETS
Hours | 8
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld INSTALL (4) BAFFLES
Hours | 6
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. INSTALL DIVIDER PLATE ASSEMBLY & WELD
Hours | 20
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 5
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
Hours | 3
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (6) ANCHOR CHAIRS
Hours | 12
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL OVERFLOW BOX
Hours | 8
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL OVERFLOW BOX
Hours | 15
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld (6) SHELL REPADS FORSQ. TUBES ***WATCH HEAT***
Hours | 6
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .745 | Install mixer bridge TEST FIT AGITATOR BRIDGE AND TOP COVERS
Hours | 20
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 12
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 30
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 2
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 4
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles BUILD (6) ANCHOR CHAIRS. TACK ONLY
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap FOR LIFT LUGS
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .215 | Burn and clean baffles (CHECK BEFORE BURNING) BUILD DIVIDER PLATE ASSEMBLY
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .220 | Form baffles FORM (4) BAFFLES
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports MAKE (8) BAFFLE SUPPORTS
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .230 | Build baffles and weld BUILD (4) BAFFLES
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .245 | Cut parts for mixer bridge CUT TUBES & ANGLES FOR AGITATION BRIDGE
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts MAKE (5) SHELL SQUARE TUBE ASSEMBLIES
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes DRILL THRU HOLES IN TUBES & BRACES
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW BOX ASSEMBLY
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean SET UP (1) DOUBLE SHELL
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL & WELD (1) DOUBLE SHELL
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .380 | Build mixer bridge
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone MAKE FLAT BOTTOM
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE & OUTSIDE
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only INSTALL TOP RING & WELD COMPLETE
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete FIT & WELD (10) TOP RING GUSSETS
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld INSTALL (4) BAFFLES
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. INSTALL DIVIDER PLATE ASSEMBLY & WELD
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL REPADS
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (6) ANCHOR CHAIRS
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL OVERFLOW BOX
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL OVERFLOW BOX
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld (6) SHELL REPADS FORSQ. TUBES ***WATCH HEAT***
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .745 | Install mixer bridge TEST FIT AGITATOR BRIDGE AND TOP COVERS
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 004-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_