## Build Plan w Hours
Job #: | 026-25
| Description: | CREPING ADHESIVE BULK TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld DO NOT WELD FLANGES ON N2 OR N5 | 11 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door BUILD N3 INCL. RAILS & CROSS BRACING | 16 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 22 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 12 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap FOR CABLE SUPPORT & SHELL REPADS | 3 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CABLE SUPPORT; CLIP FOR N2 | 2 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes PARTS FOR HATCH N3 | 1 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks FORM N5 CONE | 3 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 3 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 2 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 8 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 4 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 6 |  |  |  | 0 | 0
PRE FAB |  | .285 | Cut/Build parts for platform | 3 |  |  |  | 0 | 0
PRE FAB |  | .290 | Burn grating for platforms, clean and band | 2 |  |  |  | 0 | 0
PRE FAB |  | .292 | Build platform - weld out | 7 |  |  |  | 0 | 0
PRE FAB |  | .295 | Mount handrail on platform | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean SET UP (2) DOUBLE SHELLS **NOTE BOTTOM HEAD SLOPE** | 12 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS ***WELD LONG SEAMS W COBOT*** | 7 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 9 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT | 8 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head FOR CABLE SUPPORT | 2 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE ***NOTE BOTTOM SLOPE*** | 10 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 3 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 3 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. HANDLE | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD | 6 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 7 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell AND TIE-OFF LUGS | 3 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 4 |  |  |  | 0 | 0
FIT |  | .721 | Weld insulation / vacuum rings, lugs, supports, etc. | 4 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL ADD FLANGE TO N2 & N5, PLUS HANDLE AND HOOK | 15 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL WELD FLANGE TO N2 & N6, PLUS HANDLE AND HOOK | 25 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld SHELL REPADS AT 330 DEG. | 4 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports N2 | 1 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 2 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 10 |  |  |  | 0 | 0
FIT |  | .760 | Fit platform - install and weld clips, bracing, etc. | 10 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test | 6 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 35 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 4 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 026-25
| Description: | CREPING ADHESIVE BULK TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld DO NOT WELD FLANGES ON N2 OR N5 | 11 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door BUILD N3 INCL. RAILS & CROSS BRACING | 16 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 22 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 12 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 4 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap FOR CABLE SUPPORT & SHELL REPADS | 3 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle | 3 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CABLE SUPPORT; CLIP FOR N2 | 2 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes PARTS FOR HATCH N3 | 1 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks FORM N5 CONE | 3 |  |  |  | 0 | 0
PRE FAB |  | .262 | Cut/make parts for ladder: rungs, rails, etc. | 3 |  |  |  | 0 | 0
PRE FAB |  | .265 | Form and roll ladder hoops | 2 |  |  |  | 0 | 0
PRE FAB |  | .270 | Build ladder - weld out | 8 |  |  |  | 0 | 0
PRE FAB |  | .272 | Cut/Build parts for handrail | 4 |  |  |  | 0 | 0
PRE FAB |  | .282 | Build handrail - weld out | 6 |  |  |  | 0 | 0
PRE FAB |  | .285 | Cut/Build parts for platform | 3 |  |  |  | 0 | 0
PRE FAB |  | .290 | Burn grating for platforms, clean and band | 2 |  |  |  | 0 | 0
PRE FAB |  | .292 | Build platform - weld out | 7 |  |  |  | 0 | 0
PRE FAB |  | .295 | Mount handrail on platform | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean SET UP (2) DOUBLE SHELLS **NOTE BOTTOM HEAD SLOPE** | 12 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS ***WELD LONG SEAMS W COBOT*** | 7 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 9 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT | 8 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head FOR CABLE SUPPORT | 2 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE ***NOTE BOTTOM SLOPE*** | 10 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 3 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 3 |  |  |  | 0 | 0
FIT |  | .615 | Install rim angle - tack only | 4 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. HANDLE | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD | 6 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 7 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell AND TIE-OFF LUGS | 3 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 4 |  |  |  | 0 | 0
FIT |  | .721 | Weld insulation / vacuum rings, lugs, supports, etc. | 4 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL ADD FLANGE TO N2 & N5, PLUS HANDLE AND HOOK | 15 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL WELD FLANGE TO N2 & N6, PLUS HANDLE AND HOOK | 25 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld SHELL REPADS AT 330 DEG. | 4 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports N2 | 1 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips | 2 |  |  |  | 0 | 0
FIT |  | .755 | Fit ladder - install and weld clips | 10 |  |  |  | 0 | 0
FIT |  | .760 | Fit platform - install and weld clips, bracing, etc. | 10 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test | 6 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 35 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 4 |  |  |  | 0 | 0
SHIPPING |  | .970 | Take parts to galvanizers | 3 |  |  |  | 0 | 0
SHIPPING |  | .972 | Pick up parts from galvanizers | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | CREPING ADHESIVE BULK TANK | Customer PO: | 20615990 OP | Quote: | 9032.4 | CREPING ADHESIVE BULK TANK | Line: | 2.000 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-02-04 | Make Qty: | 1 | / | ea | Est Hours: | 365
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 51632 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 51633 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 51634 | 0 | Cut Nozzle Pipe and Clean | 0 | 5 | FixedHrs | 5 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 51635 | 0 | Build Nozzles-Weld | 0 | 11 | FixedHrs | 11 | .105 | 0 | Build nozzles and weld DO NOT WELD FLANGES ON N2 OR N5 | _________________ | _________________ | _________________
PRE FAB | 51636 | 0 | Make Manway Parts | 0 | 1 | FixedHrs | 1 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 51637 | 0 | Brn MW Neck, Clean, Bevel | 0 | 1 | FixedHrs | 1 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 51638 | 0 | Roll Manway Neck | 0 | 1 | FixedHrs | 1 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 51639 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 2 | FixedHrs | 2 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 51640 | 0 | Bld Davit Arm Aby Cover | 0 | 2 | FixedHrs | 2 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 51641 | 0 | Build Hatch/Door | 0 | 16 | FixedHrs | 16 | .140 | 0 | Build hatch/door BUILD N3 INCL. RAILS & CROSS BRACING | _________________ | _________________ | _________________
PRE FAB | 51642 | 0 | Cut Parts on Burn Table | 0 | 22 | FixedHrs | 22 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 51643 | 0 | Clean & Prep Parts | 0 | 12 | FixedHrs | 12 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 51644 | 0 | Build Supports | 0 | 4 | FixedHrs | 4 | .165 | 0 | Build supports: legs, lugs, saddles | _________________ | _________________ | _________________
PRE FAB | 51645 | 0 | Roll Repads-Drill & Tap | 0 | 3 | FixedHrs | 3 | .170 | 0 | Roll repads: drill and tap FOR CABLE SUPPORT & SHELL REPADS | _________________ | _________________ | _________________
PRE FAB | 51646 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS | _________________ | _________________ | _________________
PRE FAB | 51647 | 0 | Roll Rim Angle | 0 | 3 | FixedHrs | 3 | .205 | 0 | Roll rim angle | _________________ | _________________ | _________________
PRE FAB | 51648 | 0 | Fab Miscellaneous Parts | 0 | 2 | FixedHrs | 2 | .252 | 0 | Fabricate miscellaneous parts CABLE SUPPORT; CLIP FOR N2 | _________________ | _________________ | _________________
PRE FAB | 51649 | 0 | Drill/Punch holes | 0 | 1 | FixedHrs | 1 | .255 | 0 | Drill/punch holes PARTS FOR HATCH N3 | _________________ | _________________ | _________________
PRE FAB | 51650 | 0 | Misc Fabrication | 0 | 3 | FixedHrs | 3 | .261 | 0 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks FORM N5 CONE | _________________ | _________________ | _________________
PRE FAB | 51693 | 0 | Cut, Build Ladder Parts | 0 | 3 | FixedHrs | 3 | .262 | 0 | Cut/make parts for ladder: rungs, rails, etc. | _________________ | _________________ | _________________
PRE FAB | 51700 | 0 | Form and Roll Ladder Hoop | 0 | 2 | FixedHrs | 2 | .265 | 0 | Form and roll ladder hoops | _________________ | _________________ | _________________
PRE FAB | 51699 | 0 | Build Ladder-Weld | 0 | 8 | FixedHrs | 8 | .270 | 0 | Build ladder - weld out | _________________ | _________________ | _________________
PRE FAB | 51701 | 0 | Cut, Build Handrail Parts | 0 | 4 | FixedHrs | 4 | .272 | 0 | Cut/Build parts for handrail | _________________ | _________________ | _________________
PRE FAB | 51698 | 0 | Build Handrail-Weld | 0 | 6 | FixedHrs | 6 | .282 | 0 | Build handrail - weld out | _________________ | _________________ | _________________
PRE FAB | 51697 | 0 | Cut, Build Platform Parts | 0 | 3 | FixedHrs | 3 | .285 | 0 | Cut/Build parts for platform | _________________ | _________________ | _________________
PRE FAB | 51696 | 0 | Burn Platform Grating | 0 | 2 | FixedHrs | 2 | .290 | 0 | Burn grating for platforms, clean and band | _________________ | _________________ | _________________
PRE FAB | 51695 | 0 | Build Platform-Weld | 0 | 7 | FixedHrs | 7 | .292 | 0 | Build platform - weld out | _________________ | _________________ | _________________
PRE FAB | 51694 | 0 | Mount Platform Handrail | 0 | 2 | FixedHrs | 2 | .295 | 0 | Mount handrail on platform | _________________ | _________________ | _________________
INSPECTION | 51651 | 0 | QC Inspection - Pre Sub C | 0 | 0 | FixedHrs | 0 | .QC2 | 0 | QC Inspection - Components prior to shipping to Subcontractor | _________________ | _________________ | _________________
INSPECTION | 51652 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 51653 | 0 | BI, SQ, T&C Shells | 0 | 12 | FixedHrs | 12 | .305 | 0 | Shells: bring in plate, square, trim and clean SET UP (2) DOUBLE SHELLS **NOTE BOTTOM HEAD SLOPE** | _________________ | _________________ | _________________
PRE FAB | 51654 | 0 | Roll Shell, Tack-Weld I/S | 0 | 7 | FixedHrs | 7 | .315 | 0 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS ***WELD LONG SEAMS W COBOT*** | _________________ | _________________ | _________________
PRE FAB | 51655 | 0 | Build Top Head/Cone | 0 | 9 | FixedHrs | 9 | .350 | 0 | Build top head/cone | _________________ | _________________ | _________________
INSPECTION | 51656 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 51657 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 51658 | 0 | Set Nozzles & Lugs - Top | 0 | 6 | FixedHrs | 6 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT | _________________ | _________________ | _________________
PRE FAB | 51659 | 0 | Weld Nozzles - Top Head | 0 | 8 | FixedHrs | 8 | .366 | 0 | Weld out top head nozzles, etc. INCL CABLE SUPPORT | _________________ | _________________ | _________________
PRE FAB | 51660 | 0 | I&W Repads -Top | 0 | 2 | FixedHrs | 2 | .370 | 0 | Install and weld out repads - top head FOR CABLE SUPPORT | _________________ | _________________ | _________________
PRE FAB | 51661 | 0 | Build Bottom Head/Cone | 0 | 6 | FixedHrs | 6 | .450 | 0 | Build bottom head/cone | _________________ | _________________ | _________________
INSPECTION | 51662 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 51663 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes | _________________ | _________________ | _________________
FIT | 51664 | 0 | Fit Bottom Head to Shell | 0 | 10 | FixedHrs | 10 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE ***NOTE BOTTOM SLOPE*** | _________________ | _________________ | _________________
FIT | 51665 | 0 | Tack Shell Courses | 0 | 3 | FixedHrs | 3 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 51666 | 0 | Weld Inside Round Seams | 0 | 3 | FixedHrs | 3 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 51667 | 0 | Install Rim Angle | 0 | 4 | FixedHrs | 4 | .615 | 0 | Install rim angle - tack only | _________________ | _________________ | _________________
FIT | 51668 | 0 | Weld Rim Angle | 0 | 4 | FixedHrs | 4 | .616 | 0 | Weld rim angle complete | _________________ | _________________ | _________________
FIT | 51669 | 0 | L/O Shell, B&C Holes | 0 | 2 | FixedHrs | 2 | .620 | 0 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________
FIT | 51670 | 0 | Install Internal Parts | 0 | 1 | FixedHrs | 1 | .630 | 0 | Install internals - wear plates, rings, clips, etc. HANDLE | _________________ | _________________ | _________________
INSPECTION | 51671 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 51672 | 0 | Fit Top to Shell | 0 | 6 | FixedHrs | 6 | .640 | 0 | Fit top head to shell - tack AND WELD | _________________ | _________________ | _________________
FIT | 51673 | 0 | Weld all Outside Seams | 0 | 7 | FixedHrs | 7 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 51674 | 0 | Move Tank to Detail Rolls | 0 | 2 | FixedHrs | 2 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 51675 | 0 | Install Lift Lugs on Shl | 0 | 3 | FixedHrs | 3 | .717 | 0 | Install lift lugs on shell AND TIE-OFF LUGS | _________________ | _________________ | _________________
FIT | 51676 | 0 | Install Support Parts | 0 | 4 | FixedHrs | 4 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt | _________________ | _________________ | _________________
FIT | 51677 | 0 | Weld rings, lugs, suppts | 0 | 4 | FixedHrs | 4 | .721 | 0 | Weld insulation / vacuum rings, lugs, supports, etc. | _________________ | _________________ | _________________
FIT | 51678 | 0 | Set Nozzles in Shell | 0 | 15 | FixedHrs | 15 | .725 | 0 | Set nozzles in shell - tack INCL ADD FLANGE TO N2 & N5, PLUS HANDLE AND HOOK | _________________ | _________________ | _________________
FIT | 51679 | 0 | Weld Shell Nozz & M/Ws | 0 | 25 | FixedHrs | 25 | .726 | 0 | Weld shell nozzles, manways, etc. INCL WELD FLANGE TO N2 & N6, PLUS HANDLE AND HOOK | _________________ | _________________ | _________________
FIT | 51680 | 0 | Add Repads-Weld | 0 | 4 | FixedHrs | 4 | .730 | 0 | Add repads and weld SHELL REPADS AT 330 DEG. | _________________ | _________________ | _________________
FIT | 51681 | 0 | Install Dip Pipe Supports | 0 | 1 | FixedHrs | 1 | .735 | 0 | Install dip pipe supports N2 | _________________ | _________________ | _________________
FIT | 51704 | 0 | Fit Handrail, I&W Clips | 0 | 2 | FixedHrs | 2 | .750 | 0 | Fit handrail - install and weld clips | _________________ | _________________ | _________________
FIT | 51703 | 0 | Fit Ladder, I&W Clips | 0 | 10 | FixedHrs | 10 | .755 | 0 | Fit ladder - install and weld clips | _________________ | _________________ | _________________
FIT | 51702 | 0 | Fit Platform, I&W Clips | 0 | 10 | FixedHrs | 10 | .760 | 0 | Fit platform - install and weld clips, bracing, etc. | _________________ | _________________ | _________________
FINISHING | 51682 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FINISHING | 51683 | 0 | Dye Pen Test | 0 | 6 | FixedHrs | 6 | .900 | 0 | Dye pen test | _________________ | _________________ | _________________
FIT | 51684 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 51685 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 51686 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 51687 | 0 | Test Tank | 0 | 10 | FixedHrs | 10 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 51688 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 51689 | 0 | Clean Tank Complete | 0 | 35 | FixedHrs | 35 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 51690 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
INSPECTION | 51691 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 51692 | 0 | Load on Truck | 0 | 4 | FixedHrs | 4 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
SHIPPING | 51706 | 0 | Take Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .970 | 0 | Take parts to galvanizers | _________________ | _________________ | _________________
SHIPPING | 51705 | 0 | P/U Parts - Galvanizers | 0 | 3 | FixedHrs | 3 | .972 | 0 | Pick up parts from galvanizers | _________________ | _________________ | _________________
| Part: | CREPING ADHESIVE BULK TANK |  |  |  | Rev:

## Tasks with Hours
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 5
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld DO NOT WELD FLANGES ON N2 OR N5
Hours | 11
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door BUILD N3 INCL. RAILS & CROSS BRACING
Hours | 16
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 22
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 12
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap FOR CABLE SUPPORT & SHELL REPADS
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CABLE SUPPORT; CLIP FOR N2
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes PARTS FOR HATCH N3
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks FORM N5 CONE
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
Hours | 8
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
Hours | 6
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .285 | Cut/Build parts for platform
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .290 | Burn grating for platforms, clean and band
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .292 | Build platform - weld out
Hours | 7
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .295 | Mount handrail on platform
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean SET UP (2) DOUBLE SHELLS **NOTE BOTTOM HEAD SLOPE**
Hours | 12
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS ***WELD LONG SEAMS W COBOT***
Hours | 7
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
Hours | 9
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT
Hours | 6
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT
Hours | 8
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head FOR CABLE SUPPORT
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
Hours | 6
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE ***NOTE BOTTOM SLOPE***
Hours | 10
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. HANDLE
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD
Hours | 6
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 7
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell AND TIE-OFF LUGS
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .721 | Weld insulation / vacuum rings, lugs, supports, etc.
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL ADD FLANGE TO N2 & N5, PLUS HANDLE AND HOOK
Hours | 15
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL WELD FLANGE TO N2 & N6, PLUS HANDLE AND HOOK
Hours | 25
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld SHELL REPADS AT 330 DEG.
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports N2
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
Hours | 10
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .760 | Fit platform - install and weld clips, bracing, etc.
Hours | 10
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test
Hours | 6
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 10
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 35
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 4
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
Hours | 3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld DO NOT WELD FLANGES ON N2 OR N5
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door BUILD N3 INCL. RAILS & CROSS BRACING
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap FOR CABLE SUPPORT & SHELL REPADS
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc. AND TIE-OFF LUGS
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CABLE SUPPORT; CLIP FOR N2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes PARTS FOR HATCH N3
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks FORM N5 CONE
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .262 | Cut/make parts for ladder: rungs, rails, etc.
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .265 | Form and roll ladder hoops
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .270 | Build ladder - weld out
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .272 | Cut/Build parts for handrail
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .282 | Build handrail - weld out
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .285 | Cut/Build parts for platform
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .290 | Burn grating for platforms, clean and band
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .292 | Build platform - weld out
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .295 | Mount handrail on platform
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean SET UP (2) DOUBLE SHELLS **NOTE BOTTOM HEAD SLOPE**
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (2) DOUBLE SHELLS ***WELD LONG SEAMS W COBOT***
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL CABLE SUPPORT
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL CABLE SUPPORT
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head FOR CABLE SUPPORT
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE AND OUTSIDE ***NOTE BOTTOM SLOPE***
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. HANDLE
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell AND TIE-OFF LUGS
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .721 | Weld insulation / vacuum rings, lugs, supports, etc.
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL ADD FLANGE TO N2 & N5, PLUS HANDLE AND HOOK
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL WELD FLANGE TO N2 & N6, PLUS HANDLE AND HOOK
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld SHELL REPADS AT 330 DEG.
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports N2
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .755 | Fit ladder - install and weld clips
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .760 | Fit platform - install and weld clips, bracing, etc.
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .970 | Take parts to galvanizers
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .972 | Pick up parts from galvanizers
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 026-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_