## Build Plan w Hours
Job #: | 035-25
| Description: | FORMING SEAL POT |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL N2 AND N4 A & B | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 12 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 8 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 3 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle CUT AND MITER ANGLES; PUNCH (4) HOLES | 4 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports CUT BAFFLE SUPPORT ANGLES | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean SEE RUTANG FOR PATTERNS | 6 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams BREAK SIDE PANELS - SEE RUTANG FOR PATTERNS | 6 |  |  |  | 0 | 0
FIT |  | .320 | Set up and weld sides - rectangular tank BUILD TANK; WELD INSIDE AND OUTSIDE | 35 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
FIT |  | .615 | Install rim angle - tack only FIT AND TACK TOP AND BOTTOM ANGLES | 6 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete WELD TOP AND BOTTOM ANGLES; USE COBOT AS POSSIBLE | 10 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes | 2 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 12 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. WELD IN BAFFLE ANGLE SUPPORTS | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack FIT STIFFENERS AND WELD; USE COBOT WHERE POSSIBLE | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 7 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 12 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test | 4 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 15 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 035-25
| Description: | FORMING SEAL POT |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL N2 AND N4 A & B | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 12 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 8 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 3 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .205 | Roll rim angle CUT AND MITER ANGLES; PUNCH (4) HOLES | 4 |  |  |  | 0 | 0
PRE FAB |  | .225 | Cut and make baffle supports CUT BAFFLE SUPPORT ANGLES | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean SEE RUTANG FOR PATTERNS | 6 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams BREAK SIDE PANELS - SEE RUTANG FOR PATTERNS | 6 |  |  |  | 0 | 0
FIT |  | .320 | Set up and weld sides - rectangular tank BUILD TANK; WELD INSIDE AND OUTSIDE | 35 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
FIT |  | .615 | Install rim angle - tack only FIT AND TACK TOP AND BOTTOM ANGLES | 6 |  |  |  | 0 | 0
FIT |  | .616 | Weld rim angle complete WELD TOP AND BOTTOM ANGLES; USE COBOT AS POSSIBLE | 10 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes | 2 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 12 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. WELD IN BAFFLE ANGLE SUPPORTS | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack FIT STIFFENERS AND WELD; USE COBOT WHERE POSSIBLE | 12 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 7 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 12 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test | 4 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 15 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | FORMING SEAL POT | Customer PO: | 20615990 OP | Quote: | 9032.4 | FORMING SEAL POT | Line: | 11.000 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-02-04 | Make Qty: | 1 | / | ea | Est Hours: | 185
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 52328 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 52329 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 52330 | 0 | Cut Nozzle Pipe and Clean | 0 | 5 | FixedHrs | 5 | .100 | 0 | Cut nozzle pipe and clean INCL N2 AND N4 A & B | _________________ | _________________ | _________________
PRE FAB | 52331 | 0 | Build Nozzles-Weld | 0 | 12 | FixedHrs | 12 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 52332 | 0 | Cut Parts on Burn Table | 0 | 8 | FixedHrs | 8 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 52333 | 0 | Clean & Prep Parts | 0 | 3 | FixedHrs | 3 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 52334 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 52335 | 0 | Roll Rim Angle | 0 | 4 | FixedHrs | 4 | .205 | 0 | Roll rim angle CUT AND MITER ANGLES; PUNCH (4) HOLES | _________________ | _________________ | _________________
PRE FAB | 52336 | 0 | Cut, Make Baffle Supports | 0 | 2 | FixedHrs | 2 | .225 | 0 | Cut and make baffle supports CUT BAFFLE SUPPORT ANGLES | _________________ | _________________ | _________________
INSPECTION | 52337 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 52338 | 0 | BI, SQ, T&C Shells | 0 | 6 | FixedHrs | 6 | .305 | 0 | Shells: bring in plate, square, trim and clean SEE RUTANG FOR PATTERNS | _________________ | _________________ | _________________
PRE FAB | 52339 | 0 | Roll Shell, Tack-Weld I/S | 0 | 6 | FixedHrs | 6 | .315 | 0 | Roll shells, tack and weld inside seams BREAK SIDE PANELS - SEE RUTANG FOR PATTERNS | _________________ | _________________ | _________________
FIT | 52340 | 0 | S/U and Build Sides | 0 | 35 | FixedHrs | 35 | .320 | 0 | Set up and weld sides - rectangular tank BUILD TANK; WELD INSIDE AND OUTSIDE | _________________ | _________________ | _________________
PRE FAB | 52341 | 0 | Build Bottom Head/Cone | 0 | 3 | FixedHrs | 3 | .450 | 0 | Build bottom head/cone | _________________ | _________________ | _________________
INSPECTION | 52342 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
FIT | 52343 | 0 | Install Rim Angle | 0 | 6 | FixedHrs | 6 | .615 | 0 | Install rim angle - tack only FIT AND TACK TOP AND BOTTOM ANGLES | _________________ | _________________ | _________________
FIT | 52344 | 0 | Weld Rim Angle | 0 | 10 | FixedHrs | 10 | .616 | 0 | Weld rim angle complete WELD TOP AND BOTTOM ANGLES; USE COBOT AS POSSIBLE | _________________ | _________________ | _________________
FIT | 52345 | 0 | L/O Shell, B&C Holes | 0 | 2 | FixedHrs | 2 | .620 | 0 | Lay out shell, burn and clean holes | _________________ | _________________ | _________________
FIT | 52346 | 0 | Install Baffles-Weld | 0 | 12 | FixedHrs | 12 | .625 | 0 | Install baffles and weld | _________________ | _________________ | _________________
FIT | 52347 | 0 | Install Internal Parts | 0 | 4 | FixedHrs | 4 | .630 | 0 | Install internals - wear plates, rings, clips, etc. WELD IN BAFFLE ANGLE SUPPORTS | _________________ | _________________ | _________________
INSPECTION | 52348 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 52349 | 0 | Install Insul/Vac Rings | 0 | 12 | FixedHrs | 12 | .715 | 0 | Install insulation/vacuum rings - tack FIT STIFFENERS AND WELD; USE COBOT WHERE POSSIBLE | _________________ | _________________ | _________________
FIT | 52350 | 0 | Set Nozzles in Shell | 0 | 7 | FixedHrs | 7 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 52351 | 0 | Weld Shell Nozz & M/Ws | 0 | 12 | FixedHrs | 12 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
FINISHING | 52352 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 52353 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 52354 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
MOVE TANK | 52355 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 52356 | 0 | Dye Pen Test | 0 | 4 | FixedHrs | 4 | .900 | 0 | Dye pen test | _________________ | _________________ | _________________
FINISHING | 52357 | 0 | Test Tank | 0 | 8 | FixedHrs | 8 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 52358 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 52359 | 0 | Clean Tank Complete | 0 | 15 | FixedHrs | 15 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 52360 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 52361 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
INSPECTION | 52362 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 52363 | 0 | Load on Truck | 0 | 2 | FixedHrs | 2 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | FORMING SEAL POT |  |  |  | Rev:

## Tasks with Hours
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL N2 AND N4 A & B
Hours | 5
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 12
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 8
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 3
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle CUT AND MITER ANGLES; PUNCH (4) HOLES
Hours | 4
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports CUT BAFFLE SUPPORT ANGLES
Hours | 2
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean SEE RUTANG FOR PATTERNS
Hours | 6
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams BREAK SIDE PANELS - SEE RUTANG FOR PATTERNS
Hours | 6
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .320 | Set up and weld sides - rectangular tank BUILD TANK; WELD INSIDE AND OUTSIDE
Hours | 35
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
Hours | 3
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only FIT AND TACK TOP AND BOTTOM ANGLES
Hours | 6
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete WELD TOP AND BOTTOM ANGLES; USE COBOT AS POSSIBLE
Hours | 10
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes
Hours | 2
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
Hours | 12
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. WELD IN BAFFLE ANGLE SUPPORTS
Hours | 4
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack FIT STIFFENERS AND WELD; USE COBOT WHERE POSSIBLE
Hours | 12
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 7
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 12
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test
Hours | 4
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 8
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 15
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 2
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL N2 AND N4 A & B
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .205 | Roll rim angle CUT AND MITER ANGLES; PUNCH (4) HOLES
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .225 | Cut and make baffle supports CUT BAFFLE SUPPORT ANGLES
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean SEE RUTANG FOR PATTERNS
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams BREAK SIDE PANELS - SEE RUTANG FOR PATTERNS
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .320 | Set up and weld sides - rectangular tank BUILD TANK; WELD INSIDE AND OUTSIDE
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .615 | Install rim angle - tack only FIT AND TACK TOP AND BOTTOM ANGLES
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .616 | Weld rim angle complete WELD TOP AND BOTTOM ANGLES; USE COBOT AS POSSIBLE
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. WELD IN BAFFLE ANGLE SUPPORTS
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack FIT STIFFENERS AND WELD; USE COBOT WHERE POSSIBLE
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 035-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_